## Sheet1
BSEIDC Ltd., Patna
Physical Status for Construction of Shiksha Bhawan
S.No. | Group No. | NAME OF DISTRICT | NAME OF SCHOOL | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Remarks | Division
[8 empty] | LL | RL | LL | RL | LL | RL
1 | SB-1 | Darbhanga | Shiksha Bhawan Darbhanga | [11 empty] | 1 | 209.759 | 171.14 |  | Darbhanga
2 | SB-2 | Gaya | Shiksha Bhawan Gaya | [10 empty] | 1 |  | 209.5319 | 35.65 |  | Magadh
3 | SB-3 | Vaishalli | Shiksha Bhawan Vaishalli | 1 | [13 empty] | Land not available | Tirhut East
4 | SB-4 | Saharsa | Shiksha BhawanSaharsa | [9 empty] | 1 |  |  | 236.3615 | 105.36 |  | Koshi
5 | SB-5 | Kaimur | Shiksha Bhawan Kaimur | 1 | [11 empty] | 201.6758 | 25.03 | Not start | Patna West
6 | SB-6 | Patna | Shiksha Bhawan Patna | 1 | [13 empty] | Not start | Patna East
7 | SB-7 | Jehanabad | Shiksha Bhawan Jehanabad | [8 empty] | 1 |  |  |  | 202.2699 |  |  | Magadh
8 | SB-8 | Samastipur | Shiksha Bhawan Samastipur |  |  |  |  | 1 | [10 empty] | Darbhanga
9 | SB-9 | Bhagalpur | Shiksha Bhawan Bhagalpur | 1 | [13 empty] | Not start | Bhagalpur
Total Number of Shiksha Bhawan |  |  | 9 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1059.5981 | 337.18