## HSS
BSEIDC, PATNA
Progress Report for the construction of HSS ( Sanc. Year 2012 - 13 )
S.N. | Group No. | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Time of Completion | Retender | Tender Process | Physical Status | [9 empty] | Remarks | Actual date of Completion
[11 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | HSS-1-1 | Patna East | Patna | Patna Sadar | 1 | Mahant Hanuman Saran Higher Secondary School, Rajapur, Mainpura | KRISHNA KUMAR-9934252394 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2015
2 | HSS-2-1 | Patna East | Patna | Bakhtiyaarpur | 1 | Sri Sunder Devi Higher Secondary School, Rupas Mahaji, | BHAWANI BUILDCON AND PROJECT PVT LTD, 9835287922 | 1 Year | [10 empty] | 1 |  | Debar
3 | HSS-5-1 | Patna East | Nalanda | Nalanda | 1 | High School G.M.K, Islampur | M/S K.D. Company 9431497838 (01.06.2012) | 1 Year | [11 empty] | 1 | Inaugurated 16.07.2015
4 | HSS-5-2 | Patna East | Nalanda | Nalanda | 2 | High School, Khudaganj | M/S K.D. Company 9431497838 (01.06.2012) | [12 empty] | 1 | Inaugurated 16.07.2015
5 | HSS-88-1 | Patna East | Patna | Nagar | 1 | vk;Z dU;k mPp fo¦ky;] u;k Vksyk | A R ENTERPRISES | [12 empty] | 1
6 | HSS-3-1 | Patna West | Buxar | Chausa | 1 | High School, Chausa | MS ANANYA CONSTRUCTION -9334745882 | 1 Year |  |  | 1 | [9 empty] | Land not available
7 | HSS-4-1 | Patna West | Buxar | Buxar | 1 | Girl's High School, Chaugain | Mahnar Infratech Pvt.Ltd -9334383960 | 1 Year |  |  | 1 | [9 empty] | Land not available
8 | HSS-106-1 | Patna West | Buxar | Dumrao | 1 | eŒmŒckfydk mPp fo¦ky;] Mqejk¡o | JITENDRA KUMAR SINGH, BUXAR |  |  |  | 1 | [9 empty] | Land not available
9 | HSS-6 -1 | Magadh | Jehanabad | Modanganj | 1 | High School, Okari | Ramjee Prasad 9334489874 | 15 Months | [11 empty] | 1
10 | HSS-7-1 | Magadh | Gaya |  | 1 | Zila School, Gaya | Sanjeet kumar 9304368289 | 15 Months |  |  | 1 | [9 empty] | Land not available
11 | HSS-7-2 | Magadh | Gaya |  | 2 | Gandhi High School, Sewtar | Sanjeet kumar 9304368289 | [11 empty] | 1
12 | HSS-8 (A) | Magadh | Nawada |  | 1 | High School, Chakwai | Retender | 15 Months | [10 empty] | 1
13 | HSS-8 (B) | Magadh | Nawada |  | 1 | High School, kutri | RAJARAM PRASAD NOUMA |  |  |  | 1 | [9 empty] | to be started
14 | HSS-8 (C) | Magadh | Nawada |  | 1 | Project Girl's High School, Pakaribarawan | NAVIN KUMAR |  |  |  | 1 | [9 empty] | no land & EMD to be return
15 | HSS-9-1 | Magadh | Nawada |  | 1 | Inter School, Meskaur | Pankaj Kumar 933445721 | 15 Months | [10 empty] | 1
16 | HSS-9-2 | Magadh | Nawada |  | 2 | High School, Medhukuri | Pankaj Kumar 933445721 | [11 empty] | 1
17 | HSS-9-3 | Magadh | Nawada |  | 3 | High School, Biju Bigha | Pankaj Kumar 933445721 | [7 empty] | 1
18 | HSS-10-1 | Magadh | Nawada |  | 1 | Inter School, Narhat | Baijnath Nirman India Pvt. Ltd., Vill- Dihuri, P.O- Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. 9939911835 (08/06/2012) | 15 Months | [10 empty] | 1
19 | HSS-10-2 | Magadh | Nawada |  | 2 | Inter School, Laund | Baijnath Nirman India Pvt. Ltd., Vill- Dihuri, P.O- Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. 9939911835 (08/06/2012) | [12 empty] | 1 | Inaugurated 16.07.2016
20 | HSS-10-3 | Magadh | Nawada |  | 3 | High School, Narpur Pakaria | Baijnath Nirman India Pvt. Ltd., Vill- Dihuri, P.O- Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. 9939911835 (08/06/2012) | [12 empty] | 1 | Inaugurated 16.07.2016
21 | HSS-11-1 | Magadh | Nawada |  | 1 | High School, Targir | Shri Chandra Mouleshwar | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2015
22 | HSS-11-2 | Magadh | Nawada |  | 2 | Project Girl's High School, Akbarpur | Shri Chandra Mouleshwar | [11 empty] | 1
23 | HSS-11-3 | Magadh | Nawada |  | 3 | High School, Shahpur | Shri Chandra Mouleshwar | [12 empty] | 1 | Inaugurated 16.07.2016
24 | HSS-12-1 | Magadh | Arwal | karpi | 1 | High School, Kinjar | Kaushlendra kumar 8409113501 | 15 Months | [11 empty] | 1 | India mark III hand pump Remaining
25 | HSS-12-2 | Magadh | Arwal |  | 2 | High School, Sahar Telpa | Kaushlendra kumar 8409113501 | [12 empty] | 1 | India mark III hand pump Remaining
26 | HSS-12-3 | Magadh | Arwal |  | 3 | High School, Anandpur | Kaushlendra kumar 8409113501 | [12 empty] | 1 | India mark III hand pump Remaining
27 | HSS-13-1 | Magadh | Aurangabad |  | 1 | High School, Dumri | Ramesh kumar Singh | 15 Months | [11 empty] | 1
28 | HSS-14-1 | Magadh | Aurangabad |  | 1 | High School, Pathraur Dewhara | Nilesh kumar 8294888140 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
29 | HSS-97-1-1 | Magadh | Gaya | Vanshi Suryapur | 1 | High School, Mali Ramgarh | Kamlesh Kumar, Teka Bigha | 15 Months | [10 empty] | 1
30 | HSS-98-1-1 | Magadh | Gaya | Govindpur | 1 | High School, Sudhari | Mitlesh Kumar, Nawada | 15 Months | [11 empty] | 1
31 | HSS-98-2-2 | Magadh | Gaya | Govindpur | 2 | Project Kanya High School, Govindpur | Mitlesh Kumar, Nawada | [12 empty] | 1
32 | HSS-15-1 | Bhagalpur | Banka | Baunsi | 1 | LND HS Baunsi | Bricks Liner | 15 Months | [7 empty] | 1 |  |  |  |  | DELAY DUE TO CHANGE IN DRAWING AND DESIGN.
33 | HSS-15-2 | Bhagalpur | Banka | Rajoun | 2 | Pro.GHS Dhoni | Bricks Liner | [12 empty] | 1 | Inaugurated 16.07.2016
34 | HSS-15-3 | Bhagalpur | Banka | Chandan | 3 | Pro.GHS Chandan | Bricks Liner | [12 empty] | 1 | Inaugurated 16.07.2015
35 | HSS-16-1 | Bhagalpur | Banka | Katoriya | 1 | ASS.HS Kharhara | Binod Kr. Singh | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2015
36 | HSS-16-2 | Bhagalpur | Banka |  | 2 | Govt.HS Katoriya | Binod Kr. Singh | [12 empty] | 1 | Inaugurated 16.07.2015
37 | HSS-16-3 | Bhagalpur | Banka |  | 3 | Pro.GHS Katoriya | Binod Kr. Singh |  |  |  | 1 | [9 empty] | Less Land (80'X60'), CONTRACTOR NOT INTERESED
38 | HSS-17-1 | Munger | Jamui | cjgV | 1 | Government High School, Lathlath | BRAJESH KUMAR SINGH-9939622814 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
39 | HSS-18-1 | Munger | Munger | eqaxsj lnj | 1 | Baijnath Girl's High School, Munger | RAJENDRA PRASAD YADAV-7765903650 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
40 | HSS-18-2 | Munger | Munger | tekyiqj | 2 | N.C Ghosh Girl's High School, Jamalpur | RAJENDRA PRASAD YADAV-7765903650 | [12 empty] | 1 | G+2
41 | HSS-19 (A) | Munger | Munger | /kjgjk | 1 | High School, Sardha | BRICKS LINER INFRA. PVT LTD. | 15 Months | [10 empty] | 1
42 | HSS-19 (B) | Munger | Munger | cfj;kjiqj | 1 | Adarsh High School, Ghorgha | Rajendra Prasad Yadav |  |  |  | 1 | [9 empty] | LOA issue
43 | HSS-20 (A) | Munger | Khagaria | pkSFke | 1 | Shiv Maha High School, Chautham | M/S AASTHA AND SAUMYA CONS. | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
44 | HSS-20 (B) | Munger | Khagaria | xksxjh | 1 | Deep Nara Ram Krishna High School, Vasua Koyla | Krishna Kumar Singh, khagaria | [8 empty] | 1
45 | HSS-20 (C) | Munger | Khagaria | [kxfM+;k | 1 | C. S High School, Mandar | M/S AASTHA AND SAUMYA CONS. |  |  |  | 1 | [9 empty] | 8 Feet Deep Land
46 | HSS- 96-1 | Munger | Khagaria | ijcŸkk | 1 | Jh d`".k mPp fo¦ky;] u;kxk¡o | Ms P N S Construction,9939704356 | 15 Months | [10 empty] | 1
47 | HSS-105-1 | Munger | Begusarai | fogV | 1 | ohŒ,lŒ,lŒ dkSysft,V] csxwljk; | MS DAYARAM SINGH, BEGUSARAI, 9801031299 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
48 | HSS-107 (A) | Munger | Lakhisarai | cMfg;k | 1 | jketkudh jke/ku flag dU;k mŒfoŒ] oMfg;k | SAI HIGHWAY AND BUILDERS PVT LTD,9771455967 | 15 Months | [7 empty] | 1 |  |  |  |  | SOME PORTION TIE BEAM LEVEL AND REST PL
49 | HSS-107 (B) | Munger | Lakhisarai | pkUu | 1 | vkjŒyky pkuu mPp fo¦ky;] yk[kkspd | MS TRIBHUWAN PD SINGH AND COMPANY,8877113003 |  |  |  | 1 | [9 empty] | land is on hill . Const not possible
50 | HSS-107 (C) | Munger | Lakhisarai | y[khljk; | 1 | mPp fo¦ky; iqjkuh cktkj] y[khljk; | RINKU KUMAR,9006180994 |  |  |  | 1 | [9 empty] | Land not available
51 | HSS-107 (D) | Munger | Lakhisarai | lq;Zx<+k | 1 | ?kkslSB mPp fo¦ky;] ihjhcktkj | MS TRIBHUWAN PD SINGH AND COMPANY,8877113003 |  |  |  | 1 | [9 empty] | Dismentling Required
52 | HSS-107 (E) | Munger | Lakhisarai | lq;Zx<+k | 1 | mPp fo¦ky; ujksRreiqj] dtjk | MS TRIBHUWAN PD SINGH AND COMPANY,8877113003 |  |  |  | 1 | [9 empty] | Tree on land
53 | HSS-29-1 | Kosi | Madhepura |  | 1 | B. L. (+2) School, Murliganj | SUBHASH KUMAR SUBHASH Patna,993421227 | 15 Months | [10 empty] | 1
54 | HSS-94-1 | Kosi | Madhepura |  | 1 | Shivnandan Prasad Mandal High School , Madhepura | FLEXICON ENGINEERS AND PLANNER PRIVATE LIMITED,9709888878 | 15 Months | [10 empty] | 1
55 | HSS-21-1 | Purnea | Purnea |  | 1 | Rajkiya Girl's High School, Purnia | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | 15 Months | [10 empty] | 1
56 | HSS-22-1 | Purnea | Katihar |  | 1 | Gyanda High School, Roshna, Pranpur | Umakant Singh, 9431096239 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
57 | HSS-22-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Bastaul, Pranpur | Umakant Singh, 9431096239 | [12 empty] | 1 | Inaugurated 16.07.2016
58 | HSS-23-1 | Purnea | Katihar |  | 1 | Project Girl's High School, Korha | ASHOK KUMAR-9431096238 | 15 Months | [11 empty] | 1
59 | HSS-23-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Falka | ASHOK KUMAR-9431096238 | [12 empty] | 1 | Inaugurated 16.07.2016
60 | HSS-24-1 | Purnea | Katihar |  | 1 | Project Girl's High School, Kumhri, Kadwan | Umakant Singh-9431096239 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
61 | HSS-24-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Barsoi | Umakant Singh-9431096239 | [12 empty] | 1 | Inaugurated 16.07.2015
62 | HSS-24-3 | Purnea | Katihar |  | 3 | Project Girl's High School, Ajamnagar | Umakant Singh-9431096239 | [12 empty] | 1 | Inaugurated 16.07.2015
63 | HSS-25-1 | Purnea | Katihar |  | 1 | High School, Abadpur | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | 15 Months | [10 empty] | 1
64 | HSS-25-2 | Purnea | Katihar |  | 2 | A.L. High School, Sonali | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | [11 empty] | 1
65 | HSS-25-3 | Purnea | Katihar |  | 3 | High School, Salmari | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | [8 empty] | 1
66 | HSS-26-1 | Purnea | Katihar |  | 1 | Jageshwer High School, Grubazar | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
67 | HSS-26-2 | Purnea | Katihar |  | 2 | High School, B. Balrampur | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | [8 empty] | 1 |  |  |  |  | FF sill level
68 | HSS-26-3 | Purnea | Katihar |  | 3 | Shiv Na. Sarvoday High School, Bareta | BIRENDRA KUMAR SINGH, KATIHAR, 9473440405 | [11 empty] | 1
69 | HSS-27-1 | Purnea | Kishanganj |  | 1 | N. A. High School, Bishanpur | MD SHAFIQUE ALAM-9431259842 | 15 Months |  |  | 1 | [9 empty] | request for name change to MS gangihat.
70 | HSS-27-2 | Purnea | Kishanganj |  | 2 | Girl's High School, Kishanganj | MD SHAFIQUE ALAM-9431259842 | [12 empty] | 1 | Inaugurated 16.07.2016
71 | HSS-28-1 | Purnea | Kishanganj |  | 1 | High School, Bishanpur | MD SHAFIQUE ALAM-9431259842 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
72 | HSS-28-2 | Purnea | Kishanganj |  | 2 | National High School, Kishanganj | MD SHAFIQUE ALAM-9431259842 | [12 empty] | 1 | Inaugurated 16.07.2016
73 | HSS-30-1 | Tirhut East | Muzaffarpur |  | 1 | B. B. Collagiate, Muzaffarpur | Amit Kumar Shahi -9835280982 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
74 | HSS-31-1 | Tirhut East | Vaishali |  | 1 | Government High School, Goraul | Anil Kumar-9931044826 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2015
75 | HSS-31-2 | Tirhut East | Vaishali |  | 2 | Government High School, Sarsai Fatehpur | Anil Kumar-9931044826 | [12 empty] | 1 | Inaugurated 16.07.2015
76 | HSS-32-1 | Tirhut East | Sitamarhi |  | 1 | Kamla Girl's High School, Dumra | RAJEEV KUMAR. DUMRA, SITAMARHI,9199022302 | 15 Months | [10 empty] | 1
77 | HSS-32-2 | Tirhut East | Sitamarhi |  | 2 | Lakshmi High School, Sitamarhi | RAJEEV KUMAR. DUMRA, SITAMARHI,9199022302 | [12 empty] | 1 | Handover
78 | HSS-32-3 | Tirhut East | Sitamarhi |  | 3 | M.R.D. Girl's High School,Sitamarhi | RAJEEV KUMAR. DUMRA, SITAMARHI,9199022302 | [12 empty] | 1 | Handover
79 | HSS-33-1 | Tirhut East | Sitamarhi |  | 1 | S. R. High School, Bariyarpur | M/S Galaxce-9431067656 | 15 Months | [11 empty] | 1
80 | HSS-33-2 | Tirhut East | Sitamarhi |  | 2 | High School, Parsauni Chowk | M/S Galaxce-9431067656 |  |  |  | 1 | [9 empty] | Land Dispute
81 | HSS-34-1 | Tirhut East | Sitamarhi |  | 1 | High School, Bairgania | Rajesh Kumar-9931490405 | 15 Months | [10 empty] | 1
82 | HSS-34-2 | Tirhut East | Sitamarhi |  | 2 | Jauharimal High School, Bairgania | Rajesh Kumar-9931490405 | [11 empty] | 1
83 | HSS-35-1 | Tirhut East | Sitamarhi |  | 1 | Praject Girl's High School, Sasaula Sabha | Rabindra Singh | 15 Months | [11 empty] | 1
84 | HSS-35-2 | Tirhut East | Sitamarhi |  | 2 | Saryu High School, Sursand | Rabindra Singh | [12 empty] | 1
85 | HSS-35-3 | Tirhut East | Sitamarhi |  | 3 | V. R Sahi Girl's High School, Sursand | Rabindra Singh | [12 empty] | 1
86 | HSS-36 (A) | Tirhut East | Sitamarhi |  | 1 | Shree Gandhi High School, Parihar | Dilip Kumar Mishra | 15 Months | [10 empty] | 1
87 | HSS-36 (B) | Tirhut East | Sitamarhi |  | 1 | High School, Koiriya Pipra | MANOHAR KUMAR, | [11 empty] | 1
88 | HSS-36 (C) | Tirhut East | Sitamarhi |  | 1 | Praject Girl's High School, Gorhari | SANJEEV KUMAR | [11 empty] | 1
89 | HSS-37 (A) | Tirhut East | Sitamarhi |  | 1 | Project Girl's High School, Siwaipatti | GLOBAL INFRASTRUCTURE | 15 Months | [6 empty] | 1 | [5 empty] | Brick work upto P.L.
90 | HSS-37 (B) | Tirhut East | Sitamarhi |  | 1 | Shree Sutha High School, Balha | SANJEEV KUMAR | [11 empty] | 1
91 | HSS-37 (C) | Tirhut East | Sitamarhi |  | 1 | High School, Bajpatti | Tender Process | [5 empty] | 1
92 | HSS-38-1 | Tirhut East | Sitamarhi |  | 1 | High School, Dumri | Manohar Kumar, AT+P.O.- Dumari Kala, P.S.- Mejorganj, Distt.- Sitamarhi, Bihar. | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2015 | hand over
93 | HSS-38-2 | Tirhut East | Sitamarhi |  | 2 | Ra. Gu. High School, Kanhauli Bhandser | Manohar Kumar, | [12 empty] | 1 | Inaugurated 16.07.2015 | hand over
94 | HSS-39 (A) | Tirhut East | Sitamarhi |  | 1 | High School, Sonbarsa | Sarda Construction | 15 Months | [10 empty] | 1
95 | HSS-39 (B) | Tirhut East | Sitamarhi |  | 1 | Project Girl's High School, Bhutahi | SHARDA CONSTRUCTION, PATNA ,9709400379 | [11 empty] | 1
96 | HSS-39 (C) | Tirhut East | Sitamarhi |  | 1 | Ja. High School, Bhutahi | SHARDA CONSTRUCTION,PATNA ,9709400379 | [11 empty] | 1
97 | HSS-40-1 | Tirhut East | Sitamarhi |  | 1 | Project Girl's High School, Majhaulia State | RAJEEV KUMAR.; DUMRA, SITAMARHI, 9199022302 | 15 Months | [10 empty] | 1 |  | Painting
98 | HSS-40-2 | Tirhut East | Sitamarhi |  | 2 | Project Girl's High School, Manik Chowk | RAJEEV KUMAR.; DUMRA, SITAMARHI, 9199022302 | [11 empty] | 1 |  | GF Plaster
99 | HSS-41-1 | Tirhut East | Sitamarhi |  | 1 | AA. High School, Madhaul | Rajesh Kumar-9931490405 | 15 Months | [11 empty] | 1
100 | HSS-41-2 | Tirhut East | Sitamarhi |  | 2 | M. High School, Tilaktajpur | Rajesh Kumar-9931490405 | [12 empty] | 1
101 | HSS-42-1 | Tirhut East | Sitamarhi |  | 1 | High School, Bela Shanti Kutir | ABHAY KUMAR SINGH,BRAHMAUL SIRSI NANPUR SITAMARHI | 15 Months | [11 empty] | 1 | Handover
102 | HSS-42-2 | Tirhut East | Sitamarhi |  | 2 | Project Girl's High School, Bahela Jahidpur | ABHAY KUMAR SINGH,BRAHMAUL SIRSI NANPUR SITAMARHI | [12 empty] | 1 | Handover
103 | HSS-43-1 | Tirhut East | Sitamarhi |  | 1 | High School, Choraut | Malti Singh-9931123641 | 15 Months | [11 empty] | 1
104 | HSS-43-2 | Tirhut East | Sitamarhi |  | 2 | L. M. High School, Pupri | Malti Singh-9931123641 |  |  |  | 1 | [9 empty] | Land dispute
105 | HSS-70-1 | Tirhut East | Sitamarhi | lksucjlk | 1 | mPp fo¦ky;] flagokfguh | SHARDA CONSTRUCTION,PATNA , 9709400379 | 15 Months | [10 empty] | 1
106 | HSS-70-2 | Tirhut East | Sitamarhi | lksucjlk | 2 | mPp fo¦ky;] t;uxj | SHARDA CONSTRUCTION,PATNA , 9709400379 | [11 empty] | 1 |  | bar binding in progress
107 | HSS-71-1 | Tirhut East | Sitamarhi | cFkukgk | 1 | mPp fo¦ky;] cFkukgk | DOLPHIN CONTRACTORS AND ENGINEERS PVT LTD, DANAPUR CANTT, PATNA. 9835464364 | [12 empty] | 1 | Inaugurated 16.07.2016
108 | HSS-71-2 | Tirhut East | Sitamarhi | cFkukgk | 2 | mPp fo¦ky;] iqjufg;k | DOLPHIN CONTRACTORS AND ENGINEERS PVT LTD, DANAPUR CANTT, PATNA. 9835464364 | [12 empty] | 1 | Inaugurated 16.07.2016
109 | HSS-71-3 | Tirhut East | Sitamarhi | cFkukgk | 3 | mPp fo¦ky;] ;ksxokukcktkj | DOLPHIN CONTRACTORS AND ENGINEERS PVT LTD, DANAPUR CANTT, PATNA. 9835464364 | [12 empty] | 1 | Inaugurated 16.07.2016
110 | HSS-72 (A) | Tirhut East | Sitamarhi | ifjgkj | 1 | mPp fo¦ky;] Hkhlok cktkj | MANOJ KUMAR AZAD,9431636894 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
111 | HSS-72 (B) | Tirhut East | Sitamarhi | ifjgkj | 1 | mPp fo¦ky;] [kSjok fo".kqiqj | MANOJ KUMAR AZAD,9431636894 | [12 empty] | 1 | Inaugurated 16.07.2016
112 | HSS-73 (A) | Tirhut East | Sitamarhi | :Uuh lSniqj | 1 | mPp fo¦ky;] eksjlaM+ | SIENN SECURITY PRIVATE LIMITED,9708011111 | 15 Months | [6 empty] | 1
113 | H.S.S-73 (B) | Tirhut East | Sitamarhi | :Uuh lSniqj | 1 | mPp fo¦ky;] fo".kqiqj oklqnso | Mother India Cons PVT LTD. | [12 empty] | 1
114 | HSS- 74 (A) | Tirhut East | Sitamarhi | csylaM | 1 | mPp fo¦ky;] pankSyh | MS SHEEL CONSTRUCTION, 9430081574 | 15 Months | [11 empty] | 1
115 | HSS-74 (B) | Tirhut East | Sitamarhi | csylaM | 1 | mPp fo¦ky;] csylaM+ | AKHILESH KUMAR CHAUDHARI,9431415700 | [12 empty] | 1 | Handover
116 | HSS-75 (A) | Tirhut East | Sitamarhi | ukuiqj | 1 | mPp fo¦ky;] jk;iqj | AKHILESH KUMAR CHAUDHARI,9431415700 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
117 | HSS-75 (B) | Tirhut East | Sitamarhi | ukuiqj | 1 | mPp fo¦ky;] tkuhiqj | MS DIVYA CONSTRUCTION,9939099775 | [11 empty] | 1 |  | electricfication
118 | HSS-76-1 | Tirhut East | Sitamarhi | cks[kM+k | 1 | mPp fo¦ky;] [kM+dk | SANJAY KUMAR, LAHERIASARAI, DARBHANGA, 8521954601 | 15 Months | [11 empty] | 1 | Handover
119 | HSS-77-1 | Tirhut East | Sitamarhi | cktiÍh | 1 | mPp fo¦ky;] okpksiÍh ujgk | PROGRESSIVE CONSTRUCTION, 8873163000 | 15 Months |  |  |  |  | 1
120 | HSS- 78-1 | Tirhut East | Sitamarhi | estjxat | 1 | mPp fo¦ky;] estjxat | MANOHAR KUMAR, MEJORGANJ, DIST.- SITAMARHI, 9430218256 | 15 Months | [11 empty] | 1
121 | HSS- 78-2 | Tirhut East | Sitamarhi | estjxat | 2 | mPp fo¦ky;] eM+ik fljiky | MANOHAR KUMAR, MEJORGANJ, DIST. - SITAMARHI,9430218256 | [12 empty] | 1
122 | HSS- 79-1 | Tirhut East | Sitamarhi | lqIih | 1 | mPp fo¦ky;] lqIih | MANOHAR KUMAR,9430218256 | 15 Months | [11 empty] | 1
123 | HSS- 80-1 | Tirhut East | Sitamarhi | jhxk | 1 | mPp fo¦ky;] oHkuxkok¡ | PRINCE INFRA TECH PRIVATE LIMITED, PATLIPUTRA, 9431017667 / 9304812067 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
124 | HSS- 80-2 | Tirhut East | Sitamarhi | jhxk | 2 | mPp fo¦ky;] jsoklh | PRINCE INFRA TECH PRIVATE LIMITED, PATLIPUTRA, 9431017667 / 9304812067 | [12 empty] | 1 | Inaugurated 16.07.2016
125 | HSS- 80-3 | Tirhut East | Sitamarhi | jhxk | 3 | mPp fo¦ky;] lgcktiqj [kjlku | PRINCE INFRA TECH PRIVATE LIMITED, PATLIPUTRA, 9431017667 / 9304812067 |  |  |  | 1 | [9 empty] | Land Dispute. Local villager dispute
126 | HSS- 81-1 | Tirhut East | Sitamarhi | lqjlaM | 1 | deynkl ckfydk mPp fo¦ky;] lqjlM | PRAVEEN KUMAR,,DUMRA SITAMARHI,9430973025 | 15 Months |  |  | 1 | [9 empty] | Land Dispute. L P old Building to be dismantle,small land
127 | HSS- 81-2 | Tirhut East | Sitamarhi | lqjlaM | 2 | mPp fo¦ky;] j/kkmj | PRAVEEN KUMAR,,DUMRA SITAMARHI,9430973025 | [12 empty] | 1
128 | HSS- 81-3 | Tirhut East | Sitamarhi | lqjlaM | 3 | mPp fo¦ky;] ekus'oj LFkku | PRAVEEN KUMAR,,DUMRA SITAMARHI,9430973025 | [12 empty] | 1 | Inaugurated 16.07.2016
129 | HSS- 82-1 | Tirhut East | Sitamarhi | pksjkSr | 1 | mPp fo¦ky;] cjjh csgVk | MALTI INFRASTRUCTURE PRIVATE LIMITED, Phulwarisarif, Patna-801505, 9471238807 | 15 Months | [11 empty] | 1 | Handover
130 | HSS- 83-1 | Tirhut East | Muzaffarpur | eq'kgjh | 1 | mPp fo¦ky;] tekykckn | HARI SHANKAR PRASAD, MINAPUR DIST MUZAFFARPUR, 9939363702 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
131 | HSS- 95 (A) | Tirhut West | West Champaran | fldVk | 1 | vkn'kZ mPp fo¦ky;] nq[khNkij | MS SARASWATI COMPANY,9431491241 | 15 Months | [10 empty] | 1
132 | HSS- 95 (B) | Tirhut West | West Champaran | fldVk | 1 | igokjh ;kno mPp fo¦ky;] txUukFkiqj | DAYA SAGAR PRASAD,9471097581, 9931004361 | [12 empty] | 1 | Inaugurated 16.07.2016
133 | HSS-99-1 | Tirhut West | East Champaran | ?kksM+klkgu | 1 | mPp fo¦ky;] Hkssyok lfdZy | Ravi Shekhar | 15 Months | [10 empty] | 1
134 | HSS-99-2 | Tirhut West | East Champaran | ?kksM+klkgu | 2 | mPp fo¦ky;] ?kksM+klkgu | Ravi Shekhar | [12 empty] | 1 | Inaugurated 16.07.2016
135 | HSS-100-1 | Tirhut West | East Champaran | <+kdk | 1 | dU;k mPp fo¦ky;] djeok | Retender | 15 Months | 1 | [11 empty] | Retender
136 | HSS-100-2 | Tirhut West | East Champaran | <+kdk | 2 | vyila[;d mPp fo¦ky;] [kSjok | Retender |  | 1 | [11 empty] | Retender
137 | HSS-100-3 | Tirhut West | East Champaran | idMhn;ky | 3 | mPp fo¦ky;] pSrk | Retender |  | 1 | [11 empty] | Retender
138 | HSS-100-4 | Tirhut West | East Champaran |  | 4 | mPp fo¦ky;] cM+dkxk¡o | Retender |  | 1 | [11 empty] | Retender
139 | HSS-101-1 | Tirhut West | East Champaran | dksVok | 1 | mPp fo¦ky;] ePNjxk¡ok | KESHAV KUMAR KESHRI, EAST CHAMPARAN, 7779830772 | 15 Months | [7 empty] | 1
140 | HSS-101-2 | Tirhut West | East Champaran | dksVok | 2 | mPp fo¦ky;] Hkqifriqj | KESHAV KUMAR KESHRI, EAST CHAMPARAN, 7779830772 | [12 empty] | 1
141 | HSS-102-1 | Tirhut West | East Champaran | dY;k.kiqj | 1 | mPp fo¦ky;] rsuqvk | RADHA DEVI,- EAST CHAMPARAN, BIHAR.,9471886673 | 15 Months | [11 empty] | 1
142 | HSS-102-2 | Tirhut West | East Champaran | pfd;k | 2 | chŒ,yŒ,lŒihŒ mPp fo¦ky;] pfd;k | RADHA DEVI,- EAST CHAMPARAN, BIHAR.,9471886673 | [10 empty] | 1
143 | HSS-102-3 | Tirhut West | East Champaran | esglh | 3 | mPp fo¦ky;] ckykdksBh | RADHA DEVI,- EAST CHAMPARAN, BIHAR.,9471886673 | [11 empty] | 1
144 | HSS-103-1 | Tirhut West | East Champaran | fpjS;k | 1 | txUukFk mPp fo¦ky;]fpjS;k | PRINCE INFRA TECH PRIVATE LIMITED, PATNA, 9431017667 / 9304812067 | 15 Months |  |  |  | 1
145 | HSS-103-2 | Tirhut West | East Champaran | fpjS;k | 2 | mPp fo¦ky;] fljkSuk | PRINCE INFRA TECH PRIVATE LIMITED, PATNA, 9431017667 / 9304812067 | [10 empty] | 1
146 | HSS-103-3 | Tirhut West | East Champaran | e/kqcu | 3 | mPp fo¦ky;] e/kqcu | PRINCE INFRA TECH PRIVATE LIMITED, PATNA, 9431017667 / 9304812067 | [12 empty] | 1 | Inaugurated 16.07.2016
147 | HSS-104-1 | Tirhut West | East Champaran | vjsjkt | 1 | mPp fo¦ky;] eykgh | ALOK KUMAR., EAST CHAMPARAN, 9631044077 | 15 Months | [10 empty] | 1
148 | HSS-104-2 | Tirhut West | East Champaran | vjsjkt | 2 | ikoZrh dU;k mPp fo¦ky;] vjsjkt | ALOK KUMAR., EAST CHAMPARAN, 9631044077 | [10 empty] | 1
149 | HSS-104-3 | Tirhut West | East Champaran | rqjdkSfy;k | 3 | mPp fo¦ky;] rqjdkSfy;k | ALOK KUMAR., EAST CHAMPARAN, 9631044077 | [11 empty] | 1
150 | HSS-44-1 | Darbhanga | Darbhanga |  | 1 | High School, Mahinam Pohaddi | MADHAV CONSTRUCTION,DARBHANGA, 9835288951, 9234460951 | 15 Months | [11 empty] | 1
151 | HSS-91-1 | Darbhanga | Samastipur | fo¦kifr uxj | 1 | fo¦kifr uxj mPp fo¦ky; em ckftriqj | MS REETA RANJAN, KUDHANI, MUZAFFARPUR, 9162406190 | 15 Months | [10 empty] | 1
152 | HSS-92-1 | Darbhanga | Samastipur | foHkwfriqj | 1 | mPp fo¦ky;] pdgcho foHkwfriqj | RITA DEVI, 9835005728 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
153 | HSS-93-1 | Darbhanga | Samastipur | f'kokthuxj | 1 | xk¡/kh Lekjd nkŒ mPp fo¦ky;] oYyhiqj | CHANDRA PRAKASH,9471232746 | 15 Months | [10 empty] | 1
154 | HSS-108-1 | Darbhanga | Darbhanga |  | 1 | mPp fo¦ky;] uoknk | DEVENDRA AND DEVENDRA INFRASTRUCTURE PRIVATE LIMITED, PATNA, 9304417600 | 15 Months | [11 empty] | 1 | Inaugurated 16.07.2016
155 | HSS-108-2 | Darbhanga | Darbhanga | fojkSy | 2 | mPp fo¦ky;] cank] fcjkSy | DEVENDRA AND DEVENDRA INFRASTRUCTURE PRIVATE LIMITED, PATNA, 9304417600 | [12 empty] | 1 | Inaugurated 16.07.2016
156 | HSS-108-3 | Darbhanga | Darbhanga | csuhiqj | 3 | mPp fo¦ky;] csgsM+k ouhiqj | DEVENDRA AND DEVENDRA INFRASTRUCTURE PRIVATE LIMITED, PATNA, 9304417600 | [12 empty] | 1 | Inaugurated 16.07.2016
157 | HSS-45-1 | Saran | Siwan |  | 1 | High School, Ander | Arbind Singh-9801721172 | 15 Months | [9 empty] | 1 |  |  | FF-RL
158 | HSS-45-2 | Saran | Siwan |  | 2 | M. S. High School Cum Inter Collage, Husainganj | Arbind Singh-9801721172 | [11 empty] | 1
159 | HSS-45-3 | Saran | Siwan |  | 3 | Kishan Majdur High School, Tari | Arbind Singh-9801721172 | [6 empty] | 1
160 | HSS-46-1 | Saran | Siwan |  | 1 | Islamia High School, Siwan | Bighnahanta Construction pvt ltd. 68 Chanakyapuri, Raja Bazar B.V. College patna-14 | 15 Months |  |  | 1 | [9 empty] | Land Problem. (EMD Refund)
161 | HSS-46-2 | Saran | Siwan |  | 2 | Smt. Rajvansi Devi Girl's High School, Siwan | Bighnahanta Construction pvt ltd. 68 Chanakyapuri, Raja Bazar B.V. College patna-14 |  |  |  | 1 | [9 empty] | Land Problem. (EMD Refund)
162 | HSS-47-1 | Saran | Siwan |  | 1 | Town High School, Mairwa | Arbind Singh-9801721172 | 15 Months |  |  | 1 | [9 empty] | Old Building To Be Demolished.
163 | HSS-47-2 | Saran | Siwan |  | 2 | High School, Nikatikala Raghunath | Arbind Singh-9801721172 |  |  |  | 1 | [9 empty] | Old Building To Be Demolished.
164 | HSS-48-1 | Saran | Siwan |  | 1 | Janta High School, Musaipur | Asiana Contractor Pvt. Ltd.-9431088485 | 15 Months | [11 empty] | 1
165 | HSS-48-2 | Saran | Siwan |  | 2 | Indira Singh High School, Hilser | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1
166 | HSS-49-1 | Saran | Saran |  | 1 | Shiv Dulari High School, Sonepur | M/S Shiva Const.- 9431662461 | 15 Months | [7 empty] | 1
167 | HSS-49-2 | Saran | Saran |  | 2 | Gogal Singh High School, Naya Gaoun, Sonepur | M/S Shiva Const.- 9431662461 | [11 empty] | 1
168 | HSS-49-3 | Saran | Saran |  | 3 | K. P. S. High School, Gangajal, Sonepur | M/S Shiva Const.- 9431662461 | [10 empty] | 1
169 | HSS-50-1 | Saran | Saran |  | 1 | S. P. S. High School, Sonepur | M/S Shiva Const.- 9431662461 | 15 Months |  |  | 1 | [9 empty] | Not start. Tree at site
170 | HSS-50-2 | Saran | Saran |  | 2 | High School, Chanwa | M/S Shiva Const.- 9431662461 |  |  |  | 1 | [9 empty] | Land not Sufficient As Per B.O.Q. : Site Is 90 Km. Away From Sonepur.
171 | HSS-50-3 | Saran | Saran |  | 3 | Sishu Sangh High School, Sonepur | M/S Shiva Const.- 9431662461 |  |  |  | 1 | [9 empty] | Not Start. Railways 's land
172 | HSS-51-1 | Saran | Saran |  | 1 | Durga High School, Sahpur, Sutihar | Asiana Contractor Pvt. Ltd.-9431088485 | [11 empty] | 1
173 | HSS-51-2 | Saran | Saran |  | 2 | Sarvoday High School, Bhagwanpur | Asiana Contractor Pvt. Ltd.-9431088485 | [11 empty] | 1
174 | HSS-52-1 | Saran | Saran |  | 1 | Raghuveer Singh High School, Mahdalichak | Ashutosh kumar vill+ po-Bithauli Bhagwanpur Vashali | [12 empty] | 1 | Inaugurated 16.07.2016
175 | HSS-52-2 | Saran | Saran |  | 2 | High School, Atersan | Ashutosh kumar vill+ po-Bithauli Bhagwanpur Vashali |  |  |  | 1 | [9 empty] | Land Problem. No way
176 | HSS-51 (A) | Saran | Saran |  | 1 | High School, Parsagarh | Shivam Const.-9973398595 | [12 empty] | 1
177 | HSS-51 (B) | Saran | Saran |  | 2 | Alakh Narain Singh High School, Ekma | Shivam Const.-9973398595 | [12 empty] | 1 | Inaugurated 16.07.2016
178 | HSS-52 (A) | Saran | Saran |  | 1 | Zila School, Chapra | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1
179 | HSS-52 (B) | Saran | Saran |  | 2 | Dr. Ram Bihari Singh High School, Vishnupura | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
180 | HSS-53-1 | Saran | Saran |  | 1 | Medauri Devi High School, Mahammadpur | Asiana Contractor Pvt. Ltd.-9431088485 | [11 empty] | 1
181 | HSS-53-2 | Saran | Saran |  | 2 | Rana Pratap High School, Rampur Kala | Asiana Contractor Pvt. Ltd.-9431088485 | [10 empty] | 1
182 | HSS-54-1 | Saran | Gopalganj |  | 1 | High School, Kalyanpur | Sai Highway And Builder Pvt.Ltd.-9771455967 | [11 empty] | 1
183 | HSS-54-2 | Saran | Gopalganj |  | 2 | High School, Vijaypur | Sai Highway And Builder Pvt.Ltd.-9771455967 | [12 empty] | 1 | Inaugurated 16.07.2016
184 | HSS-54-3 | Saran | Gopalganj |  | 3 | High School, Koreya | Sai Highway And Builder Pvt.Ltd.-9771455967 | [11 empty] | 1
185 | HSS-55-1 | Saran | Gopalganj |  | 1 | High School, Gaura | Sona Engicon Pvt.Ltd.-9431008581 | [12 empty] | 1 | Inaugurated 16.07.2016
186 | HSS-55-2 | Saran | Gopalganj |  | 2 | High School, Bagahi | Sona Engicon Pvt.Ltd.-9431008581 | [11 empty] | 1
187 | HSS-55-3 | Saran | Gopalganj |  | 3 | High School, Belhikhas | Sona Engicon Pvt.Ltd.-9431008581 | [11 empty] | 1
188 | HSS-56-1 | Saran | Gopalganj |  | 1 | High School, Sashamusa | Ramajee mishra & co sirisia sasamusa gopalganj | [12 empty] | 1 | Inaugurated 16.07.2016
189 | HSS-56-2 | Saran | Gopalganj |  | 2 | High School, Ratanpura | Ramajee mishra & co sirisia sasamusa gopalganj | [11 empty] | 1
190 | HSS-57-1 | Saran | Gopalganj |  | 1 | Sahu Jain Girl's High School, Mirganj | Anand Mishra-9931648331 | [11 empty] | 1
191 | HSS-57-2 | Saran | Gopalganj |  | 2 | High School, Jamunaha Bazar | Anand Mishra-9931648331 | [11 empty] | 1
192 | HSS-58-1 | Saran | Gopalganj |  | 1 | Sahu Jain High School, Mirganj | Akhileshwar Kumar Singh-9431264865 | [12 empty] | 1 | Inaugurated 16.07.2016
193 | HSS-58-2 | Saran | Gopalganj |  | 2 | Ialamia Urdu Academy, Mirganj | Akhileshwar Kumar Singh-9431264865 | [12 empty] | 1
194 | HSS-59-1 | Saran | Gopalganj |  | 1 | High School, Sadaua | M/S Co hesive Infrastructure Developer Pvt.Ltd-9431212019 | [12 empty] | 1 | Inaugurated 16.07.2016
195 | HSS-59-2 | Saran | Gopalganj |  | 2 | High School , Haluaar, Pipra | M/S Co hesive Infrastructure Developer Pvt.Ltd-9431212019 | [12 empty] | 1 | Inaugurated 16.07.2016
196 | HSS-59-3 | Saran | Gopalganj |  | 3 | High School, Devapur | M/S Co hesive Infrastructure Developer Pvt.Ltd-9431212019 | [12 empty] | 1 | Inaugurated 16.07.2016
197 | HSS-60-1 | Saran | Gopalganj |  | 1 | High School, Dharamparsa | Sona Engicon | [12 empty] | 1 | Inaugurated 16.07.2016
198 | HSS-60-2 | Saran | Gopalganj |  | 2 | High School , Madhopur | Sona Engicon | [12 empty] | 1 | Inaugurated 16.07.2016
199 | HSS-61-1 | Saran | Gopalganj |  | 1 | High School, Uchkagaon | Sai Highway And Builder Pvt.Ltd.-9771455967 | [12 empty] | 1 | Inaugurated 16.07.2016
200 | HSS-61-2 | Saran | Gopalganj |  | 2 | Maya Chota High School, Uchkagaon | Sai Highway And Builder Pvt.Ltd.-9771455967 | [12 empty] | 1
201 | HSS-62-1 | Saran | Gopalganj |  | 1 | High School, Sankhe Ramdas | M/S Shaeb singh | [11 empty] | 1
202 | HSS-62-2 | Saran | Gopalganj |  | 2 | High School, Dahibhatta | M/S Shaeb singh | [12 empty] | 1 | Inaugurated 16.07.2016
203 | HSS-63-1 | Saran | Gopalganj |  | 1 | High School, Ganeshsthan, Manjha | Kumar Manash Const. Pvt.Ltd.-9801582832 | [12 empty] | 1 | Inaugurated 16.07.2016
204 | HSS-63-2 | Saran | Gopalganj |  | 2 | High School , Koiladeva | Kumar Manash Const. Pvt.Ltd.-9801582832 | [12 empty] | 1 | Inaugurated 16.07.2016
205 | HSS-63-3 | Saran | Gopalganj |  | 3 | High School, Kusaundhi | Kumar Manash Const. Pvt.Ltd.-9801582832 | [12 empty] | 1 | Inaugurated 16.07.2016
206 | HSS-64-1 | Saran | Gopalganj |  | 1 | High School, Sahpur, Sindhwalia | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
207 | HSS-64-2 | Saran | Gopalganj |  | 2 | High School, Sher | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
208 | HSS-65-1 | Saran | Gopalganj |  | 1 | High School, Larauli | Asiana Contractor Pvt. Ltd.-9431088485 | [11 empty] | 1
209 | HSS-65-2 | Saran | Gopalganj |  | 2 | High School, Shirsha | Asiana Contractor Pvt. Ltd.-9431088485 | [11 empty] | 1
210 | HSS-66-1 | Saran | Gopalganj |  | 1 | High School, Nechua Jalalpur | M/S Shri Krishna Const.Pvt.Ltd.- | [11 empty] | 1
211 | HSS-66-2 | Saran | Gopalganj |  | 2 | High School, Baliwan Sagar | M/S Shri Krishna Const.Pvt.Ltd.- | [12 empty] | 1 | Inaugurated 16.07.2016
212 | HSS-67-1 | Saran | Gopalganj |  | 1 | High School, Bishunpur Yadavpur | Rand S Const.Pvt.Ltd.-9234272194 | [12 empty] | 1 | Inaugurated 16.07.2016
213 | HSS-67-2 | Saran | Gopalganj |  | 2 | M. S. Urdu High School, Gopalganj | Rand S Const.Pvt.Ltd.-9234272194 | [12 empty] | 1 | Inaugurated 16.07.2016
214 | HSS-68-1 | Saran | Gopalganj |  | 1 | High School, Sonhula | Akhileshwar Kr. Singh-9431264865 | [12 empty] | 1 | Inaugurated 16.07.2016
215 | HSS-68-2 | Saran | Gopalganj |  | 2 | High School, Bathuwa Bazar | Akhileshwar Kr. Singh-9431264865 | [12 empty] | 1 | Inaugurated 16.07.2016
216 | HSS-68-3 | Saran | Gopalganj |  | 3 | High School, Ramchandpur | Akhileshwar Kr. Singh-9431264865 | [12 empty] | 1 | Inaugurated 16.07.2016
217 | HSS-69-1 | Saran | Gopalganj |  | 1 | D. A. V. High School, Gopalganj | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
218 | HSS-69-2 | Saran | Gopalganj |  | 2 | D. G. High School, Dumaria | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
219 | HSS-84-1 | Saran | Siwan |  | 1 | D.A.V.High school Siwan | Brajesh kumar vill- Dhanuanti Tola ,po- Dhanuanti math Siwan | [12 empty] | 1 | Inaugurated 16.07.2016
220 | HSS-85-1 | Saran | Siwan |  | 1 | High school Basantpur | Asiana Contractor Pvt. Ltd.-9431088485 | [12 empty] | 1 | Inaugurated 16.07.2016
221 | HSS-86-1 | Saran | Siwan |  | 1 | High School Hadsar Dhanauti | BALINDRA SINGH, 9472288573 | [11 empty] | 1
222 | HSS-87-1 | Saran | Siwan |  | 1 | High school Rajpur | Pankaj kumar vill- Benaut, po-Srawan, distt-Chhapra | [12 empty] | 1 | Inaugurated 16.07.2016
223 | HSS-89-1 | Saran | Saran | fjfoyxat | 1 | jked`".k mPp fo¦ky;] flefj;k] fjfoyxat | EKLAVYA INFRA CONSULTECH PVT. LTD, CHAPRA SARAN,9430010264 | [12 empty] | 1 | Inaugurated 16.07.2016
224 | HSS-89-2 | Saran | Saran |  | 2 | jktdh; ckfydk mPp ek/;fed fo¦ky;] Nijk | EKLAVYA INFRA CONSULTECH PVT. LTD, CHAPRA SARAN,9430010264 | [12 empty] | 1 | Inaugurated 16.07.2016
225 | HSS-90-1 | Saran | Saran | lnj | 1 | rkilh flag mPp fo¦ky;] fpjkan | SHOBH NATH PRASAD, CHAPRA (SARAN),9431692381 | [9 empty] | 1
226 | HSS-90-2 | Saran | Saran |  | 2 | vkuan mPp fo¦ky;] jkeiqj izrkiiqj nfj;kiqj | SHOBH NATH PRASAD, CHAPRA (SARAN),9431692381 | [11 empty] | 1
Total Number of Schools (HSS) |  |  |  |  | 226 |  |  |  | 4 | 0 | 26 | 1 | 2 | 1 | 3 | 7 | 1 | 6 | 56 | 119

## Sheet1 (hidden)
BSEIDC, PATNA
Completed List of HSS ( Sanc. Year 2012 - 13 )
S.N. | Group No. | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Time of Completion | Retender | Tender Process | Physical Status | [9 empty] | Remarks
[11 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | HSS-1-1 | Patna East | Patna | Patna Sadar | 1 | Mahant Hanuman Saran Higher Secondary School, Rajapur, Mainpura | [11 empty] | 1 | Inaugurated
2 | HSS-5-1 | Patna East | Nalanda | Nalanda | 1 | High School G.M.K, Islampur | [11 empty] | 1 | Inaugurated
3 | HSS-5-2 | Patna East | Nalanda | Nalanda | 2 | High School, Khudaganj | [11 empty] | 1 | Inaugurated
4 | HSS-6 -1 | Magadh | Jehanabad | Modanganj | 1 | High School, Okari | [11 empty] | 1
5 | HSS-10-2 | Magadh | Nawada |  | 2 | Inter School, Laund | [11 empty] | 1
6 | HSS-10-3 | Magadh | Nawada |  | 3 | High School, Narpur Pakaria | [11 empty] | 1
7 | HSS-11-1 | Magadh | Nawada |  | 1 | High School, Targir | [11 empty] | 1
8 | HSS-11-3 | Magadh | Nawada |  | 3 | High School, Shahpur | [11 empty] | 1
9 | HSS-12-1 | Magadh | Arwal | karpi | 1 | High School, Kinjar | [11 empty] | 1
10 | HSS-15-2 | Bhagalpur | Banka | Rajoun | 2 | Pro.GHS Dhoni | [11 empty] | 1
11 | HSS-15-3 | Bhagalpur | Banka | Chandan | 3 | Pro.GHS Chandan | [11 empty] | 1 | Inaugurated
12 | HSS-16-1 | Bhagalpur | Banka | Katoriya | 1 | ASS.HS Kharhara | [11 empty] | 1 | Inaugurated
13 | HSS-16-2 | Bhagalpur | Banka |  | 2 | Govt.HS Katoriya | [11 empty] | 1 | Inaugurated
14 | HSS-17-1 | Munger | Jamui |  | 1 | Government High School, Lathlath | [11 empty] | 1
15 | HSS-18-1 | Munger | Munger |  | 1 | Baijnath Girl's High School, Munger | [11 empty] | 1
16 | HSS-105-1 | Munger | Begusarai | fogV | 1 | ohŒ,lŒ,lŒ dkSysft,V] csxwljk; | [11 empty] | 1
17 | HSS-22-1 | Purnea | Katihar |  | 1 | Gyanda High School, Roshna, Pranpur | [11 empty] | 1 | Handover
18 | HSS-22-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Bastaul, Pranpur | [11 empty] | 1
19 | HSS-23-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Falka | [11 empty] | 1
20 | HSS-24-1 | Purnea | Katihar |  | 1 | Project Girl's High School, Kumhri, Kadwan | [11 empty] | 1
21 | HSS-24-2 | Purnea | Katihar |  | 2 | Project Girl's High School, Barsoi | [11 empty] | 1 | Handover
22 | HSS-24-3 | Purnea | Katihar |  | 3 | Project Girl's High School, Ajamnagar | [11 empty] | 1 | Handover
23 | HSS-26-1 | Purnea | Katihar |  | 1 | Jageshwer High School, Grubazar | [11 empty] | 1
24 | HSS-27-2 | Purnea | Kishanganj |  | 2 | Girl's High School, Kishanganj | [11 empty] | 1 | Handover
25 | HSS-28-1 | Purnea | Kishanganj |  | 1 | High School, Bishanpur | [11 empty] | 1
26 | HSS-28-2 | Purnea | Kishanganj |  | 2 | National High School, Kishanganj | [11 empty] | 1
27 | HSS-30-1 | Tirhut East | Muzaffarpur |  | 1 | B. B. Collagiate, Muzaffarpur | [11 empty] | 1
28 | HSS-31-1 | Tirhut East | Vaishali |  | 1 | Government High School, Goraul | [11 empty] | 1
29 | HSS-31-2 | Tirhut East | Vaishali |  | 2 | Government High School, Sarsai Fatehpur | [11 empty] | 1
30 | HSS-38-1 | Tirhut East | Sitamarhi |  | 1 | High School, Dumri | [11 empty] | 1 | Inaugurated | hand over
31 | HSS-38-2 | Tirhut East | Sitamarhi |  | 2 | Ra. Gu. High School, Kanhauli Bhandser | [11 empty] | 1 | Inaugurated | hand over
32 | HSS- 80-1 | Tirhut East | Sitamarhi | jhxk | 1 | mPp fo¦ky;] oHkuxkok¡ | [11 empty] | 1 | Handover
33 | HSS- 80-2 | Tirhut East | Sitamarhi | jhxk | 2 | mPp fo¦ky;] jsoklh | [11 empty] | 1 | Handover
34 | HSS- 83-1 | Tirhut East | Muzaffarpur | eq'kgjh | 1 | mPp fo¦ky;] tekykckn | [11 empty] | 1
35 | HSS- 95 (B) | Tirhut West | West Champaran | fldVk | 1 | igokjh ;kno mPp fo¦ky;] txUukFkiqj | [11 empty] | 1 | Handover
36 | HSS-103-3 | Tirhut West | East Champaran | e/kqcu | 3 | mPp fo¦ky;] e/kqcu | [11 empty] | 1 | Handover
37 | HSS-92-1 | Darbhanga | Samastipur | foHkwfriqj | 1 | mPp fo¦ky;] pdgcho foHkwfriqj | [11 empty] | 1
38 | HSS-108-1 | Darbhanga | Darbhanga |  | 1 | mPp fo¦ky;] uoknk | [11 empty] | 1
39 | HSS-108-2 | Darbhanga | Darbhanga | fojkSy | 2 | mPp fo¦ky;] cank] fcjkSy | [11 empty] | 1
40 | HSS-108-3 | Darbhanga | Darbhanga | csuhiqj | 3 | mPp fo¦ky;] csgsM+k ouhiqj | [11 empty] | 1
41 | HSS-52 (B) | Saran | Saran |  | 2 | Dr. Ram Bihari Singh High School, Vishnupura | [11 empty] | 1
42 | HSS-55-1 | Saran | Gopalganj |  | 1 | High School, Gaura | [11 empty] | 1
43 | HSS-56-1 | Saran | Gopalganj |  | 1 | High School, Sashamusa | [11 empty] | 1
44 | HSS-58-1 | Saran | Gopalganj |  | 1 | Sahu Jain High School, Mirganj | [11 empty] | 1
45 | HSS-59-1 | Saran | Gopalganj |  | 1 | High School, Sadaua | [11 empty] | 1
46 | HSS-59-3 | Saran | Gopalganj |  | 3 | High School, Devapur | [11 empty] | 1
47 | HSS-60-1 | Saran | Gopalganj |  | 1 | High School, Dharamparsa | [11 empty] | 1
48 | HSS-60-2 | Saran | Gopalganj |  | 2 | High School , Madhopur | [11 empty] | 1
49 | HSS-61-1 | Saran | Gopalganj |  | 1 | High School, Uchkagaon | [11 empty] | 1
50 | HSS-64-1 | Saran | Gopalganj |  | 1 | High School, Sahpur, Sindhwalia | [11 empty] | 1
51 | HSS-64-2 | Saran | Gopalganj |  | 2 | High School, Sher | [11 empty] | 1
52 | HSS-67-1 | Saran | Gopalganj |  | 1 | High School, Bishunpur Yadavpur | [11 empty] | 1
53 | HSS-67-2 | Saran | Gopalganj |  | 2 | M. S. Urdu High School, Gopalganj | [11 empty] | 1
54 | HSS-69-1 | Saran | Gopalganj |  | 1 | D. A. V. High School, Gopalganj | [11 empty] | 1
55 | HSS-69-2 | Saran | Gopalganj |  | 2 | D. G. High School, Dumaria | [11 empty] | 1
56 | HSS-84-1 | Saran | Siwan |  | 1 | D.A.V.High school Siwan | [11 empty] | 1
57 | HSS-85-1 | Saran | Siwan |  | 1 | High school Basantpur | [11 empty] | 1
58 | HSS-87-1 | Saran | Siwan |  | 1 | High school Rajpur | [11 empty] | 1
59 | HSS-89-1 | Saran | Saran | fjfoyxat | 1 | jked`".k mPp fo¦ky;] flefj;k] fjfoyxat | [11 empty] | 1
60 | HSS-89-2 | Saran | Saran |  | 2 | jktdh; ckfydk mPp ek/;fed fo¦ky;] Nijk | [11 empty] | 1