## Summary
BSEIDC, PATNA
Progress report for the construction of Model School building (2009-10) | [22 empty] | Date:-31.08.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [9 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | 6 | 15 | 3830.42 | 5 | 12 | 1263.41 |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 6 | 6 | 0 | 544.87 |  | 0
2 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 5 | 13 | 3195.2 | 2 | 5 | 1228.47 |  | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 5 | 0 | 622.33 |  | 0
3 | BHAGALPUR | Ranvijay Kr. Sinha (9934961293) E.E. BSEIDC, Div.- Bhagalpur | 2 | 5 | 1281.12 | 2 | 5 | 1281.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 912.09 |  | 0
4 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 6 | 14 | 3581.02 | 6 | 14 |  |  | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 6 | 1 | 13 | 0 | 1908.04 |  | 0
5 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 3 | 8 | 549.11 | 3 | 8 | 549.11 |  | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 4 | 0 | 8 | 0 | 1153.7 |  | 0
6 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnea | 4 | 11 | 2951.14 | 3 | 8 | 2154.55 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 4 | 2 | 6 | 0 | 1150.03 |  | 0
7 | TIRHUT | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 6 | 17 | 4541.23 | 6 | 17 | 4541.23 |  | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 16 | 0 | 2537.6 |  | 0
8 | DARBHANGA | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Darbhanga | 3 | 7 | 1881.33 | 3 | 7 | 1881.33 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 7 | 0 | 1418.45 |  | 0
9 | SARAN | Pramod Kumar (9955128483) E.E. BSEIDC, Div.- Saran | 3 | 8 | 2069.66 | 3 | 8 | 2069.66 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 6 | 2 | 1535.42 |  | 0
Total (Modal School) |  |  | 38 | 98 | 23880.23 | 33 | 84 | 14968.88 | 0 | 1 | 5 | 4 | 1 | 4 | 2 | 6 | 1 | 6 | 42 | 10 | 72 | 2 | 11782.53

## Patna
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Patna | [21 empty] | Date:-31.08.2014
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-12 | Patna | Masaurhi | 1 | H/S.Masaurhi | Retender | 769.06
|  |  | Punpun | 2 | H/S.Punpun
|  |  | paliganj | 3 | H/S Chandhosh
2 | MS-13 | Nalanda | Asthawan | 1 | Govt. Basic School, Balwapur | Umakant Singh, Mirchaibari, Officer Colony, Katihar | 764.08 |  | 24 SBD of 2013-14/8.5.2013 | 15 Month | [8 empty] | 1 |  |  | 349.77 | Shuttering
|  |  | Rahui | 2 | H/S.Mauriyachak Supasan | [13 empty] | 1 |  |  |  | Shuttering & steel binding
|  |  | Hilsa | 3 | H/S.Hilsa | [6 empty] | 1 | [10 empty] | Work stoped as per instruction of MD
3 | MS-14 | Bhojpur | Piro | 1 | Govt. Basic School, Rajaiya | B. K. Enterprises | 509.3 | 1
|  |  | Tarari | 2 | H/S.Barkagaon |  |  | 1
4 | MS-15 | Rohtas | Sasaram | 1 | H/S.Takia | Shailendra Kumar, AT+P.O.- Sedaha, Distt.- Bhojpur, Bihar, 9525333478/ 9431841316 | 499.33 | 1 | 16 SBD of 2013-14/25.4.2013 | 15 Month | [11 empty] | 195.1 | Foundation work stoped due to Land Dispute (Playground)
|  |  | Kargahar | 2 | Govt. Basic School, Sawan Bahar | [14 empty] | 1
5 | MS-16 | Buxar | Rajpur | 1 | H/S.Rajpur | Ram Babu Prasad | 511.85 | 1
|  |  | Itarhi | 2 | Govt. Basic School, Unwas | [6 empty] | 1
6 | MS-17 | Kaimur | Mohaniya | 1 | Govt. Basic School, Mohaniya | Ajay Kumar Singh | 776.8 |  |  |  |  | 1
|  |  | Bhabhua | 2 | H/S.Akhlashpur |  |  | 1
|  |  | Durgawati | 3 | H/S.Kampura |  |  | 1
|  | Total nos. of school |  | 15 |  |  | 3830.42 | 6 |  |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 544.87

## Magadh
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Magadh | [20 empty] | Date:-31.08.2014
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-24 | Gaya | Fatehpur | 1 | H/S.Fatehpur | Retender | 726.77
|  |  | wazirganj | 2 | H/S.Wazirgznj
|  |  | Sherghati | 3 | P.T.T.C. Sherghati
2 | MS-25 | Aurangabad | Madanpur | 1 | H/S.Beri | Retender | 740.41
|  |  | Nabinagar | 2 | H/S.Nabinagar
|  |  | Kutumba | 3 | Govt. Basic School, Rampur Parsa
3 | MS-26 | Jahanabad | Makhadumpur | 1 | Govt. Basic School, Meera Bigha | M/S B.K. Interprises | 490.85 |  | 11.4.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 233.62
|  |  | Hulashganj | 2 | Govt. Basic School, Dogra | [11 empty] | 1
4 | MS-27 | Arwal | Karpi | 1 | Govt. Basic School, Pariyahi Bazar | Tender Process | 499.55 | [14 empty] | 96.12
|  |  | Kaler | 2 | H/S.Kaler
5 | MS-28 | Nawada | Sirdala | 1 | H/S.Sirdala | Sujay Bhan Singh, Par Nawada, Bundelkhand, Distt.- Nawada. | 737.62 |  | 26.2.2013 | 15 Month | [8 empty] | 1 |  |  | 292.59
|  |  | Rajouli | 2 | H/S.Chiraita | [9 empty] | 1
|  |  | Hisua | 3 | Govt.Basic School Wagodar | [12 empty] | 1
|  | Total nos. of school |  | 13 |  |  | 3195.2 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 622.33

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Bhagalpur | [21 empty] | Date:-31.08.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-7 | Bhagalpur | Sanhoula | 1 | Govt. Basic School Bhuriya | Satyendra Kumar Construction Pvt. Ltd., 202, Hera Enclave, New Dak Bunglow Rd, Patna- 1 | 755.21 |  | 24.1.2013 | 15 Month | [9 empty] | 1 |  | 648.89
|  |  | Kahalgaon | 2 | Govt. Basic School Shobhnathpur | [14 empty] | 1
|  |  | Pirpainty | 3 | Govt. Basic School Panchrukhi | [14 empty] | 1
2 | MS-8 | Banka | katoriya | 1 | Govt. Basic School Karjhausa | Kanhaiya Contractors Pvt. Ltd., Reg. off: Sahjanand Nagar, Begusarai, Bihar, Mob. No.-9939230505 | 525.91 |  | 26.2.2013 | 15 Month | [9 empty] | 1 |  | 263.2
|  |  | Bounsi | 2 | H/S.Maniyarpur | [14 empty] | 1
|  | Total nos. of school |  | 5 |  |  | 1281.12 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 912.09

## Munger
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Munger | [21 empty] | Date:-31.08.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-18 | Munger | Dharhara | 1 | Govt. Basic School, Ghatwari | Balkrishna Bhalotia Construction Pvt. Ltd. | 516.71 | 1 | [13 empty] | 63.61
|  |  | H.Kharagpur | 2 | Govt. Basic School, Khand Bihari | [7 empty] | 1
2 | MS-19 | Jamui | Chakai | 1 | H/S.Chakai | Rajendra Kumar, AT- Pipradih, P.O.- Jhajha, Distt.- Jamui, Mob. No.- 9939195777 | 774.01 |  | 21.1.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 299.17
|  |  | Khaira | 2 | Govt. Basic School, Dawilgadh | [13 empty] | 1
|  |  | Sono | 3 | M/S Batiya | [7 empty] | 1
3 | MS-20 | Lakhisarai | Surajgarha | 1 | Govt. Basic School, Kiranpur | M/S Sri Ram Enterprises, Prem Kunj Apartment, Naya Bazar | 497.05 |  | 22.5.2013 | 15 Month | [8 empty] | 1 |  |  | 243.97
|  |  | Halsi | 2 | H/S. Halsi | [10 empty] | 1
4 | MS-21 | Sheikhpura | Barbigha | 1 | Govt. Basic School Sarba | M/S Baba Parshuram Nirman Pvt. Ltd., Moldiyara Tola, Mokama, Patna, Bihar. | 496.42 |  | 28.2.2013 | 15 Month | [9 empty] | 1 |  | 355.59
|  |  | Sheikhpura | 2 | M/S. Sheikhpura | [14 empty] | 1
5 | MS-22 | Khagaria | Khagaria | 1 | Govt. Basic School , Durgapur | Rajendra Singh Const. Pvt. Ltd., Bengali Tola, Laheriasarai | 529.87 |  | 2.3.2013 | 15 Month | [9 empty] | 1 |  | 321.1
|  |  | Gogari | 2 | Govt. Basic School , Basua | [10 empty] | 1
6 | MS-23 | Begusarai | Begusarai | 1 | Govt. Basic School, Ulao | M/S Surendra Prasad Singh, Sarvodya Nagar, Begusarai, Bihar | 766.96 |  | 16.1.2013 | 15 Month | [9 empty] | 1 |  | 624.6
|  |  | Garhpura | 2 | H/S. Mortar | [14 empty] | 1
|  |  | Naokothi | 3 | H/S Samsa | [14 empty] | 1
| Total nos. of school |  |  | 14 |  |  | 3581.02 | 1 |  |  | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 6 | 0 | 1908.04

## Kosi
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Kosi | [23 empty] | Date:-31.08.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Fin. Exp. (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[10 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL | LL | RL
1 | MS-1 | Saharsa | Sonbarsha | 1 | High School Sonbarsha | Avaneesh Enterprises, III K - 35/3A, Nehru Nagar, Ghaziabad (exe. comm.) | 804.03 |  |  |  | 24.5.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 465.78 | FIRST FLOOR ROOF LEVEL WORK IN PROGRESS
|  |  | Sonbarsha | 2 | Govt. Basic School Surath | [16 empty] | 1 |  |  | PLSTERING WORK IN PROGRESS
|  |  | Attar Kataiya | 3 | High School Menha | [16 empty] | 1 |  |  | PLSTERING WORK IN PROGRESS
2 | MS-2 | Madhepura | Kumarkhand | 1 | High School Kumarkhand | Avaneesh Enterprises, III K - 35/3A, Nehru Nagar, Ghaziabad | 801.92 |  |  |  | 24.5.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 397.93 | GROUND FLOOR ROOF COMP. OF PRINCIPAL & COMMON ROOM WORK IN PROGRESS
|  |  | Madhepura | 2 | Shiv Nandan Pd.+2 School | [16 empty] | 1 |  |  | PLSTERING WORK IN PROGRESS
|  |  | AlamNagar | 3 | A.K.M. H/S Shah Alam Nagar | [15 empty] | 1 |  |  |  | SECOND FLOOR ROOF LEVEL OF MAIN BUILDING WORK IN PROGRESS
3 | MS-3 | Supoul | Triveniganj | 1 | M/S.Daparkha | M/S K.D. Company, Koshi Colony, Ward No. 20, Supaul, Mob. No.- 9431497838 | 554.91 |  |  |  | 20.2.2013 | 15 Month | [9 empty] | 1 |  | 289.99 | WORK IN PROGRESS
|  |  | Basantpur | 2 | H/S.Hirdya Nagar | [11 empty] | 1 | [7 empty] | GROUND FLOOR ROOF LEVEL WORK IN PROGRESS
|  | Total nos. of school |  | 8 |  |  | 2160.86 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 4 | 0 | 1153.7

## Purnea
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Purnea | [23 empty] | Date:-31.08.2014
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Date of start | Fin. Exp. (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[10 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL | LL | RL
1 | MS-35 | Purnia | Dhamdaha | 1 | Govt. Basic School Purandaha | Retender | 796.59
|  |  | Darharakothi | 2 | Govt. Basic School Diwrawanar
|  |  | Banmankhi | 3 | Govt. Basic School Dheema
2 | MS-36 | Araria | Raniganj | 1 | H./S.Raniganj | M/S R.P. Construction, Rahika Tola, Ward No.-17, Near N.H.-57, Araria, Mob. No.- 9431412396 & 9661254325 | 809.56 |  |  |  | 2.5.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 423.09
|  |  | Farbesganj | 2 | Govt. Basic School Haripur | [11 empty] | 1
|  |  | Bhargama | 3 | H/S.Bhargama | [16 empty] | 1
3 | MS-37 | Katihar | Korha | 1 | Govt. Basic School, Gorawari | Uma Kant Singh, Mirchaibari, Officer Colony, Katihar | 795.88 |  |  | 1 | 8.5.2013 | 15 Month | [11 empty] | 247.92 | Land not available
|  |  | Katihar | 2 | P.T.T.C Musapur |  |  |  |  | 1 | [14 empty] | Land not available
|  |  | Manihari | 3 | H/S.Nawabganj | [16 empty] | 1
4 | MS-38 | Kishanganj | Dighalbank | 1 | H/S. Tulsiya | M/S R.P. Construction, Rahika Tola, Ward No.-17, Near N.H.-57, Araria, Mob. No.- 9431412396 & 9661254325 | 549.11 |  |  |  | 26.2.2013 | 15 Month | [9 empty] | 1 |  | 479.02
|  |  | Thakurganj | 2 | H/S. Thakurganj | [16 empty] | 1
|  | Total nos. of school |  | 11 |  |  | 2951.14 | 0 | 0 | 2 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 4 | 0 | 1150.03

## Tirhut
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Tirhut | [21 empty] | Date:-31.08.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-29 | Muzaffarpur | Kurhni | 1 | G.T.T.C, Turki | M/S Durga contruction, Vill+ P.O.- Baithania, P.S.- Majhalia | 791.95 |  | 15.1.2013 | 15 Month | [9 empty] | 1 |  | 662.69
|  |  | Sakara | 2 | Govt. Basic School, Rapeura | [14 empty] | 1
|  |  | Mushahari | 3 | H/S.Meghmath | [14 empty] | 1
2 | MS-30 | Vaishali | Jandaha | 1 | R.B.S.Loma | Satyam Construction, 9835610045 | 1042.14 | [5 empty] | 1 | [8 empty] | 104.97
|  |  | Patepur | 2 | Govt. Basic School Bardiha | [6 empty] | 1
|  |  | Hajipur | 3 | Govt. Basic School Jagdishpur | [7 empty] | 1
|  |  | Mahua | 4 | M.S Singhara | [6 empty] | 1
3 | MS-31 | East Champaran | Kalyanpur | 1 | Govt. Basic School Madhopur Govind | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj | 532.78 |  | 12.2.2013 | 15 Month | [9 empty] | 1 |  | 412.74
|  |  | Chakia | 2 | B.A.A.P. H/S. Barachakia | [14 empty] | 1
4 | MS-32 | West Champaran | Bagaha-I | 1 | Govt. Basic School Patilar | Sisley Construction, Basantpur, Mainatand, West Champaran | 821.09 |  | 5.1.2013 | 15 Month | [9 empty] | 1 |  | 519.01
|  |  | Narkatiaganj | 2 | H/S. Mathura Gokhula | [14 empty] | 1
|  |  | Manjhaulia | 3 | Govt. Basic School Mahna Mirjapur | [14 empty] | 1
5 | MS-33 | Sitamarhi | Runnisaidpur | 1 | H./S.Morsand | Mother India Const. Pvt. Ltd., Aspura House, Road No.-3, Sanjay Ghandhi Nagar, Kankarbagh, Patna-800020 | 540.69 |  | 4.4.2013 | 15 Month | [9 empty] | 1 |  | 428.65
|  |  | Sonbarsha | 2 | H/S. Sonbarsha | [14 empty] | 1
6 | MS-34 | Sheohar | Tariyani | 1 | H.S.Taiyari | M/S Anoj Enterprises, Matiariya, Turkauliya, East Champaran | 812.58 | 1 | 11.12.2012 | 15 Month | [11 empty] | 409.54
|  |  | Sheohar | 2 | Govt. Basic School Bishahi | [14 empty] | 1
|  |  | Purnahiya | 3 | H/S. Sonoul Sultan | [14 empty] | 1
|  | Total nos. of school |  | 17 |  |  | 4541.23 | 1 |  |  | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 2537.6

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Darbhanga | [21 empty] | Date:-31.08.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-9 | Darbhanga | Bahadurpur | 1 | Govt. Basic School Ughara | Avaneesh Enterprises, III K- 35/3A, Nehru Nagar, Ghaziabad | 800.55 |  | 5.2.2013 | 15 Month | [9 empty] | 1 |  | 709.05
|  |  | Baheri | 2 | Govt. Basic School Machchhi | [14 empty] | 1
|  |  | Darbhanga | 3 | H/S,Atihar | [14 empty] | 1
2 | MS-10 | Madhubani | Benipatti | 1 | Lalidhar H.S. Benipatti * | Mother Indi Cont. Pvt. Ltd., Aspura House, Road No.-3 Sanjay Gandhi Nagar, Kankarbagh, Patna- 800020 | 553.89 |  | 8.2.2013 | 15 Month |  |  |  | 1 | [7 empty] | 294.81
|  |  | Andhra Thari | 2 | H/S.Andhra Thari | [14 empty] | 1
3 | MS-11 | Samstipur | Kalyanpur | 1 | Govt. Basic School,Janardanpur | M/S Surendra Prasad Singh, Sarvodya Nagar, Begusarai, Bihar | 526.89 |  | 16.1.2013 | 15 Month | [9 empty] | 1 |  | 414.59
|  |  | Samstipur | 2 | Govt. Basic School,Chatauna | [14 empty] | 1
|  | Total nos. of school |  | 7 |  |  | 1881.33 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1418.45
Note-* School name hasbeen changed as per instruction of SPD (BMSP) vide letter no.- 11/ Uk 5- 03/08-422 dated 12.06.2013

## Saran
BSEIDC, PATNA
Progress Report for the construction of Model School (2009-10)
Name of Division :- Saran | [21 empty] | Date:-31.08.2014
Name & contact no. of EE :- Pramod Kumar (9939599803), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-4 | Saran | Manjhi | 1 | M/S. Tajpur | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj | 764.14 |  | 30.5.2013 | 15 Month | 1 | [10 empty] | 453.85 | Excvation complete
|  |  | Garkha | 2 | H/S. Rampur Birbhan | [14 empty] | 1 |  |  | Roof complete
|  |  | Dariyapur | 3 | Govt. Basic School Bhagwanpur | [15 empty] | 1 |  | hand over
2 | MS-5 | Siwan | Panchrukhi | 1 | H/S.Pachrukhi | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj | 779.28 |  | 26.12.2012 | 15 Month | [9 empty] | 1 |  | 594.93
|  |  | Andar | 2 | Govt. Basic School Jayjor | [14 empty] | 1
|  |  | Raghunathpur | 3 | Govt. Basic School Sarhara | [11 empty] | 1
3 | MS-6 | Gopalganj | Uchkagoan | 1 | H/S.Rahua Jamsar | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj | 526.24 |  | 26.12.2012 | 15 Month | [10 empty] | 1 | 486.64 | hand over
|  |  | Barauli | 2 | H/S.Sher | [14 empty] | 1
|  | Total nos. of school |  | 8 |  |  | 2069.66 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 2 | 1535.42