## USSS (2011-12)
BSEIDC Ltd., Patna
Physical Status of USSS (2011-12)
S.N. | Group No. | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Retrender | Tender Process | Physical Status | [9 empty] | Remarks | Session
[10 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USSS-26 (A) | Patna East | ukyUnk |  | 1 | Middle School, Basuan | No bidder | 1 | [11 empty] | Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
2 | USSS-26 (B) | Patna East | ukyUnk |  | 2 | Middle School, Malikpur | DHARMENDRA KUMAR 9771493663 |  |  | 1 | [9 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
3 | USSS-26 (C) | Patna East | ukyUnk |  | 3 | Middle School, Mohaddinpur | ANJANI KUMAR. 7033094100, 9204611556 |  |  | 1 | [9 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
4 | USSS-26 (D) | Patna East | ukyUnk |  | 4 | Middle School, Jagdishpur Tayari | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 |  |  |  | 1 | [8 empty] | E/W | 2011-12
5 | USSS-26 (E) | Patna East | ukyUnk |  | 5 | Middle School, Puraini | DHARMENDRA KUMAR 9771493663 |  |  | 1 | [9 empty] | LOA Issue. Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-578 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
6 | USSS-26 (F) | Patna East | ukyUnk |  | 6 | Middle School, Lodipur | Tender Process |  | 1 | [10 empty] | Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-577 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
7 | USSS-27 (A) | Patna East | iVuk |  | 1 | Middle School, Diwra | SRI SACHCHIDA NAND SINGH 9631260151 |  |  |  | 1 | [8 empty] | E/W start (Place को लेकर स्थानीय लोगों द्वारा Dispute) | 2011-12
8 | USSS-27 (B) | Patna East | iVuk |  | 2 | Middle School, Samstichak | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 |  |  |  |  | 1 | [7 empty] | Fondation PCC | 2011-12
9 | USSS-27 (C) | Patna East | iVuk |  | 3 | Middle School, Pirbarhouna | RANA CONSTRUCTION 9334104328 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
10 | USSS-27 (D) | Patna East | iVuk |  | 4 | Middle School, Gangachak | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
11 | USSS-28-1 | Patna East | iVuk |  | 1 | Middle School, Karai | Shilendra kumar |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-582 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
12 | USSS-29-1 | Patna East | Hkkstiqj | Barhara | 1 | Govt. Middle School, Kudariya Parshurampur | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
13 | USSS-29-2 | Patna East | Hkkstiqj | Barhara | 2 | Upgraded Middle School, Paiga | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
14 | USSS-29-3 | Patna East | Hkkstiqj | Ara | 3 | Upgraded Middle School, Barouli | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
15 | USSS-29-4 | Patna East | Hkkstiqj | Ara | 4 | Middle School, Barka Dumra | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
16 | USSS-29-5 | Patna East | Hkkstiqj | Garahni | 5 | Upgraded Middle School, Dadiyabag | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
17 | USSS-29-6 | Patna East | Hkkstiqj | Koielwar | 6 | Upgraded Middle School, Bhoparpur | Tender Process |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-584 /20.11.16 द्वारा अनुरोध किया गया. 46/2013-19 | 2011-12
18 | USSS-30-1 | Patna East | Hkkstiqj | Tarari | 1 | Middle School, Sara | Narendra kumar |  |  |  |  | 1 | [7 empty] | E/W | 2011-12
19 | USSS-30-2 | Patna East | Hkkstiqj | Tarari | 2 | Middle School, Bhakura | Narendra kumar |  |  |  |  | 1 | [7 empty] | E/w | 2011-12
20 | USSS-30-3 | Patna East | Hkkstiqj | Pero | 3 | Middle School, Dhanpura | Narendra kumar |  |  |  |  | 1 | [7 empty] | E/w | 2011-12
21 | USSS-30-4 | Patna East | Hkkstiqj | Sahar | 4 | Middle School, Perhap | Narendra kumar |  |  | 1 | [9 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
22 | USSS-30-5 | Patna East | Hkkstiqj | Sahar | 5 | Middle School, Nonuar | Narendra kumar |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-580 /20.11.16 तथा DEO से पत्रांक 661 दिनांक 24.12.16 द्वारा अनुरोध किया गया है | 2011-12
23 | USSS-30-6 | Patna East | Hkkstiqj | Sahar | 6 | Middle School, Purhara | Tender Process | 1 | [11 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
24 | USSS-31 (A) | Patna West | बक्‍सर | ब्रहम्‍पुर | 1 | Middle School, Bhadwar | Sanjay Kumar Tiwary |  |  |  |  | 1 | [8 empty] | 2011-12
25 | USSS-31 (B) | Patna West | बक्‍सर | ब्रहम्‍पुर | 2 | Girl Middle School, Akrasi | Satyam Enterprises |  |  | 1 | [9 empty] | LOA Issue. Low land about 4'. | 2011-12
26 | USSS-32-1 | Patna West | भभुआ कैमूर | चैनपुर | 1 | Middle School, Dhardihan | KRISHNA | [10 empty] | 1 |  |  | 2011-12
27 | USSS-32-2 | Patna West | भभुआ कैमूर | चॉंद | 2 | Upgraded Middle School, Chouri | KRISHNA |  |  | 1 | [9 empty] | Encrochment | 2011-12
28 | USSS-32-3 | Patna West | भभुआ कैमूर | भगवानपुर | 3 | Middle School, Dadar | KRISHNA | [11 empty] | 1 | Handover | 2011-12
29 | USSS-32-4 | Patna West | भभुआ कैमूर | रामपुर | 4 | Middle School, Lohandi | KRISHNA | [10 empty] | 1 |  |  | 2011-12
30 | USSS-32-5 | Patna West | भभुआ कैमूर | मोहनियॉं | 5 | Middle School, Badhani | KRISHNA | [9 empty] | 1 |  |  |  | 2011-12
31 | USSS-33 (A) | Patna West | रोहतास | दावत | 1 | Middle School, Parmdiha | RAJENDRA SINGH 9430226175 |  |  |  |  | 1 | [8 empty] | 2011-12
32 | USSS-33 (B) | Patna West | रोहतास | नोखा | 2 | Middle School, Hathini | ARSA INFRATECH PRIVATE LIMITED 9308676177 |  |  | 1 | [9 empty] | LOA Issue. Land not available. | 2011-12
33 | USSS-33 (C) | Patna West | रोहतास | काराकाट | 3 | Middle School, Itdhiyan | A B CONSTRUCTION 7250583221 | [5 empty] | 1 | [6 empty] | LOA Issue | 2011-12
34 | USSS-34-1 | Patna West | रोहतास | अकोढ़ीगोला | 1 | Middle School, Gobardhanpur | SHALINI SINGH | [10 empty] | 1 |  |  | 2011-12
35 | USSS-34-2 | Patna West | रोहतास | डिहरी | 2 | Middle School, Tandwa | SHALINI SINGH | [11 empty] | 1 |  | 2011-12
36 | USSS-34-3 | Patna West | रोहतास | काराकाट | 3 | Middle School, Danwar | SHALINI SINGH | [11 empty] | 1 |  | 2011-12
37 | USSS-35 (A) | Patna West | रोहतास | करहगर | 1 | Upgraded Middle School, Rehari | ANIL RAY 9507466444 |  |  |  |  | 1 | [8 empty] | 2011-12
38 | USSS-35 (B) | Patna West | रोहतास | रोहतास | 2 | Middle School, Majhiyawan | UDAY KUMAR 9955691188 |  |  | 1 | [9 empty] | LOA Issue. Less land and dispute | 2011-12
39 | USSS-35-3 | Patna West | रोहतास |  | 3 | Middle School, Ghordihi | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
40 | USSS-36 (A) | Magadh | tgkukckn |  | 1 | Middle School, Ahiyasa | PRAVEEN KUMAR 7033712900 |  |  |  | 1 | [9 empty] | 2011-12
41 | USSS-36 (B) | Magadh | tgkukckn |  | 2 | Middle School,Sewnon | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
42 | USSS-36 (C) | Magadh | tgkukckn |  | 3 | Middle School, Dewra | PRAVEEN KUMAR 7033712900 |  |  |  | 1 | [9 empty] | 2011-12
43 | USSS-37 (A) | Magadh | vkSjaaxkckn |  | 1 | Middle School, Kusumbasdiha | DHANANJAY KUMAR SINGH 9931845497 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
44 | USSS-37 (B) | Magadh | vkSjaaxkckn |  | 2 | Middle School, Pandu | DHANANJAY KUMAR SINGH 9931845497 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
45 | USSS-38-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Gamharia | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land | 2011-12
46 | USSS-38-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School,Sondiha | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [8 empty] | 2011-12
47 | USSS-38-3 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Raslpur | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land | 2011-12
48 | USSS-39-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Chourahi | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land | 2011-12
49 | USSS-39-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Sonbarsa | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land | 2011-12
50 | USSS-39-3 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Dandwan | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land | 2011-12
51 | USSS-40 (A) | Magadh | vkSjaaxkckn |  | 1 | Middle School, Meh | MANOJ SINGH, 9939822131, 7033944511 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
52 | USSS-40 (B) | Magadh | vkSjaaxkckn |  | 2 | Middle School, Tamoli | MANOJ SINGH, 9939822131, 7033944511 |  |  |  | 1 | [9 empty] | 2011-12
53 | USSS-41 (A) | Magadh | x;k |  | 1 | Middle School, Shyamnagar Nima | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
54 | USSS-41 (B) | Magadh | x;k |  | 2 | Middle School, Khajuria | NAGENDRA SINGH 9631326479 |  |  |  | 1 | [9 empty] | 2011-12
55 | USSS-41 (C) | Magadh | x;k |  | 3 | Middle School, Parsawan Khurd | SURENDRA KUMAR 9128027943 |  |  |  | 1 | [9 empty] | 2011-12
56 | USSS-41 (D) | Magadh | x;k |  | 4 | Middle School, Belauti | SANJAY KUMAR SINGH 9973456006 |  |  |  | 1 | [9 empty] | 2011-12
57 | USSS-41 (E) | Magadh | x;k |  | 5 | Middle School,Bindhua | MRITUNJAY KUMAR SINGH 9097394660 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
58 | USSS-42 (A) | Magadh | x;k |  | 1 | Middle School, Sondiha | SANJAY KUMAR SINGH 9973456006 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
59 | USSS-42 (B) | Magadh | x;k |  | 2 | Middle School, Angara | NARENDRA YADAB 99315315191 |  |  | 1 | [10 empty] | 2011-12
60 | USSS-42 (C) | Magadh | x;k |  | 3 | Middle School, Punakalan | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
61 | USSS-42 (D) | Magadh | x;k |  | 4 | Middle School, Noni | RAVIN KUMAR 8797253525 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
62 | USSS-43-1 | Magadh | x;k |  | 1 | Upgraded Middle School, Pater | Mithlesh Kumar Singh, 9931471924 | [10 empty] | 1 |  |  | 2011-12
63 | USSS-43-2 | Magadh | x;k |  | 2 | Middle School, Bitho | Mithlesh Kumar Singh, 9931471924 |  |  | 1 | [9 empty] | Local Dispute | 2011-12
64 | USSS-44 (A) | Magadh | uoknk |  | 1 | Middle School, Bardhauna | RAJNISH VATS 8051666426 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
65 | USSS-44 (B) | Magadh | uoknk |  | 2 | Upgraded Middle School, Puraini | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
66 | USSS-44 (C) | Magadh | uoknk |  | 3 | Middle School, Kalound | SUDHIR KUMAR 9430411061 |  |  |  |  | 1 | [8 empty] | 2011-12
67 | USSS-44 (D) | Magadh | uoknk |  | 4 | Middle School, Paingari | SUDHIR KUMAR 9430411061 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
68 | USSS-44 (E) | Magadh | uoknk |  | 5 | Upgraded Middle School, Bhatta | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
69 | USSS-17 (A) | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kishanpur | Dayanand Singh |  |  | 1 | [9 empty] | LOA Issue | 2011-12
70 | USSS-17 (B) | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Tarchha | Retender |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
71 | USSS-18-1 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Ghanshyamchak | Retender |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
72 | USSS-19-1 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kalgiganj | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
73 | USSS-19-2 | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Dayalpur | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
74 | USSS-19-3 | Bhagalpur | Hkkxyiqj |  | 3 | Middle School Siya | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
75 | USSS-19-4 | Bhagalpur | Hkkxyiqj |  | 4 | Middle School Kishunichak | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
76 | USSS-20 (A) | Bhagalpur | ckadk |  | 1 | Middle School kairi | Kundan Kumar Singh |  |  | 1 | [9 empty] | LOA Issue | 2011-12
77 | USSS-20 (B) | Bhagalpur | ckadk |  | 2 | Middle School Bank | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
78 | USSS-20 (C) | Bhagalpur | ckadk |  | 3 | Middle School Pathdda | Lalan Kumar |  |  | 1 | [9 empty] | LOA Issue | 2011-12
79 | USSS-21 (A) | Munger | ewaxsj |  | 1 | Middle School Harinmar Bishunpur | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
80 | USSS-21 (B) | Munger | ewaxsj |  | 2 | Middle School Manik Mandal Tola | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
81 | USSS-21 (C) | Munger | ewaxsj |  | 3 | Middle School Kalyanpur | ANIL KUMAR SINGH 9570904951 |  |  | 1 | [10 empty] | 2011-12
82 | USSS-21 (D) | Munger | ewaxsj |  | 4 | Middle School Teghara | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
83 | USSS-21 (E) | Munger | ewaxsj |  | 5 | Middle School Dhudhaladih | No bidder | 1 | [11 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
84 | USSS-22 (A) | Munger | ewaxsj |  | 1 | Middle School Ramcharit Maidan | DIGBIJAY KUMAR 8084371876 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
85 | USSS-22 (B) | Munger | ewaxsj |  | 2 | Middle School Madhura / Katiyari | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
86 | USSS-22 (C) | Munger | ewaxsj |  | 3 | Middle School, Dhobai | Retender | 1 | [11 empty] | Retender | 2011-12
87 | USSS-22 (D) | Munger | ewaxsj |  | 4 | Middle School Nabgoi | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
88 | USSS-23-1 | Munger | y[khljk; |  | 1 | Middle School, Bahachha | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
89 | USSS-23-2 | Munger | y[khljk; |  | 2 | Middle School Tarhari | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
90 | USSS-23-3 | Munger | y[khljk; |  | 3 | Middle School Nongarh | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
91 | USSS-23-4 | Munger | y[khljk; |  | 4 | Upgraded Middle School Surari | SUGEET KUMAR,9504681342 | [7 empty] | 1 | [5 empty] | 2011-12
92 | USSS-24 (A) | Munger | y[khljk; |  | 1 | Upgraded Middle School Bihraura | MS BALRAM KUMAR 9430065800 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
93 | USSS-24 (B) | Munger | y[khljk; |  | 2 | Middle School Pokhrama | SAI HIGHWAY AND BUILDERS PVT LTD 9771455967 |  |  |  |  | 1 | [8 empty] | 2011-12
94 | USSS-24 (C) | Munger | y[khljk; |  | 3 | Upgraded Middle School Dhoni Kundi | MONEY CONSTRUCTION PRIVATE LIMITED 9386596373 |  |  |  |  | 1 | [8 empty] | 2011-12
95 | USSS-25-1 | Munger | 'ks[kiqjk |  | 1 | Middle School, Akrama | Epitome Construction Pvt Ltd,8935825344 | [10 empty] | 1 |  |  | 2011-12
96 | USSS-25-2 | Munger | 'ks[kiqjk |  | 2 | Upgraded Middle School, Diha | Epitome Construction Pvt Ltd,8935825344 | [7 empty] | 1 |  |  |  |  | WORK STOPPED BY DIST ADMN (upto FF sill lv) | 2011-12
97 | USSS-25-3 | Munger | 'ks[kiqjk |  | 3 | Middle School, Kutout | Epitome Construction Pvt Ltd,8935825344 | [11 empty] | 1 |  | 2011-12
98 | USSS-45 (A) | Munger | tewbZ |  | 1 | Upgraded Middle School, Harla | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
99 | USSS-45 (B) | Munger | tewbZ |  | 2 | Middle School, Kairakado | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
100 | USSS-45 (C) | Munger | tewbZ |  | 3 | Middle School, Shobhakhan | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
101 | USSS-45 (D) | Munger | tewbZ |  | 4 | Middle School, Abgila Chourasa | NATHUNI YADAV 9931012527 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
102 | USSS-47 (A) | Munger | Munger | Birpur | 1 | Middle School Parra | MS KUMAR TRADING COMPANY 9431276100 |  |  | 1 | [10 empty] | 2011-12
103 | USSS-47 (B) | Munger | Munger | Bakhari | 2 | Middle School Lauchhe | No bidder | 1 | [11 empty] | NIT-46 (2015-16). Retender | 2011-12
104 | USSS-47 (C) | Munger | Munger | Birpur | 3 | Middle School Kharmauli | MS BALRAM KUMAR 9430065800 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
105 | USSS-47 (D) | Munger | Munger | Sahebpur Kamal | 4 | Middle School Hira Tol | RAM NIWAS KUMAR 9431067357 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
106 | USSS-47 (E) | Munger | Munger | Mansurchak | 5 | Middle School Makdhampur | No bidder | 1 | [11 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
107 | USSS-48-1 | Munger | Munger | Begusarai | 1 | Middle School Akaha | RAM NARESH SHARMA 9430088029 |  |  |  | 1 | [9 empty] | 2011-12
108 | USSS-48-2 | Munger | Munger | Begusarai | 2 | Middle School Bhitsari | Tender Process | 1 | [11 empty] | Retender | 2011-12
109 | USSS-10 (A) | Kosi | lgjlk |  | 1 | Middle School Dhamsaina | JIWAN LAXMI CONSTRUCTION PVT LTD 9431089386 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
110 | USSS-6 (A) | Purnea | vjfj;k |  | 1 | Middle School Mangalwar Chariya | Shining Madhusudan Construction |  |  | 1 | [9 empty] | LOA Issue | 2011-12
111 | USSS-6 (B) | Purnea | vjfj;k |  | 2 | Middle School Maldwar East | WALKS n WALKS MANAGE PRIVATE LIMITED 8434514666 |  |  | 1 | [9 empty] | NIT-46 (2015-16) | 2011-12
112 | USSS-7-1 | Purnea | fd'kuxat |  | 1 | Middle School Daula | BIRENDRA KUMAR SINGH,9473440405 |  |  | 1 | [9 empty] | H.M. not giving permission to construct the building | 2011-12
113 | USSS-8 (A) | Purnea | iwf.kZ;k¡ |  | 1 | Middle School Rupauli | Walks n Walks Manage Pvt. Ltd. |  |  | 1 | [9 empty] | LOA Issue | 2011-12
114 | USSS-8 (B) | Purnea | iwf.kZ;k¡ |  | 2 | Middle School Rampur Tilak East | Tender Process |  | 1 | [10 empty] | Double Scheme | 2011-12
115 | USSS-8 (C) | Purnea | iwf.kZ;k¡ |  | 3 | Middle School ,Mahendra Nagar Diyara | Tender Process | 1 | [11 empty] | Retender | 2011-12
116 | USSS-9-1 | Purnea | dfVgkj |  | 1 | Middle School Belwa | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2011-12
117 | USSS-9-2 | Purnea | dfVgkj |  | 2 | Middle School Kharsauta | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 |  |  |  |  | FF sill level | 2011-12
118 | USSS-9-3 | Purnea | dfVgkj |  | 3 | Middle School Kalyan Gaon | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | 2011-12
119 | USSS-9-4 | Purnea | dfVgkj |  | 4 | Middle School Rampur | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  | 2011-12
120 | USSS-4 (A) | Tirhut East | lhrke<+h |  | 1 | Middle School Sutihara | Shashi Kant Singh |  |  | 1 | [9 empty] | LOA Issue | 2011-12
121 | USSS-4 (B) | Tirhut East | lhrke<+h |  | 2 | Middle School Bhantawari | Shashi Kant Singh 9771952932 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
122 | USSS-4 (C) | Tirhut East | lhrke<+h |  | 3 | Middle School Rajwara | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
123 | USSS-12-1 | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bariyarpur | S R CONSTRUCTIONS PVT LTD, 7739441850 | [10 empty] | 1 |  | Painting sanitary plumbing | 2011-12
124 | USSS-12-2 | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Dhabauli | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | Land Dispute | 2011-12
125 | USSS-12-3 | Tirhut East | eqt¶Qjiqj |  | 3 | Middle School Lakhanpur | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | Land Dispute | 2011-12
126 | USSS-13 (A) | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bhatauna | VIJAY KUMAR SHAHI 9507385720 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
127 | USSS-13 (B) | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Sirkohiya | DEVENDRA KUMAR 9708256685 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
128 | USSS-15 (A) | Tirhut East | oS'kkyh |  | 1 | Upgraded Middle School Panapur Silaut | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
129 | USSS-15 (B) | Tirhut East | oS'kkyh |  | 2 | Upgraded Middle School Totha | SACHIN CONSTRUCTION |  |  | 1 | [9 empty] | LOA Issue | 2011-12
130 | USSS-15 (C) | Tirhut East | oS'kkyh |  | 3 | Middle School Shital Bhakurhar | GAJENDRA PATEL 9708793426 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
131 | USSS-1 (A) | Tirhut West | if'pe pEikj.k |  | 1 | Govt. Middle School Kumhiya | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
132 | USSS-1 (B) | Tirhut West | if'pe pEikj.k |  | 2 | Middle School Panchgawa | SHARDA CHANDEL CONTRACT PVT 9792083771 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
133 | USSS-1 (C) | Tirhut West | if'pe pEikj.k |  | 3 | Middle School Donwar | MOHD SHAFIQUE 9939886786 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
134 | USSS-1 (D) | Tirhut West | if'pe pEikj.k |  | 4 | Ugraded middle school malahi tola | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
135 | USSS-2-1 | Tirhut West | iwohZ pEikj.k |  | 1 | Middle School Mali | ASIANA CONSTRACT PVT LTD, 9431088485 |  |  | 1 | [9 empty] | Not Start | 2011-12
136 | USSS-2-2 | Tirhut West | iwohZ pEikj.k |  | 2 | Middle School Chand parsa | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  | 2011-12
137 | USSS-2-3 | Tirhut West | iwohZ pEikj.k |  | 3 | Middle School Sitalpur | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  | 2011-12
138 | USSS-3 (A) | Tirhut West | f'kogj |  | 1 | Middle School Dhankaul | SHEEL CONSTRUCTION 9430081574 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
139 | USSS-3 (B) | Tirhut West | f'kogj |  | 2 | Middle School Narayanpur | Shashi Kant Singh 9771952932 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
140 | USSS-3 (C) | Tirhut West | f'kogj |  | 3 | Middle School Khairadarp | Shashi Kant Singh 9771952932 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
141 | USSS-5-1 | Darbhanga | e/kqcuh |  | 1 | Govt. Middle School Rudrapur | Kamlesh Kumar 934808205 | [11 empty] | 1 | inugurated | 2011-12
142 | USSS-5-2 | Darbhanga | e/kqcuh |  | 2 | Govt. Middle School Bhatra Ghat | Kamlesh Kumar 934808205 | [10 empty] | 1 |  |  | 2011-12
143 | USSS-11 (A) | Darbhanga | njHkaxk |  | 1 | Upgraded Middle School Raj kharwar | ASHOK KUMAR YADAV 9386050569 | 1 | [11 empty] | Tender Process | 2011-12
144 | USSS-11 (B) | Darbhanga | njHkaxk |  | 2 | Upgraded Middle School Tilkeshwar Sthan | ASHOK KUMAR YADAV 9386050569 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
145 | USSS-11 (C) | Darbhanga | njHkaxk |  | 3 | Upgraded Middle School Raipur | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 |  |  | 1 | [9 empty] | LOA Issue | 2011-12
146 | USSS-16-1 | Darbhanga | leLrhiqj |  | 1 | Middle School Isar Tola | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
147 | USSS-14-1 | Saran | lhoku |  | 1 | Middle School Sahadulpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [9 empty] | 1 |  |  |  | 2011-12
148 | USSS-14-2 | Saran | lhoku |  | 2 | Middle School Gamiyar | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land not available | 2011-12
149 | USSS-14-3 | Saran | lhoku |  | 3 | Middle School Daraunda | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  | 2011-12
150 | USSS-14-4 | Saran | lhoku |  | 4 | Middle School, Baluya | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  | 2011-12
151 | USSS-14-5 | Saran | lhoku |  | 5 | Middle School Barka Manjha | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  | 2011-12
152 | USSS-46-1 | Saran | lhoku |  | 1 | Middle School Sikatiya | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [10 empty] | 2011-12
153 | USSS-46-2 | Saran | lhoku |  | 2 | Middle School Kilpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [8 empty] | 1 |  |  |  |  | 2011-12
154 | USSS-46-3 | Saran | lhoku |  | 3 | Middle School Pratapur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  | 2011-12
155 | USSS-46-4 | Saran | lhoku |  | 4 | Middle School Shivpur Sakra | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land Problem | 2011-12
156 | USSS-46-5 | Saran | lhoku |  | 5 | Middle School Balaipur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  | 2011-12
Total No. of USSS (2011-12) |  |  |  |  | 156 |  |  | 10 | 21 | 69 | 9 | 11 | 1 | 0 | 3 | 1 | 3 | 16 | 12
[6 empty] | USSS 2011-12 |  |  |  |  | 9 | 11 | 1 | 0 | 3 | 1 | 3 | 16 | 12
[6 empty] | USSS 2013-14 |  |  |  |  | 3 | 2 | 5 | 2 | 15 | 6 | 14 | 66 | 60
[11 empty] | 12 | 13 | 6 | 2 | 18 | 7 | 17 | 82 | 72
Note on H114: Cancel