## Summary
BSEIDC, PATNA
Progress report for the construction of USS school building (2009-10) & State Funded | [19 empty] | Date:-31.01.2014
S.N. | Division | Name & Designation |  | Total USS |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[14 empty] | LL | RL | LL | RL | [6 empty] | chek
1 | Patna | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | Central Funded (Fin. Year 2009-2010) | 14 | 53 | 2482.11 | 14 | 53 | 2482.11 |  | 0 | 0 | 1 | 1 | 5 | 1 | 1 | 3 | 9 | 12 | 32 | 1397.16 |  | 0
|  | Enarch-JV-PIDC (A.K.Dutta -9470353415 & Prakash Ji-9431018537) | State Funded | 2 | 2 | 89.01 | 2 | 2 | 89.01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 18.21 |  | 0
2 | Magadh | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | Central Funded (Fin. Year 2009-2010) | 10 | 35 | 1539.29 | 10 | 35 | 1539.29 |  | 0 | 2 | 1 | 0 | 6 | 2 | 0 | 9 | 3 | 20 | 12 | 657.15 |  | 0
|  | Enarch-JV-PIDC (A.K.Dutta -9470353415 & Prakash Ji-9431018537) | State Funded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3 | Bhagalpur | Ranvijay Kr. Sinha (9934961293) E.E. BSEIDC, Div.- Bhagalpur | Central Funded (Fin. Year 2009-2010) | 5 | 21 | 970.3 | 5 | 21 | 970.3 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 5 | 15 | 619.53 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | State Funded | 3 | 3 | 134.53 | 3 | 3 | 134.53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 22.16 |  | 0
4 | Munger | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | Central Funded (Fin. Year 2009-2010) | 8 | 24 | 1107.98 | 8 | 24 | 1107.98 |  | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 2 | 6 | 16 | 746.95 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | State Funded | 1 | 1 | 45.5 | 1 | 1 | 45.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
5 | Kosi | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | Central Funded (Fin. Year 2009-2010) | 6 | 21 | 1034.88 | 6 | 21 | 1034.88 |  | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 9 | 1 | 16 | 4 | 0 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | State Funded | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
6 | Purnea | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | Central Funded (Fin. Year 2009-2010) | 10 | 38 | 1843.1 | 10 | 38 | 1843.1 |  | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 15 | 8 | 20 | 10 | 813.4 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | State Funded | 7 | 30 | 1489.81 | 7 | 30 | 1489.81 |  | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 6 | 8 | 11 | 11 | 585.51 |  | 0
7 | Tirhut | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | Central Funded (Fin. Year 2009-2010) | 18 | 69 | 3291.68 | 18 | 69 | 3291.68 |  | 1 | 2 | 3 | 3 | 11 | 0 | 4 | 8 | 5 | 32 | 32 | 1760.12 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | State Funded | 3 | 4 | 188.12 | 3 | 4 | 188.12 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 37.06 |  | 0
8 | Darbhanga | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Darbhanga | Central Funded (Fin. Year 2009-2010) | 10 | 36 | 1724.29 | 10 | 36 | 1724.29 |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 3 | 2 | 7 | 27 | 1317.17 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | State Funded | 2 | 2 | 97.99 | 1 | 1 | 97.99 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
9 | Saran | Pramod Kumar (9955128483) E.E. BSEIDC, Div.- Saran | Central Funded (Fin. Year 2009-2010) | 6 | 26 | 1208.06 | 6 | 26 | 1208.06 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 4 | 0 | 9 | 17 | 819.45 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | State Funded | 3 | 3 | 139.09 | 3 | 3 | 139.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 6.63 |  | 0 | 25
Total (Fin. Year 2009-2010) |  |  |  | 87 | 323 | 15201.69 | 87 | 323 | 15201.69 | 0 | 2 | 7 | 8 | 5 | 34 | 4 | 11 | 56 | 31 | 127 | 165 | 8130.93 |  | 0 | 113
Total (STATE FUNDED) |  |  |  | 21 | 45 | 2184.05 | 20 | 44 | 2184.05 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 2 | 7 | 17 | 15 | 12 | 669.57 |  | 0

## Patna
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Patna | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Satish Prasad (8987263065) , AE :- S. Tiwari (9431495949), AE :- Atul Kr. Varanwal (9835658494) | [13 empty] | Name & Contact no. of PMC :- Enarch-JV-PIDC (A.K.Dutta- 9470353415/ Prakash-9431018537)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-1 | ukyUnk | p.Mh | 1 | eŒfoŒlwedk 9931607862 | M/S Uma Shankar & Co. Naya Gaon, Gulzarbagh Patna. 9162544014 (14.12.2011) | 187.41 |  | 14.12.2011 | 1 Year | [8 empty] | 1 | 159.9
|  |  | bLykeiqj | 2 | eŒfoŒenkjxat 9631262679 | [13 empty] | 1 |  | 8th A/C Bill paid
|  |  | fgylk | 3 | eŒfoŒvdcjiqj 9470085363 | [13 empty] | 1
|  |  | fcgkj 'kjhQ | 4 | eŒfoŒflaxFkq 9204881769 | [13 empty] | 1
2 | USS-2 | ukyUnk | fxfj;d | 1 | eŒfoŒblqvk 9934451313 | Roy Engineers Flat no. 103, First floor, Rajendra Enclave, Exhibition Road, Patna- 800001. 9431011395 (13.12.2011) | 230.12 | 1 | 13.12.2011 | 1 Year | [9 empty] | 114.92 | sufficient land not available
|  |  | drjhljk; | 2 | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | [13 empty] | 1
|  |  | jktxhj | 3 | eŒfoŒygqvkj 9798642205@9504394778 | [13 empty] | 1 |  | 8th A/C Bill paid
|  |  | flyko | 4 | eŒfoŒujgj fcxgk 8002186727 | [13 empty] | 1
|  |  | uwjljk; | 5 | eŒfoŒdqUnh 9798241195 |  |  | 1 | [12 empty] | soil test done near old building, now HM not intrested to demolis this old building & want to const this proposed building in aprox. 8-10 feet low & water logged land. This land is situated outside of presrent school campus.
3 | USS-3 | iVuk | ck<+ | 1 | eŒfoŒngkSj 8804003367 | Bihar Sharif Construction Pvt. Ltd., Dhaneshwar Ghat, Biharr Sharif, Nalanda-803101. 9308021620 (26.11.2011) | 245.37 | 1 | 26.12.2011 | 1 Year | [9 empty] | 139.76 | Project Director instruct to DEO to arrange land with corporation of local public
|  |  | ck<+ | 2 | eŒfoŒeqckjdiqj 9631978359 | [13 empty] | 1
|  |  | Qrqgk¡ | 3 | eŒfoŒMqejh 8521893444 | [13 empty] | 1 |  | 9th A/C Bill paid
|  |  | Qrqgk¡ | 4 | mRØŒeŒfoŒip:f[k;k 9801459905 | [12 empty] | 1
|  |  | [kq'k:iqj | 5 | mRØŒeŒfoŒfueZyhpd 9097610852 |  |  | 1 | [12 empty] | sufficient land not available
4 | USS-4 | iVuk | nkukiqj | 1 | eŒfoŒvdhyiqj 9835490244 | M/S Vivek and co.,B/M/23, Bahadurpur Housing colony, Patna. 9430955974/ 8757956582 (15.12.2011) | 147.16 |  | 15.12.2011 | 1 Year | [8 empty] | 1 | 85.48
|  |  | ukScriqj | 2 | eŒfoŒvgqvkjk 9939680617 | [13 empty] | 1 |  | 6th A/C Bill paid
|  |  | ikyhxat | 3 | eŒfoŒHksM+gfj;k 9199997796 |  |  | 1 | [12 empty] | dispute
5 | USS-5 | iVuk | /ku:vk | 1 | eŒfoŒdkslqr 9973270948@9974270948 | M/S Patliputra Construction Dhanarua, Patna. 9934417366 (26.12.2011) | 195.49 |  | 26.12.2011 | 1 Year | [8 empty] | 1 | 104.82
|  |  | elkS<+h | 2 | eŒfoŒNkrk 8084994281 | [13 empty] | 1
|  |  | iquiqu | 3 | eŒfoŒdY;k.kiqj 9507549063 |  |  | 1 | [12 empty] | 8th A/C Bill paid
|  |  | lairpd | 4 | eŒfoŒyadk dNqvkjk 9162137790 | [13 empty] | 1
6 | USS-6 | Hkkstiqj | ihjks | 1 | eŒfoŒrkj 8969213005 | M/S B K Enterprises Vill- Dhanupra, Po- Ara PS-Ara Town, Dist- Bhojpur 9431052084 (14.03.2012) | 139.51 |  | 14.3.2012 | 1 Year | [6 empty] | 1 |  |  | 25.95
|  |  | ihjks | 2 | mRØŒeŒfoŒ nsopUnk 9386992853 | [9 empty] | 1 | [5 empty] | 5th A/C Bill paid
|  |  | rjkjh | 3 | eŒfoŒ[kqVgk¡ 7631530412 |  |  | 1 | [12 empty] | low land available
7 | USS-7 | Hkkstiqj | fcfg;k¡ | 1 | eŒfoŒ:nzuxj 9308401427 | M/S B K Enterprises Vill- Dhanupra, Po- Ara PS-Ara Town, Dist- Bhojpur 9431052084 (14.03.2012) | 141.09 |  | 14.30.2012 | 1 Year | [8 empty] | 1 | 36.79
|  |  | txnh'kiqj | 2 | eŒfoŒtaxynkok¡ 9931492812 | [9 empty] | 1 | [5 empty] | 6th A/C Bill paid
|  |  | 'kkgiqj | 3 | eŒfoŒykyw Msjk 8873932298@9973022234 | [7 empty] | 1 | [7 empty] | Land not available
8 | USS-8 | Hkkstiqj | vfxvk¡o | 1 | eŒfoŒukjk;.kiqj 9852411014 | M/S B K Enterprises Vill- Dhanupra, Po- Ara PS-Ara Town, Dist- Bhojpur 9431052084 (14.03.2012) | 187.21 |  | 14.3.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 44.85
|  |  | cM+gjk | 2 | eŒfoŒxqaMh 7739111542 | [10 empty] | 1
|  |  | mnoUruxj | 3 | eŒfoŒds'kksiqj cdjh 9771242640 | [8 empty] | 1 | [6 empty] | 5th A/C Bill paid
|  |  | dksbyoj | 4 | mRØŒeŒfoŒ folquiqjk 9334151672 | [12 empty] | 1
9 | USS-9 | cDlj | cDlj | 1 | eŒfoŒd`riqjk 9576622685 | M/s Ramchhabila Rai 9431027154 (09.04.2012) | 187.37 |  | 9.4.2012 | 1 Year | [8 empty] | 1 | 124.23
|  |  | pkSlk | 2 | eŒfoŒcukjiqj 8873946373 | [13 empty] | 1 |  | 7th A/C Bill paid
|  |  | jktiqj | 3 | eŒfoŒjlsu 9006272320 | [13 empty] | 1
|  |  | bVkM+h | 4 | eŒfoŒcSdqUBiqj 9931755863 | [13 empty] | 1
10 | USS-10 | cDlj | Mqejk¡o | 1 | eŒfoŒiqjkuk Hkkstiqj 9771052120 | Jai Mata Di Road Const. Pvt. Ltd.,3/97, LIG Hanuman Nagar, Kankarbagh,Patna-20 9430828486 (13.12.2011) | 186.1 |  | 13.12.2011 | 1 Year |  |  |  |  | 1 |  |  |  |  | 67.89
|  |  | flejh | 2 | eŒfoŒ<+dkbZp 9934519481 | [13 empty] | 1 |  | 7th A/C Bill paid
|  |  | czg~eiqj | 3 | eŒfoŒegqvkj 7250949713 |  |  | 1 | [12 empty] | Sufficient land not available
|  |  | ukokuxj | 4 | eŒfoŒ/kuc[kjk 9771286504 | [9 empty] | 1
11 | USS-11 | dSeqj | dqnjk | 1 | eŒfoŒvojS;k 9973613935 | Ajay kumar Singh, vill- Bare, P.o- Bare, P.S- Bhabua, Kaimur, Bihar. 9934962360 (17.01.2012) | 183.57 |  | 17.1.2012 | 1 Year | [8 empty] | 1 | 155.85
|  |  | eksgfu;k¡ | 2 | eŒfoŒdVjkdyk 9006263731 | [13 empty] | 1
|  |  | jkex<+ | 3 | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | [13 empty] | 1 |  | 8th A/C Bill paid
|  |  | nqxkZorh | 4 | eŒfoŒnqxkZorh 9430340748@9955221828 | [13 empty] | 1
12 | USS-12 | dSeqj | HkHkqvk | 1 | eŒfoŒdqM+klu 9031437647 | Shiv Murat Bind Vill- Bhadaura, Po- Biur PS-Chainpur, Dist- Kaimur 9934204800 (14.12.2011) | 91.1 |  | 14.12.2011 | 1 Year | [8 empty] | 1 | 73.4
|  |  | pSuiqj | 2 | eŒfoŒdasok 9430026932 | [13 empty] | 1 |  | 10th A/C Bill paid
13 | USS-13 | jksgrkl | djxgj | 1 | eŒfoŒrksjuh 9631253327 | Anita Singh,Vill+Po: Nahauna, P.S-sasaram, Mufassil, Dist- Rohatas (Bihar) 9955710222/ 9934848051 (16.01.2012) | 179.49 |  | 16.1.2012 | 1 Year | [7 empty] | 1 |  | 109.84
|  |  | f'kolkxj | 2 | eŒfoŒxMqjk 9771022208 |  |  | 1 | [12 empty] | Foundation work stopped due to local disturbance (in school campus sufficient land available & soil test also done in schl. Campus but some local public want to construct this build. In other land wich is situated out of campus & no aproach road available & about 800 m(aprox.) away from campus
|  |  | lklkjke | 3 | eŒfoŒfldfj;k 9431464894 | [13 empty] | 1 |  | 8th A/C Bill paid
|  |  | dkspl | 4 | eŒfoŒegqvkjh 9661222301 | [13 empty] | 1
14 | USS-14 | jksgrkl | fMgjh | 1 | eŒfoŒxaxkSyh 7352200057 | Bharat Infrastructure,1429 Opposite M-2/10,North S.K. Puri, Boring Road,Patna. 9334125109 (14.12.2011) | 181.12 |  | 14.12.2011 | 1 Year | [8 empty] | 1 | 153.48
|  |  | fnukjk | 2 | eŒfoŒljuk 9771634397 | [13 empty] | 1 |  | 10th A/C Bill paid
|  |  | dkjkdkV | 3 | eŒfoŒeksguiqj 9801296392 | [13 empty] | 1
|  |  | uks[kk | 4 | eŒfoŒ?kksjfMgk 9801894133 | [13 empty] | 1
| Total nos. of school |  |  | 53 |  |  | 2482.11 | 9 |  |  | 0 | 0 | 1 | 1 | 5 | 1 | 1 | 3 | 32 | 1397.16
(B) STATE FUNDED
1 | USS-218 | jksgrkl | fnukjk | 1 | eŒ foŒ fnukjk 8294218392 | Sudarshan Mahto, At- Jagdishpur, Arrah 8092775732 (11.09.2012) | 43.98 | 1 | 11.9.2012 | 10 Month | [10 empty] | Required old building demolision
2 | USS-219 | Hkkstiqj | cjgkjk | 1 | dqnfj;k ij'kqjke eŒ foŒ] | Sudarshan Mahto, At- Jagdishpur, Arrah 8092775732 (11.09.2012) | 45.03 |  | 11.9.2012 | 10 Month | [6 empty] | 1 |  |  | 18.21 | 4th A/C Bill paid
| Total nos. of school |  |  | 2 |  |  | 89.01 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 18.21

## Magadh
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Magadh | [8 empty] | Date:-31.01.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Mallu Singh (9835471249/ 9471211134) | [6 empty] | Name & contact no. of PMC :- Enarch-JV-PIDC (A.K.Dutta- 9470353415 & Prakash ji- 9431018537)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-28 | tgkukckn | tgkukckn | 1 | eŒfoŒveSu 9473327625 | Baijnath Nirman India Pvt. Ltd., East Gandhai Maidan, Jehanabad 9939911835 (06/02/2012) | 171.95 | [11 empty] | 1 | 112.63
|  |  | dkdks | 2 | eŒfoŒHknljk 9006927848 | [13 empty] | 1
|  |  | e[knqeiqj | 3 | eŒfoŒdksgjk 9162155024 | [13 empty] | 1 |  | 7th A/C bill paid
|  |  | jruhQjhniqj | 4 | mRØŒeŒfoŒyk[kkiqj 9934235714 |  |  | 1 | [12 empty] | Disputed (Land not available)
2 | USS-29 | vkSjaxkckn | nso | 1 | eŒfoŒcs<+uh 9631266207 | Anita Singh, Vill.+P.o.-Nahauna, P.S- Sasaram, Mufassil ,Distt.- Rohtas (Sasaram). 9472252400 (14.03.2012) | 177.51 | [10 empty] | 1 |  | 80.71
|  |  | enuiqj | 2 | eŒfoŒfijok¡ 9934340488 | [13 empty] | 1
|  |  | jQhxat | 3 | eŒfoŒ[kjks[kj 9006027690 | [9 empty] | 1 | [5 empty] | 8th A/C bill paid
|  |  | xksg | 4 | eŒfoŒcktkj oekZ 9939868217 | [12 empty] | 1
3 | USS-30 | vkSjaxkckn | vkscjk | 1 | eŒfoŒ'kadjiqj 7739690373 | Baijnath Nirman India Pvt. Ltd., Vill- Dihuri, P.O- Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. 9939911835 (08/06/2012) | 175.18 | [10 empty] | 1 |  | 97.14
|  |  | nkmnuxj | 2 | eŒfoŒteqvkok¡ 9801563600 | [13 empty] | 1 |  | 12 th A/C bill paid
|  |  | nkmnuxj | 3 | eŒfoŒpkSjh 9934434990 | [12 empty] | 1
|  |  | gliqjk | 4 | eŒfoŒdksbyok¡ 9135312996 | [12 empty] | 1
4 | USS-31 | vkSjaxkckn | dqVqEck | 1 | eŒfoŒfjfl;i 9955874942 | Him Shikha constr. Pvt. Ltd. 9546092330/ 9430223194 (16/04/2012) | 132.78 | [11 empty] | 1 | 79.62
|  |  | uohuxj | 2 | eŒfoŒiM+fj;k 9931622753 | [13 empty] | 1 |  | 10 th A/C bill paid
|  |  | ok:.k | 3 | eŒfoŒikSFkq 9471060433 | [10 empty] | 1
5 | USS-32 | x;k | cks/k x;k | 1 | eŒfoŒchjgqr 9934480418 | Waris Buildicon Pvt. Ltd. Waris Kuteer, Lakhibag, Manpur, Gaya 9471091151/ 7277915222 (13.04.2012) | 172.27 | [7 empty] | 1 |  |  |  |  | 96.18
|  |  | uxj | 2 | eŒfoŒpwjh 9199466924 | [13 empty] | 1
|  |  | osykxat | 3 | mRØŒeŒfoŒve>j 9931835374 | [12 empty] | 1 |  |  | 9th A/C bill paid
|  |  | fVdkjh | 4 | eŒfoŒrkik Qrsgiqj 9430070517 | [12 empty] | 1
6 | USS-33 | x;k | MksHkh | 1 | eŒfoŒihjklhu 9473140628 | Mithlesh Kumar Singh, Moh- Janakpur, P.O- Buniyadganj, Distt.- Gaya 9931471924 (08/02/2012) | 173.39 | [10 empty] | 1 |  | 89.19
|  |  | dksp | 2 | eŒfoŒfnX?kh 9576852929 | [13 empty] | 1 |  | 7th A/C bill paid
|  |  | f[ktjljk; | 3 | eŒfoŒvkneiqj 9771084118 | [9 empty] | 1
|  |  | cthjxat | 4 | eŒfoŒikys 9955418354 | [12 empty] | 1
7 | USS-34 A | x;k | ckjkpV~Vh | 1 | mRØŒeŒfoŒ/kuxbZ 9931313425 | Er. Ashok Kr. Singh | 129.984 | 1 | [12 empty] | aproach road unavailable
|  |  | Qrsgiqj | 2 | eŒfoŒckiwxzke 9934840966 | [10 empty] | 1
|  |  | eksguiqj | 3 | eŒfoŒvedksyk 9955837262 | [7 empty] | 1
8 | USS-34 B |  | xq:vk | 1 | eŒfoŒpk¡lh 9006129640 | Sanju Kumari | 86.656 |  |  |  |  | 1
|  |  | bekexat | 2 | mRØŒeŒfoŒ]dksBh 9931625800 | [6 empty] | 1
9 | USS-35 | uoknk | uoknk | 1 | eŒfoŒiVok ljk; 9006212577 | M/S Dhanpat Prasad Linepar Mirzapur, Nawada. 9931555514 (09/04/2012) | 182.85 | [7 empty] | 1 |  |  |  |  | 40.44
|  |  | idjhojkok¡ | 2 | eŒfoŒxqyuh 995563436 | [13 empty] | 1
|  |  | jksg 1 | 3 | mRØŒeŒfoŒf'k[kjiqj 9661237533 | [9 empty] | 1 | [5 empty] | 7th A/C bill paid
|  |  | okfjlyhxat | 4 | mRØŒeŒfoŒelwnk 9708007113 | [9 empty] | 1
10 | USS-36 | uoknk | vdcjiqj | 1 | eŒfoŒrs;kj | Sujay Bhan Singh Par Nawada, Bundelkhand Distt- Nawada 9431257115/ 8002569999 (14/12/2011) | 136.72 | 1 | [11 empty] | 61.24 | aproach road unavailable
|  |  | jtkSyh | 2 | mRØŒeŒfoŒ]ckjkVk¡M loS;k | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | fljnyk | 3 | eŒfoŒlka< 9771960601 | [13 empty] | 1
|  | Total nos. of school |  | 35 |  |  | 1539.29 | 3 |  |  | 0 | 2 | 1 | 0 | 6 | 2 | 0 | 9 | 12 | 657.15

## Bhagalpur
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Bhagalpur | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar (9431487994) | [6 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-15 | Hkkxyiqj | 'kkgdqaM | 1 | eŒfoŒfnun;kyiqj 8809672417 | D P Maheshwari Construction India Pvt. AT+P.O.- Maheshwari P.S.-Sonu,Dist-jamui, 9162255747 (19.01.2012) | 185.7 |  | 19.1.2012 | 1 Year | [8 empty] | 1 | 126.37
|  |  | lqYrkuxat | 2 | eŒfoŒm/kkMhg 9801583582 | [13 empty] | 1
|  |  | ukFkuxj | 3 | eŒfoŒvtesjh cSfj;k 8969037136 | [7 empty] | 1 | [7 empty] | 9th A/C bill paid
|  |  | txnh'kiqj | 4 | eŒfoŒegEeniqj 9279216759 | [13 empty] | 1
2 | USS-16 | Hkkxyiqj | lUgkSyk | 1 | eŒfoŒenkjxat 9955488107@9471611402 | Lalan Kumar,Adampur, Bhagalpur. 9904275265 (28.02.2012) | 181.86 |  | 28.2.2012 | 1 Year | [8 empty] | 1 | 93.3
|  |  | ihjiSarh | 2 | eŒfoŒfnykSjh 9801095027 | [13 empty] | 1
|  |  | dgyxkWo | 3 | eŒfoŒiUuqpd 9279457160 | [13 empty] | 1 |  | 7th A/C bill paid
|  |  | xksjkMhg | 4 | eŒfoŒxjgksfr;k 9931865594 | [13 empty] | 1
3 | USS-17 | Hkkxyiqj | lokSj | 1 | eŒfoŒf'kok;Mhg 9973394344 | Kuhu Construction 9431431148/ 9470070171 (16.04.2012) | 187.28 |  | 16.4.2012 | 1 Year | [8 empty] | 1 | 126.36
|  |  | [kjhQ | 2 | eŒfoŒnkniqj 8051625862@9934408562 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | fcgiqj | 3 | eŒfoŒdgkjiqj 9934602158 |  |  | 1 | [12 empty] | Land Dispute
|  |  | bLekbyiqj | 4 | eŒfoŒy{ehiqj 9546492998 | [13 empty] | 1
4 | USS-18 | ckadk | ckjkgkV | 1 | eŒfoŒlgjuk 9431689507@9709969696 | Amar Kumar Mishra Banka, Bihar-813102 9939707470 (20.12.2011) | 184.37 |  | 20.12.2011 | 1 Year | [8 empty] | 1 | 149.7
|  |  | ckSalh | 2 | mRØŒeŒfoŒ fo'kuiqj 9006554728 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | /kksjS;k | 3 | mRØŒeŒfoŒ Hkrqvkpd 9955916141 | [13 empty] | 1
|  |  | jtkSu | 4 | eŒfoŒe>xka; 9771243197 | [13 empty] | 1
5 | USS-19 | ckadk | vejiqj | 1 | eŒfoŒHknjh;k 9939749402 | Amar Kumar Mishra Banka, Bihar-813102 9939707470 (20.12.2011) | 231.09 |  | 20.12.2012 | 1 Year | [8 empty] | 1 | 123.8
|  |  | pkanu | 2 | mRØŒeŒfoŒ vlq/kk eqdqank 9199722081 | [12 empty] | 1
|  |  | dVksfj;k | 3 | eŒ foŒ] Hkksjlkj 9304136524 | [12 empty] | 1 |  |  | 7th A/C bill paid
|  |  | csygj | 4 | mRØŒeŒfoŒ uxsy 9934928705 | [12 empty] | 1
|  |  | 'kaHkqxat | 5 | eŒfoŒjkt?kkV 9199067916 | [12 empty] | 1
| Total nos. of school |  |  | 21 |  |  | 970.3 | 1 |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 15 | 619.53
(B) STATE FUNDED
1 | USS-213 | 'ks[kiqjk | gFkh;kok¡ | 1 | mRŒ eŒ foŒ] jke jk;iqj 8757419360 9431474761 | Arbind Prasad, Purankama, P.O.+ Distt.- Sheikhpura, Bihar 9431258802 | 43.08 | [10 empty] | 1 |  | 22.16 | 2nd on A/C bill paid
2 | USS-215 | eqaxsj | eklqexat] Hkkxyiqj | 1 | mnkMhg eŒ foŒ | D.P.Maheshwari Construction India Pvt. Ltd. 9162255747 | 45.64 | 1
3 | USS-221 | ckadk | pdeqfu;k | 1 | eŒ foŒ] pdeqfu;k | D.P.Maheshwari Construction India Pvt. Ltd. 9162255747 | 45.81 | 1 | [12 empty] | Land not available
| Total nos. of school |  |  | 3 |  |  | 134.53 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 22.16

## Munger
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Munger | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214) | [6 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-20 | eqaxsj | gosyh [kM+xiqj | 1 | eŒfoŒj?kqukFkiqj | D P Maheshwari Construction India Pvt. AT+P.O.- Maheshwari P.S.-Sonu,Dist-jamui, 9162255747 (19.05.2012) | 131.15 | 1 | 19.5.2012 | 1 Year | [9 empty] | 8.83 | Sufficient Land not available
|  |  | eqaxsj lnj | 2 | eŒfoŒVhdkjkeiqj 9431612789 |  |  | 1 | [12 empty] | In soil test poor soil found
|  |  | /kjgjk | 3 | eŒfoŒegjuk 9504681361@9852445511 | [11 empty] | 1 |  |  |  | 2nd A/C bill paid
2 | USS-21 | 'ks[kiqjk | 'ks[kiqjk | 1 | eŒfoŒckn'kkgiqj 9709066149 | Arbind Prasad, P.O+ Distt.- Sheikhpura. 9431258802/ 8757503857 (09.04.2012) | 44 |  | 9.4.2012 | 1 Year | [8 empty] | 1 | 39.02 | 6th A/C bill paid
3 | USS-22 | teqbZ | pdkbZ | 1 | eŒfoŒnqyeiqj 9973390953@9661984491 | Rajendra Kumar , At- Pipradih, P.O- Jhajha, Distt.- Jamui. 9939195777/ 9473044777 (01.03.2012) | 131.86 |  | 1.3.2012 | 1 Year | [8 empty] | 1 | 120.28
|  |  | >k>k | 2 | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | [13 empty] | 1 |  | 7th A/C bill paid
|  |  | lksuks | 3 | eŒfoŒiSjk efVgkuk 9801576608 | [13 empty] | 1
4 | USS-23 | teqbZ | teqbZ | 1 | mRØŒeŒfoŒ HkkVpd 9430818763 | Lal Rupak Kumar Singh At- Ugnichak, P.O- Amrath Distt.- Jamui. 9576391000/ 8809977286 (06.02.2012) | 177.37 |  | 6.2.2012 | 1 Year | [8 empty] | 1 | 135.33
|  |  | y{ehiqj | 2 | eŒfoŒgjyk 9162733763@9006655639 | [11 empty] | 1 |  |  |  | 7th A/C bill paid
|  |  | [kSjk | 3 | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | [13 empty] | 1
|  |  | bZŒ vyhxat | 4 | eŒfoŒfetkZxat 8292659272 | [13 empty] | 1
5 | USS-24 | csxwljk; | cNokM+k | 1 | eŒfoŒQrsg 9570919206 | Ray & Raj Engineering Pvt. Ltd. 9430047216 (07.05.2012) | 142.74 |  | 7.5.2012 | 1 Year | [8 empty] | 1 | 119.79
|  |  | Hkxokuiqj | 2 | eŒfoŒeksf[r;kjiqj 9934441250 | [13 empty] | 1 |  | 7th A/C bill paid
|  |  | psfj;k cfj;kjiqj | 3 | eŒfoŒldjoklk 9939576953 | [13 empty] | 1
6 | USS-25 | csxwljk; | cfy;k | 1 | eŒfoŒelwnuiqj 9955252445 | M/S Brij Deo Singh 9430885959 (25.07.2012) | 141.58 |  | 10.10.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 46.06
|  |  | rs?kjk | 2 | eŒfoŒxkSjk&1 9973170370 | [12 empty] | 1 |  |  | 4rd A/C bill paid
|  |  | lkgsciqj deky | 3 | eŒfoŒfo".kqiqj vkgksd 9534757293 | [5 empty] | 1 | [9 empty] | Land Dispute
7 | USS-26 | csxwljk; | cjkSuh | 1 | eŒfoŒcFkkSyh 9801572247@9534334080 | M/S Daya Ram Singh At- Kapasiya Nagdah(RTS) Dist- Begusarai 9801031299 (21.05.2012) | 93.2 |  | 21.5.2012 | 1 Year | [8 empty] | 1 | 83.76
|  |  | efVgkuh | 2 | eŒfoŒtxriqjk 9939465778 | [13 empty] | 1 |  | 6th A/C bill paid
8 | USS-27 | [kxfM+;k | ijoÙkk | 1 | eŒfoŒdjuk 9939629342@9006237936 | Rajendra Singh Const. Pvt. Ltd.,Bengali Tola, Laheriasarai, Darbhanga. 9931996161 (14.12.2011) | 246.08 |  | 14.12.2011 | 1 Year | [8 empty] | 1 | 193.88
|  |  | vykSyh | 2 | eŒfoŒes?kkSuk 9534870633 | [13 empty] | 1
|  |  | pkSFke | 3 | eŒfoŒigkM+pd 9431651745 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | xksxjh | 4 | eŒfoŒidjSy 9955068112 | [13 empty] | 1
|  |  | [kxfM+;k | 5 | eŒfoŒeksjdkgh Fkkuk 9534404397 | [9 empty] | 1
| Total nos. of school |  |  | 24 |  |  | 1107.98 | 2 |  |  | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 16 | 746.95
(B) STATE FUNDED
1 | USS-214 | osxwljk; | cfy;k | 1 | dykorh egknso eŒ foŒ] cjoh/kh | Raja Enterprises & Co. 9431694183 (19.10.2012) | 45.5 | 1 | 19.10.2012 | 10 Month | [10 empty] | Land problem
| Total nos. of school |  |  | 1 |  |  | 45.5 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Kosi
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Kosi | [8 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790) | [7 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A) Central Funded (Fin. Year 2009-2010)
1 | USS-71 | e/ksiqjk | e/ksiqjk | 1 | eŒfoŒHkjkZgh cktkj 9852057904 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (04.05.2012) | 191.68 | 1 | 4.5.2012 | 1 Year | [9 empty] | 74.5 | Land dispute
|  |  | eqjyhxat | 2 | eŒfoŒij"kk uoVksy 9973625392 | [12 empty] | 1 |  |  | 6th A/C bill paid
|  |  | flags'oj | 3 | eŒfoŒflaX;kSu 9430633497 | [11 empty] | 1
|  |  | dqekj[kaM | 4 | eŒfoŒd:oSyh 9771194253 | [12 empty] | 1
2 | USS-72 | e/ksiqjk | mnk fd'kquxat | 1 | eŒfoŒckM+kVSuh 9631850096 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (04.07.2012) | 147.57 |  | 4.7.2012 | 1 Year |  |  |  | 1 | [5 empty] | 53.58
|  |  | pkSlk | 2 | ykyth eŒfoŒykSvk yxku 8969228737 | [11 empty] | 1 |  |  |  | 6th A/C bill paid
|  |  | vkyeuxj | 3 | eŒfoŒcjxk¡o 9939489984 | [12 empty] | 1
3 | USS-73 | lgjlk | lkSj cktkj | 1 | eŒfoŒ[ktqjh 9472653157@9430632563 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (10.07.2012) | 144.85 |  | 26.9.2012 | 12 Month | [7 empty] | 1 |  | 63.73
|  |  | uogêk | 2 | eŒfoŒdsnyh iêh 9939942137@8987203752 | [10 empty] | 1 |  |  |  |  | 5th A/C bill paid
|  |  | lksuo"kkZ | 3 | eŒfoŒiapy[k 7549317375 | [12 empty] | 1
4 | USS-74 | lgjlk | ly[kqvk | 1 | eŒfoŒfiijk oxsok 9905964384 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (10.07.2012) | 146.08 |  | 26.9.2012 | 12 Month |  |  |  |  | 1 |  |  |  |  | 45.63
|  |  | flejh cf[r;kjiqj | 2 | eŒfoŒ?kks?kle 9471654377 | [7 empty] | 1
|  |  | efg"kh | 3 | eŒfoŒ>kM+k 9430696742 | [9 empty] | 1 | [5 empty] | 4th A/C bill paid
5 | USS-75 | lqikSy | olariqj | 1 | eŒ foŒcyHknziqj 9472034607 | M/S K.D. Company 9431497838 (01.06.2012) | 206.86 |  | 1.6.2012 | 1 Year | [7 empty] | 1 |  | 146.9
|  |  | Nkrkiqj | 2 | eŒ foŒe/kqcuh 9631295927 | [12 empty] | 1 |  |  | 4th A/C Bill paid
|  |  | ejkSuk | 3 | eŒ foŒifjdksap 9931662963 | [12 empty] | 1
|  |  | jk?kksiqj | 4 | y[khpan lkgq eŒfoŒgfjjkgk 9470047275 | [13 empty] | 1
6 | USS-76 | lqikSy | fd'kuiqj | 1 | eŒfoŒQqyofj;k 8298274284 | M/S K.D. Company 9431497838 (04.06.2012) | 197.84 |  | 4.6.2012 | 1 Year | [8 empty] | 1 | 111.05
|  |  | fiijk | 2 | eŒfoŒjkeuxj 9472335572@9570603091 | [13 empty] | 1 |  | 4th A/C Bill paid
|  |  | lqikSy | 3 | eŒfoŒdfjgks 9430029088 | [13 empty] | 1
|  |  | f=os.khxat | 4 | eŒfoŒdqe;kgh 8986062906 | [12 empty] | 1
| Total nos. of school |  |  | 21 |  |  | 1034.88 | 1 |  |  | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 9 | 4 | 495.39

## Purnea
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Purnea | [8 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-77 | vjfj;k | Hkjxkek | 1 | mRØŒeŒfoŒjgfM+;k 9534388120 | Raj Kishore Singh 9431412396 (24.07.2012) | 197.18 |  | 24.7.2012 | 1 Year | [8 empty] | 1 | 128.6
|  |  | jkuhxat | 2 | ckfydk eŒfoŒxq.korh 9771105449 | [13 empty] | 1 |  | 5th A/C Bill paid
|  |  | jkuhxat | 3 | eŒfoŒijekuaniqj 9631149958 | [12 empty] | 1
|  |  | ujirxat | 4 | eŒfoŒuksfu;k Vksyk pdyk 9973417759 | [12 empty] | 1
2 | USS-78 | vjfj;k | Qkjfclxat | 1 | eŒfoŒe/kqcuh 9661601762 | MD. IFTEKHAR ALAM | 195.36 |  |  |  |  | 1
|  |  | Qkjfclxat | 2 | eŒfoŒVs<+h eqlgjh 9801199615 | [6 empty] | 1
|  |  | vjfj;k | 3 | eŒfoŒiSdVksyk 9431087519@9431471118 | [7 empty] | 1
|  |  | vjfj;k | 4 | eŒfoŒck¡lckM+h 9430264342 | [6 empty] | 1
3 | USS-79 | vjfj;k | dqlkZdk¡Vk | 1 | eŒfoŒdikjQksM+k 9931414194 | Iftakhar Alam 9431835133 / 9934724033 (24.07.2012) | 197 |  | 10.10.2012 | 12 Month | [8 empty] | 1 | 98.33
|  |  | fldVh | 2 | eŒfoŒlksgkxekM+ksa 9661752676@9006316855 | [12 empty] | 1 |  |  | 5th A/C Bill paid
|  |  | tksdhgkV | 3 | eŒfoŒHkwuk 9570679546 |  |  | 1 | [12 empty] | water logging & low land 8'-0"
|  |  | iyklh | 4 | eŒfoŒ:iSy e/kSy 9771866133 | [12 empty] | 1
4 | USS-80 | fd'kuxat | fnX?kycSad | 1 | eŒfoŒgjokMaxk 8987208103 | Md. Shafique Alam, Dhanpura, Kishanganj. (Ph:9431259842) (09.04.2012) | 248.24 |  | 9.4.2012 | 1 Year | [8 empty] | 1 | 224.99
|  |  | Bkdqjxat | 2 | eŒfoŒtaxyHkhVk 8987254242 | [13 empty] | 1
|  |  | dksapk/kkeu | 3 | eŒfoŒ/kuiqjk 9470868499 | [13 empty] | 1 |  | 6th A/C bill paid
|  |  | iksfB;k | 4 | eŒfoŒgfjiks[kj ØkafrxkN 9430677962 | [13 empty] | 1
|  |  | cgknqjxat | 5 | eŒfoŒgfjHkk"kk 9471834254 | [13 empty] | 1
5 | USS-81 | iwf.kZ;k¡ | dsŒ uxj | 1 | vkn'kZ eŒfoŒijksjk 9631003614 | Shankar Sharan Singh 9934724833 (25.05.2012) | 141.49 |  | 25.5.2012 | 1 Year | [7 empty] | 1 |  | 89.57
|  |  | dlok | 2 | mRØŒeŒfoŒdnok 9006717685@9162698638 | [12 empty] | 1 |  |  | 8th A/C bill paid
|  |  | Mx:vk | 3 | eŒfoŒeksgEeniqj 8877902279@9852305617 | [13 empty] | 1
6 | USS-82 | iwf.kZ;k¡ | /kenkgk | 1 | vkn'kZ eŒfoŒfo'kuiqj 8002692294 | Shankar Sharan Singh 9934724833 (25.05.2012) | 193.67 |  | 25.5.2012 | 1 Year | [7 empty] | 1 |  | 104.88
|  |  | Hkokuhiqj | 2 | eŒfoŒczãKkuh 9931249419 | [12 empty] | 1 |  |  | 9th A/C bill paid
|  |  | :ikSyh | 3 | eŒfoŒykyxat 9934565697 | [12 empty] | 1
|  |  | cueu[kh | 4 | eŒfoŒtkudh uxj gkV 9430675018 | [12 empty] | 1
7 | USS-83 | iwf.kZ;k¡ | ok;lh | 1 | eŒfoŒvkltk ecS;k 9931676786 | Bala Ji Construction 9006169540 (04.07.2012) | 144.88 | 1 | 28.9.2012 | 12 Month | [10 empty] | Water logged low land
|  |  | vekSj | 2 | eŒfoŒePNÍk 9470487168@9934622591 |  |  | 1
|  |  | oSlk | 3 | eŒfoŒekyksikM+k 9939083102 |  |  | 1
8 | USS-84 | dfVgkj | cyjkeiqj | 1 | eŒfoŒ>y>yh 9434962404@8986444230 | Bala Ji Construction 9006169540 (10.07.2012) | 193.41 | 1 | 28.9.2012 | 12 Month | [9 empty] | 71.45 | Encroachment
|  |  | ckjlksbZ | 2 | eŒfoŒclyxkao 9126846409 | [12 empty] | 1
|  |  | ckjlksbZ | 3 | eŒfoŒ<ëk 9471674809 | [12 empty] | 1 |  |  | 5th A/C bill paid
|  |  | vkteuxj | 4 | eŒfoŒtydh 9470423557@8877799621 | [12 empty] | 1
9 | USS-85 | dfVgkj | cjkjh | 1 | eŒfoŒcfd;k lq[kk; 9572154446 | Bala Ji Construction 9006169540 (11.07.2012) | 189.08 | 1 | 28.9.2012 | 12 Month | [9 empty] | 50.15
|  |  | efugkjh | 2 | eŒfoŒiVuh ukjk;.kiqj 9430970158 | [9 empty] | 1 | [5 empty] | 6th A/C bill paid
|  |  | Qydk | 3 | eŒfoŒ>x:pd 0431668067 | [12 empty] | 1
|  |  | dks<+k | 4 | eŒfoŒf'kf'k;k 9431625914@0430582029 | [12 empty] | 1
10 | USS-86 | dfVgkj | venkckn | 1 | eŒfoŒfnYyh fnokuxat 9431667161@7631741488 | Umakant Singh 9431229132 (16.04.2012) | 142.79 | 1 | 28.9.2012 | 12 Month | [9 empty] | 45.43
|  |  | dnok | 2 | eŒfoŒvk'k;kuh 8986509086 | [13 empty] | 1 |  | 4th A/C bill paid
|  |  | dnok | 3 | eŒfoŒpkSdh 9470208190 |  |  | 1 | [12 empty] | Land not available
| Total nos. of school |  |  | 38 |  |  | 1843.1 | 8 |  |  | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 15 | 10 | 813.4
(B) STATE FUNDED
1 | USS-201 | fd'kuxat | fd'kuxat | 1 | e/; fo¦ky;] pdyk?kkV 7250532741 | Md. Shafique Alam, Dhanpura, Kishanganj, 9431259842 (16.05.2012) | 240.59 |  | 10.10.2012 | 12 Month | [8 empty] | 1 | 189.63
|  |  | fd'kuxat | 2 | e/; fo¦ky;] xkNikMk+ 9973279595 | [13 empty] | 1
|  |  | fd'kuxat | 3 | e/; fo¦ky;] nkSyk 8987031909 | [13 empty] | 1 |  | 4th A/C bill paid
|  |  | fd'kuxat | 4 | e/; fo¦ky;] eghuxk¡o 7549846854 | [13 empty] | 1
|  |  | fd'kuxat | 5 | e/; fo¦ky;] cssyok] dk'khiqj 9470077789 |  |  | 1 | [12 empty] | Sufficient land not available
2 | USS-202 | fd'kuxat | Vs<+kxkNh | 1 | e/; fo¦ky;] cSfj;k 8292434525 | M/S Bala Jee Construction, Co-Operative Colony, Purnea, 9006169540 (16.05.2012) | 249.84 |  | 16.5.2012 | 1 Year | [7 empty] | 1 |  | 101.03
|  |  | Vs<+kxkNh | 2 | e/; fo¦ky;] cSxuk 9939791780 | [12 empty] | 1
|  |  | Vs<+kxkNh | 3 | e/; fo¦ky;] lqfg;k jgeriqj 8544018037 |  |  | 1 | [12 empty] | 6th A/C bill paid
|  |  | Vs<+kxkNh | 4 | e/; fo¦ky;] dekrh 8757640064 | [13 empty] | 1
|  |  | Vs<+kxkNh | 5 | e/; fo¦ky;] csuqx<+ 9801048554 | [13 empty] | 1
3 | USS-203 | fd'kuxat | fnX?kycSad | 1 | e/; fo¦ky;] fla/khekjh 8986097091 | Md. Shafique Alam, Dhanpura, Kishanganj, 9431259842 (21.05.2012) | 199.91 |  | 10.10.2012 | 12 Month | [8 empty] | 1 | 119.97
|  |  | fnX?kycSad | 2 | e/; fo¦ky;] tj>qyk 9973230476 | [13 empty] | 1 |  | 5th A/C bill paid
|  |  | fnX?kycSad | 3 | e/; fo¦ky;] dqjgSyh 9661248448 | [13 empty] | 1
|  |  | fnX?kycSad | 4 | e/; fo¦ky;] dVgyckMh | [13 empty] | 1
4 | USS-204 | fd'kuxat | Ckgknqjxat | 1 | e/; fo¦ky;] nsfl;kVksyh 9934444776 | Md. Shafique Alam, Dhanpura, Kishanganj, 9431259842 | 198.66 | 1 | [12 empty] | land not available
|  |  | Ckgknqjxat | 2 | e/; fo¦ky;] [skryckMh |  |  | 1 | [12 empty] | land not available
|  |  | Ckgknqjxat | 3 | e/; fo¦ky;] yksgkxkMkgkV 9955726430 |  |  | 1 | [12 empty] | land not available
|  |  | Ckgknqjxat | 4 | e/; fo¦ky;] egs'kcFkuk 9973612231 |  |  | 1 | [12 empty] | site not accessible
5 | USS-205 | fd'kuxat | dkspk/kkeu | 1 | e/; fo¦ky;] /kuirxat 9430017157 | Birendra Kumar | 194.6 | 1 | 23.10.2013 | 12 Month
|  |  | dkspk/kkeu | 2 | e/; fo¦ky;] gYnh[kksMk+ 9470077991 | [9 empty] | 1
|  |  | dkspk/kkeu | 3 | e/; fo¦ky;] eksnksg 9470611886 | [9 empty] | 1
|  |  | dkspk/kkeu | 4 | e/; fo¦ky;] cMhtku 9471276232 |  |  | 1 | [12 empty] | Land dispute
6 | USS-206 | fd'kuxat | Bkdqjxat | 1 | e/; fo¦ky;] dknksxk¡o 9431002508 | M/S C.S. Construction, Gayatari Nagar, Motihari, Bihar 9473290979/ 8235161126/ 9304566888 | 200.06 |  | 29.12.2012 | 12 Month |  |  |  |  | 1 |  |  |  |  | 51.25
|  |  | Bkdqjxat | 2 | e/; fo¦ky;] jktkxk¡o 7250327554 | [9 empty] | 1
|  |  | Bkdqjxat | 3 | e/; fo¦ky;] jfl;k 9472898877 | [12 empty] | 1 |  |  | 4th on A/C bill paid
|  |  | Bkdqjxat | 4 | e/; fo¦ky;] xyxfy;k 9472979439 | [6 empty] | 1
7 | USS-207 | fd'kuxat | iksfB;k | 1 | e/; fo¦ky;] dfy;kxat 9661821842 | M/S Bala Jee Construction, Co-Operative Colony, Purnea, 9006169540 (08.06.2012) | 206.15 |  | 28.9.2012 | 12 Month | [7 empty] | 1 |  | 123.63
|  |  | iksfB;k | 2 | e/; fo¦ky;] jk;iqj 9430948041 | [13 empty] | 1 |  | 5th A/C bill paid
|  |  | iksfB;k | 3 | e/; fo¦ky;] efj;k 8969807582 | [12 empty] | 1
|  |  | iksfB;k | 4 | e/; fo¦ky;] nyqvkgkV 9801908155 | [12 empty] | 1
| Total nos. of school |  |  | 30 |  |  | 1489.81 | 8 |  |  | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 6 | 11 | 585.51

## Tirhut
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Tirhut | [8 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & Contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-37 | if'pe pEikj.k | e>kSfy;k | 1 | eŒ foŒ]vgcj 'ks[k 9470655463 | M/S Prem Pratap Ray 9386878517/ 9852833505 (10.05.2012) | 194.51 |  | 10.5.2012 | 1 Year | [8 empty] | 1 | 159.67
|  |  | e>kSfy;k | 2 | eŒ foŒ] ijlk cgqvjok 9470859628 | [13 empty] | 1 |  | 11th A/C bill paid
|  |  | cSfj;k | 3 | eŒ foŒ]cFkuk 9431466192 | [13 empty] | 1
|  |  | ukSru | 4 | eŒ foŒ]eaxyiqj xqnfj;k 9430691686 | [13 empty] | 1
2 | USS-38 | if'pe pEikj.k | cxgk&I | 1 | eŒ foŒdksYgqvk pkSrjok 9430668747 | Sarswati Company 9431491214 (09.04.2012) | 199.78 |  | 9.4.2012 | 1 Year | [8 empty] | 1 | 178.72
|  |  | cxgk& II | 2 | eŒ foŒ] jkeiqjok 9572454264 | [13 empty] | 1 |  | 10th A/C bill paid
|  |  | ykSfj;k | 3 | eŒ foŒ]/kkscuh 9430571439 | [13 empty] | 1
|  |  | xkSukgk | 4 | jkŒ dŒ eŒ foŒ]xkSukgk¡ 9430421378 | [13 empty] | 1
3 | USS-39 | if'pe pEikj.k | eSukVk¡M+ | 1 | eŒ foŒ]rktiqj 8986956152 | M/S Amit Kr. Rai 9934056756/ 9470249005 (21.05.2012) | 149.83 |  | 21.5.2012 | 1 Year | [7 empty] | 1 |  | 70.96
|  |  | eSukVk¡M+ | 2 | eŒ foŒ]lq[kykgh 9546120109 | [9 empty] | 1 | [5 empty] | 6th A/C bill paid
|  |  | fldVk | 3 | eŒ foŒ]cS'k[kok 9955233530 | [12 empty] | 1
4 | USS-40 | if'pe pEikj.k | ujdfV;kxat | 1 | eŒ foŒ]lksex<+ 9470256119 | M/S Diamond Construction, Murarpur, East Champarn 9471299381 (17.07.2012) | 148.68 |  | 17.7.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 32.32
|  |  | ;ksxkiêh | 2 | eŒ foŒ]dksgjk 9934686513 | [9 empty] | 1 | [5 empty] | 4th A/C bill paid
|  |  | jkeuxj | 3 | eŒ foŒ]'ksj gok nksu 9470860764 | [7 empty] | 1
5 | USS-41 | iwohZ pEikj.k | eksfrgkjh | 1 | eŒ foŒ] teyk 9934828027 | Ranjeet Kumar 9470235016 (16.05.2012) | 190.91 |  | 16.5.2012 | 1 Year | [6 empty] | 1 |  |  | 83.96
|  |  | cutfj;k | 2 | eŒ foŒ] dqdqjtjh 9708975580 | [9 empty] | 1
|  |  | rqjdkSfy;k | 3 | eŒ foŒ] fo".kqiqjok 9801485906 | [12 empty] | 1 |  |  | 9th A/C bill paid
|  |  | fpjS;k | 4 | eŒ foŒ] ijsok 9386155278 | [9 empty] | 1
6 | USS-42 | iwohZ pEikj.k | vjsjkt | 1 | eŒ foŒ] jf<+;k 9576399366 | Shiv Shankar Singh Construction Pvt. Ltd. , Rajendra Nagar, Gopalganj (Ph: 9431217515) (16.04.2012) | 192.7 |  | 16.4.2012 | 1 Year | [8 empty] | 1 | 141.25
|  |  | laxzkeiqj | 2 | eŒ foŒ] ';keiqj 8969622208 | [13 empty] | 1
|  |  | gjflf) | 3 | eŒ foŒ] ?khok<kj 9162288480@8298836365 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | dksVok | 4 | eŒ foŒ] vfgjkSfy;k 9546303762 | [13 empty] | 1
7 | USS-43 | iwohZ pEikj.k | jDlkSy | 1 | eŒ foŒ] xksugk 9470284937 | M/S Jagdamba Construction, 9470606400 (08.11.2012) | 189.4 |  | 8.11.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 13.02
|  |  | lqxkSyh | 2 | eŒ foŒ] eqlok 9471878742 | [9 empty] | 1
|  |  | vknkiqj | 3 | eŒ foŒ] csynjok 9771769291@9472911484 | [7 empty] | 1 | [7 empty] | 1st A/C bill paid
|  |  | NkSM+knkukS | 4 | eŒ foŒ] idfM+;k mnwZ 9470233197 |  |  | 1 | [12 empty] | Land not available
8 | USS-44 | iwohZ pEikj.k | pfd;k | 1 | eŒ foŒ fparkeuiqj 9546123872 | Ashiyana Contract Pvt. Ltd. 9431088485 (16.04.2012) | 239.09 |  | 16.4.2012 | 1 Year | [7 empty] | 1 |  | 135.5
|  |  | dY;k.kiqj | 2 | eŒ foŒ] es?kok mnwZ 9939516692 |  |  | 1 | [12 empty] | Land prob.
|  |  | dslfj;k | 3 | eŒ foŒ] lqUnjiqj 9006381049 | [13 empty] | 1 |  | 9th A/C bill paid
|  |  | esglh | 4 | eŒ foŒ] f>Vdfg;k 9162250321 | [12 empty] | 1
|  |  | igkM+iqj | 5 | eŒ foŒ] fllok cktkj 8809296371 | [13 empty] | 1
9 | USS-45 | iwohZ pEikj.k | <+kdk | 1 | eŒ foŒ] pnuckjk mnwZ 9931213480 | M/S Diamond Construction, Murarpur, East Champarn 9471299381 (17.07.2012) | 193.17 |  | 17.7.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 47.52
|  |  | irkgh | 2 | eŒ foŒ] csrkSuk 9708717133 | [8 empty] | 1 | [6 empty] | 5th A/C bill paid
|  |  | e/kqcu | 3 | eŒ foŒ] xqjfe;k¡ | [7 empty] | 1
|  |  | ?kksM+klgu | 4 | eŒ foŒ] y{ehiqj ykS[kku 9431652891 | [11 empty] | 1
10 | USS-46 | f'kogi | rfj;kuh | 1 | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | Sadafal Construction Pvt. Ltd. | 190.96 | 1
|  | flrke<+h | :Uuh lSniqj | 2 | eŒ foŒ] cyqvk 9771099254 | [6 empty] | 1
|  |  | :Uuh lSniqj | 3 | eŒ foŒ] FkqEek 9472379528 |  |  | 1
|  |  | csylaM | 4 | eŒ foŒ] ipukSj | [6 empty] | 1
11 | USS-47 | flrke<+h | jhxk | 1 | eŒ foŒ] ;ksxokuk 9534893264 | Malti Singh Darbhanga 8969355977 (02.05.2012) | 241.41 |  | 2.5.2012 | 1 Year | [8 empty] | 1 | 218.47
|  |  | cFkukgk | 2 | eŒ foŒ] fMgBh 9973981418 | [13 empty] | 1
|  |  | ukuiqj | 3 | eŒ foŒ] cÙkjk 9931668054 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | ukuiqj | 4 | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | [13 empty] | 1
|  |  | lksucjlk | 5 | eŒ foŒ] bVgjok 9546578977 | [13 empty] | 1
12 | USS-48 | eqt¶Qjiqj | vkSjkbZ | 1 | eŒ foŒ] cSaxuk 7209905677 | Mother India Pvt. Ltd.9431018204 (04.05.2012) | 188.66 |  | 4.5.2012 | 1 Year | [8 empty] | 1 | 168.11
|  |  | ckspgk¡ | 2 | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | [13 empty] | 1
|  |  | xk; ?kkV | 3 | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | [13 empty] | 1 |  | 10th A/C bill paid
|  |  | dVjk | 4 | eŒ foŒ] cq/kdkjk 9934016332 | [13 empty] | 1
13 | USS-49 | eqTk¶Qjiqj | dkaVh | 1 | eŒ foŒ] J~axkj 8809637605 | Ramji Prasad 9334489874 (06.06.2012) | 139.31 | 1 | 6.6.2012 | 1 Year | [9 empty] | 84.57 | Dispute
|  |  | eM+ou | 2 | eŒ foŒ] jsiqjk 8252129824 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | ehukiqj | 3 | eŒ foŒ] tkfeu efB;k 9934619525 | [13 empty] | 1
14 | USS-50 | eqT¶Qjiqj | ik: | 1 | eŒ foŒ] HkkstiV~Vh 9931888752 | M/S Diamond Construction, Murarpur, East Champarn 9471299381 (17.07.2012) | 186.38 |  | 17.7.2012 | 1 Year |  |  |  | 1 | [5 empty] | 40.19
|  |  | ik: | 2 | eŒ foŒ] pkaniqj 9801265669 | [9 empty] | 1 | [5 empty] | 4rd A/C bill paid
|  |  | lkgscxat | 3 | eŒ foŒ] 'kkgiqj iV~Vh 9801128043 | [8 empty] | 1
|  |  | ljS;k | 4 | eŒ foŒ] xksjhxkekMhg 9431615151 | [9 empty] | 1
15 | USS-51 | eqT¶Qjiqj | ldjk | 1 | eŒ foŒ] ckth cqtqxZ 9572907300 | Mother India Pvt. Ltd.9431018204 (07.08.2012) | 140.08 |  | 7.8.2012 | 1 Year | [8 empty] | 1 | 109.55
|  |  | eq'kgjh | 2 | eŒ foŒ] fn?kM+k 9430051489@9304110351 | [13 empty] | 1 |  | 10th A/C bill paid
|  |  | eksrhiqj | 3 | eŒ foŒ] ckjthMhg 9934895236 | [12 empty] | 1
16 | USS-52 | oS'kkyh | lgnsbZ cqtqxZ | 1 | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | Man Mardan Shukla Construction Pvt. Ltd., Naya Tola , Muzaffarpur (Ph: 9431013056/ 9507328440) (17.02.2012) | 184.94 |  | 17.2.2012 | 1 Year | [6 empty] | 1 |  |  | 128.59
|  |  | egukj | 2 | eŒ foŒ deyk dU;k] djukSrh 8002747546 | [13 empty] | 1 |  | 9th A/C bill paid
|  |  | tUnkgk | 3 | eŒ foŒ] jlqyiqj 8651291731 | [13 empty] | 1
|  |  | fonqiqj | 4 | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | [13 empty] | 1
17 | USS-53 | oS'kkyh | gkthiqj | 1 | eŒ foŒ] yksek 9470638549 | Man Mardan Shukla Construction Pvt. Ltd., Naya Tola , Muzaffarpur (Ph: 9431013056/ 9507328440) (17.02.2012) | 182.83 |  | 17.2.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 85.27
|  |  | gkthiqj | 2 | eŒ foŒ] dqrqciqj 9905099533 | [12 empty] | 1 |  |  | 8th A/C bill paid
|  |  | ykyxat | 3 | eŒ foŒ] xqjfe;k 8651626851 | [12 empty] | 1
|  |  | xksjkSy | 4 | eŒ foŒ] Bhdgk¡ 9431254109 | [13 empty] | 1
18 | USS-54 | oS'kkyh | jktkikdj | 1 | eŒ foŒ] csydqaMk 7677785326 | M/S Aditi Annanya Construction, Sneh Plaza Appartment, North S.K. Puri, Patna- 800013 9473241221 | 139.04 |  | 11.12.2012 | 12 Month | 1 | [8 empty] | 62.45 | Land dispute
|  |  | ikrsiqj | 2 | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | [13 empty] | 1 |  | 4th A/C bill paid
|  |  | jk?kksiqj | 3 | eŒ foŒ] ohjiqj 9931458401 | [11 empty] | 1
| Total nos. of school |  |  | 69 |  |  | 3291.68 | 5 |  |  | 1 | 2 | 3 | 3 | 11 | 0 | 4 | 8 | 32 | 1760.12
(B) STATE FUNDED
1 | USS-208 | iwohZ pEikj.k | ckjk pfd;k | 1 | eŒ foŒ] ?ku';ke idjh 9431054693 | M/S Babban Singh, Patpariya, Motihari 9431269941 | 94.46 | 1
|  |  | lqxkSyh | 2 | eŒ foŒ] pSuiqj 9661300867 |  |  | 1
2 | USS-209 | if'pe pEikj.k | oxgk&II | 1 | eŒ foŒ] jruiqjok | M/S Shri Krishna Const. Company, Sushila Swami Sadan, North Womens College, Gopalganj 9801697295 | 47.79 |  | 31.12.2012 | 10 Month | 1 | [9 empty] | Land prob.
3 | USS-220 | oS'kkyh | xksjkSy | 1 | eŒ foŒ bLykeiqj 9430036055 | M/S Shanti Construction, Vill-Mahua Singh Ray Purvi, P.O-Mahua, P.S-Mahua, P.S- Mahua, Distt.-Vaishali | 45.87 |  | 26.12.2012 | 9 Month | [8 empty] | 1 | 37.06 | 4th A/C bill paid
| Total nos. of school |  |  | 4 |  |  | 188.12 | 2 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 37.06

## Darbhanga
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Darbhanga | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & Contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-61 | e/kqcuh | ?kks?kjMhgk | 1 | eŒ foŒ] xax}kj 9934407620 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (04.05.2012) | 148.86 |  | 4.5.2012 | 1 Year | [8 empty] | 1 | 119.55
|  |  | >a>kjiqj | 2 | eŒ foŒ]ykSguk 9430835195 | [12 empty] | 1 |  |  | 10th A/C bill paid
|  |  | ykSdgh | 3 | eŒ foŒ] dyqvkgh 9572025500 | [13 empty] | 1
2 | USS-62 | e/kqcuh | t;uxj | 1 | eŒ foŒ] flyukFk cjgh 9572618953 | Rajesh Kumar,C/o Shiv Hardware, Sadar Bazar, Phulwari sharif, Patna.(Ph:9334374660) (05.03.2012) | 145.84 |  | 5.3.2012 | 1 Year | [7 empty] | 1 |  | 81.36
|  |  | i.MkSy | 2 | eŒ foŒ] 'kkgiqj 9973048002 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | jktuxj | 3 | mRØŒ eŒ foŒ] eaxjkSuh 9931643145 | [11 empty] | 1
3 | USS-63 | njHkaxk | guqeku uxj | 1 | eŒfoŒ]Fkyokjk 9771791978 | Rajendra Singh Construction Pvt. Ltd., Bengali Tola, Laheriasarai, Darbhanga (Ph:9931996161) (06.03.2012) | 142.77 |  | 5.3.2012 | 1 Year | [8 empty] | 1 | 116.92
|  |  | cgsM+h | 2 | mRØŒeŒfoŒ fctqfy;k 9939521323 | [13 empty] | 1 |  | 11th A/C bill paid
|  |  | cgknqjiqj | 3 | mRØŒeŒfoŒ dejkSyh 9801391631 | [13 empty] | 1
4 | USS-64 | njHkaxk | ?ku';keiqj | 1 | eŒfoŒ]rqekSy 9939754496 | Avaneesh Enterprises, III K 35/3A, Nehru Nagar, Ghaziabad (Ph:9473282030) (02.03.2012) | 193.17 |  | 2.3.2012 | 1 Year | [8 empty] | 1 | 138.03
|  |  | csuhiqj | 2 | mRØŒeŒfoŒ jf<+;ke 9770623526 | [13 empty] | 1 |  | 10th A/C bill paid
|  |  | euhxkNh | 3 | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | [13 empty] | 1
|  |  | rkjMhg | 4 | mRØŒeŒfoŒ rkjMhg 9934870957 |  |  | 1 | [12 empty] | Land not available
5 | USS-65 | njHkaxk | dq'ks'oj LFkku iwŒ | 1 | mRØŒeŒfoŒ egknso eB 9973391579 | Rajendra Singh Construction Pvt. Ltd., Bengali Tola, Laheriasarai, Darbhanga (Ph:9931996161) (06.03.2012) | 148.34 |  | 6.3.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 51.29
|  |  | dq'ks'oj LFkku iŒ | 2 | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | [9 empty] | 1 | [5 empty] | 5th A/C bill paid
|  |  | fojkSy | 3 | eŒfoŒ]iVfu;k¡ 9771113614 | [12 empty] | 1
6 | USS-66 | njHkaxk | fal?kokM+k | 1 | mRØŒeŒfoŒ e/kqiqj 9934911481 | Rajesh Kumar,C/o Shiv Hardware, Sadar Bazar, Phulwari sharif, Patna.(Ph:9334374660) (05.03.2012) | 142.15 |  | 5.3.2012 | 1 Year | [8 empty] | 1 | 101.54
|  |  | dsoVh | 2 | eŒfoŒ]dks;yk LFkku 9905459110 | [11 empty] | 1 |  |  |  | 9th A/C bill paid
|  |  | njHkaxk xzkeh.k | 3 | mRØŒeŒfoŒ cygk 9570479967 | [13 empty] | 1
7 | USS-67 | leLrhiqj | iVksjh | 1 | eŒfoŒ]njok 8757084952 | Vinod Kumar Singh, Vill + P.O- Ahmadpur, Sarairanjan, Distt.-Samastipur. (Ph:9431898568) (21.05.2012) | 238.71 | 1 | 21.5.2012 | 1 Year | [9 empty] | 178.2 | Land not available
|  |  | nyflag ljk; | 2 | eŒfoŒ]ekyiqj 9934140121 | [13 empty] | 1
|  |  | eksfgmÌhu uxj | 3 | eŒfoŒ]fcUn ckspgk 9939988449 | [13 empty] | 1 |  | 5th A/C bill paid
|  |  | fo¦kifr uxj | 4 | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | [13 empty] | 1
|  |  | eksfgmÌhu uxj | 5 | eŒfoŒ]efu;kj 7549600801 | [13 empty] | 1
8 | USS-68 | leLrhiqj | foHkwfriqj | 1 | eŒfoŒ]nsljh 9939816100 | Ray and Raj Engineering Pvt. Ltd., Vill+P.O-Kharahia, Distt.-Samastipur,Pin-848208. (Ph:9430047216) (07.05.2012) | 285.39 |  | 7.5.2012 | 1 Year | [8 empty] | 1 | 250.54
|  |  | fcFkku | 2 | eŒfoŒ]NsNuh 9934979521 | [13 empty] | 1
|  |  | gluiqj | 3 | mRØŒeŒfoŒ egqyh 9801690551 | [13 empty] | 1
|  |  | f'kokth uxj | 4 | eŒfoŒ]Jhiqj etjfg;k 9955507715 | [13 empty] | 1 |  | 9th A/C bill paid
|  |  | foHkwfriqj | 5 | eŒfoŒ]irSfy;k 9973163333 | [13 empty] | 1
|  |  | f'kokth uxj | 6 | eŒfoŒ]jkuhiêh 9955989162 | [13 empty] | 1
9 | USS-69 | leLrhiqj | dY;k.kiqj | 1 | eŒfoŒ]eksjokjk 9162249115 | Sudhakant Enterprises Pvt. Ltd., 5/6, Punjab Colony, Dharampur, Samastipur. (Ph:9931640405) (03.05.2012) | 185.32 |  | 3.5.2012 | 1 Year | [8 empty] | 1 | 152.8
|  |  | leLrhiqj | 2 | eŒfoŒ][kksM+h 9263781760 | [13 empty] | 1
|  |  | mft;kiqj | 3 | eŒfoŒ]vaxkj ?kkV 9204971619 | [13 empty] | 1 |  | 6th A/C bill paid
|  |  | mft;kiqj | 4 | mRØŒeŒfoŒ dksjc)k] irSyh 9263731315 | [13 empty] | 1
10 | USS-70 | leLrhiqj | eksjok | 1 | eŒfoŒ iq:"kksreiqj 9973123260 | Rajendra Singh Construction Pvt. Ltd., Bengali Tola, Laheriasarai, Darbhanga (Ph:9931996161) (13.04.2012) | 93.74 |  | 4.5.2012 | 1 Year | [8 empty] | 1 | 126.94
|  |  | iwlk | 2 | eŒfoŒ]efYydkSj 9934528902 | [13 empty] | 1 |  | 6th A/C bill paid
| Total nos. of school |  |  | 36 |  |  | 1724.29 | 2 |  |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 3 | 27 | 1317.17
(B) STATE FUNDED
1 | USS-216 | njHkaxk | yksvke | 1 | eŒ foŒ] yksvke 8987280647 | Amrendra Kumar, AT-Pokhraira, P.O-Senduari, Distt.-Vaishali. | 48.05 | 1 | [12 empty] | Land not available
2 | USS-217 | e/kqcuh | [kqVkSuk | 1 | eŒ foŒ ,dFFkk 9931014148 9771934377 | No Bidder | 49.94
| Total nos. of school |  |  | 2 |  |  | 97.99 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Saran
BSEIDC, PATNA
Progress report for the construction of USS school building ( Fin. Year. 2009-10)
Name of Division :- Saran | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Hemant kr. (7488022930), AE :- Chandramadhav Singh (9431474663) | [14 empty] | Name & contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
(A)Central Funded (Fin. Year 2009-2010)
1 | USS-55 | xksikyxat | cSdq.Biqj | 1 | eŒ foŒ] nsodqyh 9708861129 | Shiv Shankar Singh Construction Pvt. Ltd. , Rajendra Nagar, Gopalganj (Ph: 9431217515) (05.03.2012) | 189.78 |  | 5.3.2012 | 1 Year | [8 empty] | 1 | 151.48
|  |  | cSdq.Biqj | 2 | eŒ foŒ] egkjkuh 9199443900 | [13 empty] | 1
|  |  | dqpk;dksV | 3 | eŒ foŒ] egqvok fgUnh 9430055420@9162622220 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | fla?kofy;k | 4 | mRØŒ eŒ foŒ] Mqefj;k iqoZ 9955648224 | [13 empty] | 1
2 | USS-56 | xksikyxat | Hkksjs | 1 | eŒ foŒ] f'kojktiqj 9973200939 | Shiv Shankar Singh Construction Pvt. Ltd. , Rajendra Nagar, Gopalganj (Ph: 9431217515) (16.04.2012) | 192.25 |  | 16.4.2012 | 1 Year | [8 empty] | 1 | 147.1
|  |  | dVs;k | 2 | eŒ foŒ] :nziqj 9628550100 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | dqpk;dksV | 3 | eŒ foŒ] iqj[kk¡l 9955647418 | [13 empty] | 1
|  |  | fot;hiqj | 4 | eŒ foŒ] eFkkSyh 9838674751 | [13 empty] | 1
3 | USS-57 | floku | cM+gfM+;k | 1 | eŒ foŒ] gfFkxkbZ 9771334715 | Shiv Shankar Singh Construction Pvt. Ltd. , Rajendra Nagar, Gopalganj (Ph: 9431217515) (05.03.2012) | 184.15 |  | 5.3.2012 | 1 Year | [8 empty] | 1 | 152.17
|  |  | lhoku lnj | 2 | mŒ eŒ foŒ] pukSj 9006388052 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | vkanj | 3 | eŒ foŒ] cjok¡ 9934499146 | [13 empty] | 1
|  |  | gqlSuxat | 4 | eŒ foŒ] cM+je 9801700327 | [13 empty] | 1
4 | USS-58 | floku | j?kqukFkiqj | 1 | eŒ foŒ] djlj 9631444459 | Shiv Shankar Singh Construction Pvt. Ltd. , Rajendra Nagar, Gopalganj (Ph: 9431217515) (05.03.2012) | 232.4 |  | 5.3.2012 | 1 Year | [8 empty] | 1 | 203.56
|  |  | xq<++uh | 2 | mŒ eŒ foŒ] c¡xjk 9801180809 | [13 empty] | 1
|  |  | njkSyh | 3 | eŒ foŒ] Mqejgj cqtqxZ 9199854822 | [13 empty] | 1 |  | 8th A/C bill paid
|  |  | eSjok | 4 | eŒ foŒ] dchjiqj 9801620606 | [13 empty] | 1
|  |  | fllou | 5 | eŒ foŒ] jkex<+ 9973555208 | [13 empty] | 1
5 | USS-59 | lkj.k | e'kj[k | 1 | eŒ foŒ] nqe&nqEek 9006658111 | M/S Nitish Raj , Rathod Newaji Tola, P.O- Gurkul Mehian, Chapra. (Ph: 9470607184/ 9572239242) | 182.53 |  | 14.12.2012 | 12 Month |  |  |  |  | 1 |  |  |  |  | 52.13
|  |  | ikukiqj | 2 | mRØŒ eŒ foŒ] ikukiqj 9199453564 | [9 empty] | 1 | [5 empty] | 7th A/C bill paid
|  |  | rjS;k | 3 | eŒ foŒ] ijkSuk ckyd 9931139238 | [9 empty] | 1
|  |  | tykyiqj | 4 | eŒ foŒ] uoknk 9431630231 | [9 empty] | 1
6 | USS-60 | lkj.k | Nijk lnj | 1 | mRØŒ eŒ foŒ] pfd;k 9852100257@9128630531 | M/S Kishore Construction Vill + P.O- Kaituka Lachi, Saran (Ph: 9473059195/ 9546578888) (21.04.2012) | 226.95 |  | 21.4.2012 | 1 Year |  |  |  |  | 1 |  |  |  |  | 113.01
|  |  | ek¡>h | 2 | eŒ foŒ] Mqejh 8083701946@8757054210 | [12 empty] | 1
|  |  | ijlk | 3 | eŒ foŒ] cgyksyiqj 9199413413 | [12 empty] | 1 |  |  | 12th A/C bill paid
|  |  | edsj | 4 | eŒ foŒ] gluiqj 8969809826 | [12 empty] | 1
|  | lkj.k | ,dek | 5 | eŒ foŒ] nsoiqjk 9934276159 | [12 empty] | 1
| Total nos. of school |  |  | 26 |  |  | 1208.06 | 0 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 4 | 17 | 819.45
(B) STATE FUNDED
1 | USS-210 | Lkkj.k | flrkc fn;kjk | 1 | Ckkfydk eŒ foŒ] flrkc fn;kjk 9648348951 | Vinay Pratap Singh, B-401, Sagar Appt., Magistrate Colony, Ashiyana Nagar, Patna 9471867563 | 45.3 | 1 | [12 empty] | Land not available
2 | USS-211 | xksikyxat | mpdkxk¡o | 1 | e/; fo¦ky;] dijiqjk | M/S Shri Krishna Const. Company, Sushila Swami Sadan, North Womens College, Gopalganj 9801697295 | 46.69 | 1 | 25.4.2013 | 10 Month | [10 empty] | Land not available
3 | USS-212 | lhoku | uoru | 1 | eŒ foŒ]vaXkkSrk 9162360244 | Ashiana Contract Pvt. Ltd., Rajendra Nagar, Gopalganj 9431088485 (18.10.2012) | 47.1 |  | 18.10.2012 | 10 Month | [6 empty] | 1 |  |  | 6.63 | 1st A/C bill paid
| Total nos. of school |  |  | 3 |  |  | 139.09 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6.63