## Summary
BSEIDC, PATNA
Progress report for the construction of USS school building (2010-11) | [18 empty] | Date:-31.01.2014
S.N. | Division | Name & Designation | Total USS |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | Patna | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | 25 | 107 | 5277.0997 | 18 | 73 | 3308.2597 |  | 2 | 8 | 4 | 3 | 19 | 2 | 8 | 5 | 21 | 51 | 1 | 332.34 |  | 0
|  | Enarch-JV-PIDC (A.K.Dutta -9470353415 & Prakash Ji-9431018537) | [20 empty] | 0
2 | Magadh | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 15 | 62 | 3032.5367 | 7 | 30 | 1480.6 |  | 1 | 0 | 2 | 2 | 6 | 1 | 3 | 2 | 8 | 17 | 5 | 301.96 |  | 0
|  | Enarch-JV-PIDC (A.K.Dutta -9470353415 & Prakash Ji-9431018537) | [20 empty] | 0
3 | Bhagalpur | Ranvijay Kr. Sinha (9934961293) E.E. BSEIDC, Div.- Bhagalpur | 6 | 23 | 1140.51 | 2 | 8 | 400.33 |  | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 2 | 112.9 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | [20 empty] | 0
4 | Munger | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 11 | 43 | 2137.3 | 8 | 28 | 1400.71 |  | 0 | 2 | 0 | 3 | 9 | 4 | 4 | 1 | 3 | 23 | 2 | 184.13 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | [20 empty] | 0
5 | Kosi | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 2 | 4 | 214.51 | 1 | 3 | 160.98 |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 0 | 12.24 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | [20 empty] | 0
6 | Purnea | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 7 | 27 | 1433.01 | 3 | 10 | 529.22 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 3 | 59.96 |  | 0
|  | Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280) | [20 empty] | 0
7 | Tirhut | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 15 | 69 | 3685.53 | 11 | 49 | 2616.86 |  | 3 | 1 | 7 | 3 | 19 | 3 | 1 | 0 | 12 | 37 | 0 | 61.15 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | [20 empty] | 0
8 | Darbhanga | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Darbhanga | 7 | 25 | 1354.7283 | 6 | 21 | 1142.1483 |  | 1 | 4 | 2 | 1 | 1 | 0 | 0 | 3 | 9 | 12 | 0 | 67.13 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | [20 empty] | 0
8 | Saran | Pramod Kumar (9955128483) E.E. BSEIDC, Div.- Saran | 13 | 43 | 2253.6463 | 12 | 41 | 2148.673 |  | 0 | 2 | 2 | 0 | 11 | 0 | 7 | 8 | 10 | 30 | 1 | 352.76 |  | 0
|  | Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051) | [20 empty] | 0
Total |  |  | 101 | 403 | 20528.871 | 68 | 263 | 13187.781 | 0 | 7 | 20 | 17 | 12 | 66 | 10 | 24 | 21 | 72 | 177 | 14 | 1484.57 |  | 0

## Patna
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Patna | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Satish Prasad (8987263065) , AE :- S. Tiwari (9431495949), AE :- Atul Kr. Varanwal (9835658494) | [13 empty] | Name & Contact no. of PMC :- Enarch-JV-PIDC (A.K.Dutta- 9470353415/ Prakash-9431018537)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin Exp. (in Lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-101 | Nalanda | Katrisarai | 1 | M.S. Bhagwanpur 9939987297 | Roy Engineers, Basant Vihar Colony, Raghunath Path, Near Plastic Factory, R.P.S Road, Danapur, Patna-801503, Mob-9431011395 | 248.66 |  | 14.5.2013 | 12 Month | [6 empty] | 1 |  |  | 44.9
|  |  | Ben | 2 | M.S. Akouna 9570951336 | [9 empty] | 1
|  |  | Giriyak | 3 | M.S. Sakuchi Sarai 9631154626 | [9 empty] | 1 | [5 empty] | 2nd A/C bill paid
|  |  | Silao | 4 | Urdu.M.S. Barakar 9931004916 | [8 empty] | 1 | [6 empty] | Invalid list
|  |  | Ben | 5 | M.S. Ramganj 9135849205 | [12 empty] | 1
2 | USS-102 | Nalanda | Biharsarif | 1 | M.S. Mahanandpur 7352573660 | Retender | 299.07
|  |  | Biharsarif | 2 | M.S. Majidpur 9570625433
|  |  | Chandi | 3 | M.S. Dariya Bigha 9931236900
|  |  | Chandi | 4 | Urdu.M.S. Baisa 9939043903
|  |  | Noorsarai | 5 | M.S. Michaiganj Sakroura 9973050555
|  |  | Sarmera | 6 | M.S.Singhaul 9934212058
3 | USS-103 | Nalanda | Parwalpur | 1 | M.S. Bawukhana 8434655776 | Ram jee prasad. At -Chandmari Road Chauraha ,near water pump cyber zone patna 20 | 199.6 |  | 3.7.2013 | 12 Month | [7 empty] | 1 |  | 31.81 | 1st A/C Bill paid
|  |  | Hilsa | 2 | M.S. Rasai Bigha 9934593683 |  |  | 1 | [12 empty] | Insufficient land
|  |  | Islampur | 3 | M.S. Bargounw 9279149331 | [12 empty] | 1
|  |  | Islampur | 4 | M.S. Banbag 9934487509 | [9 empty] | 1
4 | USS-104 | Patna | Khushrupur | 1 | M.S. Jagmat Bigha 9771442400 | Vikash Kumar Singh, Kankarbagh, Patna | 203.16 | 1 | [12 empty] | Insufficient land
|  |  | Khushrupur | 2 | U.M.S. Arrai Benipur 9135748584 |  |  | 1 | [12 empty] | Insufficient land
|  |  | Barh | 3 | U.M.S. Malahi 7250940590 | [6 empty] | 1 | [8 empty] | Tie beam
|  |  | Fatuha | 4 | M.S. Gabaspur 9955241716 | [6 empty] | 1 | [8 empty] | Tie beam
5 | USS-105 | Patna | Patna Sadar | 1 | M.S. Khokhna 9135334773 | Shristi Developers Pvt. Ltd., Krishi Utpadan Bazar Samiti Katra Bazar, Patna City, Mob-9334998030 | 202.104 |  | 3.5.2013 | 12 Month | [6 empty] | 1 |  |  | 43.59 | Roof casted
|  |  | Patna Sadar | 2 | M.S. Marchi 9430934711 | [9 empty] | 1
|  |  | Punpun | 3 | Urdu.M.S. Painarghat 9546616297 9572202274 | [9 empty] | 1 | [5 empty] | 2nd A/C bill paid
|  |  | Phulwarisarif | 4 | M.S. Kurthoul 9431817223 | [12 empty] | 1
6 | USS-106 | Patna | Bihta | 1 | M.S. Kateshar 7250695245 | Durga Electric, Vill+P.O-Amhara, P.S-Bihta, Distt.-Patna- 801118, Mob-9431219007 | 149.88 | 1 | [12 empty] | Low Land about 12'-0"
|  |  | Bikram | 2 | M.S. Barah 8084301353 |  |  | 1 | [12 empty] | Land not regitered to school
|  |  | Bihta | 3 | M.S. Kanhauli 9386873458 |  |  | 1 | [12 empty] | Land dispute between School & college
7 | USS-107 | Patna | Dhanrua | 1 | M.S. Gawaspur Tubhara 8298503210 | Vijay kumar | 50.2567 | 1 | [12 empty] | Insufficient land
8 | USS-108 | Bhojpur | Agioan | 1 | M.S. Berath 09955434210 | Amrendra Kumar Singh, Vill- Janakpuria, P.O-Panwari, P.S-Chauri,(Sahar), Distt.-Bhojpur. | 245.76 |  | 5.1.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 61.2
|  |  | Charpokhari | 2 | M.S. Mukundpur 9525995189 9931418305 | [11 empty] | 1
|  |  | Charpokhari | 3 | M.S. Kumhaila 8294303061 | [9 empty] | 1 | [5 empty] | 4th A/C bill paid
|  |  | Charpokhari | 4 | M.S. Sonbarsa 9771517920 | [9 empty] | 1 | [5 empty] | Roof casted
|  |  | Agioan | 5 | M.S. Lasarhi 9661399087 |  |  | 1 | [12 empty] | Land not available
9 | USS-109 | Bhojpur | Garhani | 1 | M.S. Aslan Bahadurpur 8092200406 | Narendra Kumar, AT-Veer Kunwar Singh Nagar, Katira, Bhojpur. | 245.97 |  | 23.1.2013 | 12 Month | [5 empty] | 1 |  |  |  | 35.58
|  |  | Garhani | 2 | M.S. Kaup 9708602077 | [5 empty] | 1 | [9 empty] | Land dispute
|  |  | Udawant Nagar | 3 | M.S. Karisath 9934636023 | [9 empty] | 1 | [5 empty] | 2nd A/C bill paid
|  |  | Udawant Nagar | 4 | M.S. Nawada Ben 9472456455 | [9 empty] | 1
|  |  | Udawant Nagar | 5 | U.M.S. Chaurai 993900732 | [9 empty] | 1
10 | USS-110 | Bhojpur | Barhara | 1 | U.M.S. Shaligram Singh Ka Tola 8409626973 | Retender | 246.68
|  |  | Barhara | 2 | M.S. Pakri 9304856454
|  |  | Barhara | 3 | Govt.M.S. Bakhorapur 9570469585
|  |  | Koilwar | 4 | M.S. Khesarhiyan 9973554537
|  |  | Koilwar | 5 | M.S. Khangaown 9631265664
11 | USS-111 | Bhojpur | Jagdishpur | 1 | M.S.Kakila 8083448999 | Sudarshan Mahto, AT- Jagdishpur, Arrah.(Bhojpur) | 197.19 |  | 16.1.2013 | 12 Month | [7 empty] | 1 |  | 75.11
|  |  | Jagdishpur | 2 | U.M.S. Isarhi 9973041304 | [10 empty] | 1
|  |  | Tarari | 3 | M.S. Jethwar 9006698116 9931037637 | [11 empty] | 1 |  |  |  | 6th A/C bill paid
|  |  | Tarari | 4 | M.S. Chakiya 9572477211 9934218390 | [9 empty] | 1
12 | USS-112 | Bhojpur | Bihiyan | 1 | M.S. Sikariya 8873764301 | Manoj Kumar, Jagdishpur, Bhojpur | 191.984 | 1
|  |  | Bihiyan | 2 | M.S. Kouriya 9431438960 | [8 empty] | 1
|  |  | Shahpur | 3 | M.S. Jawainiya 8083447757 7677504269 |  |  | 1
|  |  | Shahpur | 4 | M.S. Suhiya 9471919316 | [6 empty] | 1
13 | USS-113 | Bhojpur | Tarari | 1 | M.S.Gahruan 9472135231 9162748057 | Arvind Kumar, 401, Shakuntala Enclave, Sahajanand Path, Patel Nagar, Patna-800023 | 246.37 |  | 6.7.2013 | 12 Month |  |  | 1
|  |  | Tarari | 2 | M.S.Kurmuri 9576176655 | [8 empty] | 1
|  |  | Tarari | 3 | M.S. Tarari 9631136009 | [9 empty] | 1
|  |  | Tarari | 4 | M.S. Kartha 8757442408 9546312131 | [9 empty] | 1
|  |  | Tarari | 5 | M.S.Bagar 9801629878 | [7 empty] | 1
14 | USS-114 | Bhojpur | Sandesh | 1 | U.M.S.Nasratpur 9334673203 | M/s Maa khamakhya madan ji kahata nawada;Ara;Dist-Bhojpur pin-802301 | 196.34 | 1 | 5.7.2013 | 12 Month | [10 empty] | Land not available
|  |  | Sahar | 2 | M.S. Baruhi 9199571702 | [6 empty] | 1 | [8 empty] | Land not available
|  |  | Ara | 3 | M.S. Basantpur 09308735308 | [9 empty] | 1
|  |  | Sahar | 4 | M.S. Nawada 9934483628 | [11 empty] | 1
15 | USS-115 | Buxar | Buxar | 1 | M.S.Nadanw 9234866577 9430015496 | M/S Nithes Raj, Rathod Newaji Tola, P.O.- Gurukul Mehian, Chapra | 198.08 | 1
|  |  | Buxar | 2 | M.S.Manjharia 9472951603 |  |  | 1
|  |  | Rajpur | 3 | M.S. Khiri 9470753325 |  |  | 1
|  |  | Rajpur | 4 | Urdu M.S. Banni 9973105344 |  |  | 1
16 | USS-116 | Buxar | Dumraon | 1 | M.S.Nuaon 9939391144 | Retender | 247.8
|  |  | Dumraon | 2 | M.S. Kanjharua 9955867071
|  |  | Dumraon | 3 | M.S. Mathila 9931890937
|  |  | Dumraon | 4 | M.S. Karuaj 9931281346
|  |  | Dumraon | 5 | M.S. Rampur Mathiya 9798067177
17 | USS-117 | Buxar | Nawanagar | 1 | M.S.Pramanpur 9386827434 | Tender Process | 198.84
|  |  | Ithari | 2 | M.S. Barkagaon 8651239720
|  |  | Ithari | 3 | M.S. Harpur 9939590039
|  |  | Ithari | 4 | M.S. Basawan Kala 7739120173
18 | USS-118 | Buxar | Simiri | 1 | M.S.Dhanpura 9199795834 | Ganga Enterprises, Gola Ghat, Buxar, Mob-9431451802 | 150.7 | 1 | [12 empty] | Name to be changed from primary to middel school change
|  |  | Simiri | 2 | M.S. Barka Singhnpura 9934740004 |  |  | 1 | [12 empty] | Land not available
|  |  | Simiri | 3 | M.S. Kharha Tarnh 9199359782 |  |  | 1 | [12 empty] | Land not available
19 | USS-119 | Kaimur | Bhabhua | 1 | M.S.Miun | Retender | 199.6
|  |  | Bhabhua | 2 | M.S.Piliyan
|  |  | Bhabhua | 3 | M.S. Mehsuan
|  |  | Bhabhua | 4 | M.S. Mohan Darwan
20 | USS-120 | Kaimur | Ramgarh | 1 | M.S.Sijhua | Retender | 251.29
|  |  | Ramgarh | 2 | M.S.Upari 9939613033
|  |  | Nuaon | 3 | Govt. Basic School Kari Ram Akhili
|  |  | Nuaon | 4 | M.S.Mushiyan 9546505256
|  |  | Durgawati | 5 | U.M.S Nuaon 9199361709
21 | USS-121 | Rohtas | Karakat | 1 | M.S.Dewmarkande 8969878557 | Retender | 238.39
|  |  | Karakat | 2 | Girl's M.S.Motha 9162106111
|  |  | Nasriganj | 3 | M.S. Paiga9955477596, 9905271092
|  |  | Nasriganj | 4 | M.S. Pawani 9473321921, 8298414859
|  |  | Akorhigola | 5 | M.S.Chhapra 9934757484
22 | USS-122 | Rohtas | Surajpura | 1 | Govt.M.S.Agrair Khurd, 9430254440 | Vikash Kumar | 287.17 | 1
|  |  | Dinara | 2 | M.S.Sarwan ,8084920823 | [6 empty] | 1
|  |  | Dinara | 3 | M.S. Baliyan, 9931111475 | [6 empty] | 1
|  |  | Dinara | 4 | M.S. Bararhi, 9955083783 | [6 empty] | 1
|  |  | Bikramganj | 5 | M.S. Jamorhi, 9955952582 |  |  | 1 | [12 empty] | Required boundarywall demolision
|  |  | Bikramganj | 6 | M.S. Dhusiyankala ,08521032016 |  |  | 1 | [12 empty] | Required old building demolision
23 | USS-123 | Rohtas | Kochas | 1 | M.S.Balthari 09162543647, 09473245646 | Anita singh; Vill+PO-Nahauna;PS-Sasaram mufussil;Dist-Rohtas(Bihar) | 291.76 |  | 29.8.2013 | 12 Month | 1 | [8 empty] | 18.71
|  |  | Kochas | 2 | M.S. Ubadhi, 8002578689 | [9 empty] | 1 | [5 empty] | Roof casted
|  |  | Kochas | 3 | M.S. Kuchila, 8002537247 | [6 empty] | 1
|  |  | Kargahar | 4 | U.M.S. Goghara, 9931721820 | [7 empty] | 1 | [7 empty] | 1st A/C Bill paid
|  |  | Kargahar | 5 | M.S. Khanethi, 9631193620 | [9 empty] | 1 | [5 empty] | 1st floor sill level
|  |  | Kargahar | 6 | M.S. Rampur Naresh, 9801892595 | [11 empty] | 1
24 | USS-124 | Rohtas | Chenari | 1 | M.S. Ramgarh 9771746971 | Lallan sukla;Indraraj Bhawan Fajalgang;Sasaram | 241.275 |  | 26.7.2013 | 12 Month |  |  |  |  | 1 | [5 empty] | Shuttering
|  |  | Chenari | 2 | M.S. Chandrakaithi, 9934281842 | [9 empty] | 1 | [5 empty] | Roof casted
|  |  | Sheosagar | 3 | M.S. Alampur, 9572407040 | [7 empty] | 1
|  |  | Sheosagar | 4 | M.S. Sonhar 9006103550 | [11 empty] | 1
|  |  | Sasaram | 5 | M.S. Akasi , 9204460486 | [11 empty] | 1
25 | USS-125 | Rohtas | Nouhatta | 1 | M.S. Anndichak, 8002169557 | M/S S.A.B. Construction, AT-Chitouli, P.O-Ramdihara, P.S+Distt.-Rohtas. | 49.17 |  | 2.2.2013 | 12 Month | [8 empty] | 1 | 21.44 | 3rd A/C bill paid
| Total nos. of school |  |  | 107 |  |  | 5277.0997 | 21 |  |  | 2 | 8 | 4 | 3 | 19 | 2 | 8 | 5 | 1 | 332.34
Following School name Attached in Disputed/ Invalid Upgraded School List vide Letter no- 132/ 22.01.13 of Directod (S.E.) & Letter no 88/ 09.11.2012 of DEO, Patna,so Following School name has been Deleted from above list
S.N. | Group No. | Name of District | Name of Block |  | Name of School
1 | USS-104 | Patna | Sampatchak |  | M.S. Chainpur 9006458543*
2 | USS-105 | Patna | Phulwarisarif |  | U.M.S.Paithani Nathupur * 9931679454
3 | USS-107 | Patna | Dhanrua |  | M.S. Nainori 9771538556*
4 | USS-107 | Patna | Dulhin Bazar |  | M.S. Sadwah 9801912969*
5 | USS-112 | Bhojpur | Bihiyan |  | M.S.Ranisagar 9939288398*
6 | USS-124 | Rohtas | Sheosagar |  | M.S. Janjara, 9661198236,* 8544238269

## Magadh
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Magadh | [8 empty] | Date:-31.01.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Mallu Singh (9835471249/ 9471211134) | [6 empty] | Name & contact no. of PMC :- Enarch-JV-PIDC (A.K.Dutta- 9470353415 & Prakash ji- 9431018537)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-143 | Jehanabad | Kako | 1 | M.S.Kajisarai 9934814478 | Kaushlendra Kumar | 192.62 |  | 21.1.2013 | 12 Month | [8 empty] | 1 | 126.26
|  |  | Kako | 2 | M.S.Dedhsaiya, 9955836404 | [13 empty] | 1 |  | 8th A/C Bill Paid
|  |  | Kako | 3 | M.S.Pinzour 9931803275 |  |  | 1 | [12 empty] | Land prob.
|  |  | Modanganj | 4 | M.S.Jalalpur , 9939911087 | [13 empty] | 1
2 | USS-144 | Jehanabad | Hulasganj | 1 | M.S.Vira, 9771693433 | Retender | 142.51
|  |  | Makhdumpur | 2 | M.S.Akbarpur, 9934858600
|  |  | Jehanabad | 3 | M.S.Bazartali, 9955297199
3 | USS-145 | Nawada | Nawada | 1 | U.M.S. Jhunathi, 9631172127 | M/S Pramod Construction, At- Kurkuri, P.O.- Phulwarisharif, Patna- 801505 | 240.54 |  | 28.6.2013 | 12 Month |  |  | 1 | [6 empty] | 16.03
|  |  | Akbarpur | 2 | U.M.S. Derma, 9931232692 | [9 empty] | 1
|  |  | Akbarpur | 3 | M.S. Kuhaila, 9771085197 | [9 empty] | 1 | [5 empty] | 2nd on A/C Bill Paid
|  |  | Akbarpur | 4 | M.S. Paharpur, 9771672098 |  |  | 1 | [12 empty] | Aproach road not available
|  |  | Nawada | 5 | M.S. Wermi, 9708857028 |  |  | 1
4 | USS-146 | Nawada | Govindpur | 1 | M.S. Rampur, 9771867218 | Retender | 246.5667
|  |  | Roh 3 | 2 | M.S. Wara panday, 9931630318
|  |  | Pakribarawan | 3 | M.S. Deodha, 8578046529
|  |  | Pakribarawan | 4 | M.S. Ukaorah
|  |  | Kashichak | 5 | U.M.S. Vishbnathpur , 9386540972
5 | USS-147 | Nawada | Narhat | 1 | M.S. Khanwa, 9905846666 | Tender Process | 95.12
|  |  | Hasua | 2 | Adarsh M.S. Bhadsaini, 9939018688
6 | USS-148 | Gaya | Bodh Gaya | 1 | M.S. Moratala, 9934282506 | Tender Process | 186.17
|  |  | Bodh Gaya | 2 | M.S. Titoiya, 9934672899
|  |  | Bodh Gaya | 3 | M.S. Bataspur, 9470447309
|  |  | Bodh Gaya | 4 | M.S. Gapha Kala, 9934972678
7 | USS-149 | Gaya | Dumariya | 1 | M.S. Bhangiya, 9472443151 9801769544 | Retender | 245.93
|  |  | Imamganj | 2 | M.S. Karsan Kala, 9199768865, 9199061230
|  |  | Imamganj | 3 | M.S. Salaiya, 9471093249, 8969123151
|  |  | Imamganj | 4 | M.S. Naudiha, 9135294703, 8235212693
|  |  | Imamganj | 5 | M.S. Mjiyarpur Bahera, 9801672105, 8092670699
8 | USS-150 | Gaya | Belaganj | 1 | M.S. Chirala, 9934883794, 9199681520 | Retender | 188.28
|  |  | Tekari | 2 | M.S. Urdu Bishnupur, 9771128251, 9135850031
|  |  | Konch | 3 | M.S. Goribigha, 9939408167
|  |  | Konch | 4 | M.S. Ahiyarpur, 9934008030
9 | USS-151 | Gaya | Bathani | 1 | Basic M.S. Radui, 7654409634 | Roy Engineers, Basant Vihar Colony, Raghunath Path, Near Plastic Factory, R.P.S Road, Danapur, Patna-801503, Mob-9431011395 | 143.87 |  | 14.5.2013 | 12 Month | [7 empty] | 1 |  | 72.86
|  |  | Bathani | 2 | M.S. Karubigha, 9934427661 | [13 empty] | 1 |  | 3rd A/C bill paid
|  |  | Khizarsarai | 3 | M.S. Sonas, 9931434932 | [13 empty] | 1
10 | USS-152 | Gaya | Tankauppa | 1 | M.S.Utalibara, 9934434061 | Sanjeet kumar, Vill-Thuthipur Nisarpura, Parsa Bazar, Patna | 290.25 |  | 25.7.2013 | 12 Month | [7 empty] | 1 |  | 30.92
|  |  | Tankauppa | 2 | M.S. Gajadharpur, 9934063626 | [11 empty] | 1 |  |  |  | 2nd A/C Bill paid
|  |  | Fatehpur | 3 | M.S. Khajuri, 8969107991 |  |  | 1
|  |  | Fatehpur | 4 | M.S. Nagwa, 9798270089 | [5 empty] | 1
|  |  | Manpur | 5 | M.S. Sadikpur, 9955056070, 9801212926 | [7 empty] | 1
|  |  | Manpur | 6 | M.S. Kaiya, 9771196567, 7277124934 | [9 empty] | 1
11 | USS-153 | Gaya | Barachatty | 1 | U.M.S. Barawadih, 9631852939 | Retender | 196.93
|  |  | Guraru | 2 | M.S. Manjhar, 9572789270
|  |  | Amas | 3 | M.S. Baliyari, 9570551566, 8294856371, 8051934469
|  |  | Sherghatty | 4 | M.S. Naknuppa, 9431289085
12 | USS-154 | Aurangabad | Kutumba | 1 | M.S. Mahsu, 9631400107 | M/S Mateshwari Construction, Mamka Niwas, New Area,Chitour Nagar, Distt.-Aurangabad,Bihar. | 256.42 |  | 2.9.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 26.75
|  |  | Kutumba | 2 | M.S. Chintaman Bigha, 9199013498 | [9 empty] | 1 | [5 empty] | 1st A/C Bill Paid
|  |  | Kutumba | 3 | M.S. Darmi, 9955519885, 9931921788 |  |  | 1 | [12 empty] | Land dispute
|  |  | Kutumba | 4 | M.S. Jhakri, 7654545570, 9162783589 | [11 empty] | 1
|  |  | Deo | 5 | M.S. Vijouli, 9801123435 | [10 empty] | 1
13 | USS-155 | Aurangabad | Barun | 1 | M.S. Tahal Amba, 9931428989 | Raj Mangal Singh, Vill-Dihuri , P.O-Malwan, P.S- Khudwan, Distt.- Aurangabad, Bihar. | 206.29 |  | 9.4.2013 | 12 Month | [6 empty] | 1 |  |  | 23.55 | 2nd A/C bill paid
|  |  | Obra | 2 | M.S. Ratwar, 9931418907 | [8 empty] | 1 | [6 empty] | Land dispute
|  |  | Obra | 3 | M.S. Tejpur, 9973299799 |  |  | 1 | [12 empty] | Land not available
|  |  | Obra | 4 | M.S. Karsawan, 9470488343 | [9 empty] | 1
14 | USS-156 | Aurangabad | Haspura | 1 | M.S. Piru, 9135064392 | M/S Mateshwari Construction, Mamka Niwas, New Area,Chitour Nagar, Distt.-Aurangabad,Bihar. | 150.61 | 1 | 8.5.2013 | 12 Month | [9 empty] | 5.59 | Land encroachment
|  |  | Haspura | 2 | M.S. Sriwanbhatt, 9939023445 |  |  | 1 | [12 empty] | Land not available
|  |  | Daudnagar | 3 | M.S. Belwan, 9162117681,9934238032 | [8 empty] | 1 | [6 empty] | 1st on A/C Bill Paid
15 | USS-157 | Aurangabad | Raphiganj | 1 | M.S. Badhopur, 9955270100 | Retender | 250.43
|  |  | Raphiganj | 2 | M.S. Pogar, 9973150471
|  |  | Madanpur | 3 | M.S. Judahi, 9931892284
|  |  | Madanpur | 4 | M.S. Saliya, 9955803641
|  |  | Raphiganj | 5 | M.S. Danai, 9097351245
|  | Total nos. of school |  | 62 |  |  | 3032.5367 | 8 |  |  | 1 | 0 | 2 | 2 | 6 | 1 | 3 | 2 | 5 | 301.96
Following School name attached in Disputed Upgraded School list Vide Letter no 132 Dated- 22.01.2013 of Director (S.E.), so Following School name has been Deleted from above list
S.N. | Group No. | Name of District | Name of Block |  | Name of School
1 | USS-146 | Nawada | Kowakole |  | M.S. Darawan,* 9939193170

## Bhagalpur
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Bhagalpur | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar (9431487994) | [6 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-126 | Bhagalpur | Kahalgaon | 1 | M.S.Basudeopur Bhaluya 9801295281 | Retender | 196.6
|  |  | Kahalgaon | 2 | M.S. Maheshmunda 8987170031
|  |  | Kahalgaon | 3 | M.S. Ekdara 9961316463
|  |  | Kahalgaon | 4 | M.S. Saur 9430428851
2 | USS-127 | Bhagalpur | Pirpaiti | 1 | M.S.Mahuadhih 9955027709, 7549131650 | Retender | 246.48
|  |  | Pirpaiti | 2 | M.S. Maultola, 9534766339
|  |  | Pirpaiti | 3 | M.S.Mahadeo Tikar 9973648394
|  |  | Pirpaiti | 4 | M.S.Ekchari Diyara 9507752647, 9934426205
|  |  | Pirpaiti | 5 | M.S.Lakshmipur 7549681618
3 | USS-128 | Bhagalpur | Goradih | 1 | M.S.Birnaugha 9955198006 | Retender | 197.28
|  |  | Goradih | 2 | M.S.Agarpur 9931629228
|  |  | Goradih | 3 | M.S.Danda Bazar 9801648849
|  |  | Sabaur | 4 | Govt. M.S.Kurpat 9204660635, 9931729153
4 | USS-129 | Bhagalpur | Rangrachauk | 1 | M.S.Murli 9534523062 | Retender | 99.82
|  |  | Gopalpur | 2 | M.S.Kelendi Nagar 9801016695
5 | USS-130 | Bhagalpur | Nath Nagar | 1 | M.S.Fathehpur 9199519165 | M/S Kuhu Construction Co., Anandgarh Colony, Jail Road, Tilakamanjhi, Bhagalpur. | 248.61 |  | 8.2013 | 12 Month | [6 empty] | 1 |  |  | 112.9
|  |  | Shahkund | 2 | M.S.Bakchapar 9939070704 | [12 empty] | 1 |  |  | 4th A/C bill paid
|  |  | Shahkund | 3 | M.S.Khaira 9931326337 | [12 empty] | 1
|  |  | Sultanganj | 4 | M.S.Abharatanpur 9939267569 | [13 empty] | 1
|  |  | Sultanganj | 5 | M.S.Kiranpur 9801149910 | [13 empty] | 1
6 | USS-131 | Banka | Amarpur | 1 | M.S.Surihari 9931727384 | Rajendra Kumar, AT-Pipradih, P.O-Jhajha, Distt.-Jamui. | 151.72 |  | 11.9.2013 | 12 Month |  | 1
|  |  | Belhar | 2 | M.S.Hatiyadadha 8521126388 |  |  | 1
|  |  | Dhoraiya | 3 | U.M.S.Jharkha 9934883358 |  |  | 1
| Total nos. of school |  |  | 23 |  |  | 1140.51 | 2 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 112.9

## Munger
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Munger | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214) | [6 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-132 | Sheikhpura | Barbigha | 1 | M.S.Keuti 9905214436 | Arbind Prasad, Vill-Purankama, Sheikhpura, Bihar- 811105. | 239.75 |  | 12.4.2013 | 12 Month | [8 empty] | 1 | 81.26
|  |  | Shekhpura | 2 | M.S.Lodipur 9631858046, 9431446473 | [13 empty] | 1 |  | 2nd on A/C bill Paid
|  |  | Chewara | 3 | M.S. Lahana 9852161874 | [11 empty] | 1
|  |  | Ghat Kushumbha | 4 | M.S. Bamghat 8809298062 | [11 empty] | 1
|  |  | Ariari | 5 | M.S.Husainawad 8651133181 | [11 empty] | 1
2 | USS-133 | Lakhisarai | Barahiya | 1 | M.S.Pali 9546977875 | Retender | 285.83
|  |  | Barahiya | 2 | M.S.LalDiyara 9097688412
|  |  | Halsi | 3 | M.S. Geruapursanda 8084044144
|  |  | Lakhisarai | 4 | U.M.S. Kachhiyana 9934788038, 9199110418
|  |  | Suryagarha | 5 | U.M.S. Lahasaurwa 9631695175, 8434346388
|  |  | Pipariya | 6 | M.S. Pawai 9263032826
3 | USS-134 | Jamui | Sono | 1 | M.S.Buijhayt 09631584296 | A.K. Construction, AT-Devpur, Khaira, Distt.-Jamui(Bihar) | 49.12 | 1
4 | USS-135 | Munger | Asarganj | 1 | M.S.Chakhand 9135065232 | Rajendra Kumar, AT-Pipradih, P.O-Jhajha, Distt.-Jamui. | 153.29 |  | 2.3.2013 | 12 Month | [5 empty] | 1 |  |  |  | 28.28
|  |  | Asarganj | 2 | M.S. Beran 9204931976 | [12 empty] | 1 |  |  | 2nd A/C bill paid
|  |  | Tarapur | 3 | M.S. Mahamadpur 9709507263 | [6 empty] | 1
5 | USS-136 | Munger | Sangrampur | 1 | M.S.Bhikhdih 9006793477 | Rajendra Kumar, AT-Pipradih, P.O-Jhajha, Distt.-Jamui. | 150.56 |  | 2.3.2013 | 12 Month | [5 empty] | 1 |  |  |  | 18.93 | 1st A/C Bill Paid
|  |  | Sangrampur | 2 | M.S.Khapra 9934832035 |  |  | 1 | [12 empty] | Land not available
|  |  | Sangrampur | 3 | M.S.Katiyari 9199782900 | [10 empty] | 1
6 | USS-137 | Munger | Bariyarpur | 1 | M.S.Ratanpur 9430453475 | M/S B.S. Construction, P.D. Road, Barmasia, Deoghar | 249.84 |  | 23.10.2013 | 12 Month |  |  |  | 1
|  |  | Haweli Khadagpur | 2 | M.S.Jamuhat 8051879837 | [9 empty] | 1
|  |  | Haweli Khadagpur | 3 | M.S.Gangata 8544287260 | [8 empty] | 1
|  |  | Haweli Khadagpur | 4 | U.M.Gangata More 9471899589 | [8 empty] | 1
|  |  | Haweli Khadagpur | 5 | M.S.Chhoti Manjhagoya 9470400961, 9934017811 |  |  | 1
7 | USS-138 | Begusarai | Mansurchak | 1 | M.S.Chhabilapur 9771848155 | Tender Process | 248.32
|  |  | Begusarai | 2 | M.S.Bharra 9204202640
|  |  | Begusarai | 3 | M.S.Babasudebpur 9934708295, 88777402400
|  |  | Matihani | 4 | M.S.Richiyahi Nayartol 9973647476, 9608273410
|  |  | Sahebpur Kamal | 5 | M.S.Rajoura 9709067460
8 | USS-139 | Begusarai | Bachhawara | 1 | M.S.Dadupur 9801471859 | Ray & Raj Engineering Pvt. Ltd. , Vill+P.O- Kharahia, Distt.-Samastipur, Pin-848208, 9430047216 | 250.83 |  | 8.5.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 24.59
|  |  | Chhaurahi | 2 | M.S.Pansalla 9939728107 | [9 empty] | 1
|  |  | Chhaurahi | 3 | M.S.Sihama 9973149590 | [9 empty] | 1 | [5 empty] | 1st A/C Bill paid
|  |  | Khodawantpur | 4 | M.S.Begampur 9631129256 | [10 empty] | 1
|  |  | Nawakothi | 5 | M.S.Rajakpur 9667863543 | [9 empty] | 1
9 | USS-140 | Begusarai | Garhpura | 1 | M.S.Kuddhar 9955509070 | Ray & Raj Engineering Pvt. Ltd. , Vill+P.O- Kharahia, Distt.-Samastipur, Pin-848208, 9430047216 | 150.71 |  | 8.5.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 16.8
|  |  | Dandari | 2 | M.S.Katarmala 9709640304 | [9 empty] | 1 | [5 empty] | 1st A/C Bill paid
|  |  | Bakhari | 3 | M.S.Ghaghara 9570665862 | [11 empty] | 1
10 | USS-141 | Khagaria | Alauli | 1 | M.S.Shumbha Ghat 8969741611 | Retender | 202.44
|  |  | Alauli | 2 | M.S.Khairi Khutaha 9471283095
|  |  | Khagaria | 3 | M.S.Nanku Mandal Tola 9955646986
|  |  | Khagaria | 4 | M.S.Mathar 9771388437
11 | USS-142 | Khagaria | Beldaur | 1 | M.S.Kainjari 7549429234 | Rajendra Kumar, AT-Pipradih, P.O-Jhajha, Distt.-Jamui. | 156.61 |  | 2.3.2013 | 12 Month |  | 1 | [7 empty] | 14.27 | work stopped due to land dispute
|  |  | Beldaur | 2 | M.S.Khairi Kurbani 9631652583 | [9 empty] | 1 | [5 empty] | 1st A/C Bill Paid
|  |  | Parbatta | 3 | M.S.Timapur Lagar 8877288448 | [9 empty] | 1
| Total nos. of school |  |  | 43 |  |  | 2137.3 | 3 |  |  | 0 | 2 | 0 | 3 | 9 | 4 | 4 | 1 | 2 | 184.13

## Kosi
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Kosi | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790) | [7 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-199C | Saharsa | Banma Ithari | 1 | Middle School Ithari 8084243454 | Tender Process | 53.53
2 | USS-199D | Madhepura | Ghailarh | 1 | Middle School Chiknotwa 9430942006 | Avneesh Enterprises | 160.98 |  | 8.7.2013 | 12 Month |  | 1 | [7 empty] | 12.24
|  |  | Singheshwar | 2 | Middle School Barhari 9661376885 | [9 empty] | 1 | [5 empty] | 2nd on A/C Bill Paid
|  |  | Kumarkhand | 3 | Middle School Rahta 9631460084 |  |  | 1 | [12 empty] | Low land, water logged
| Total nos. of school |  |  | 4 |  |  | 214.51 | 1 |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12.24

## Purnea
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Purnea | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & contact no. of PMC :- Ranchi Design & consultancy Service Pvt. Ltd. (9431357124 & 9931102280)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-194 | Purnia | Amaur | 1 | U. M. S. Bagdar 9939096309 | M/S Shining Madhusudan Construction, Punia | 207.53 | 1
|  |  | K. Nagar | 2 | M S Gauasi 9473124829 |  |  | 1
|  |  | Purnia East | 3 | M S Maranga 9939732346 | [6 empty] | 1
|  |  | Rupauli | 4 | M. S. Bairiya 9434821065 |  |  | 1
2 | USS-195 | Katihar | Amdabad | 1 | M. S. Laxmipur Daiwa 7549854721 | Anil Kumar Singh | 162.45 | 1
|  |  | Manihari | 2 | Middle School Mirjapur 8084519254 941640318 |  |  | 1
|  |  | Mansahi | 3 | Middle School Mohanpur 9472890120 |  |  | 1
3 | USS-196 | Katihar | Pranpur | 1 | Middle School Kast Hawar 8809776384 9162325809 | Retender | 213.47
|  |  | Ajamnagar | 2 | Middle School Arihana 8809322797
|  |  | Ajamnagar | 3 | Middle School Dhena Baghchhala 9801372634
|  |  | Pranpur | 4 | Middle School Ghanhar Vighocha 9939688768
4 | USS-197 | Katihar | Barsoi | 1 | Middle School Barsoi Ghat 9431626189 | Retender | 212.56
|  |  | Dhankhora | 2 | Middle School Durgasthan Dhankhora9431869787
|  |  | Kodha | 3 | Middle School Marwa Najrachowki 9006363823
|  |  | Kadwa | 4 | Dukhi Ram Middle School Chandpur9709755452
5 | USS-198 | Araria | Brari | 1 | Middle School Laxmipur | Tender Process | 263.03
|  |  | Brari | 2 | Middle School Anarkali
|  |  | Hasanganj | 3 | Middle School Hasanganj
|  |  | Phalka | 4 | Middle School Morsanda
|  |  | Sameli | 5 | Middle School Dumar
6 | USS-199A | Araria | Forbesganj | 1 | Adarsh Middle School Mirjapur 9430521363, 9006224356 | Retender | 214.73
|  |  | Forbesganj | 2 | Middle School Hingna Aurahi 9771866450
|  |  | Narpatganj | 3 | Middle School Khabdah Dumriya 9661102737
|  |  | Narpatganj | 4 | Middle School Achra 9801296055
7 | USS-199B | Araria | Jokihat | 1 | Middle School Jhanpur 9471219710 | MD. Iftakhar Alam, AT-Sisauna, P.O+PS- Jokihat, Distt.- Araria, Pin- 854329, Bihar. | 159.24 |  | 28.5.2013 | 12 Month | [8 empty] | 1 | 59.96
|  |  | Raniganj | 2 | Middle School Koskapur 9199673607 | [13 empty] | 1 |  | 2nd A/C Bill paid
|  |  | Araria | 3 | Middle School Araria Basti 9661185784 | [13 empty] | 1
| Total nos. of school |  |  | 27 |  |  | 1433.01 | 6 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 59.96

## Tirhut
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Tirhut | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & Contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-158 | East Champaran | Turkauliya | 1 | M.S. Belwa Ray 9430645457 | Ranjeet Kumar, Vill- Shankar Saraiya,Fateh Tola,P.O-Turkaulia, Distt.-East Champaran (Bihar) | 161.64 |  | 10.9.2013 | 12 Month |  |  | 1
|  |  | Turkauliya | 2 | M.S. Jaishinghpur 9430209305 | [9 empty] | 1
|  |  | Motihari | 3 | M.S. Basantpur 9576483588 |  |  | 1 | [12 empty] | Land problem
2 | USS-159 | East Champaran | Pakridayal | 1 | M.S.Sishani 9934715029 | M/S C.S. Construction, Gayatri Nagar, Motihari. | 271.31 |  | 21.9.2013 | 12 Month |  |  | 1 | [6 empty] | 23.96
|  |  | Chaaiya | 2 | M.S.Madhudih 9430565177 |  |  | 1 | [12 empty] | Land not available
|  |  | Tetraiya | 3 | M.S.Maniyarpur 9471297810 | [7 empty] | 1 | [7 empty] | 1st A/C bill paid
|  |  | Pipra Kahi | 4 | M.S.Jhakracolony 9431270018 | [9 empty] | 1
|  |  | Ghorashahan | 5 | M.S.Samanpur 9939403946 | [7 empty] | 1
3 | USS-160 | West Champaran | Lauriya | 1 | Govt.M.S. Phulwariya 9431674559 | M/S C.S. Construction, Gayatri Nagar, Motihari. | 281.09 |  | 8.10.2013 | 12 Month |  |  |  |  | 1
|  |  | Narkatiyaganj | 2 | Govt.M.S. Bhadiharwa 8986137181 |  |  | 1 | [12 empty] | Land not available
|  |  | Mainatand | 3 | Govt.M.S. Damrapur 9572125416 | [8 empty] | 1
|  |  | Madhubani | 4 | M.S.Pakri Ahawa Khothwa 08002571785 | [9 empty] | 1
|  |  | Nautan | 5 | M.S.Sansariya 8757124792 |  |  | 1 | [12 empty] | Land not available
4 | USS-161 | Sheohar | Purnhiya | 1 | M.S.Basant Jagivan 9430526421 | Shushil kumar | 107.72 |  | 27.8.2013 | 12 Month |  |  |  |  | 1
|  |  | Dumri Katsari | 2 | M.S.Phulkaha 9631003475 |  |  | 1 | [12 empty] | Land not available
5 | USS-162 | Sitamarhi | Bathnaha | 1 | M.S.Belahi Jairam 9973134925 | Retender | 326.63
|  |  | Parsauni | 2 | M.S.Jisara 9931684677
|  |  | Suppi | 3 | M.S.Aktha 9470821881
|  |  | Riga | 4 | M.S.Ramnagara 9570781314
|  |  | Parihar | 5 | M.S.Sirsiya Bazar 8102085348 7654040371
|  |  | Dumri | 6 | M.S.Pakri Sanakarit 8294843032
6 | USS-163 | Sitamarhi | Runni Saidpur | 1 | M.S.Dhanukhi 9006835850 | Retender | 216.11
|  |  | Pupri | 2 | M.S.Maulanagar 9608713501
|  |  | Sursand | 3 | M.S.Bhitta Bazar 8271527471
|  |  | Bokhara | 4 | M.S.Chakauti 8986347412
7 | USS-164 | Vaishali | Lalganj | 1 | M.S. Paramanandpur 9939709788 | Man Mardan Shukla Construction Pvt. Ltd, Speaker Chowk, Naya Tola, Muzaffarpur. | 260.4 |  | 12.4.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 15.64
|  |  | Lalganj | 2 | M.S. Sathiyauta 9939770494 | [9 empty] | 1 | [5 empty] | 1st A/C Bill paid
|  |  | Bhagwanpur | 3 | M.S. Askaranpur |  |  | 1 | [12 empty] | Land not available
|  |  | Bhagwanpur | 4 | M.S. Kutubpur 9534509369 |  |  | 1 | [12 empty] | Dispute
|  |  | Lalganj | 5 | U.M.S. Basanta 9934417163 |  |  | 1 | [12 empty] | Land not available
8 | USS-165 | Vaishali | Jandaha | 1 | U. M.S. Shahpur Rohuya 9934414222 | M/S Samrat Construction | 260.45 |  | 23.8.2013 | 12 Month |  |  |  |  | 1
|  |  | Jandaha | 2 | M. S, Mahhisaur 9661844106 | [5 empty] | 1
|  |  | Sahadei Bujurg | 3 | M.S, Toimath 9939693675 | [7 empty] | 1
|  |  | Sahadei Bujurg | 4 | M.S, Nayaganj 9934912623 |  |  | 1 | [12 empty] | Land not available
|  |  | Jandaha | 5 | M.S, Bijrauti 9973922533 | [7 empty] | 1
9 | USS-166 | Vaishali | Raghopur | 1 | M. S,Tersiya 9631970772 | Retender | 263.68
|  |  | Raghopur | 2 | M.S,Paharpur 7654539556
|  |  | Bidupur | 3 | M. S, Mohanpur Kajipatti 9199314551
|  |  | Desari | 4 | M. S, Bhikhanpura 9973319373
|  |  | Rajapakar | 5 | M. S, Makhadumpur Pokhraira 9934478747
10 | USS-167 | Muzaffarpur | Kurhani | 1 | M. S, Chhitrauli 9934656924 | Man Mardan Shukla Construction Pvt. Ltd, Speaker Chowk, Naya Tola, Muzaffarpur. | 263.48 |  | 12.4.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 21.55
|  |  | Kurhani | 2 | U. M.S, Drohiratan 9801136261 | [11 empty] | 1
|  |  | Kurhani | 3 | M. S, Jhitki 9934019395 | [9 empty] | 1 | [5 empty] | 1st A/C bill paid
|  |  | Kurhani | 4 | M. S, Dariyapur Kefen 8051703323 | [9 empty] | 1
|  |  | Kurhani | 5 | M. S, Balbhadrapur 8809991008 | [9 empty] | 1
11 | USS-168 | Muzaffarpur | Paroo | 1 | M. S, Lal Chapra 9934760982 | Minni Devi | 212.1 |  | 1.7.2013 | 12 Month |  |  | 1
|  |  | Sahebganj | 2 | M. S, Bhagwanpur Kashi 8084360691 | [8 empty] | 1
|  |  | Sahebganj | 3 | M.S ,Rajwara 9934809051 | [6 empty] | 1
|  |  | Sahebganj | 4 | M. S, Jitachhapra 9939926195 | [9 empty] | 1
12 | USS-169 | Muzaffarpur | Bandra | 1 | M. S, Bendra 9939297191 | Minni Devi | 267.86 |  | 1.7.2013 | 12 Month |  |  |  |  | 1
|  |  | Bandra | 2 | M. S, Sakriman 9006863747 | [9 empty] | 1
|  |  | Bandra | 3 | M. S, Keshopur 9135823204 | [10 empty] | 1
|  |  | Sakra | 4 | M. S. Munni Baingari 9955660204 | [9 empty] | 1
|  |  | Bandra | 5 | M. S, Cachhahi 8757974704 | [10 empty] | 1
13 | USS-170 | Muzaffarpur | Motipur | 1 | M. S,Semra 9771240801 9835814768 | Rama Construction | 265.46 | 1
|  |  | Motipur | 2 | M. S, Mahamada 9934659092 | [5 empty] | 1
|  |  | Motipur | 3 | M. S, Nakta 9430864377 8235157414 | [5 empty] | 1
|  |  | Minapur | 4 | M. S,Ranikhaira 9430864835 9934203612 |  |  | 1
|  |  | Minapur | 5 | M. S,Rampur Ratan 9430865561 9798455140 |  |  | 1
14 | USS-171 | Muzaffarpur | Gaighat | 1 | M. S, Kothiya 9973191481 9931842980 | Tender Process | 262.25
|  |  | Gaighat | 2 | M. S,Balaur Bhatgama 8434895543 8434868088
|  |  | Gaighat | 3 | M. S,Dahila 9973658759
|  |  | Katra | 4 | M. S, Bakhari 9631173639
|  |  | Bochahan | 5 | Middle, Kefen 9162802550
15 | USS-172 | Muzaffarpur | Aurai | 1 | M. S, Chahuta 9973925814 | Rakesh Ranjan, At- Narayan Bhawan, J.P. Colony Chandanwara, Muzaffarpur | 265.35 |  | 30.10.2013 | 12 Month |  |  |  | 1
|  |  | Aurai | 2 | M. S, Rajkhand 9431806467 | [9 empty] | 1
|  |  | Marwan | 3 | M S, Bishunpur 9471621233 9939934993 | [10 empty] | 1
|  |  | Mushhari | 4 | M. S, Dronpur | [9 empty] | 1
|  |  | Muraul | 5 | M. S, Pilkhi | [9 empty] | 1
| Total nos. of school |  |  | 69 |  |  | 3685.53 | 12 |  |  | 3 | 1 | 7 | 3 | 19 | 3 | 1 | 0 | 0 | 61.15

## Darbhanga
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Darbhanga | [10 empty] | Date:-31.01.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115) | [7 empty] | Name & Contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-187 | Madhubani | Babu Barhi | 1 | Govt. Middle School, Barhara | Avaneesh Enterprises, III-K-35/3A, Nehru Nagar, Ghaziabad. | 276.08 |  | 24.4.2013 | 12 Month |  |  | 1 | [6 empty] | 16.96 | 1st on A/C Bill paid
|  |  | Lakhanpur | 2 | Govt. Middle School, Belaucha 7739262788 |  |  | 1 | [12 empty] | Land not available
|  |  | Jaynagar | 3 | Middle School, Dhaniyapatti 9931037199 9661794550 |  |  | 1 | [12 empty] | No land
|  |  | Rajnagar | 4 | Govt. Middle School, Kewalpatti 9430032594 8051418065 | [8 empty] | 1
|  |  | Khutauna | 5 | Govt. Middle School, Malin Belha 9572178379 | [7 empty] | 1
2 | USS-188 | Madhubani | Banipatti | 1 | Govt. Middle School, Ganguli 9431629001 | Narendra Prasad Singh, Chakla Nirmali, Supaul. | 163.67 | 1
|  |  | Kaluahi | 2 | Govt. Middle School, Kalikapur 9973900631 |  |  | 1
|  |  | Bisfi | 3 | Govt. Middle School, Singhaso 9162249674 8051935537 |  |  | 1
3 | USS-189 | Samastipur | Shivajinagar | 1 | Middle School, Shripur Bhataura 9955507715 | Arvind Kumar | 105.625 |  |  |  | 1
|  |  | Vibhutipur | 2 | U. M. S, Mustafapur 7654688593 | [6 empty] | 1
4 | USS-190 | Darbhanga | Kusheshwarsthan East | 1 | U. M. S, Barniya 7870017996 | Madhav Construction, Vill- Andama, P.O.-Kusauthar, Distt- Darbhanga | 108.6333 | 1
|  |  | Kusheshwarsthan West | 2 | U. M. S, Sihariya 8969431987 |  |  | 1
5 | USS-191 | Darbhanga | Manigachhi | 1 | U. M. S, Dahaura 9431405480 | Rajesh Kumar, C/O Shiva Hardware, Sadar Bazar, Phulwari Sharif, Patna. | 271 | 1 | 24.4.2013 | 12 Month | [9 empty] | 6.46 | Land not available
|  |  | Kewati | 2 | M. S, Koila Majhigama 9304020023 | [6 empty] | 1 | [8 empty] | Dispute
|  |  | Kewati | 3 | Mahant Bansi Das Jagdish Das Middle School, Pachadi 9708287712 | [9 empty] | 1 | [5 empty] | 1st on A/C Bill paid
|  |  | Singheshwar | 4 | Middle School, Sanhapur 9801444701 | [6 empty] | 1
|  |  | Singheshwar | 5 | U. M. S, Katka 9473151051 | [6 empty] | 1 | [8 empty] | Land not available
6 | USS-192 | Darbhanga | Bahadurpur | 1 | M. S, Daing 9199229540 | Retender | 212.58
|  |  | Biraul | 2 | M. S, Koilajan 9939650547
|  |  | Benipur | 3 | U. M. S, Ramouli 9931745776
|  |  | Biraul | 4 | U. M. S, Balha 7631905606
7 | USS-193 | Darbhanga | Alinagar | 1 | U M S, Jayantipur 9431691474 | Kailash Prasad Yadav Construction Pvt. Ltd., R/O- AT+P.O- Hulas, P.S- Raghopur, Distt.-Supaul, Pin-852111 | 217.14 |  | 24.5.2013 | 12 Month | [7 empty] | 1 |  | 43.71
|  |  | Alinagar | 2 | U.M S, Garaul Chakka 9430640027 | [12 empty] | 1 |  |  | 1st on A/C Bill paid
|  |  | Alinagar | 3 | U. M. S, Rampur Uday 9546520079 |  |  | 1 | [12 empty] | Land not available
|  |  | Hanuman Nagar | 4 | M. S, Tarlahi 9608648110 | [12 empty] | 1
| Total nos. of school |  |  | 25 |  |  | 1354.7283 | 9 |  |  | 1 | 4 | 2 | 1 | 1 | 0 | 0 | 3 | 0 | 67.13
Following School name Attached in Disputed/ Invalid Upgraded School List vide Letter no- 132/ 22.01.13 of Directod (S.E.) ,so Following School name hasbeen Deleted from above list
S.N. | Group No. | Name of District | Name of Block |  | Name of School
1 | USS-189 | Samastipur | Mohanpur |  | Middle School, Jaunpur * 9973115253
2 | USS-189 | Samastipur | Warishnagar |  | Middle School, Satmalpur * 8002399228
3 | USS-190 | Darbhanga | Baheri |  | Middle School, Paghari * 9934872732 9470624497

## Saran
BSEIDC, PATNA
Progress report for the construction of USS school building
Name of Division :- Saran | [14 empty] | Date:-31.01.2014
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Hemant kr. (7488022930), AE :- Chandramadhav Singh (9431474663) | [14 empty] | Name & contact no. of PMC :- Dynamic consultancy (Manik Sarkar-9308533268/ 09804903257, Raj Kr. Chowdhary 09830757051)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USS-173 | Siwan | Husainganj | 1 | M. S, Hata Tola Chhata 9546660912 | Retender | 104.9733
|  |  | Raghunathpur | 2 | M. S, Kandhauli 9934615203
2 | USS-174 | Siwan | Goriya Kothi | 1 | M. S, Agayan 9931238480 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 208.64 |  | 28.2013 | 12 Month | [7 empty] | 1 |  | 57.54
|  |  | Mahrajganj | 2 | U. M. S, Shahpur 9934425050 |  |  | 1 | [12 empty] | Land not available
|  |  | Mahrajganj | 3 | U M S, Balui(Boys) 9430845490 | [11 empty] | 1 |  |  |  | 3rd on A/C bill paid
|  |  | Basantpur | 4 | U M S, Shekhpura (Urdu) 9431051956 | [12 empty] | 1
3 | USS-175 | Siwan | Siswan | 1 | M. S, Gyaspur 8809341191 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 208.19 |  | 28.2013 | 12 Month | [7 empty] | 1 |  | 112.89
|  |  | Siwan Sadar | 2 | U.M.S,Sarawe 9931980061 | [13 empty] | 1 |  | 4th A/C bill paid
|  |  | Siwan Sadar | 3 | M. S, Sarsar 9430206854 | [12 empty] | 1
|  |  | Siwan Sadar | 4 | M. S, Baletha 9973162074 | [12 empty] | 1
4 | USS-176 | Siwan | Andar | 1 | M. S, Pateji Bahadur 9939697369 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 156.3675 |  | 2.3.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 40.77
|  |  | Gudhani | 2 | M. S, Belauri 8809165382 | [9 empty] | 1 | [5 empty] | 2nd A/C bill paid
|  |  | Andar | 3 | M. S, Bangra Ujjain 9955673604 | [9 empty] | 1
5 | USS-177 | Saran | Dariyapur | 1 | Middle School, Saraiya 9431647901 | M/S Aditi Annanya Construction, Jai Ram Bhawan, Sadar Bazar, Danapur Cantt., Patna | 205.768 |  | 6.9.2013 | 12 Month | [6 empty] | 1
|  |  | Dariyapur | 2 | Middle School, Bhongha 9006298659 | [9 empty] | 1
|  |  | Dariyapur | 3 | Middle School, BarkaBaniya 8434756046 9934920997 |  |  | 1 | [12 empty] | Land not available
|  |  | Dighwara | 4 | Middle School, Malkhachak 9135336330 |  |  | 1 | [12 empty] | Land not available
6 | USS-178 | Saran | Sonpur | 1 | Middle School, Shikharpur 9631221348 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 51.51 |  | 2.3.2013 | 12 Month |  |  |  |  | 1 |  |  |  |  | 13.95 | 2nd on A/C bill paid
7 | USS-179 | Saran | Lahaladpur | 1 | Middle School, Basahi Urdu | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 264.22 |  | 8.10.2013 | 12 Month |  |  | 1
|  |  | Ekma | 2 | Middle School, Bhodasa | [9 empty] | 1
|  |  | Ekma | 3 | Middle School, Betbaniya 8294839353 | [9 empty] | 1
|  |  | Ekma | 4 | Middle School, Eksar 9572740280 | [9 empty] | 1
|  |  | Lahaladpur | 5 | Middle School,Mirjapur Murarpur 9955645700 | [7 empty] | 1
8 | USS-181 | Saran | Riwilganj | 1 | Middle School, Shekhpura 9162298688 | Hariom Construction | 52.2225 |  | 16.9.2013 | 12 Month |  |  |  |  | 1
9 | USS-182 | Saran | Parsa | 1 | Middle School, Bankarwa Mau 8757804020 | M/S Kishore Construction, AT- Kaituka Lashi, Saran | 155.115 |  | 22.5.2013 | 12 Month | [6 empty] | 1 |  |  | 48.54
|  |  | Garkha | 2 | Upgraded Middle School, Itwa 09401585033 | [11 empty] | 1 |  |  |  | 3rd on A/C bill paid
|  |  | Madhaura | 3 | Upgraded Middle S, Nethua 8809143641 | [11 empty] | 1
10 | USS-183 | Gopalganj | Kuchaikot | 1 | Middle School, Barnaya Rajaram 9801382670 | Siemens Construction Corporation, B-9, Abhiyanta Nagar, Patna-800025 | 213.96 |  | 23.8.2013 | 12 Month |  |  |  |  | 1
|  |  | Kuchaikot | 2 | Middle School, Chhatarpati 09695415475 |  |  | 1 | [12 empty] | Required old building demolision
|  |  | Kuchaikot | 3 | Middle School, Balthari 9973181137 |  |  | 1 | [12 empty] | Land not available
|  |  | Kuchaikot | 4 | Middle School, Mateya 9771369553 | [9 empty] | 1
11 | USS-184 | Gopalganj | Baikunthpur | 1 | Middle School, Chamanpura 9708223803 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 211.85 |  | 28.2013 | 12 Month | [7 empty] | 1 |  | 46.81
|  |  | Baikunthpur | 2 | Middle School, Gandhua 9097163144 9631026226 | [11 empty] | 1 |  |  |  | 3rd A/C bill paid
|  |  | Baikunthpur | 3 | Upgraded Middle School,Banaura 9661229932 9835052184 | [12 empty] | 1
|  |  | Singhwaliya | 4 | Middle School, Amarpura Jagiraha 9801115115 |  |  | 1 | [12 empty] | Land not available
12 | USS-185 | Gopalganj | Bhore | 1 | Middle School, Kuaridih 9006390431 | Burnwala Contract Pvt. Ltd., AT- Hajiyapur Road, Gopalganj. | 210.06 |  | 2.3.2013 | 12 Month | [7 empty] | 1 |  | 32.26
|  |  | Gopalganj | 2 | Middle School, Karariya 9934499260 |  |  | 1 | [12 empty] | Land problem
|  |  | Thawe | 3 | Middle School, Lakshawar 9570377954 | [11 empty] | 1 |  |  |  | 4th A/C bill paid
|  |  | Gopalganj | 4 | Middle School, Baraipatti 9955771721 |  |  | 1 | [12 empty] | Land problem
13 | USS-186 | Gopalganj | Hathua | 1 | U. M. S, Satai 8757888461 | Shiv Shankar Singh Contract Pvt. Ltd., Rajendra Nagar, Gopalganj. | 210.77 |  | 8.10.2013 | 12 Month |  | 1
|  |  | Hathua | 2 | Upgraded Middle School, Singha Tola 9771268847 | [6 empty] | 1
|  |  | Hathua | 3 | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 |  |  | 1 | [12 empty] | Land problem
|  |  | Hathua | 4 | M. S., Baraipatti (Ananta) 9546066924 |  |  | 1 | [12 empty] | Land problem
| Total nos. of school |  |  | 43 |  |  | 2253.6463 | 10 |  |  | 0 | 2 | 2 | 0 | 11 | 0 | 7 | 8 | 1 | 352.76
Following School name attached in Invalid Upgraded School list Vide Letter no 132 Dated- 22.01.2013 of Director (S.E.), so Following School name hasbeen Deleted from above list
S.N. | Group No. | Name of District | Name of Block |  | Name of School
1 | USS-173 | Siwan | Darauli |  | M. S, Harnatar * 9801693449
2 | USS-176 | Siwan | Mairwa |  | M. S, English* 09006776913
3 | USS-177 | Saran | Dighwara |  | Middle School, Manopur* 8873883362
4 | USS-178 | Saran | Sonpur |  | Middle School, Govindchak* 9534417539
5 | USS-178 | Saran | Panapur |  | Middle School, Belaur* 9546748080 9771991771
6 | USS-180 | Saran | Mashrakh |  | Middle School, Brahimpur* 9955826351
7 | USS-180 | Saran | Baniyapur |  | Middle School, Baropur* 9572417282
8 | USS-180 | Saran | Baniyapur |  | Middle School, Chorauwa* 9006023139
9 | USS-180 | Saran | Baniyapur |  | Middle School, Maricha* 9931521996
10 | USS-181 | Saran | Riwilganj |  | Upgraded Middle School, Mukrera * 9572809412
11 | USS-181 | Saran | Manjhi |  | Middle School, Madan sadh * 9934822882
12 | USS-181 | Saran | Manjhi |  | Middle School, Saryupar * 9934632634
13 | USS-182 | Saran | Garkha |  | Middle School, Pirauna* 9504435453
14 | USS-182 | Saran | Nagra |  | Middle School, Gopalpur* 9973179573
15 | USS-182 | Saran | Parsa |  | Middle School, Bari Sirisiya* 9162602176