## BRC
BSEIDC Ltd., Patna
World Bank Project
Physical Progress Report of BRC (Block Resource Centre)
SL. NO. | Group No. | Division | Name of District |  | Name of School | Name of Agency | Retender | Tender Process | Not Start | Physical Status | [10 empty] | Remarks | Date of Completion |  | Financial Expenditure (in Lacs)
|  |  |  | Name of Block | [5 empty] | Layout | Foundation | PL | GF-LL | GF-RL | FF-LL | FF-RL | SF- LL | SF-RL | Finishing | Complete |  |  | Agreement Amount |  | Financial Achievement (%)
1 | BRC-1 | Saran | Saran |  | BRC Ekma,Saran | ASIANA CONSTRACT PVT LTD 9431088485 | [8 empty] | 1 | [7 empty] | 67.2368
2 | BRC-2 | Saran | Saran |  | BRC Baniyapur,Saran | Retender | 1 | [13 empty] | NIT-31 (2016-17)
3 | BRC-3 | Saran | Saran |  | BRC Masrak,Saran | VIJAY NARAYAN SINGH 9470059120 |  |  | 1
4 | BRC-4 | Saran | Saran |  | BRC Marhowrah,Saran | Retender | 1 | [13 empty] | NIT-31 (2016-17)
5 | BRC-5 | Saran | Saran |  | BRC Amnour,Saran | MOHAN PRASAD DEVELOPERS & CONSTRUCTIONS PRIVATE LIMITED 9931019004 |  |  | 1 | [13 empty] | 66.2587
6 | BRC-6 | Saran | Saran |  | BRC,Dariyapur,Saran | CHANDRA BHUSHAN PRASAD 9939325343 | [9 empty] | 1 | [6 empty] | 65.9094 | 11.4264
7 | BRC-7 | Saran | Saran |  | BRC,Garkha,Saran | VIJAY NARAYAN SINGH 9470059120 |  |  |  | 1
8 | BRC-8 | Darbhanga | Darbhanga |  | BRC,Manigachhi, Darbhanga | Retender | 1 | [13 empty] | NIT-31 (2016-17) |  | 69.0876
9 | BRC-9 | Darbhanga | Darbhanga |  | BRC, Keoti,Darbhanga | GIRDHARI LAL PODDAR 9334934135 | [9 empty] | 1 | [6 empty] | 68.8448 | 13.7361
10 | BRC-10 | Darbhanga | Darbhanga |  | BRC,kusheshwarsthan,Darbhanga | RAMESH CHANDRA YADAV 9472800478 | [9 empty] | 1
11 | BRC-11 | Darbhanga | Darbhanga |  | BRC,Ghanshyampur,Darbhanga | Retender | 1 | [13 empty] | NIT-31 (2016-17)
12 | BRC-12 | Darbhanga | Darbhanga |  | BRC,Kiratpur, Darbhanga | Retender | 1 | [13 empty] | NIT-31 (2016-17) |  | 68.0388
13 | BRC-13 | Darbhanga | Darbhanga |  | BRC,Baheri,Darbhanga | RAMESH CHANDRA YADAV 9472800478 | [5 empty] | 1
14 | BRC-14 | Darbhanga | Darbhanga |  | BRC,Hanumannagar, Darbhanga | Retender | 1 | [13 empty] | NIT-31 (2016-17)
15 | BRC-15 | Darbhanga | Madhubani |  | BRC, Lakhnaur,Madhubani | Retender | 1 | [13 empty] | NIT-31 (2016-17)
16 | BRC-16 | Darbhanga | Madhubani |  | BRC,Jhanjharpur,Madhubani | JUGNOO KUMAR 8083370525 |  |  |  |  | 1 | [11 empty] | 70.3761
17 | BRC-17 | Darbhanga | Madhubani |  | BRC,Phulparas,Madhubani | AKASH KUMAR 9334362048 |  |  |  |  | 1
18 | BRC-18 | Darbhanga | Madhubani |  | BRC,Khutauna,Madhubani | JUGNOO KUMAR 8083370525 | [12 empty] | 1 |  |  |  | 71.4935 | 34.9914
19 | BRC-19 | Darbhanga | Madhubani |  | BRC, Khajouli,Madhubani | BHAWANI SHANKAR CONSTRUCTION PVT LTD 9430084612 | [10 empty] | 1 | [5 empty] | 69.7376
20 | BRC-20 | Darbhanga | Madhubani |  | BRC,Bisfi,Madhubani | Retender | 1 | [13 empty] | NIT-31 (2016-17)
21 | BRC-21 | Darbhanga | Madhubani |  | BRC,Rahika,Madhubani | Retender | 1 | [13 empty] | NIT-31 (2016-17)
22 | BRC-22 | Darbhanga | Madhubani |  | BRC, Harlakhi,Madhubani | KANHAIYA KUMAR MEHTA 9934949629 | [5 empty] | 1
23 | BRC-23 | Darbhanga | Madhubani |  | BRC,Babubarhi,Madhubani | GIRDHARI LAL PODDAR 9334934135 | [12 empty] | 1 |  |  |  | 70.2073 | 16.2221
24 | BRC-24 | Darbhanga | Samastipur |  | BRC Rosada,Samastipur | JEEWAN KISHORE SINGH 9934795831 | [7 empty] | 1 | [8 empty] | 67.356
25 | BRC-25 | Darbhanga | Samastipur |  | BRC Samastipur | Retender | 1 | [13 empty] | NIT-31 (2016-17)
26 | BRC-26 | Darbhanga | Samastipur |  | BRC, Khanpur,Samastipur | Retender | 1 | [13 empty] | NIT-31 (2016-17)
27 | BRC-27 | Darbhanga | Samastipur |  | BRC, Hasanpur,Samastipur | NITISH KUMAR 9473452853 | [6 empty] | 1
28 | BRC-28 | Darbhanga | Samastipur |  | BRC, Mohanpur,Samastipur | vipin kumar sahni 9931468694 |  |  |  |  | 1 | [11 empty] | 67.9095
29 | BRC-29 | Darbhanga | Samastipur |  | BRC, Patori,Samastipur | Kaushlendra Kumar Singh 9939646103,9334633151 | [10 empty] | 1 | [5 empty] | 67.6779 | 13.6251
30 | BRC-30 | Darbhanga | Samastipur |  | BRC, Shivajinagar,Samastipur | ABHAY KUMAR SINGH 9934279823 | [9 empty] | 1 | [6 empty] | 67.606
31 | BRC-31 | Tirhut West | East Champaran |  | BRC,Sangrampur,E.Champaran | ARUN KUMAR 9470421603 | [9 empty] | 1 | [7 empty] | 10.8876
32 | BRC-32 | Tirhut West | East Champaran |  | BRC,Kalyanpur,E.Champaran | Retender | 1 | [13 empty] | Re-Tender
33 | BRC-33 | Tirhut West | East Champaran |  | BRC Chakia,E.Champaran | KESHAV KUMAR KESHRI 9430096435 | [6 empty] | 1
34 | BRC-34 | Tirhut West | East Champaran |  | BRC Sugauli,E.Champaran | KESHAV KUMAR KESHRI 9430096435 | [7 empty] | 1
35 | BRC-35 | Tirhut West | East Champaran |  | BRC Madhuban,E.Champaran | DHIRAJ KUMAR PANDEY 9430214702 | [12 empty] | 1 |  |  |  |  | 14.3897
36 | BRC-36 | Tirhut West | East Champaran |  | BRC Patahi,E.Champaran | SATISH NARAYAN SINGH | [7 empty] | 1
37 | BRC-37 | Tirhut West | East Champaran |  | BRC Raxaul,E.Champaran | Retender | 1 | [13 empty] | Re-Tender
38 | BRC-38 | Tirhut West | East Champaran |  | BRC Adapur,E.Champaran | M/S MAA VAISHNO CONSTRUCTION | [7 empty] | 1
39 | BRC-39 | Tirhut West | East Champaran |  | BRC Bankatwa,E.Champaran | Retender | 1 | [13 empty] | Re-Tender
40 | BRC-40 | Tirhut West | East Champaran |  | BRC Dhaka,E.Champaran | Retender | 1 | [13 empty] | Re-Tender
41 | BRC-41 | Tirhut West | West Champaran |  | BRC Bairia,W.Champaran | Retender | 1 | [13 empty] | Re-Tender
42 | BRC-42 | Tirhut West | West Champaran |  | BRC Narkatiaganj,W.Champaran | KHURSHID ALAM 9955971081 | [5 empty] | 1
43 | BRC-43 | Tirhut West | West Champaran |  | BRC Sikta,W.Champaran | SANTOSH BHAGAT | [5 empty] | 1
44 | BRC-44 | Tirhut West | West Champaran |  | BRC Bhithan,W.Champaran | Retender | 1 | [13 empty] | Re-Tender
45 | BRC-45 | Tirhut West | West Champaran |  | BRC Lauriya,W.Champaran | ASIANA CONSTRACT PVT LTD 9431088485 | [12 empty] | 1
46 | BRC-46 | Tirhut West | West Champaran |  | BRC,Piprasi,W.Champaran | Retender | 1 | [13 empty] | Re-Tender
47 | BRC-47 | Tirhut West | West Champaran |  | BRC,Majhaulia,W.Champaran | RAJ KISHORE AKELA 9507118626 | [11 empty] | 1
48 | BRC-48 | Saran | Siwan |  | BRC Darauli,Siwan | Pratap construction 9953584047 |  |  |  |  | 1 | [11 empty] | 70.0971
49 | BRC-49 | Saran | Siwan |  | BRC Hussainganj,Siwan | BALINDRA CHAUDHARY 8804119555 |  |  | 1
50 | BRC-50 | Saran | Siwan |  | BRC Mairwa,Siwan | BALINDRA CHAUDHARY 8804119555 |  |  |  |  | 1
51 | BRC-51 | Saran | Siwan |  | BRC Basantpur,Siwan | ASIANA CONSTRACT PVT LTD 9431088485 | [7 empty] | 1 | [8 empty] | 66.9295
52 | BRC-52 | Saran | Siwan |  | BRC Maharajganj,Siwan | RENU DEVI 9931003551 |  |  | 1
53 | BRC-53 | Saran | Siwan |  | BRC,Bhagwanpur,Siwan | ASIANA CONSTRACT PVT LTD 9431088485 | [7 empty] | 1 | [8 empty] | 67.1663
54 | BRC-54 | Saran | Siwan |  | BRC,Hasanpur,Siwan | Retender | 1
55 | BRC-55 | Saran | Gopalganj |  | BRC Uchkagaon,Gopalganj | RAJ TANAY RAI CONSTRUCTION PVT LTD 9431812498, 9801764647 |  |  | 1
56 | BRC-56 | Saran | Gopalganj |  | BRC Sidhwalia,Gopalganj | RAM PUKAR PRASAD 9631395563 | [5 empty] | 1
57 | BRC-57 | Saran | Gopalganj |  | BRC Bhorey,Gopalganj | GIRIDHAR GOPAL CONSTRUCTION PVT LTD 9973556452 | [7 empty] | 1 | [8 empty] | 70.0968
58 | BRC-58 | Saran | Gopalganj |  | BRC,Bijaipur,Gopalganj | PREM SAGAR YADAV 7763953930 | [9 empty] | 1 | [6 empty] | 68.6692
59 | BRC-59 | Saran | Gopalganj |  | BRC Pachdeuri,Gopalganj | Retender | 1
60 | BRC-60 | Saran | Gopalganj |  | BRC Kuchaikot,Gopalganj | Retender | 1
61 | BRC-61 | Patna West | Kaimur |  | BRC,Ramgarh,Kaimur | VIJAY VARDDHAN | [5 empty] | 1 | [10 empty] | 68.3795
62 | BRC-62 | Patna West | Kaimur |  | BRC Chainpur,Kaimur | VIJAY VARDDHAN | [7 empty] | 1 | [8 empty] | 68.2022
63 | BRC-63 | Patna West | Kaimur |  | BRC Bhagwanpur,Kaimur | RAM LAL PASWAN | [7 empty] | 1 | [8 empty] | 75.7366
64 | BRC-64 | Patna West | Buxar |  | BRC Chakki, Buxar | Retender | 1 | [13 empty] | Not Started
65 | BRC-65 | Patna West | Buxar |  | BRC Buxar | Retender | 1 | [13 empty] | Not Started
66 | BRC-66 | Patna West | Buxar |  | BRC, Chausa, Buxar | GOVIND KUMAR SINGH |  |  | 1 | [11 empty] | LAND IS NOT AVAILABLE.
67 | BRC-67 | Patna West | Rohtas |  | BRC Dinara, Rohtas | MS S A B CONSTRUCTION | [12 empty] | 1 |  |  |  | 67.2575
68 | BRC-68 | Patna West | Rohtas |  | BRC Karahgar, Rohtas | SMRITI TECHNOCRATE PRIVATE LIMITED | [8 empty] | 1 | [7 empty] | 67.1816
69 | BRC-69 | Patna West | Rohtas |  | BRC Kochas, Rohtas | SANJAY SINGH | [5 empty] | 1
70 | BRC-70 | Patna West | Rohtas |  | BRC Tilauthu, Rohtas | ISHIKA CONSTRUCTION | [12 empty] | 1 |  |  |  | 65.7062 | 17.1437
71 | BRC-71 | Patna West | Rohtas |  | BRC Karakat, Rohtas | LAVA KUMAR SINGH |  |  | 1
72 | BRC-72 | Patna West | Rohtas |  | BRC Dawat, Rohtas | SHAILENDRA KUMAR | [7 empty] | 1
73 | BRC-73 | Purnea | Katihar |  | BRC,Mansahi,Katihar | MS MOTI LAL AGARWAL 919431229375 |  |  | 1 | [11 empty] | land not given , letter issued to DEO/ DM katihar to make the land available .
74 | BRC-74 | Purnea | Katihar |  | BRC,Manihar,Katihar | MAHMAD JAFIRUDDIN 8051267203 |  |  | 1
75 | BRC-75 | Purnea | Katihar |  | BRC,Pranpur,Katihar | MS MOTI LAL AGARWAL 919431229375 |  |  | 1
76 | BRC-76 | Purnea | Katihar |  | BRC, Kadwa,Katihar | PRAKASH KUMAR SAH 9162909186 | [7 empty] | 1
77 | BRC-77 | Purnea | Katihar |  | BRC,Barsoi,Katihar | MS MOTILAL AGARWAL 919431229375 |  |  | 1 | [11 empty] | land not given , letter issued to DEO/ DM katihar to make the land available .
78 | BRC-78 | Purnea | Katihar |  | BRC,Azamnagar,Katihar | PANKAJ KUMAR SINGH 9431229327 |  |  | 1
79 | BRC-79 | Purnea | Araria |  | BRC,Narpatganj,Araria | BINOD YADAV 9534413473 |  |  | 1 | [11 empty] | 5 feet deep land made available, sand filling estimate sent to HQ.
80 | BRC-80 | Purnea | Araria |  | BRC, Araria | SHASHI RANJAN 7488173962 |  |  | 1 | [11 empty] | land available
81 | BRC-81 | Purnea | Araria |  | BRC, Jokihat,Araria | Retender | 1 | [13 empty] | land available
82 | BRC-82 | Purnea | Araria |  | BRC,Bhargama,Araria | KUNAL KUSH | [7 empty] | 1
83 | BRC-83 | Purnea | Araria |  | BRC,Kursakata,Araria | Retender | 1 | [13 empty] | land available
84 | BRC-84 | Purnea | Purnea East |  | BRC,Purnea East, | RAJESH KUMAR 8405012179 | [10 empty] | 1 | [6 empty] | 14.9264
85 | BRC-85 | Purnea | Purnea |  | BRC, Baisi,Purnea | PARASNATH CONSTRUCTION 9431097240 | [12 empty] | 1
86 | BRC-86 | Purnea | Purnea |  | BRC,Amour,Purnea | PARASNATH CONSTRUCTION 9431097240 | [12 empty] | 1
87 | BRC-87 | Purnea | Purnea |  | BRC, Dhamdaha,Purnea | KUMAR CHAMAN,7352999201 | [9 empty] | 1
88 | BRC-88 | Purnea | Purnea |  | BRC,Banmankhi,Purnea | PARASNATH CONSTRUCTION 9431097240 | [11 empty] | 1
89 | BRC-89 | Purnea | Kishanganj |  | BRC,Tarhagach,Kishanganj | Navnit kumar 8541818406 | [7 empty] | 1 | [6 empty] | work stoped by villages since last 3months , letter has been issued to D.M. kishanganj to solve the dispute. |  |  | 16.4
90 | BRC-90 | Purnea | Kishanganj |  | BRC,Thakurganj,Kishanganj | Retender | 1 | [13 empty] | land available
91 | BRC-91 | Purnea | Kishanganj |  | BRC,Pothia,Kishanganj | Retender | 1 | [13 empty] | land not available near old BRC, but land available at block campus which is 300 feet away from old BRC
92 | BRC-92 | Bhagalpur | Banka |  | BRC Katoria,Banka | MK ENTERPRISES 7301740211 | [9 empty] | 1
93 | BRC-93 | Bhagalpur | Banka |  | BRC Rajaun,Banka | SHYAM SUNDER YADAV 9934769886 | [5 empty] | 1
94 | BRC-94 | Bhagalpur | Banka |  | BRC,Barhat,Banka | NIWESH KUMAR 9576272505 | [9 empty] | 1
95 | BRC-95 | Bhagalpur | Banka |  | BRC Belhar,Banka | NIWESH KUMAR 9576272505 | [7 empty] | 1
96 | BRC-96 | Munger | Jamui |  | BRC Jamui | PRABHAT KUMAR SINGH 9471615433 |  |  |  | 1
97 | BRC-97 | Munger | Jamui |  | BRC Barhat,Jamui | Retender | 1
98 | BRC-98 | Munger | Jamui |  | BRC Chakai,Jamui | BRAJESH KUMAR SINGH 8521839685 |  |  |  |  | 1
99 | BRC-99 | Munger | Jamui |  | BRC Gidhour,Jamui | SAI HIGHWAY AND BUILDERS PVT LTD, 9771455967 |  |  | 1 | [11 empty] | Land not avilable
100 | BRC-100 | Munger | Jamui |  | BRC Sikandra,Jamui | ASHIS RANJAN 9931215326 | [6 empty] | 1 | [9 empty] | 65.3921
101 | BRC-101 | Munger | Munger |  | BRC Asharganj,Munger | MS KUHU CONSTRUCTION CO 9431431148'/ 9470070171 | [12 empty] | 1 |  |  |  | 66.1878 | 9.9069
102 | BRC-102 | Bhagalpur | Bhagalpur |  | BRC Naugachhia,Bhagalpur | Retender | 1
103 | BRC-103 | Bhagalpur | Bhagalpur |  | BRC Pirpainti,Bhagalpur | Retender | 1
104 | BRC-104 | Bhagalpur | Bhagalpur |  | BRC Shahkund,Bhagalpur | RAKESH KUMAR SINGH 9431422504 | [7 empty] | 1
105 | BRC-105 | Koshi | Madhepura |  | BRC Puraini,Madhepura | SHIV CHANDRA KUMAR 9431046145 | [11 empty] | 1 |  |  | Work in progress |  | 69.0485
106 | BRC-106 | Koshi | Madhepura |  | BRC Gwalpada,Madhepura | SHIV CHANDRA KUMAR 9431046145 |  |  |  | 1 | [10 empty] | NOC Pending
107 | BRC-107 | Koshi | Madhepura |  | BRC Kumarkhand,Madhepura | AKASH KUMAR 9334362048 |  |  | 1 | [11 empty] | Land Available after demolished of old building
108 | BRC-108 | Koshi | Madhepura |  | BRC Gailarh,Madhepura | AJAY KUMAR 9472208858 | [8 empty] | 1 | [5 empty] | Work in progress |  | 69.148
109 | BRC-109 | Koshi | Saharsa |  | BRC Saurbazar,Saharsa | AJAY KUMAR 9472208858 |  |  |  | 1
110 | BRC-110 | Koshi | Saharsa |  | BRC,Navhatta,Saharsa | MADAN KUMAR SINGH 9521267060 | [5 empty] | 1 | [8 empty] | Work in progress |  | 69.9174
111 | BRC-111 | Koshi | Saharsa |  | BRC Mahensi,Saharsa | AJAY KUMAR 9472208858 |  |  |  | 1
112 | BRC-112 | Koshi | Saharsa |  | BRC Sonbarsa,Saharsa | BAMBAM KUMAR SINGH 9934071093 |  |  | 1 | [11 empty] | Low Land/Ditch available about 7ft
113 | BRC-113 | Koshi | Saharsa |  | BRC Simri, Bakhtiyarpur Saharsa | MK ENTERPRISES 7301740211 | [6 empty] | 1 | [7 empty] | Work in progress
114 | BRC-114 | Koshi | Supual |  | BRC Supaul | DHIRAJ KUMAR AGRAWAL 9771645678 | [9 empty] | 1 |  |  |  |  | Work in progress |  | 69.3764
115 | BRC-115 | Koshi | Supual |  | BRC Pipra,Supaul | BAMBAM KUMAR SINGH 9934071093 | [6 empty] | 1 | [7 empty] | Work in progress |  | 70.5658
116 | BRC-116 | Koshi | Supual |  | BRC Pratapganj,Supaul | MADAN KUMAR SINGH 9521267060 | [10 empty] | 1 |  |  |  | Work in progress |  | 71.0597 | 15.8708
117 | BRC-117 | Koshi | Supual |  | BRC Nirmali,Supaul | BALRAM SINGH 9431082277 |  |  |  | 1
118 | BRC-118 | Koshi | Supual |  | BRC Raghopur,Supaul | SACHINDRA KUMAR 9955032820 | [6 empty] | 1 | [7 empty] | Work in progress
119 | BRC-119 | Magadh | Gaya |  | BRC, Atari,Gaya | Mithlesh Kumar Singh 9931471924 |  |  |  |  | 1 | [11 empty] | 63.3513
120 | BRC-120 | Magadh | Gaya |  | BRC, Neemchak,Gaya | GUDDU KUMAR 9386927378 | [7 empty] | 1
121 | BRC-121 | Magadh | Gaya |  | BRC,Wazirganj,Gaya | Mithlesh Kumar Singh 9931471924 |  |  | 1 | [11 empty] | Land Available
122 | BRC-122 | Magadh | Gaya |  | BRC, Mohanpur,Gaya | KEOLA CONSTRUCTION 9931222534 |  |  | 1 | [11 empty] | Land not available but Land possible to available & Agreement not done by agency.
123 | BRC-123 | Magadh | Gaya |  | BRC, Imamganj,Gaya | MRITUNJAY KUMAR SINGH |  |  |  | 1 | [10 empty] | Land Available |  | 67.3151
124 | BRC-124 | Magadh | Gaya |  | BRC Amas,Gaya | JAI KUMAR 9835202464 | [9 empty] | 1
125 | BRC-125 | Magadh | Gaya |  | BRC, Koch,Gaya | SURENDRA KUMAR 9431085035 |  |  | 1 | [11 empty] | Recently Land Available & Agreement not done by agency |  | 63.6741
126 | BRC-126 | Magadh | Jehanabad |  | BRC,Jehanabad | Satish kumar 9973881398 | [6 empty] | 1
127 | BRC-127 | Magadh | Jehanabad |  | BRC,Kako,Jehanabad | Mithlesh Kumar Singh 9931471924 | [5 empty] | 1
128 | BRC-128 | Magadh | Jehanabad |  | BRC,Ghosi,Jehanabad | Progressive Engicon Pvt Ltd 930419639 |  |  | 1
129 | BRC-129 | Magadh | Arwal |  | BRC Arwal | BRAJESH KUMAR 9939124848 |  |  |  |  | 1
130 | BRC-130 | Magadh | Arwal |  | BRC Karpi,Arwal | Kaushlendra Kumar Singh 9939646103,9334633151 | [7 empty] | 1
131 | BRC-131 | Magadh | Aurangabad |  | BRC,Obra,Aurangabad | DIGITAL CONSTRUCTION PVT. LTD 9430569021 | [8 empty] | 1 | [7 empty] | 65.5247
132 | BRC-132 | Magadh | Aurangabad |  | BRC,Dev,Aurangabad | SATISH KUMAR SINGH 9430044277 | [8 empty] | 1 | [7 empty] | 64.9511
133 | BRC-133 | Magadh | Aurangabad |  | BRC Madanpur,Aurangabad | DHANANJAY KUMAR SINGH 9931128631 | [6 empty] | 1 | [9 empty] | 64.2073 | 9.6116
134 | BRC-134 | Magadh | Aurangabad |  | BRC Kutumba,Aurangabad | DHANANJAY KUMAR SINGH 9931128631 | [7 empty] | 1 | [8 empty] | 66.0325 | 9.1571
135 | BRC-135 | Tirhut East | Sitamarhi |  | BRC, Rega,Sitamarhi | MUKESH KUMAR 99344665703 |  |  | 1 | [11 empty] | Land Available ,Agreement Not Done |  | 64.6629 | 19.5669
136 | BRC-136 | Tirhut East | Sitamarhi |  | BRC,Merajgang,Sitamarhi | Retender | 1 | [13 empty] | Land Available ,Agreement Not Done
137 | BRC-137 | Tirhut East | Sitamarhi |  | BRC,Pupri,Sitamarhi | RAJEEV KUMAR SINGH 9939219159 | [5 empty] | 1 | [8 empty] | brick work upto plinth |  | 64.2036 | 7.957
138 | BRC-138 | Tirhut East | Sitamarhi |  | BRC,Barthnaha,Sitamarhi | MUKESH KUMAR 99344665703 |  |  | 1 | [11 empty] | TO BE START SOON
139 | BRC-139 | Tirhut East | Sitamarhi |  | BRC,Runisaidpur,Sitamarhi | Manoj Kumar Singh 7870317817 | [9 empty] | 1 |  |  |  |  | Roof Casted
140 | BRC-140 | Tirhut East | Sitamarhi |  | BRC,Suppi,Sitamarhi | AMRESH KUMAR 9525120333 | [5 empty] | 1 | [8 empty] | BRICK WORK ABOVE PL
141 | BRC-141 | Magadh | Nawada |  | BRC, Pakribarawan,Nawada | ASHIS RANJAN 9931215326 | [11 empty] | 1 |  |  |  |  | 64.6629 | 19.5669
142 | BRC-142 | Magadh | Nawada |  | BRC,Warisaliganj,Nawada | Retender | 1 | [13 empty] | Land Available
143 | BRC-143 | Magadh | Nawada |  | BRC, Akabarpur,Nawada | KEERAN DEVI 9931271533 | [12 empty] | 1 |  |  |  | 64.2036 | 7.957
144 | BRC-144 | Magadh | Nawada |  | BRC, Narhat,Nawada | Retender | 1 | [13 empty] | Land Available
145 | BRC-145 | Patna East | Nawada |  | BRC, Chandi,Nalanda | SHAURYA PREMIER INFRASTRUCTURE PVT LTD | [7 empty] | 1 | [6 empty] | Shuttering & steel binding |  | 66.5157
146 | BRC-146 | Patna East | Nalanda |  | BRC, Austhawan ,Nalanda | NIKHIL SRI ENTERPRISES | [7 empty] | 1 | [6 empty] | Shuttering & steel binding |  | 66.5262
147 | BRC-147 | Patna East | Nalanda |  | BRC, Rahui,Nalanda | ARBIND PRASAD | [7 empty] | 1 | [6 empty] | RC |  | 66.6236
148 | BRC-148 | Patna East | Nalanda |  | BRC, Ekangarsarai,Nalanda | NARAYANI BUILDCON & CONSTRUCTION | [9 empty] | 1 |  |  |  |  | RC |  | 65.2065 | 8.3276
149 | BRC-149 | Patna East | Nalanda |  | BRC,Silaw,Nalanda | BHOLA SINGH | [9 empty] | 1 |  |  |  |  | Sill Level |  | 65.427
150 | BRC-150 | Patna East | Nalanda |  | BRC, Katrisarai,Nalanda | ASHOK KUMAR | [10 empty] | 1 | [5 empty] | 66.2311
151 | BRC-151 | Patna East | Nalanda |  | BRC, Karaiparsurai,Nalanda | NAWAL KISHORE SHARMA |  |  | 1 | [11 empty] | DPR में अंकित स्थल Road से 11 फीट गहरा है तथा 4 फीट जलजमाव है, नये स्थल हेतु BEO से L.No.- 558 /19.11.16 द्वारा अनुरोध किया गया है
152 | BRC-152 | Tirhut East | Muzaffarpur |  | BRC,Motipur,Muzaffarpur | Kameshwar Prasad Singh,9507383184 |  |  | 1 | [11 empty] | land for work still not given by C.O. |  | 65.8405 | 13.5539
153 | BRC-153 | Tirhut East | Muzaffarpur |  | BRC Gaighat,Muzaffarpur | Retender | 1 | [13 empty] | NOC Awaited, Letter Given |  | 65.9001
154 | BRC-154 | Tirhut East | Muzaffarpur |  | BRC,Aurai,Muzaffarpur | Manoj Kumar Singh 7870317817 |  |  | 1 | [11 empty] | NOC Awaited, Letter Given |  | 64.9972
155 | BRC-155 | Tirhut East | Muzaffarpur |  | BRC,Bandra,Muzaffarpur | MANOJ KUMAR 9931470561 | [10 empty] | 1 |  |  |  | Brickwork Running |  | 65.448 | 14.9597
156 | BRC-156 | Tirhut East | Muzaffarpur |  | BRC,Minapur,Muzaffarpur | Manoj Kumar Singh 7870317817 |  |  | 1 | [11 empty] | NOC Awaited, Letter Given
157 | BRC-157 | Tirhut East | Muzaffarpur |  | BRC,Bhagwanpur,Muzaffarpur | AKASH KUMAR |  |  | 1 | [11 empty] | No named Block Present Letter Given to HQ
158 | BRC-158 | Patna East | Bhojpur |  | BRC,Jagdishpur,Bhojpur | TRIVENI PRASAD SINGH, | [11 empty] | 1 |  |  | Shuttering & steel binding |  | 65.8405 | 13.5539
159 | BRC-159 | Patna East | Bhojpur |  | BRC ,Charpokhri,Bhojpur | RAMSIGASAN SINGH | [5 empty] | 1 | [10 empty] | 65.9001
160 | BRC-160 | Patna East | Bhojpur |  | BRC, Udwantnagar,Bhojpur | MANOJ KUMAR SINGH | [7 empty] | 1 | [6 empty] | Shuttering |  | 64.9972
161 | BRC-161 | Patna East | Bhojpur |  | BRC,Garhani,Bhojpur | TRIVENI PRASAD SINGH, | [11 empty] | 1 |  |  |  |  | 65.448 | 14.9597
162 | BRC-162 | Patna East | Bhojpur |  | BRC ,Koilwar,Bhojpur | J.K.S. CONSTRUCTION | [5 empty] | 1 | [8 empty] | B/W upto PL
163 | BRC-163 | Patna East | Patna |  | BRC, Fatuhan,Patna | Arvind Kumar |  |  | 1 | [11 empty] | CO के पत्रांक 597 दिनांक 28.07.17 द्वारा भूमि उपलब्ध कराया गया
164 | BRC-164 | Patna East | Patna |  | BRC, Bakhtiyarpur,Patna | Umakant Singh |  |  | 1 | [11 empty] | उपलब्ध कराया गया भूमि पूर्व में किसी अन्य विभाग को आवंटित था पुन: अन्य भूमि उपलब्ध कराने का अनुरोध BEO से L.N.-93/ 03.03.17 एवं 140/ 20.04.17 द्वारा अनुरोध किया गया है तथा DEO पटना द्वारा भी सम्बंधित को निदेशित किया गया
165 | BRC-165 | Patna East | Patna |  | BRC,Naubatpur,Patna | SHAURYA PREMIER INFRASTRUCTURE PVT LTD | [11 empty] | 1 |  |  | RC |  | 64.6629 | 20.4255
166 | BRC-166 | Patna East | Patna |  | BRC,Maner,Patna | ASHOK KUMAR YADAV |  |  | 1 | [11 empty] | DPR में स्थल अंकित नहीं है स्थल उपलब्ध कराने हेतु BEO से L.No.-574 /20.11.16, L.No.-33 /20.01.17 एवं 138/ 20.04.17 द्वारा अनुरोध किया गया है तथा DEO पटना द्वारा भी सम्बंधित को निदेशित किया गया
167 | BRC-167 | Munger | Begusarai |  | BRC,Begusarai | SAI HIGHWAY AND BUILDERS PVT LTD, 9771455967 |  |  | 1 | [11 empty] | Land not avilable
168 | BRC-168 | Munger | Begusarai |  | BRC,Matihani,Begusarai | NITISH KUMAR 9473452853 | [10 empty] | 1 | [5 empty] | 65.6728 | 17.9262
169 | BRC-169 | Munger | Begusarai |  | BRC, Bhagwanpur,Begusarai | NITISH KUMAR 9473452853 | [9 empty] | 1 | [6 empty] | 66.2062
170 | BRC-170 | Munger | Begusarai |  | BRC, Bakhri,Begusarai | MS BINOD KUMAR 9431287763 |  |  | 1 | [11 empty] | Land not avilable
171 | BRC-171 | Munger | Begusarai |  | BRC, Mansoorchak,Begusarai | MS B P SINGH AND CO 9431834042 |  |  | 1 | [11 empty] | Land not avilable
172 | BRC-172 | Munger | Begusarai |  | BRC, Cheria Bariyarpur,Begusarai | NITISH KUMAR 9473452853 |  |  | 1 | [11 empty] | Land not avilable
173 | BRC-173 | Munger | Khagariaa |  | BRC ,Chuatham,Khagaria | RANA CONSTRUCTION 9334104328 |  |  | 1 | [11 empty] | Land allotment in process
174 | BRC-174 | Munger | Khagariaa |  | BRC ,Gogari,Khagaria | MS BINOD KUMAR 9431287763 | [9 empty] | 1
175 | BRC-175 | Munger | Khagariaa |  | BRC, Beldour,Khagaria | MS DHANPAT KUMAR JAIN 9470016700 |  |  | 1 | [11 empty] | Land allotment in process
176 | BRC-176 | Munger | Khagariaa |  | BRC,Parbatta,Khagaria | SANJAY KUMAR 9430003830 | [12 empty] | 1
177 | BRC-177 | Tirhut East | Vaishali |  | BRC,Raghopur,Vaishali | Retender | 1 | [13 empty] | Land Available
178 | BRC-178 | Tirhut East | Vaishali |  | BRC ,Desari,Vaishali | ROHIT RAJ CONSTRUCTION PVT LTD 9931059796 | [5 empty] | 1 | [8 empty] | Brickwork Running upto sill band
179 | BRC-179 | Tirhut East | Vaishali |  | BRC, Bidupur,Vaishali | ROHIT RAJ CONSTRUCTION PVT LTD 9931059796 | [9 empty] | 1 |  |  |  |  | Brickwork Running upto sill band SF |  |  | 12.4091
180 | BRC-180 | Tirhut East | Vaishali |  | BRC,Jandaha,Vaishali | RANJAN GAYATRI CONSTRUCTIONPVT LTD. |  |  |  |  | 1 | [9 empty] | Soling Done Work stop due to water Logging
181 | BRC-181 | Tirhut East | Vaishali |  | BRC ,Mahua,Vaishali | ROHIT RAJ CONSTRUCTION PVT LTD 9931059796 | [8 empty] | 1 | [5 empty] | Brickwork Running above F F Lintel Level |  |  | 11.7883
182 | BRC-182 | Tirhut East | Vaishali |  | BRC, Garoul,Vaishali | ROHIT RAJ CONSTRUCTION PVT LTD 9931059796 | [7 empty] | 1 | [6 empty] | roof casted
183 | BRC-183 | Munger | Shekhpura |  | BRC,Chewada,Shekhpura | SANJAY KUMAR TECHNOCRATE PRIVATE LIMITED 9162333009 | [8 empty] | 1
184 | BRC-184 | Munger | Lakhisarai |  | BRC,Barhiya,Lakhisarai | SAI HIGHWAY AND BUILDERS PVT LTD, 9771455967 |  |  | 1 | [11 empty] | Land allotment in process
185 | BRC-185 | Munger | Lakhisarai |  | BRC ,Alinagar, Suryagarha,Lakhisarai | SAI HIGHWAY AND BUILDERS PVT LTD, 9771455967 |  |  | 1 | [11 empty] | Land allotment in process
Total Number of BRC |  |  |  |  | 185 |  | 35 | 0 | 39 | 7 | 9 | 15 | 8 | 23 | 7 | 17 | 7 | 7 | 11 | 0