## EXAM HALL
BSEIDC, PATNA
Progress Report for the Construction of Examination Hall Building at Commissionary Headquarter
S.N. | Group No. | Division | Name of District | Name of Schools | Name of Agency | Physical Status | [35 empty] | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%) | Remarks
[6 empty] | A/A | T/S | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting | L.O.A &Issued Date | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date | Date of Aggrement | Time of Completion | Inaugurtation | Not start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd floor |  | 3rd floor |  | 4th floor |  | 5th floor |  | Finishing | Complete
[28 empty] | LL | RL | LL | RL | LL | RL | LL | RL | LL | RL | LL | RL
1 | BSEB - 1 | Patna East | Patna | Exam Hall Patna | M/s. S.K Enterprises |  |  | 1536.5843 | [12 empty] | 93 SBD of 2016-17 (10.11.16) | 18 Months |  |  |  | 1 | [15 empty] | 1382.9259
2 | BSEB - 2 | Bhagalpur | Bhagalpur | Exam Hall Bhagalpur | Budha Infrastructure Pvt Ltd |  |  | 1544.3799 | [12 empty] | 41 SBD of 2017-18 (11.05.17) | 18 Months |  |  |  | 1 | [15 empty] | 1389.9419
3 | BSEB - 3 | Darbhanga | Darbhanga | Exam.Hall Darbhanga | Bal Krishna Bhalotia |  |  | 1570.6036 | [12 empty] | 29 SBD of 2017-18 (03.05.17) | 18 Months | [7 empty] | 1 | [11 empty] | 1413.5432
4 | BSEB - 4 | Magadh | Gaya | Exam Hall, Magadh | Satyendra Kumar Const. Pvt Ltd. |  |  | 1445.8213 | [12 empty] | 223 SBD of 2016-17 (22.02.17) | 18 Months | [6 empty] | 1 | [12 empty] | 1301.2392
5 | BSEB - 5 | Tirhut East | Muzaffarpur | Exam Hall Muzuffarpur | Man Mardan Sukla |  |  | 1547.588 | [12 empty] | 241 SBD of 2016-17 (10.03.17) | 18 Months | [6 empty] | 1 | [12 empty] | 1392.8292
6 | BSEB - 6 | Saran | Chhapra | Exam Hall Saran | Mohan Prasad D.C Pvt Ltd. |  |  | 1219.6816 | [12 empty] | 22 SBD of 2017-18 (26.04.17) | 18 Months |  |  |  | 1 | [15 empty] | 1097.7135
7 | BSEB - 7 | Munger | Munger | Exam Hall Munger | Bal Krishna Bhalotia |  |  | 1206.2514 | [13 empty] | 18 Months |  | 1 | [17 empty] | 1085.6262 |  |  | Soil test
8 | BSEB - 8 | Purnea | Purnea | Exam Hall Purnia | M/S Daya Ram Singh |  |  | 1237.3916 | [12 empty] | 94 SBD of 2016-17 (11.11.16) | 18 Months | [5 empty] | 1 | [13 empty] | 1113.6524
9 | BSEB - 9 | Koshi | Saharsa | Exam Hall Koshi | Sudesh Kumar S.C. Pvt. Ltd. |  |  | 1246.1657 | [12 empty] | 168 SBD of 2016-17 (19.01.17.) | 18 Months | [6 empty] | 1 | [12 empty] | 1121.5492 |  |  | LADIES , GENTS TOILET & GENERATOR ROOM ROOF COMP. AND GROUND FLOOR ROOF LEVEL WORK IN PROGRESS
Total No. of BSEB Examination Hall |  |  |  | 9 | [19 empty] | 1 | 0 | 3 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11299.0207 | 0 | 0
[22 empty] | PATNA EAST |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1382.9259 | 0 | 0
[22 empty] | PATNAWEST |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | MAGADH |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301.2392 | 0 | 0
[22 empty] | BHAGALPUR |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389.9419 | 0 | 0
[22 empty] | MUNGER |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.6262 | 0 | 0
[22 empty] | KOSI |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121.5492 | 0 | 0
[22 empty] | PURNIA |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113.6524 | 0 | 0
[22 empty] | TIRHUT EAST |  |  | 0 | 1 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392.8292 | 0 | 0
[22 empty] | TIRHUT WEST |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | DARBHANGA |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413.5432 | 0 | 0
[22 empty] | SARAN |  |  | 1 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097.7135 | 0 | 0
[22 empty] | TOTAL |  |  | 1 | #REF! | 0 | 1 | #REF! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11299.0207 | 0 | 0