## SSS
BSEIDC Ltd., Patna
Physical Status of Senior Secondary Schools (SSS)
S.N. | Group No. | Name of District | Name of Block | Name of School | Name of Agency | City | State | Mobile No. | Retender | Tender Process | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | DOC | Remarks |  | Division
[15 empty] | LL | RL | LL | RL
1 | SSS-98-1 | Patna | fcgVk | e/; fo¦ky;] jk?kksiqj] fcgVk] iVuk | Jai Mata Di Road Const. Pvt. Ltd.,3/97, LIG Hanuman Nagar, Kankarbagh,Patna-20, 9430828486 | [13 empty] | 1 |  |  |  |  | Patna East
2 | SSS-99-1 | Patna | nkukiqj | mRØfer e/; fo¦ky;] cfj;kjiqj | Jai Mata di Construction | [5 empty] | 1 | [10 empty] | School not locate, DPO द्वारा बताया गया सही नाम बृजनारायणपुर है एवं RMSA को सुधार हेतु पत्र भेजा गया है जो अभी तक अप्राप्त) |  | Patna East
3 | SSS-100-1 | Nalanda | bLykeiqj | e/; fo¦ky;] dksfcy | Baba Hans Construction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
4 | SSS-100-2 | Nalanda | bLykeiqj | e/; fo¦ky;] pkSjek | Baba Hans Construction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
5 | SSS-101-1 | Nalanda | fcgkj | mRØfer e/; fo¦ky;] gosyh | Pinku Kumari | [14 empty] | 1 |  |  |  | Patna East
6 | SSS-102-1 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] gjxk¡o | Krishandeo prasad | [14 empty] | 1 |  |  |  | Patna East
7 | SSS-102-2 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] ldjkSy | Krishandeo prasad | [5 empty] | 1 | [10 empty] | Land not available |  | Patna East
8 | SSS-102-3 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] ijkSgk | Krishandeo prasad | [14 empty] | 1 |  |  |  | Patna East
9 | SSS-103-1 | Nalanda | fgylk | e/; fo¦ky;] diflvkou | Prem Kumar Sinha | [14 empty] | 1 |  |  |  | Patna East
10 | SSS-104-1 | Nalanda | flyko | mnwZ e/; fo¦ky;] lkscbZr | Raj Kumar Singh Raja Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Patna East
11 | SSS-104-2 | Nalanda | flyko | e/; fo¦ky;] pk¡nh ekWm | Raj Kumar Singh Raja Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Patna East
12 | SSS-104-3 | Nalanda | flyko | e/; fo¦ky;] dqy | Raj Kumar Singh Raja Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Patna East
13 | SSS-104-4 | Nalanda | flyko | mRØfer e/; fo¦ky;] ikadh | Raj Kumar Singh Raja Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Patna East
14 | SSS-104-5 | Nalanda | flyko | mRØfer e/; fo¦ky;] t;fd'kqu fcxgk | Raj Kumar Singh Raja Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Patna East
15 | SSS-105-1 | Nalanda | fxfj;d | e/; fo¦ky;] vkneiqj | M/S Rama Construction | [5 empty] | 1 | [10 empty] | Land not available |  | Patna East
16 | SSS-105-2 | Nalanda | fxfj;d | e/; fo¦ky;] pkSjlqvk | M/S Rama Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
17 | SSS-106-1 | Nalanda | gjukSr | e/; fo¦ky;] usgqlk | Prem Kumar Sinha | [14 empty] | 1 |  | Handover |  | Patna East
18 | SSS-107-1 | Nalanda | ijoyiqj | m0vk0e/; fo¦ky;] ebZ | Pappu Singh | [5 empty] | 1 | [10 empty] | Land not available. EMD Return |  | Patna East
19 | SSS-108-1 | Nalanda | jgqbZ | e/; fo¦ky;] eksM+kryko | Vikash Kumar Singh | [5 empty] | 1 | [10 empty] | Land not available |  | Patna East
20 | SSS-108-2 | Nalanda | jgqbZ | e/; fo¦ky;] dFkkSyh | Vikash Kumar Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
21 | SSS-109-1 | Nalanda | ljesjk | e/; fo¦ky;] dkthpd | Budha Infrastructure Pvt. Ltd | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
22 | SSS-109-2 | Nalanda | ljesjk | e/; fo¦ky;] eykou | Budha Infrastructure Pvt. Ltd | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
23 | SSS-120-1 | Nalanda | uwjljk; | e/; fo¦ky;] eeqjknkckn | M/S Uma Shankar & Company | [14 empty] | 1 |  | Handover |  | Patna East
24 | SSS-120-2 | Nalanda | uwjljk; | e/; fo¦ky;] ljnkjfoxgk | M/S Uma Shankar & Company | [14 empty] | 1 |  | Handover |  | Patna East
25 | SSS-121-1 | Nalanda | vLFkkok¡ | mnZw e/; fo¦ky;] mxkou | Budha Infrastructure Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Problem |  | Patna East
26 | SSS-121-2 | Nalanda | vLFkkok¡ | mRØfer e/; fo¦ky;] vksb;kc | Budha Infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
27 | SSS-121-3 | Nalanda | vLFkkok¡ | e/; fo¦ky;] [ksryiqjk | Budha Infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
28 | SSS-121-4 | Nalanda | vLFkkok¡ | e/; fo¦ky;] tkuk | Budha Infrastructure Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land problem |  | Patna East
29 | SSS-121-5 | Nalanda | vLFkkok¡ | e/; fo¦ky;] vkSUMk | Budha Infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
30 | SSS-122-1 | Bhojpur | cM+gjk | e/; fo¦ky;] uFkeyiqj | Bhawani Buidcon & Project Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Patna East
31 | SSS-123-1 | Bhojpur | fcfg;kW | mRØfer e/; fo¦ky;] ohjiqj | Sudarshan Mahato | [14 empty] | 1 |  |  |  | Patna East
32 | SSS-123-2 | Bhojpur | fcfg;kW | çk;ksfxd e/; fo¦ky;] fcfg;kW | Sudarshan Mahato | [13 empty] | 1 |  |  |  |  | Patna East
33 | SSS-124-1 | Bhojpur | ihjks | mRØfer e/; fo¦ky;] ,;kj | Manoj Kumar | [13 empty] | 1 |  |  |  |  | Patna East
34 | SSS-124-2 | Bhojpur | ihjks | e/; fo¦ky;] ygjkckn | Manoj Kumar | [10 empty] | 1 | [5 empty] | B/W upto RL |  | Patna East
35 | SSS-125-1 | Bhojpur | lans'k | e/; fo¦ky;] ppkj | Kalaratri Associates | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
36 | SSS-126-1 | Bhojpur | lkgiqj | e/; fo¦ky;] ygax Mqefj;k | M/S Kalaratri Associates | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
37 | SSS-127-1 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky;] [kyhlk | Ashok Kumar | [5 empty] | 1 | [10 empty] | DEO के L.No. 1417/ 29.03.14 के द्वारा उत्क्रमण से संबंधित विवाद के कारण कार्य स्थगित किया गया |  | Patna East
38 | SSS-127-2 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky;] ckeikWyh | Ashok Kumar | [14 empty] | 1 |  |  |  | Patna East
39 | SSS-127-3 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky; ohjeiqj | Ashok Kumar | [14 empty] | 1 |  |  |  | Patna East
40 | SSS-128-1 | Bhojpur | rjkjh | e/; fo¦ky;] pank | Sadhu Saran Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
41 | SSS-128-2 | Bhojpur | rjkjh | e/; fo¦ky;] csjbZ | Sadhu Saran Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna East
42 | SSS-129-1 | Bhojpur | txnh'kiqj | mRØfer e/; fo¦ky;] nkWok | Sudarshan Mahto | [13 empty] | 1 |  |  |  |  | Patna East
43 | SSS-129-2 | Bhojpur | txnh'kiqj | mRØfer e/; fo¦ky;] cSjgh | Sudarshan Mahto | [12 empty] | 1 | [5 empty] | Patna East
44 | SSS-130-1 | Bhojpur | vkjk | e/; fo¦ky;] [ktqfj;kW | Janardan Yadav | [12 empty] | 1 |  |  |  | B/W upto RL |  | Patna East
45 | SSS-130-2 | Bhojpur | vkjk | mRØfer e/; fo¦ky;] y{e.kiqj | Janardan Yadav | [12 empty] | 1 |  |  |  | RC |  | Patna East
46 | SSS-415-1 | Patna | ikyhxat | e/; fo¦ky;] /kks[kjk | JITENDRA KUMAR, jkjkvijay@gmail.com |  |  | 9835205052 | [11 empty] | 1 |  | Handover |  | Patna East
47 | SSS-451-1 | Nalanda | bLykeiqj | e/; fo¦ky;] ekSyukpd | DAYANAND PRASAD SINHA & CO. JANTA PATH | [10 empty] | 1 | [5 empty] | निदेशक(मा०शि०) से कार्य पुनः प्रारम्भ किये जाने की अनुमति माँगी गयी है |  | Patna East
48 | SSS-374-1 | Patna | ikyhxat | e/; fo¦ky;] esjk[kkuiqjk | MS VATSHYAN CONSTRUCTION 9546109122 |  |  | 9546109122 | [11 empty] | 1 |  |  |  | Patna East
49 | SSS-374-2 | Patna | ikyhxat | e/; fo¦ky;] lsgjk | MS VATSHYAN CONSTRUCTION 9546109122 |  |  | 9546109122 | [11 empty] | 1 |  | Inaugurated 2016 |  | Patna East
50 | SSS-374-3 | Patna | ikyhxat | e/; fo¦ky;] dY;k.kiqj | MS VATSHYAN CONSTRUCTION 9546109122 |  |  | 9546109122 | [11 empty] | 1 |  |  |  | Patna East
51 | SSS-375 (A) | Patna | /ku:vk | e/; fo¦ky;] vatuh xksfoUniqj | CHANDRA BHUSHAN KUMAR | [13 empty] | 1 |  |  |  |  | Patna East
52 | SSS-376-1 | Patna | fcgVk | e/; fo¦ky;] fgjkeuiqj idM+hundred | NEER GAGAN CONSTRUCTION 9308641711 |  |  | 9308641711 | [11 empty] | 1 |  |  |  | Patna East
53 | SSS-376-2 | Patna | Qqyokjh 'kjhQ | mPp ek/;fed fo¦ky;] xksuiqjk ¼funs'kd] ek/;fed f'k{kk ds Kkikad&11@;ksŒ&02&03@2012&123] fnukad&29-01-2014 esa fn, x, vkns'kkuqlkj xzke iapk;Rs.&xksuiqjk ds csfld Ldwy ds tehu ij Hkou fuekZ.k gksxkA½ | NEER GAGAN CONSTRUCTION 9308641711 |  |  | 9308641711 | [11 empty] | 1 |  | Inaugurated 2016 |  | Patna East
54 | SSS-377-1 | Patna | iquiqu | mRØfer e/; fo¦ky;] jkt?kkV uoknk | KAMESHWAR PRASAD SINGH, 9386235888 |  |  | 9386235888 |  |  |  |  | 1 | [10 empty] | Patna East
55 | SSS-131-1 | Rohtas | djxgj | e/; fo¦ky;] efu;kjh | Krishna Ganeshpur, PO- Mamrejpur, PS- chenari, Rohtas | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna West
56 | SSS-131-2 | Rohtas | djxgj | mRØfer e/; fo¦ky;] :iSBk | Krishna Ganeshpur, PO- Mamrejpur, PS- chenari, Rohtas | [13 empty] | 1 |  |  |  |  | Patna West
57 | SSS-132-1 | Rohtas | dkspl | mRdzfer e/; fo¦ky;] ygsjh | Vikash Kumar | [10 empty] | 1 | [7 empty] | Patna West
58 | SSS-132-2 | Rohtas | dkspl | e/; fo¦ky;] dq:lk | Vikash Kumar | [12 empty] | 1 | [5 empty] | Patna West
59 | SSS-133-1 | Rohtas | f'kolkxj | e/; fo¦ky;] eqgEeniqj | Shree Jogmaya Infrastructure Co. Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated | 28.12.2016 | Patna West
60 | SSS-133-2 | Rohtas | f'kolkxj | mRdzfer e/; fo¦ky;] xksrgj | Shree Jogmaya Infrastructure Co. Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated | 28.12.2016 | Patna West
61 | SSS-133-3 | Rohtas | f'kolkxj | mRdzfer e/; fo¦ky;] lsejh | Shree Jogmaya Infrastructure Co. Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Dispute |  | Patna West
62 | SSS-133-4 | Rohtas | f'kolkxj | e/; fo¦ky;] FkuqvkW | Shree Jogmaya Infrastructure Co. Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated | 28.12.2016 | Patna West
63 | SSS-134-1 | Rohtas | fMgjh | mRdzfer e/; fo¦ky;] HkMdqfM;k | Uday Nath Dubey,Pahari Tola,Ranchi | [13 empty] | 1 |  |  |  |  | Patna West
64 | SSS-134-2 | Rohtas | fMgjh | e/; fo¦ky;] nqxkZiqj | Uday Nath Dubey,Pahari Tola,Ranchi | [13 empty] | 1 |  |  |  |  | Patna West
65 | SSS-135 (A) | Rohtas | fnukjk | e/; fo¦ky;] osyoS;k | Sidheshwar Singh,Rohtas,Bihar | [14 empty] | 1 |  | Inaugurated 2016 | 20.05.2016 | Patna West
66 | SSS-135 (B) | Rohtas | fnukjk | e/; fo¦ky;] cjk<hdyk | Kanchan Cons. | [5 empty] | 1 | [10 empty] | Land Problem |  | Patna West
67 | SSS-135 (C) | Rohtas | fnukjk | e/; fo¦ky;] esnuhiqj | Sidheshwar Singh, Rohtas, Bihar | [14 empty] | 1 |  | Inaugurated 2016 | 20.05.2016 | Patna West
68 | SSS-135 (D) | Rohtas | fnukjk | mRdzfer e/; fo¦ky;] [kylkiqj | Suraj Traders | [14 empty] | 1 |  |  | 30.12.2016 | Patna West
69 | SSS-136-1 | Rohtas | frykSFkq | e/; fo¦ky;] lsogh | Anil Ray,Rohtas | [14 empty] | 1 |  | Inaugurated. (CD-20.05.2016) | 15.05.2016 | Patna West
70 | SSS-137-1 | Rohtas | frykSFkw | e/; fo¦ky;] Hknks[kjk | Chandra Bhushan Roy,Kaimur | [5 empty] | 1 | [10 empty] | Low Land about 12'-0" |  | Patna West
71 | SSS-138-1 | Rohtas | Lkklkjke | mRdzfer e/; fo¦ky;] nouiqj | Shree Jogmaya Infrastrunture Co. Pvt. Ltd,Sasaram.Bihar | [14 empty] | 1 |  | Inaugurated | 25.07.2016 | Patna West
72 | SSS-138-2 | Rohtas | Lkklkjke | e/; fo¦ky;] nfjxkao | Shree Jogmaya Infrastrunture Co. Pvt. Ltd,Sasaram.Bihar | [14 empty] | 1 |  | Inaugurated | 25.07.2016 | Patna West
73 | SSS-138-3 | Rohtas | Lkklkjke | e/; fo¦ky;] xksVik | Shree Jogmaya Infrastrunture Co. Pvt. Ltd,Sasaram.Bihar | [14 empty] | 1 |  | Inaugurated | 25.07.2016 | Patna West
74 | SSS-139-1 | Rohtas | lklkjke | e/; fo¦ky;] HkSlgha | A. K. Construction | Rohtas | Bihar | [12 empty] | 1 |  | Inaugurated | 01.04.2016 | Patna West
75 | SSS-139-2 | Rohtas | lklkjke | e/; fo¦ky;] ukSxkbZ | A. K. Construction | Rohtas | Bihar | [12 empty] | 1 |  | Inaugurated | 01.04.2016 | Patna West |  | DOC (Date of Complete
76 | SSS-139-3 | Rohtas | lklkjke | e/; fo¦ky;] ifr;k< | A. K. Construction | Rohtas | Bihar | [12 empty] | 1 |  | Inaugurated | 01.04.2016 | Patna West
77 | SSS-140-1 | Rohtas | psukjh | e/; fo¦ky;] HkqMdqfM;k | Krishna,Ganeshpur,Rohtas | [7 empty] | 1 | [10 empty] | Patna West
78 | SSS-140-2 | Rohtas | psukjh | mRdzfer e/; fo¦ky;] x.ks'kiqj | Krishna,Ganeshpur,Rohtas | [14 empty] | 1 |  | Inaugurated 2016 | 30.03.2016 | Patna West
79 | SSS-141-1 | Rohtas | uks[kk | e/; fo¦ky;] ef<;kW | Maa Pragati ConstructionCo-Ramanand Singh,Rohtas | [14 empty] | 1 |  | Inaugurated |  | Patna West
80 | SSS-142-1 | Rohtas | ukSgêk | mRØfer e/; fo¦ky;] HkoukFkiqj | M/S Manoj Singh,Rohtas | [14 empty] | 1 |  | Inaugurated (DOC-30.04.2016) | 17.03.2016 | Patna West
81 | SSS-143-1 | Rohtas | vdks<+hxksyk | mRdzfer e/; fo¦ky;] lyS;k | Sidheshwar Singh,Rohtas,Bihar | [14 empty] | 1 |  | Inaugurated (DOC- 20.12.2015) | 20.12.2015 | Patna West
82 | SSS-143-2 | Rohtas | vdks<+hxksyk | e/; fo¦ky;] dkSik | Sidheshwar Singh,Rohtas,Bihar | [14 empty] | 1 |  | Inaugurated (DOC- 20.12.2015) | 20.12.2015 | Patna West
83 | SSS-144-1 | Buxar | bVk<+h | e/; fo¦ky;] fc>kSjk | Buxar Construction | [14 empty] | 1 |  | Inaugurated 2016 | 28.07.2016 | Patna West
84 | SSS-144-2 | Buxar | bVk<+h | e/; fo¦ky;] cSjh | Buxar Construction | [14 empty] | 1 |  | Inaugurated 2016 | 28.07.2016 | Patna West
85 | SSS-145-1 | Buxar | cDlj | e/; fo¦ky;] cksDlk | Bablu Kumar Singh Ram Jee chak,Patna | [14 empty] | 1 |  | Inaugurated 2016 | 30.06.2016 | Patna West
86 | SSS-145-2 | Buxar | cDlj | e/; fo¦ky;] tklks | Bablu Kumar Singh Ram Jee chak,Patna | [14 empty] | 1 |  | Inaugurated 2016 | 30.07.2016 | Patna West
87 | SSS-146-1 | Buxar | czãiqj | g0m0 e/; fo¦ky;] j?kqukFkiqj | Sharda Construction,sri Kung,Patna | [14 empty] | 1 |  |  | 10.02.2017 | Patna West
88 | SSS-146-2 | Buxar | czãiqj | e/; fo¦ky;] cjk<+h | Sharda Construction,sri Kung,Patna | [12 empty] | 1 | [5 empty] | Patna West
89 | SSS-147-1 | Buxar | flejh | d0 e/; fo¦ky;] nqYygiqj | Ranjan kumar Singh,Civil Lines,buxer,Bihar | [13 empty] | 1 |  |  | Inaugurated 2016 |  | Patna West
90 | SSS-147-2 | Buxar | flejh | e/; fo¦ky;] NksVdk flaguiqjk | Ranjan kumar Singh,Civil Lines,buxer,Bihar | [13 empty] | 1 |  |  | Inaugurated 2016 |  | Patna West
91 | SSS-147-3 | Buxar | flejh | e/; fo¦ky;] ,dkSuk | Ranjan kumar Singh,Civil Lines,buxer,Bihar | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna West
92 | SSS-148-1 | Buxar | jktiqj | e/; fo¦ky;] eaxjko | M/S Darshita Buildres and Developers pvt. Ltd,Kaimur,Bhabua | [14 empty] | 1 |  | Inaugurated 2016 | 25.11.2016 | Patna West
93 | SSS-149-1 | Buxar | pkSlk | e/; fo¦ky;] iouh | Krishna pratap Singh,Ramgarh,kaimur-9801133880 |  |  | 9801133880 | [11 empty] | 1 | 12.05.2015 | Inaugurated 2016 | 10.05.2016 | Patna West
94 | SSS-149-2 | Buxar | pkSlk | e/; fo¦ky;] lxjk | Krishna pratap Singh,Ramgarh,kaimur-9801133880 |  |  | 9801133880 | [11 empty] | 1 | 12.05.2015 | Inaugurated 2016 | 10.05.2016 | Patna West
95 | SSS-149-3 | Buxar | pkSlk | e/; fo¦ky;] pqUuh | Krishna pratap Singh,Ramgarh,kaimur-9801133880 |  |  | 9801133880 | [11 empty] | 1 | 12.05.2015 | Inaugurated | 10.05.2016 | Patna West
96 | SSS-150-1 | Buxar | ukokuxj | e/; fo¦ky;] Hknkj | M/S Aditya Construction,Govindpur,Buxer | [10 empty] | 1 | [7 empty] | Patna West
97 | SSS-150-2 | Buxar | ukokuxj | e/; fo¦ky;] xksfoUniqj | M/S Aditya Construction,Govindpur,Buxer | [10 empty] | 1 | [7 empty] | Patna West
98 | SSS-151-1 | Kaimur | eksgfu;ka | mRØfer e/; fo¦ky;] nknj | Ashtbhuja Construction,Kanchanapur,rohtas | [14 empty] | 1 |  |  | 15.02.2017 | Patna West
99 | SSS-151-2 | Kaimur | eksgfu;ka | e/; fo¦ky;] Hkj[kj | Ashtbhuja Construction, Kanchanapur, Rohtas | [14 empty] | 1 |  |  | 15.03.2017 | Patna West
100 | SSS-151-3 | Kaimur | eksgfu;ka | mRØfer e/; fo¦ky;] vesB | Ashtbhuja Construction, Kanchanapur, Rohtas | [14 empty] | 1 |  |  | 10.02.2017 | Patna West
101 | SSS-152-1 | Kaimur | HkHkqvk | e/; fo¦ky;] Hksdkl | Nav Nirman Construction,bhabhua,Kaimur | [13 empty] | 1 |  |  |  |  | Patna West
102 | SSS-153-1 | Kaimur | Hkxokuiqj | mRØfer e/; fo¦ky;] dlsj | Ajay kumar Singh,Bhabua,Kaimur | [14 empty] | 1 |  | Inaugurated 2016 | 10.10.2016 | Patna West
103 | SSS-153-2 | Kaimur | Hkxokuiqj | mRØfer e/; fo¦ky;] fla/kh | Ajay kumar Singh,Bhabua,Kaimur | [14 empty] | 1 |  | Inaugurated 2015 | 10.10.2016 | Patna West
104 | SSS-154-1 | Kaimur | nwxkZorh | mRØfer e/; fo¦ky;] xksjkj | Baba vishwannath construction,Nowan,Kaimur | [14 empty] | 1 |  | Inaugurated 2016 | 02.04.2016 | Patna West
105 | SSS-155-1 | Kaimur | pkWan | e/; fo¦ky;] Hkjkjh | Gupta dham Construction, bhabhua | [14 empty] | 1 | 31.05.2016 | Inaugurated 2016 | 31.05.2016 | Patna West
106 | SSS-156-1 | Kaimur | pSuiqj | e/; fo¦ky;] c<kSuk | Gupta dham Construction,Kaimur | [14 empty] | 1 | 05.05.2016 | Inaugurated 2015 | 05.05.2016 | Patna West
107 | SSS-157-1 | Kaimur | v/kkSjk | mRØfer e/; fo¦ky;] pQuk | Ajay Kumar Singh , Bhabua,Kaimur | [13 empty] | 1 |  |  |  |  | Patna West
108 | SSS-157-2 | Kaimur | v/kkSjk | mRØfer e/; fo¦ky;] U;w | Ajay Kumar Singh , Bhabua,Kaimur | [14 empty] | 1 |  |  |  | Patna West
109 | SSS-391 (A) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] cnokadyk | THAKUR SAAH | [5 empty] | 1 | [12 empty] | Patna West
110 | SSS-391 (B) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] cgsM+k | THAKUR SAAH | [10 empty] | 1 | [7 empty] | Patna West
111 | SSS-391 (C) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] dUgukj | SANJAY KUMAR SINGH | [7 empty] | 1 | [10 empty] | Patna West
112 | SSS-391 (D) | Kaimur | v/kkSjk | e/; fo¦yk;] ngkj | SANJAY KUMAR SINGH | [10 empty] | 1 | [7 empty] | Patna West
113 | SSS-392-1 | Kaimur | jkeiqj | e/; fo¦ky;] veho | GUPTA DHAM CONSTRUCTIONS | [13 empty] | 1 |  |  |  |  | Patna West
114 | SSS-393-1 | Kaimur | Hkxokuiqj | e/; fo¦ky;] tSrqiqjdyk | NAV NIRMAN CONSTRUCTION, 9507456472 |  |  | 9507456472 | [10 empty] | 1 |  |  |  |  | Patna West
115 | SSS-394-1 | Kaimur | eksguh;k¡ | e/; fo¦ky;] dFkst | RISHABH KUMAR MISHRA | [14 empty] | 1 |  | Inaugurated 2016 |  | Patna West
116 | SSS-395-1 | Kaimur | uqvk¡o | e/; fo¦ky;] dksVk | Shri Ram Constructions | [13 empty] | 1 |  |  |  |  | Patna West
117 | SSS-396-1 | Kaimur | jkex<+ | e/; fo¦ky;] uksukj | DARSHITA BUILDER AND DEVELOPERS PVT LTD, 09801134120 |  |  | 9801134120 | [10 empty] | 1 |  |  |  |  | Patna West
118 | SSS-397-1 | Kaimur | pSuiqj | mRØfer e/; fo¦ky;] Mqekjdksu | SHARDA SECURITY AND ALLIED SERVICES, 9708277777 |  |  | 9708277777 | [10 empty] | 1 |  |  |  |  | Patna West
119 | SSS-429-1 | Rohtas | foØexat | e/; fo¦ky;] uksugj | MANOJ KUMAR SINGH, 8804224510 |  |  | 8804224510 | [11 empty] | 1 |  | Inaugurated 2016 | 30.12.2016 | Patna West
120 | SSS-429-2 | Rohtas |  | e/; fo¦ky;] mn; fMgjh | MANOJ KUMAR SINGH, 8804224510 |  |  | 8804224510 | [11 empty] | 1 |  |  | 30.12.2016 | Patna West
121 | SSS-430-1 | Rohtas | jksgrkl | mRØfer e/; fo¦ky;] VqEck | MAA MUNDESHWARI CONSTRUCTION,9430895576 |  |  | 9430895576 | [11 empty] | 1 |  | Inaugurated 2016 | 25.11.2016 | Patna West
122 | SSS-431-1 | Rohtas | psukjh | mRØfer e/; fo¦ky;] fi;kdyk | MANOJ KUMAR SINGH, 8804224510 |  |  | 8804224510 | [11 empty] | 1 |  |  | 10.10.2016 | Patna West
123 | SSS-254 (A) | Gaya | bekexat | e/; fo¦ky;] oa'kh | Satendra Kumar | [14 empty] | 1 |  |  |  | Magadh
124 | SSS-254 (B) | Gaya | bekexat | e/; fo¦ky;] fojkt | Koela Construction | Gaya | Bihar | [6 empty] | 1 | [9 empty] | Magadh
125 | SSS-254 (C) | Gaya | bekexat | e/; fo¦ky;] f>dfV;kdyk | Sunil Kumar | [14 empty] | 1 |  |  |  | Magadh
126 | SSS-254 (D) | Gaya | bekexat | e/; fo¦ky;] olsrk | Gautam Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
127 | SSS-255-1 | Gaya | cFkkuh | mnwZ e/; fo¦ky;] oaMh | Roy Engineers | [14 empty] | 1 |  |  |  | Magadh
128 | SSS-256-1 | Gaya | ckads ctkj | e/; fo¦ky;] jkS'kuxat | Sanju kuamri | [14 empty] | 1 |  | Inaugurated 2015 |  | Magadh
129 | SSS-257-1 | Gaya | ckds ctkj | e/; fo¦ky;] yqVqvk | Koela Construction, Gaya | [5 empty] | 1 | [10 empty] | Land Problem (Local) |  | Magadh
130 | SSS-257-2 | Gaya | ckds ctkj | e/; fo¦ky;] eksus;k | Koela Construction, Gaya | [13 empty] | 1 |  |  |  |  | Magadh
131 | SSS-258-1 | Gaya | ckjkpV~Vh | e/; fo¦ky;] fnofu;ka | MS Azad Construction, Gaya | [14 empty] | 1 |  |  |  | Magadh
132 | SSS-258-2 | Gaya | ckjkpV~Vh | e/; fo¦ky;] uokMhg | MS Azad Construction, Gaya | [14 empty] | 1 |  |  |  | Magadh
133 | SSS-259-1 | Gaya | cks/kx;k | e/; fo¦ky;] teM+h | Om Shakti Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
134 | SSS-259-2 | Gaya | cks/kx;k | e/; fo¦ky;] ijfj;k | Om Shakti Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
135 | SSS-259-3 | Gaya | cks/kx;k | e/; fo¦ky;] ekspkfje | Om Shakti Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
136 | SSS-259-4 | Gaya | cks/kx;k | e/; fo¦ky;] 'ksjokjk | Om Shakti Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
137 | SSS-260-1 | Gaya | cthjxat | e/; fo¦ky;] fo'kquiqj | Sidhnath Construction | [13 empty] | 1 |  |  |  |  | Magadh
138 | SSS-261-1 | Gaya | eksguiqj | e/; fo¦ky;] tsBqvkMkgk | Keol Construction | [8 empty] | 1 | [7 empty] | work stoped due to Court Order & B/W Up to Sill level |  | Magadh
139 | SSS-261-2 | Gaya | eksguiqj | e/; fo¦ky;] [kqMqvk | Keol Construction | [13 empty] | 1 |  |  |  |  | Magadh
140 | SSS-262-1 | Gaya | ekuiqj | e/; fo¦ky;] xsjs | Satish Kusum Raj | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
141 | SSS-262-2 | Gaya | ekuiqj | e/; fo¦ky;] Hkksjs | Satish Kusum Raj | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
142 | SSS-263-1 | Gaya | f[ktjljk; | e/; fo¦ky;] lfj;k | Ranjan Kumar Gajraj Singh | [13 empty] | 1 |  |  |  |  | Magadh
143 | SSS-264-1 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] mfpjek | Narendra Yadav | [14 empty] | 1 |  | Inaugurated 2015 |  | Magadh
144 | SSS-264-2 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] eksguiqj | Narendra Yadav | [5 empty] | 1 | [10 empty] | Land Dispute |  | Magadh
145 | SSS-264-3 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] dpkSM+h | Narendra Yadav | [14 empty] | 1 |  | Inaugurated 2015 |  | Magadh
146 | SSS-265 (A) | Gaya | Mqefj;k | e/; fo¦ky;] cjgk | MS Azad Construction, | [9 empty] | 1 | [8 empty] | Magadh
147 | SSS-265 (B) | Gaya | Mqefj;k | e/; fo¦ky;] gsljk jkeiqj | Sunil Kumar | [5 empty] | 1 | [10 empty] | Not Start. Under proces for land registry in favour of hon. Governer |  | Magadh
148 | SSS-266-1 | Gaya | Qrsgiqj | e/; fo¦ky;] lyS;kdyk | Ms Sidhnath Construction | [14 empty] | 1 |  |  |  | Magadh
149 | SSS-267-1 | Gaya | uxj | xzke&dsokyh] Fkkuk laŒ&197 | Satish Kusum Raj | [13 empty] | 1 |  |  |  |  | Magadh
150 | SSS-267-2 | Gaya | uxj | e/; fo¦ky;] dksjeka | Satish Kusum Raj | [12 empty] | 1 | [5 empty] | Magadh
151 | SSS-267-3 | Gaya | uxj | xzke&/kqosZ Fkkuk laŒ&177 | Satish Kusum Raj | [10 empty] | 1 | [7 empty] | Magadh
152 | SSS-268-1 | Gaya | vkel | e/; fo¦ky;] ';kedyk | Jai Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
153 | SSS-268-2 | Gaya | vkel | e/; fo¦ky;] fuek cq)kSy | Jai Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
154 | SSS-269-1 | Gaya | Vsdkjh | e/; fo¦ky;] cych?kk | Ram Pukar Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
155 | SSS-270-1 | Gaya | VudqIik | e/; fo¦ky;] ukSokx<+ | Sidhnath Consdtruction | [14 empty] | 1 |  |  |  | Magadh
156 | SSS-270-2 | Gaya | VudqIik | e/; fo¦ky;] HksVkSjk | Sidhnath Consdtruction | [14 empty] | 1 |  |  |  | Magadh
157 | SSS-271 (A) | Gaya | xq:vk | e/; fo¦ky;] 'ksjiqj | Sheel Construction | [13 empty] | 1 |  |  |  |  | Magadh
158 | SSS-271 (B) | Gaya | xq:vk | e/; fo¦ky;] ukSfMgk | Sanjeev Kumar | [5 empty] | 1 | [10 empty] | Not Start. File pending at DCLR sherghati since seven month for registry process |  | Magadh
159 | SSS-271 (C) | Gaya | xq:vk | e/; fo¦ky;] fojfgek | Sheel Construction | [13 empty] | 1 |  |  |  |  | Magadh
160 | SSS-271 (D) | Gaya | xq:vk | e/; fo¦ky;] dkt | Sharwan Kumar Singh | [14 empty] | 1 |  |  |  | Magadh
161 | SSS-272-1 | Nawada | esLdkSj | mRØfer e/; fo¦ky;] iokbZ | Om Shakti Construction | [14 empty] | 1 |  |  |  | Magadh
162 | SSS-272-2 | Nawada | esLdkSj | mRØfer e/; fo¦ky;] vdfj | Om Shakti Construction | [13 empty] | 1 |  |  |  |  | Magadh
163 | SSS-273-1 | Nawada | fglqvk | mRØfer e/; fo¦ky;] ,dukj | Arvind Kumar | [13 empty] | 1 |  |  |  |  | Magadh
164 | SSS-274-1 | Nawada | fljnyk | mRØfer e/; fo¦ky;] dksyfMgk | MD. Rais Khan | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
165 | SSS-274-2 | Nawada | fljnyk | e/; fo¦ky;] [kuiqjk | MD. Rais Khan | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
166 | SSS-274-3 | Nawada | fljnyk | e/; fo¦ky;] vdEck | MD. Rais Khan | [5 empty] | 1 | [10 empty] | Land Dispute |  | Magadh
167 | SSS-275-1 | Nawada | idjhcjkok¡ | e/; fo¦ky;] ds'kkSjh | Gopal Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
168 | SSS-276-1 | Nawada | jksg | e/; fo¦ky;] dqat | Arvind Kumar | [14 empty] | 1 |  |  |  | Magadh
169 | SSS-277 (A) | Nawada | jtkSyh | mRØfer e/; fo¦ky;] /kkeqpd | Nawin Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
170 | SSS-277 (B) | Nawada | jtkSyh | e/; fo¦ky;] pijk | Dhirendra Prasad, Nalanda | [13 empty] | 1 |  |  |  |  | Magadh
171 | SSS-279-1 | Nawada | ujgV | mRØfer e/; fo¦ky;] cjcŸkk | Ramesh Kumar | [5 empty] | 1 | [10 empty] | CROSSING HIGH TENSION WIRE |  | Magadh
172 | SSS-279-2 | Nawada | ujgV | mRØfer e/; fo¦ky;] nkbZfcxgk | Ramesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
173 | SSS-280-1 | Nawada | uoknk | mRØfer e/; fo¦ky;] ifN;k Mhg | Shiv Shakti Construction | [14 empty] | 1 |  |  |  | Magadh
174 | SSS-281-1 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] Qjgk | Dhirendra prasad | [13 empty] | 1 |  |  |  |  | Magadh
175 | SSS-281-2 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] rsyHknzks | Dhirendra prasad | [14 empty] | 1 |  |  |  | Magadh
176 | SSS-281-3 | Nawada | vdcjiqj | e/; fo¦ky;] Hkusy | Dhirendra prasad | [13 empty] | 1 |  |  |  |  | Magadh
177 | SSS-281-4 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] Qqyek | Dhirendra prasad | [14 empty] | 1 |  |  |  | Magadh
178 | SSS-281-5 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] ifl;k | Dhirendra prasad | [13 empty] | 1 |  |  |  |  | Magadh
179 | SSS-282-1 | Nawada | xksfoUniqj | mRØfer e/; fo¦ky;] rsrfj;k | Arbind Prasad | [10 empty] | 1 | [7 empty] | Magadh
180 | SSS-282-2 | Nawada | xksfoUniqj | e/; fo¦ky;] cq/kokM+k | Arbind Prasad | [10 empty] | 1 | [7 empty] | Magadh
181 | SSS-283-1 | Arwal | djih | e/; fo¦ky;] [ktqjh | Kaushalendra Kumar | [14 empty] | 1 |  |  |  | Magadh
182 | SSS-283-2 | Arwal | djih | e/; fo¦ky;] v/kkjpd | Kaushalendra Kumar | [14 empty] | 1 |  |  |  | Magadh
183 | SSS-284-1 | Arwal | dysj | e/; fo¦ky; mljh | Raj kumar Singh raja ConstructionPvt Ltd | [5 empty] | 1 | [10 empty] | Land Dispute |  | Magadh
184 | SSS-284-2 | Arwal | dysj | e/; fo¦ky; ofynkn | Raj kumar Singh raja ConstructionPvt Ltd | [14 empty] | 1 |  |  |  | Magadh
185 | SSS-285-1 | Arwal | dqFkkZ | mRØfer e/; fo¦ky;] dSFkksyksnhiqj | Kaushlendra Kumar | [14 empty] | 1 |  |  |  | Magadh
186 | SSS-286-1 | Arwal | lksuHknz oa'kh lw;Ziqj | e/; fo¦ky;] iksfUny | Kaushalendra Kumar | [14 empty] | 1 |  |  |  | Magadh
187 | SSS-287-1 | Arwal | vjoy | e/; fo¦ky; jkeiqj pkSje | M/s Maa KamaKhya | [14 empty] | 1 |  |  |  | Magadh
188 | SSS-288-1 | Aurangabad | ck:.k | e/; fo¦ky;] dnks[kjh | Arvind Kumar Singh | [8 empty] | 1 | [9 empty] | Magadh
189 | SSS-288-2 | Aurangabad | ck:.k | e/; fo¦ky;] fiBuqvk | Arvind Kumar Singh | [13 empty] | 1 |  |  |  |  | Magadh
190 | SSS-289-1 | Aurangabad | dqVqEck | e/; fo¦ky;] pkS[kMk | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
191 | SSS-289-2 | Aurangabad | dqVqEck | e/; fo¦ky;] fd'kquiqj | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
192 | SSS-289-3 | Aurangabad | dqVqEck | e/; fo¦ky;] cStkfcxgk | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
193 | SSS-289-4 | Aurangabad | dqVqEck | e/; fo¦ky;] cSjko | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
194 | SSS-289-5 | Aurangabad | dqVqEck | e/; fo¦ky;] ?ksmjk | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
195 | SSS-289-6 | Aurangabad | dqVqEck | e/; fo¦ky;] iksyk xksjMhgk | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
196 | SSS-289-7 | Aurangabad | dqVqEck | e/; fo¦ky;] ihijk cxkgh | Maa Sharda Construction | [13 empty] | 1 |  |  |  |  | Magadh
197 | SSS-290 (A) | Aurangabad | jQhxat | e/; fo¦ky;] ljkod | Pankaj Kumar Suman | [5 empty] | 1 | [10 empty] | Not Start. Agreement pending |  | Magadh
198 | SSS-290 (B) | Aurangabad | jQhxat | e/; fo¦ky;] i[kukSj | Hari Om Construction, Aurangabad | [13 empty] | 1 |  |  |  |  | Magadh
199 | SSS-291-1 | Aurangabad | nso | e/; fo¦ky;] ukjk;.kiqj | M/s Darshita Builders & Developers Pvt Ltd. | [13 empty] | 1 |  |  |  |  | Magadh
200 | SSS-292-1 | Aurangabad | nso | e/; fo¦ky;] cjaMk jkeiqj | M/s Hari Om Construction | [13 empty] | 1 |  |  |  |  | Magadh
201 | SSS-292-2 | Aurangabad | nso | e/; fo¦ky;] dVS;k | M/s Hari Om Construction | [13 empty] | 1 |  |  |  |  | Magadh
202 | SSS-292-3 | Aurangabad | nso | e/; fo¦ky;] csyk | M/s Hari Om Construction | [14 empty] | 1 |  |  |  | Magadh
203 | SSS-293-1 | Aurangabad | uchuxj | e/; fo¦ky;] jkeuxj | Satyendra Kumar Consyruction, Patna | [14 empty] | 1 |  |  |  | Magadh
204 | SSS-293-2 | Aurangabad | uchuxj | e/; fo¦ky;] e>hvko | Satyendra Kumar Consyruction, Patna | [14 empty] | 1 |  |  |  | Magadh
205 | SSS-293-3 | Aurangabad | uchuxj | e/; fo¦ky;] dadsj | Satyendra Kumar Consyruction, Patna | [14 empty] | 1 |  |  |  | Magadh
206 | SSS-293-4 | Aurangabad | uchuxj | e/; fo¦ky;] csykbZ | Satyendra Kumar Consyruction, Patna | [14 empty] | 1 |  |  |  | Magadh
207 | SSS-294-1 | Aurangabad | vkSjaxkckn | e/; fo¦ky;] cHkUMh | M/S Raj Construction, Aurangabad | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
208 | SSS-295-1 | Aurangabad | xksg | e/; fo¦ky;] ?kkVks | MS Om Enterprises | [13 empty] | 1 |  |  |  |  | Magadh
209 | SSS-295-2 | Aurangabad | xksg | e/; fo¦ky;] 'ks[kiqjk | MS Om Enterprises | [12 empty] | 1 | [5 empty] | Magadh
210 | SSS-296-1 | Aurangabad |  | e/; fo¦ky;] rqjrk | Bhole Shankar Construction pvt Ltd,aurangabad | [14 empty] | 1 |  |  |  | Magadh
211 | SSS-297-1 | Jahanabad | dkdks | mRØfer e/; fo¦ky;] nso/kjk | M/S Uma Shankar & Co,Patna-7 | [14 empty] | 1 |  |  |  | Magadh
212 | SSS-297-2 | Jahanabad | dkdks | mRØfer e/; fo¦ky;] mÙkjlsjFkq | M/S Uma Shankar & Co,Patna-7 | [5 empty] | 1 | [10 empty] | Land not available |  | Magadh
213 | SSS-298-1 | Jahanabad | e[knqeiqj | mRØfer e/; fo¦ky;] mnwZ eykBh | M/s shree krishna Engineering Works,Jehanabad | [14 empty] | 1 |  |  |  | Magadh
214 | SSS-299-1 | Jahanabad | eksnuxat | e/; fo¦ky;] oSuk | Rajesh Kumar | [13 empty] | 1 |  |  |  |  | Magadh
215 | SSS-300-1 | Jahanabad | gqyklxat | e/; fo¦ky;] dsmj | Maa Sherawali Construction , Patna | [13 empty] | 1 |  |  |  |  | Magadh
216 | SSS-301-1 | Jahanabad | jruh | e/; fo¦ky;] ?kstu | Kaushlendra Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
217 | SSS-301-2 | Jahanabad | jruh | mRØfer e/; fo¦ky;] iaMkSy | Kaushlendra Kumar | [14 empty] | 1 |  |  |  | Magadh
218 | SSS-301-3 | Jahanabad | jruh | mRØfer e/; fo¦ky;] tgk¡xhjiqj | Kaushlendra Kumar | [14 empty] | 1 |  |  |  | Magadh
219 | SSS-301-4 | Jahanabad | jruh | mRØfer e/; fo¦ky;] c<srk | Kaushlendra Kumar | [7 empty] | 1 | [10 empty] | Magadh
220 | SSS-302-1 | Jahanabad | tgkukckn | mRØfer e/; fo¦ky;] /kqfj;k | M/s Shree Krishna Engineering | [14 empty] | 1 |  |  |  | Magadh
221 | SSS-452-1 | Nawada | jtkSyh | e/; fo¦ky;] fljSyk | Mahnar Infratech Pvt. Ltd,9771410513 | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
222 | SSS-453-1 | Nawada | fljnyk | e/; fo¦ky;] pkScs | SUJAY BHAN SINGH,9473297677 | [13 empty] | 1 |  |  |  |  | Magadh
223 | SSS-454-1 | Nawada | dksvkdksy | e/; fo¦ky;] /keku | MS ANANYA CONSTRUCTION, 9334745882 | [10 empty] | 1 | [7 empty] | Magadh
224 | SSS-454-2 | Nawada | dksvkdksy | mRØfer e/; fo¦ky;] dkyqvkckj | MS ANANYA CONSTRUCTION, 9334745882 | [14 empty] | 1 |  | Inaugurated 2016 |  | Magadh
225 | SSS-457-1 | Aurangabad | gliqjk | e/; fo¦ky;] vfg;kiqj | DARSHITA BUILDER AND DEVELOPERS PVT LTD, 09801134120 | [5 empty] | 1 | [10 empty] | Land Problem. (Proposed for refund of EMD. Letter no.- BSEIDC/MAG/EX/719/2016. Dated- 04.03.2016) |  | Magadh
226 | SSS-458-1 | Aurangabad | jQhxat | e/; fo¦ky;] flMqyh njxkg | MS GUPTA DHAM CONSTRUCTION, 9661648500 | [5 empty] | 1 | [10 empty] | Land Problem. (Project Cancelled by the order of court (according to DPO, RMSA, Aurangabad) |  | Magadh
227 | SSS-458-2 | Aurangabad | jQhxat | e/; fo¦ky;] yksgjk | MS GUPTA DHAM CONSTRUCTION, 9661648500 | [13 empty] | 1 |  |  |  |  | Magadh
228 | SSS-459-1 | Aurangabad | uohxat | e/; fo¦ky;] Fksxks | SHAMSHER KUMAR | [13 empty] | 1 |  |  |  |  | Magadh
229 | SSS-459-2 | Aurangabad | uohxat | e/; fo¦ky;] daMh | SHAMSHER KUMAR | [10 empty] | 1 | [7 empty] | Magadh
230 | SSS-460-1 | Aurangabad | nso | e/; fo¦ky; nykjs | TRADEWELL CONSTRUCTION PVT LTD,9801181475 | [5 empty] | 1 | [10 empty] | Not Start |  | Magadh
231 | SSS-461-1 | Aurangabad | enuiqj | e/; fo¦ky;] Nkyhnksgj | Maa Bangla Mukhi Infrastructure | [8 empty] | 1 | [9 empty] | Magadh
232 | SSS-462-1 | Aurangabad | xksg | e/; fo¦ky;] egnhuiqj | Nilesh Kumar | [13 empty] | 1 |  |  |  |  | Magadh
233 | SSS-463-1 | Gaya | gfFk;kok¡ | e/; fo¦ky;] egdkj | KAUSHLENDRA KUMAR,8409113501 | [14 empty] | 1 |  | Inaugurated 2015 |  | Magadh
234 | SSS-464-1 | Gaya | xq:vk | e/; fo¦ky;] ljS;kVkM+ | SANJAY KUMAR SINGH, 9973456006 | [14 empty] | 1 |  |  |  | Magadh
235 | SSS-465-1 | Gaya | bekexat | e/; fo¦ky; cgsM+k pkSHkkj | SANJU KUMARI, 9430676434 | [14 empty] | 1 |  |  |  | Magadh
236 | SSS-465-2 | Gaya | bekexat | e/; fo¦ky;] njHkaxk | SANJU KUMARI, 9430676434 | [14 empty] | 1 |  |  |  | Magadh
237 | SSS-356-1 | Aurangabad | xksg | e/; fo¦ky;] cUns;k | MS OM ENTERPRISESMS | [13 empty] | 1 |  |  |  |  | Magadh
238 | SSS-356-2 | Aurangabad | xksg | e/; fo¦ky;] csuh dSFkh | MS OM ENTERPRISESMS | [13 empty] | 1 |  |  |  |  | Magadh
239 | SSS-230 (A) | Bhagalpur | [kjhd | e/; fo¦ky;] vykyiqj | Sai Highway | [14 empty] | 1 |  | Handover |  | Bhagalpur
240 | SSS-230 (B) | Bhagalpur | [kjhd | e/; fo¦ky;] cxMh | Sai Highway And Builders Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Bhagalpur
241 | SSS-231 (A) | Bhagalpur | bLekbZyiqj | e/; fo¦ky;] jkeuxj | Kanhaiya Contractors | [14 empty] | 1 |  |  |  | Bhagalpur
242 | SSS-231 (B) | Bhagalpur | bLekbZyiqj | e/; fo¦ky;] eksrh Vksyk | Kanhaiya Contractors Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Dispute |  | Bhagalpur
243 | SSS-232-1 | Bhagalpur | dgyxkao | e/; fo¦ky;] dVksfj;k | Daya Nand singh, 3-lp-2, Barari | [14 empty] | 1 |  | Inaugurated 2015 |  | Bhagalpur
244 | SSS-233-1 | Bhagalpur | fcgiqj | e/; fo¦ky;] vkSfy;kokn | M/S Sai Highway & Builders pvt ltd, Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
245 | SSS-234-1 | Bhagalpur | ihjiSarh | e/; fo¦ky;] clariqj | Baba bateshwar Construction Pvt.Ltd, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
246 | SSS-234-2 | Bhagalpur | ihjiSarh | e/; fo¦ky;] nmok | Baba bateshwar Construction Pvt.Ltd, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
247 | SSS-234-3 | Bhagalpur | ihjiSarh | e/; fo¦ky;] Kkuorh Viqvk | Baba bateshwar Construction Pvt.Ltd, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
248 | SSS-234-4 | Bhagalpur | ihjiSarh | e/; fo¦ky;] ij'kqjkeiqj | Baba bateshwar Construction Pvt.Ltd, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
249 | SSS-235 (A) | Bhagalpur | jaxjk pkSd | e/; fo¦ky;] Hkokuhiqj Vksyk | Mahnar Infratech Pvt. Ltd. |  |  | 9771410513 | [10 empty] | 1 |  |  |  |  | Bhagalpur
250 | SSS-235 (B) | Bhagalpur | jaxjk pkSd | e/; fo¦ky;] cfu;k | Kanhaiya Contractors | [14 empty] | 1 |  |  |  | Bhagalpur
251 | SSS-236-1 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] oklqnsoiqj | Kuhu Construction | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
252 | SSS-236-2 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] iap:[kh | Kuhu Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
253 | SSS-236-3 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] HkaMkjou | Kuhu Construction | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Bhagalpur
254 | SSS-237-1 | Bhagalpur | lckSj | e/; fo¦ky;] cStukFkiqj | Shyam Sundar Yadav,Banka | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
255 | SSS-238-1 | Bhagalpur | lUgkSyk | e/; fo¦ky;] rsykaS/kk | Sai Highway | [14 empty] | 1 |  |  |  | Bhagalpur
256 | SSS-239-1 | Bhagalpur | ukFkuxj | e/; fo¦ky;] fo'kuiqj | Kanhaiya Contractors | [14 empty] | 1 | 1 |  |  | Bhagalpur
257 | SSS-240-1 | Bhagalpur | ukjk;.kiqj | e/; fo¦ky;] jk;iqj | Sudhir Prasad, Jamui | [14 empty] | 1 |  |  |  | Bhagalpur
258 | SSS-240-2 | Bhagalpur | ukjk;.kiqj | e/; fo¦ky;] Hkokuhiqj | Sudhir Prasad, Jamui | [14 empty] | 1 |  |  |  | Bhagalpur
259 | SSS-240-3 | Bhagalpur | ukjk;.kiqj | dU;k e/; fo¦ky;] eFkqjkiqj | Sudhir Prasad, Jamui | [14 empty] | 1 |  |  |  | Bhagalpur
260 | SSS-241-1 | Bhagalpur | uoxfN;k | e/; fo¦ky;] txriqj | Dharmendra Kumar Choudhary, Bhagalpur | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
261 | SSS-241-2 | Bhagalpur | uoxfN;k | e/; fo¦ky;] [kSjiqj | Dharmendra Kumar Choudhary, Bhagalpur | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Bhagalpur
262 | SSS-242-1 | Bhagalpur | xksikyiqj | e/; fo¦ky;] edUniqj | M/S Daya Ram Singh, Begusarai | [14 empty] | 1 |  | Inaugurated 2015 |  | Bhagalpur
263 | SSS-243-1 | Bhagalpur | xksikyiqj | e/; fo¦ky;] ipxfN;k | Karnawati Builders Pvt. Ltd, Samastipur | [5 empty] | 1 | [10 empty] | Land not available |  | Bhagalpur
264 | SSS-243-2 | Bhagalpur | xksikyiqj | e/; fo¦ky;] fMegk | Karnawati Builders Pvt. Ltd, Samastipur | [5 empty] | 1 | [10 empty] | Agreement not done |  | Bhagalpur
265 | SSS-244-1 | Bhagalpur | xksjkMhg | e/; fo¦ky;] fo'kuiqj ftPNksa | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
266 | SSS-244-2 | Bhagalpur | xksjkMhg | e/; fo¦ky;] lksuwMhg | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
267 | SSS-244-3 | Bhagalpur | xksjkMhg | e/; fo¦ky;] eksguiqj | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
268 | SSS-244-4 | Bhagalpur | xksjkMhg | e/; fo¦ky;] xaxkdjgfj;k | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
269 | SSS-244-5 | Bhagalpur | xksjkMhg | e/; fo¦ky;] eqDrkiqj | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
270 | SSS-244-6 | Bhagalpur | xksjkMhg | e/; fo¦ky;] dk'khy | Lalan Kumar Radha Rani Sinha road, Bhagalpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Bhagalpur
271 | SSS-245-1 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] vLlh edSrk | CHITRAGUPTA CONSTRUCTION PVT LTD,9431258544, 9931823577 | [12 empty] | 1 |  |  |  | G.F. ROOF CASTING |  | Bhagalpur
272 | SSS-245-2 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] pUnkMhg | CHITRAGUPTA CONSTRUCTION PVT LTD,9431258544, 9931823577 | [12 empty] | 1 |  |  |  | G.F. SHUTTERING |  | Bhagalpur
273 | SSS-245-3 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] eFkqjkiqj | CHITRAGUPTA CONSTRUCTION PVT LTD,9431258544, 9931823577 | [14 empty] | 1 |  |  |  | Bhagalpur
274 | SSS-246-1 | Banka | ckadk | izksŒ e/; fo¦ky;] vejiqj | Amarpur Construction Co. Pvt. Ltd, Banka | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Bhagalpur
275 | SSS-247-1 | Banka | ckjkgkV | izksŒ e/; fo¦ky;] egqvk | Bricks Liner Infrastructure | [14 empty] | 1 |  | Inaugurated 2015 |  | Bhagalpur
276 | SSS-248-1 | Banka | ckSalh | izksŒ e/; fo¦ky;] cHkuxkek | Dilendra Prasad Singh, jamui | Jamui | [9 empty] | 1 | [5 empty] | DEBAR |  | Bhagalpur
277 | SSS-248-2 | Banka | ckSalh | izksŒ e/; fo¦ky;] >ifu;ka | Dilendra Prasad Singh, jamui | [12 empty] | 1 |  |  |  | DEBAR |  | Bhagalpur
278 | SSS-249-1 | Banka | csygj | e/; fo¦ky;] Jhuxj | Rajesh kumar Singh,Jamui | [8 empty] | 1 | [9 empty] | Bhagalpur
279 | SSS-250-1 | Banka | dVksfj;k | e/; fo¦ky;] bukjkoj.k | Dilendra Prasad Singh, jamui | [5 empty] | 1 | [10 empty] | Land not available |  | Bhagalpur
280 | SSS-250-2 | Banka | dVksfj;k | izksŒ e/; fo¦ky;] Nkrkdq:e | Dilendra Prasad Singh, jamui | [10 empty] | 1 | [5 empty] | LETTER FOR RECINED TO C.E(SLOW WORK) |  | Bhagalpur
281 | SSS-251 (A) | Banka | jtkSu | izksŒ e/; fo¦ky;] vyhiqj /kfu;ka | Lalan Kumar | [13 empty] | 1 |  |  |  |  | Bhagalpur
282 | SSS-251 (B) | Banka | jtkSu | e/; fo¦ky;] y'kdjh | Om Enterprises, Bhagalpur | [14 empty] | 1 |  |  |  | Bhagalpur
283 | SSS-252-1 | Banka | QqYyhMwej | e/; fo¦ky;] dksfM+;k bukjkoj.k | M/s Satya Narayan singh, deoghar | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
284 | SSS-252-2 | Banka | QqYyhMwej | izksŒ e/; fo¦ky;] /kkok dU;k | M/s Satya Narayan singh, deoghar | [11 empty] | 1 | [6 empty] | Bhagalpur
285 | SSS-252-3 | Banka | QqYyhMwej | izksŒ e/; fo¦ky;] lkniqj | M/s Satya Narayan singh, deoghar | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Bhagalpur
286 | SSS-252-4 | Banka | QqYyhMwej | e/; fo¦ky;] /kudqfM+;k | M/s Satya Narayan singh, deoghar | [11 empty] | 1 | [6 empty] | Bhagalpur
287 | SSS-253-1 | Banka | vejiqj | izksŒ e/; fo¦ky;] eSuek | M/s Tribhuwan prasad Singh & Co, Jamui | [14 empty] | 1 |  |  |  | Bhagalpur
288 | SSS-253-2 | Banka | vejiqj | xjhciqj mjnq | M/s Tribhuwan prasad Singh & Co, Jamui | [14 empty] | 1 |  |  |  | Bhagalpur
289 | SSS-384 (A) | Banka | pkUnu | mRØfer e/; fo¦ky; Qqygjk | Nathuni Yadav | [13 empty] | 1 |  |  | DEBAR |  | Bhagalpur
290 | SSS-384 (B) | Banka | pkUnu | e/; fo¦ky;] Hkksjk cktkj | Bricks Liner Instrastrucutre | [14 empty] | 1 |  |  |  | Bhagalpur
291 | SSS-385 (A) | Banka | csygj | mRØfer e/; fo¦ky;] Vsaxjk | Bricks Liner Instrastrucutre | [13 empty] | 1 |  |  | DEBAR |  | Bhagalpur
292 | SSS-385 (B) | Banka | csygj | mRØfer e/; fo¦ky;] csyk fctgjk | Arvind Kumar | [13 empty] | 1 |  |  | DEBAR |  | Bhagalpur
293 | SSS-410-1 | Bhagalpur | ihjiSrh | mRØfer e/; fo¦ky;] ckcqiqj | Shyam Sundar Yadav | [12 empty] | 1 | [5 empty] | Bhagalpur
294 | SSS-158 (A) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] lenk gfFk;k | Bricks Liner Infra. | [9 empty] | 1 | [6 empty] | Not start |  | Munger
295 | SSS-158 (B) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] yMqbZ | M/S Tribhuwan Prasad Singh,Jamui | [14 empty] | 1 |  |  |  | Munger
296 | SSS-158 (C) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] dUnuh | Tender Process |  |  |  |  | 1 | [11 empty] | Tender Process. NIT-15 (2016-17) |  | Munger
297 | SSS-158 (D) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] vxzg.k | M/S Tribhuwan Pd. Singh | [14 empty] | 1 |  |  |  | Munger
298 | SSS-159-1 | Munger | laxzkeiqj | e/; fo¦ky;] pUnfu;ka | Rajesh kumar Singh Sikandara,Jamui | [13 empty] | 1 |  |  |  |  | Munger
299 | SSS-160-1 | Munger | rkjkiqj | e/; fo¦ky;] fcgek | Rajendra Kumar | [5 empty] | 1 | [10 empty] | Land Problem. 20 feet Deep land |  | Munger
300 | SSS-160-2 | Munger | rkjkiqj | e/; fo¦ky;] jkeiqj | Rajendra Kumar | [13 empty] | 1 |  |  |  |  | Munger
301 | SSS-160-3 | Munger | rkjkiqj | e/; fo¦ky;] [kqfV;k | Rajendra Kumar | [13 empty] | 1 |  |  |  |  | Munger
302 | SSS-161-1 | Munger | tekyiqj | e/; fo¦ky;] ckspkgh | Puja Kumari | [13 empty] | 1 |  |  |  |  | Munger
303 | SSS-162-1 | Munger | vljxat | e/; fo¦ky;] eklqexat | Rajesh kumar Singh Sikandara, Jamui | [13 empty] | 1 |  |  |  |  | Munger
304 | SSS-163-1 | Munger | VsfV;kcEcj | e/; fo¦ky;] Hkquk | Puja Kumari, Munger | [13 empty] | 1 |  |  |  |  | Munger
305 | SSS-163-2 | Munger | VsfV;kcEcj | e/; fo¦ky;] /kkSjh | Puja Kumari, Munger | [13 empty] | 1 |  |  |  |  | Munger
306 | SSS-164-1 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] djdh | Anil Kumar Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
307 | SSS-164-2 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] csyNh | Anil Kumar Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
308 | SSS-164-3 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] o:.kk | Anil Kumar Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
309 | SSS-165-1 | Shekhpura | psojk | e/; fo¦ky;] Nfr;kjk | Anil Kumar Singh,Sheikhpura | [14 empty] | 1 |  |  |  | Munger
310 | SSS-166-1 | Shekhpura | 'ks[kiqjk | e/; fo¦ky;] cSfj;k ch?kk | Ashok Kumar ,Sheikhpura | [14 empty] | 1 |  |  |  | Munger
311 | SSS-167-1 | Begusarai | [kksnkoUriqqj | mRØfer e/; fo¦ky;] elqjkt | M/S Balram Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
312 | SSS-167-2 | Begusarai | [kksnkoUriqqj | mRØfer e/; fo¦ky;] eq'kgjh | M/S Balram Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
313 | SSS-168-1 | Begusarai | c[kjh | e/; fo¦ky;] c[kjh | M/S BalramKumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
314 | SSS-168-2 | Begusarai | c[kjh | e/; fo¦ky;] pDdjehM] unSy | M/S BalramKumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
315 | SSS-169-1 | Begusarai | cjkSuh | e/; fo¦ky;] fetkZiqj pkWn | Budha infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
316 | SSS-169-2 | Begusarai | cjkSuh | e/; fo¦ky;] Hkouxkek | Budha infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
317 | SSS-169-3 | Begusarai | cjkSuh | mRØfer e/; fo¦ky;] pdh;k iquokZl | Budha infrastructure Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
318 | SSS-169-4 | Begusarai | cjkSuh | mRØfer e/; fo¦ky;] vlqjkjh | Budha infrastructure Pvt. Ltd. | [14 empty] | 1 |  |  |  | Munger
319 | SSS-169-5 | Begusarai | cjkSuh | e/; fo¦ky;] ds'kos | Budha infrastructure Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land not available |  | Munger
320 | SSS-170-1 | Begusarai | cjkSuh | e/; fo¦ky;] iijkSj | M/s Daya Ram singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
321 | SSS-171-1 | Begusarai | csxwljk; | mRØfer e/; fo¦ky;] dqlekSr | Saheb Singh Construction | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
322 | SSS-172-1 | Begusarai | efVgkuh | e/; fo¦ky;] nfj;kiqj | M/S Daya Ram Singh, Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
323 | SSS-172-2 | Begusarai | efVgkuh | e/; fo¦ky;] xksnjxkek | M/S Daya Ram Singh, Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
324 | SSS-173-1 | Begusarai | Hkxokuiqj | e/; fo¦ky;] rktiqj | M/S Brij Deo Singh, Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
325 | SSS-174-1 | Begusarai | lkgsciqj deky | e/; fo¦ky;] lkniqj | M/S Imperial Foundation Pvt.Ltd. Kankarbag | [13 empty] | 1 |  |  |  |  | Munger
326 | SSS-174-2 | Begusarai | lkgsciqj deky | e/; fo¦ky;] jgqvk | M/S Imperial Foundation Pvt.Ltd. Kankarbag | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
327 | SSS-174-3 | Begusarai | lkgsciqj deky | e/; fo¦ky;] jlyiqj | M/S Imperial Foundation Pvt.Ltd. Kankarbag | [5 empty] | 1 | [10 empty] | Land not available |  | Munger
328 | SSS-174-4 | Begusarai | lkgsciqj deky | e/; fo¦ky;] nhgk | M/S Imperial Foundation Pvt.Ltd. Kankarbag | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
329 | SSS-174-5 | Begusarai | lkgsciqj deky | e/; fo¦ky;] j?kqukFkiqj | M/S Imperial Foundation Pvt.Ltd. Kankarbag | [14 empty] | 1 |  |  |  | Munger
330 | SSS-175-1 | Begusarai | MaMkjh | mRØfer e/; fo¦ky;] u;k Vksyk] dY;k.kiqj | Ms. Arpana Construction Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
331 | SSS-175-2 | Begusarai | MaMkjh | e/; fo¦ky;] jktksiqj | Ms. Arpana Construction Begusarai | [14 empty] | 1 |  |  |  | Munger
332 | SSS-175-3 | Begusarai | MaMkjh | e/; fo¦ky;] fllkSuh | Ms. Arpana Construction Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
333 | SSS-176-1 | Begusarai | rs?kM+k | e/; fo¦ky;] vdkgk jkeiqj | M/S Chandra Shekhar Singh & Co.Bihat, Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
334 | SSS-176-2 | Begusarai | rs?kM+k | mRØfer e/; fo¦ky;] vks>k Vksy | M/S Chandra Shekhar Singh & Co.Bihat, Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
335 | SSS-176-3 | Begusarai | rs?kM+k | e/; fo¦ky;] fi<+kSyh | M/S Chandra Shekhar Singh & Co.Bihat, Begusarai | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
336 | SSS-177 (A) | Begusarai | ukodksBh | mRØfer e/; fo¦ky;] pdeqt¶Qj | Ganga Yamuna Cons. | [14 empty] | 1 |  |  |  | Munger
337 | SSS-177 (B) | Begusarai | ukodksBh | dU;k e/; fo¦ky;] igljk | Guddu Kumar | Patna | Bihar |  |  |  | 1 | [10 empty] | Land not available |  | Munger
338 | SSS-178-1 | Begusarai | x<+iqjk | e/; fo¦ky;] eNjkgk] jtkSj | M/Raja Enterprises & Co.,Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
339 | SSS-178-2 | Begusarai | x<+iqjk | mRØfer e/; fo¦ky;] dksfj;ek | M/Raja Enterprises & Co.,Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
340 | SSS-178-3 | Begusarai | x<+iqjk | mRØfer e/; fo¦ky;] çk.kiqj fgUnh | M/Raja Enterprises & Co.,Begusarai | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
341 | SSS-179-1 | Lakhisarai | cM+fg;k | e/; fo¦ky;] izrkiiqj | Ravi Bhushan Singh, Alawaalpur | [5 empty] | 1 | [10 empty] | Not start |  | Munger
342 | SSS-179-2 | Lakhisarai | cM+fg;k | mRØfer e/; fo¦ky;] y{ehiqj] lgtkniqj | Ravi Bhushan Singh, Alawaalpur | [5 empty] | 1 | [10 empty] | Not start |  | Munger
343 | SSS-180-1 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] ?kks?kh cfj;kjiqj | M/S Tribhuwan Prasad Singh, Jamui | [13 empty] | 1 |  |  |  |  | Munger
344 | SSS-180-2 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] uodkMhg mjSu | M/S Tribhuwan Prasad Singh, Jamui | [14 empty] | 1 |  |  |  | Munger
345 | SSS-180-3 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] dtjk | M/S Tribhuwan Prasad Singh, Jamui | [14 empty] | 1 |  |  |  | Munger
346 | SSS-181 (A) | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] fr;kpd | Stanely Engineering | [14 empty] | 1 |  |  |  | Munger
347 | SSS-181 (B) | Lakhisarai | pkuu | e/; fo¦ky;] Hkkanj | Ms. Tribhuwan Pd. Singh | [13 empty] | 1 |  |  |  |  | Munger
348 | SSS-182-1 | Lakhisarai | pkuu | e/; fo¦ky;] cUuw cxhpk | Dilendra Prasad Singh, Jamui | [5 empty] | 1 | [10 empty] | Land not available |  | Munger
349 | SSS-182-2 | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] clqvkpd | Dilendra Prasad Singh, Jamui | [10 empty] | 1 | [7 empty] | Munger
350 | SSS-183-1 | Lakhisarai | y[khljk; | mRØfer e/; fo¦ky;] [kxkSj | Rama Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
351 | SSS-184-1 | Jamaui | [kSjk | e/; fo¦ky;] :ikosy | M/S Satyanarayan Singh, Deoghar | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
352 | SSS-184-2 | Jamaui | [kSjk | e/; fo¦ky;] /kjeiqj | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  |  |  | Munger
353 | SSS-184-3 | Jamaui | [kSjk | mRØfer e/; fo¦ky;] fVfg;kfnukjh | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
354 | SSS-184-4 | Jamaui | [kSjk | e/; fo¦ky;] dSM+kdknks | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
355 | SSS-185-1 | Jamaui | >k>k | e/; fo¦ky;] iSjxkgk | Rajesh Kumar Singh, Jamui | [13 empty] | 1 |  |  |  |  | Munger
356 | SSS-185-2 | Jamaui | >k>k | mRØfer e/; fo¦ky;] lqUnjh VkaM | Rajesh Kumar Singh, Jamui | [13 empty] | 1 |  |  |  |  | Munger
357 | SSS-185-3 | Jamaui | >k>k | e/; fo¦ky;] ps;u | Rajesh Kumar Singh, Jamui | [13 empty] | 1 |  |  |  |  | Munger
358 | SSS-186-1 | Jamaui | cjgV | e/; fo¦ky;] yk[ks; | Sudhir Prasad,Jamui | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
359 | SSS-186-2 | Jamaui | cjgV | e/; fo¦ky;] iaps'ojh | Sudhir Prasad,Jamui | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
360 | SSS-187-1 | Jamaui | fldUnjk | e/; fo¦ky;] lcych?kk | Dilendra Prasad Singh, jamui | [13 empty] | 1 |  |  |  |  | Munger
361 | SSS-187-2 | Jamaui | fldUnjk | e/; fo¦ky;]uodkMhg | Dilendra Prasad Singh, jamui | [13 empty] | 1 |  |  |  |  | Munger
362 | SSS-188-1 | Jamaui | pdkbZ | e/; fo¦ky;] /keukMhg | M/S Satyanarayan Singh, Deoghar | [13 empty] | 1 |  |  |  |  | Munger
363 | SSS-188-2 | Jamaui | pdkbZ | e/; fo¦ky;] flejk | M/S Satyanarayan Singh, Deoghar | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
364 | SSS-188-3 | Jamaui | pdkbZ | e/; fo¦ky;] njok | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
365 | SSS-188-4 | Jamaui | pdkbZ | e/; fo¦ky;] ejgh clcqfV;k | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
366 | SSS-188-5 | Jamaui | pdkbZ | e/; fo¦ky;] ikaMsMhg | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
367 | SSS-188-6 | Jamaui | pdkbZ | e/; fo¦ky;] Bk<+h | M/S Satyanarayan Singh, Deoghar | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
368 | SSS-188-7 | Jamaui | pdkbZ | e/; fo¦ky;] ek/kksiqj | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
369 | SSS-188-8 | Jamaui | pdkbZ | e/; fo¦ky;] flefj;k | M/S Satyanarayan Singh, Deoghar | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
370 | SSS-189-1 | Jamaui | teqbZ | e/; fo¦ky;] izrkiiqj | M/S tribhuwan Prasad Singh,Jamui | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
371 | SSS-190-1 | Jamaui | y{ehiqj | mRØfer e/; fo¦ky;] flaf?k;k | Mukesh Kumar | [14 empty] | 1 |  |  |  | Munger
372 | SSS-191 (A) | Khagaria | csynkSj | e/; fo¦ky;] cksfcy Qqyofj;k | M/S DHANPAT KR JAIN | [9 empty] | 1 | [8 empty] | Munger
373 | SSS-191 (B) | Khagaria | csynkSj | e/; fo¦ky;] ekyh | KUMARI SHWETA BHARTI | [10 empty] | 1 | [7 empty] | Munger
374 | SSS-191 (C) | Khagaria | csynkSj | e/; fo¦ky;] ldjksgj | HARI SHANKAR GAUTAM | [8 empty] | 1 | [9 empty] | Munger
375 | SSS-191 (D) | Khagaria | csynkSj | e/; fo¦ky;] ipkSr | Mahendra Kumar | Khagaria | Bihar | [11 empty] | 1 |  |  |  |  | Munger
376 | SSS-192-1 | Khagaria | ekulh | e/; fo¦ky;] veuh | Krishna Kumar Singh, khagaria | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
377 | SSS-193-1 | Khagaria | pkSFke | e/; fo¦ky;] jksfg;kj | Puja kumari,Munger | [12 empty] | 1 | [5 empty] | Munger
378 | SSS-379-1 | Khagaria | ekulh | e/; fo¦ky; vjs;k | P.N.S Construction | [5 empty] | 1 | [10 empty] | Land not available |  | Munger
379 | SSS-380 (A) | Khagaria | ijoÙkk | e/; fo¦ky; cUnsgjk | Rana Construction, PATNA | [13 empty] | 1 |  |  |  |  | Munger
380 | SSS-380 (B) | Khagaria | ijoÙkk | e/; fo¦ky; dcSyk | Ms Dhanpat Kumar | [14 empty] | 1 |  |  |  | Munger
381 | SSS-380 (C) | Khagaria | ijoÙkk | e/; fo¦ky;] [khjk Mhg | Ms Dhanpat Kumar | [14 empty] | 1 |  |  |  | Munger
382 | SSS-381 (A) | Khagaria | xksxjh | e/; fo¦ky; jkeiqj | Regal Infratrading private limited | [14 empty] | 1 |  |  |  | Munger
383 | SSS-381 (B) | Khagaria | xksxjh | e/; fo¦ky; cM+h iSdkr | Rana Construction | [13 empty] | 1 |  |  |  |  | Munger
384 | SSS-381 (C) | Khagaria | xksxjh | e/; fo¦ky; enkjiqj | Ms Shiv Shakti Construction | [5 empty] | 1 | [10 empty] | Not start. (8 Feet deep land) |  | Munger
385 | SSS-381 (D) | Khagaria | xksxjh | e/; fo¦ky; u'dhiqj | Regal Infratrading Private Limited | [5 empty] | 1 | [10 empty] | Not start |  | Munger
386 | SSS-381 (E) | Khagaria | xksxjh | e/; fo¦ky; nsoBk | MS Dhanpat kumar | [13 empty] | 1 |  |  |  |  | Munger
387 | SSS-382-1 | Khagaria | pkSFke | e/; fo¦ky; /kuNkj cqPpk | Ms Dhanpat Kumar | [13 empty] | 1 |  |  |  |  | Munger
388 | SSS-383-1 | Khagaria | [kxfM+;k | e/; fo¦ky; dkf'keiqj | Ms Dhanpat Kumar | [14 empty] | 1 |  |  |  | Munger
389 | SSS-386-1 | Begusarai | ukodkVh | e/; fo¦ky;] vdgk jfjvkSuk | M/S AASTHA AND SAUMYA CONSTRUCTION, 9570856865 | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
390 | SSS-387-1 | Begusarai | [kksnkoUriqj | mnwZ e/; foZ¦ky;] rq:Yykgiqj | M/S AASTHA AND SAUMYA CONSTRUCTION, 9570856865 | [5 empty] | 1 | [10 empty] | Land problem |  | Munger
391 | SSS-388-1 | Begusarai | NkSMkgh | e/; fo¦ky;] xhjhMhg | Ms R K Construction | [14 empty] | 1 |  |  |  | Munger
392 | SSS-400-1 | Munger | tekyiqj | e/; fo¦ky;] bUnz:[k | Ms Sai Highway Builders Pvt. Ltd. | [14 empty] | 1 |  |  |  | Munger
393 | SSS-401-1 | Munger | eqaxsj lnj | e/; fo¦ky;] pjkSu | Ms Sai Highway Builders Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Munger
394 | SSS-402-1 | Munger | BsVh;k cEcj | e/; fo¦ky;] eksguiqj | Rajesh Kumar | [12 empty] | 1 | [5 empty] | Munger
395 | SSS-403-1 | Munger | /kjgjk | dU;k e/; fo¦ky;] f'kodqaM | Ms Sai Highway Builders Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
396 | SSS-445-1 | Jamaui | teqÃ | e/; fo¦ky;] cqdkj | SUDESH KUMAR AND CO CONST PVT LTD | [14 empty] | 1 |  |  |  | Munger
397 | SSS-445-2 | Jamaui | teqÃ | e/; fo¦ky;] lksuis | SUDESH KUMAR AND CO CONST PVT LTD | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
398 | SSS-445-3 | Jamaui | teqÃ | e/; fo¦ky;] uohuxj | SUDESH KUMAR AND CO CONST PVT LTD | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
399 | SSS-446-1 | Jamaui | cjgV | e/; fo¦ky;] xqxqyMhg | BRAJESH KUMAR SINGH | [13 empty] | 1 |  |  |  |  | Munger
400 | SSS-446-2 | Jamaui | cjgV | mRØfer e/; fo¦ky;] nsopd | BRAJESH KUMAR SINGH | [13 empty] | 1 |  |  |  |  | Munger
401 | SSS-447 (A) | Jamaui | [kSjk | e/; fo¦ky;] pkuuokj | Ashish Ranjan | [5 empty] | 1 | [10 empty] | Land Problem |  | Munger
402 | SSS-447 (B) | Jamaui | [kSjk | e/; fo¦ky;] Á/kkupd | A. K. Construction | Rohtas | Bihar | [8 empty] | 1 | [7 empty] | Munger
403 | SSS-448-1 | Jamaui | lksuks | e/; fo¦ky;] cfV;k | JAY KISHOR SINGH | [7 empty] | 1 | [10 empty] | Munger
404 | SSS-448-2 | Jamaui | lksuks | mRØfer e/; fo¦ky;] jtkSy | JAY KISHOR SINGH | [10 empty] | 1 | [7 empty] | Munger
405 | SSS-449 (A) | Jamaui | >k>k | e/; fo¦ky;] fleqyryk | Lal Rupak Kumar Singh | [11 empty] | 1 | [6 empty] | Munger
406 | SSS-449 (B) | Jamaui | >k>k | e/; fo¦ky;] ckftyk | Ashish Ranjan | [13 empty] | 1 |  |  |  |  | Munger
407 | SSS-449 (C) | Jamaui | >k>k | e/; fo¦ky;] cq/kh[kj | Ashish Ranjan | [12 empty] | 1 | [5 empty] | Munger
408 | SSS-450 (A) | Jamaui | pdkÃ | e/; fo¦ky;] cksub | Nitesh kumar Singh | [10 empty] | 1 | [7 empty] | Munger
409 | SSS-450 (B) | Jamaui | pdkÃ | e/; fo¦ky;] csUnzk | Puja Engicon Company Pvt. Ltd. | Patna |  |  |  |  | 1 | [10 empty] | DISTURBED AREA JCB BURNT |  | Munger
410 | SSS-467-1 | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] dqanj | Pintu Kumar | Lakhisarai | Bihar | [11 empty] | 1 |  |  |  |  | Munger
411 | SSS-468 (A) | Lakhisarai | lw;Zx<+k | e/; fo¦ky;] jlqyiqj | MK Enterprises | [5 empty] | 1 | [10 empty] | Land Problem. (8-10 FEET DEEP LAND) |  | Munger
412 | SSS-468 (B) | Lakhisarai | lw;Zx<+k | mRØfer e/; fo¦ky;] dfueksg | Tender Process |  |  |  |  | 1 | [11 empty] | Tender Process (NIT-15/2016-17) |  | Munger
413 | SSS-469-1 | Shekhpura | 'ks[kksiqj | e/; fo¦ky;] i{kh | MS Dayanand Prasad Sinha and Co | [14 empty] | 1 |  |  |  | Munger
414 | SSS-358-1 | Shekhpura | 'ks[kiqjk | e/; fo¦ky;] iSu | GOPAL KUMAR 9234334864 | [14 empty] | 1 |  | Inaugurated 2016 |  | Munger
415 | SSS-378-1 | Lakhisarai | fiifj;k | mRØfer e/; fo¦ky;] fiifj;k fn;kjk ¼fo¦ky; ds LokfeRo esa 50 fMlfey ijrh Hkwfe gksus ds 'krZ ds lkFk½ | Pintu Kumar | Lakhisarai | Bihar | [11 empty] | 1 |  |  |  |  | Munger
416 | SSS-303-1 | Saharsa | cuek bVgjh | e/; fo¦ky;] ikjlcUuh | M/S ALAM CONSTRUCTION | [8 empty] | 1 | [9 empty] | Kosi
417 | SSS-304-1 | Saharsa | dgjk | e/; fo¦ky;] lqfyaUnkckn | Jiwan Laxmi Construction Pvt Ltd, Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
418 | SSS-305-1 | Saharsa | efg"kh | e/; fo¦ky;] dUnkgk | M/S ALAM CONSTRUCTION | [12 empty] | 1 | [5 empty] | Kosi
419 | SSS-305-2 | Saharsa | efg"kh | e/; fo¦ky;] Fkuokj | M/S ALAM CONSTRUCTION | [12 empty] | 1 | [5 empty] | Kosi
420 | SSS-305-3 | Saharsa | efg"kh | e/; fo¦ky;] rsygj | M/S ALAM CONSTRUCTION | [12 empty] | 1 | [5 empty] | Kosi
421 | SSS-305-4 | Saharsa | efg"kh | e/; fo¦ky;] eaxjkSuh | M/S ALAM CONSTRUCTION | [9 empty] | 1 | [8 empty] | Kosi
422 | SSS-306-1 | Saharsa | flejh | e/; fo¦ky;] osyokjk | Archana Contractors Pvt Ltd, Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
423 | SSS-307-1 | Saharsa | flejh c[fr;kjiqj | e/; fo¦ky;] dFkMqej | Samrat Construction | [5 empty] | 1 | [10 empty] | Land Not Available |  | Kosi
424 | SSS-308-1 | Saharsa | irj?kV | e/; fo¦ky;] fd'kuiqj | M/S ALAM CONSTRUCTION | [13 empty] | 1 |  |  |  |  | Kosi
425 | SSS-308-2 | Saharsa | irj?kV | e/; fo¦ky;] iLrij | M/S ALAM CONSTRUCTION | [13 empty] | 1 |  |  |  |  | Kosi
426 | SSS-309-1 | Saharsa | lksuo"kkZ | e/; fo¦ky;] xksnjke | M/S Alam Construction, Madhepura | [12 empty] | 1 | [5 empty] | Kosi
427 | SSS-309-2 | Saharsa | lksuo"kkZ | e/; fo¦ky;] dksik | M/S Alam Construction, Madhepura | [12 empty] | 1 | [5 empty] | Kosi
428 | SSS-309-3 | Saharsa | lksuo"kkZ | e/; fo¦ky;] [ktqjkgk | M/S Alam Construction, Madhepura | [11 empty] | 1 | [6 empty] | Kosi
429 | SSS-309-4 | Saharsa | lksuo"kkZ | e/; fo¦ky;] vkjlh | M/S Alam Construction, Madhepura | [12 empty] | 1 | [5 empty] | Kosi
430 | SSS-310-1 | Saharsa | lrj dVS;k | e/; fo¦ky;] fcgjk | Ashok Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
431 | SSS-311-1 | Saharsa | ly[kqvk | e/; fo¦ky;] vyuh | M/s Krishna Construction,Saharsa | [14 empty] | 1 |  |  |  | Kosi
432 | SSS-311-2 | Saharsa | ly[kqvk | e/; fo¦ky;] [kkspjnsok | M/s Krishna Construction,Saharsa | [14 empty] | 1 |  |  |  | Kosi
433 | SSS-312-1 | Saharsa | uogêk | dU;k e/; fo¦ky;] dkfleiqj | Bholi Nath Roy | [14 empty] | 1 |  |  |  | Kosi
434 | SSS-313-1 | Supaul | clariqj | e/; fo¦ky; cuSyhiÍh | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  |  |  | Kosi
435 | SSS-313-2 | Supaul | clariqj | e/; fo¦ky;] lenk | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
436 | SSS-313-3 | Supaul | clariqj | e/; fo¦ky;] fueZyh | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
437 | SSS-313-4 | Supaul | clariqj | e/; fo¦ky; <k<k | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  |  |  | Kosi
438 | SSS-313-5 | Supaul | clariqj | e/; fo¦ky; gn;uxj | Satendra Kumar Construction Pvt. Ltd., Patna | [5 empty] | 1 | [10 empty] | Work cancelled as per order no. 28 dt. 14.05.2015 |  | Kosi
439 | SSS-313-6 | Supaul | clariqj | e/; fo¦ky; iVsjok | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  |  |  | Kosi
440 | SSS-313-7 | Supaul | clariqj | e/; fo¦ky;] ijlk mnwZ | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
441 | SSS-313-8 | Supaul | clariqj | e/; fo¦ky;] fo'kuiqj pkS/kjh | Satendra Kumar Construction Pvt. Ltd., Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
442 | SSS-314-1 | Supaul | çrkixat | e/; fo¦ky;] Vsdquk | M/S Sri Krishna Construction.Co., C/Osudhila Swami Sdan,Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
443 | SSS-315 (A) | Supaul | f=os.khxat | e/; fo¦ky;] xksugk | Akash Kumar khaijpura | [13 empty] | 1 |  |  |  |  | Kosi
444 | SSS-315 (B) | Supaul | f=os.khxat | e/; fo¦ky; ijlkgh gkV | Madan Kumar Singh, Supaul/95721030516 | [13 empty] | 1 |  |  |  |  | Kosi
445 | SSS-315 (C) | Supaul | f=os.khxat | e/; fo¦ky;] ik.Ms;iÍh | Akash Kumar Khajpura Post BV | [12 empty] | 1 | [5 empty] | Kosi
446 | SSS-315 (D) | Supaul | f=os.khxat | e/; fo¦ky;] fejtkok | Akash Kumar khaijpura | [13 empty] | 1 |  |  |  |  | Kosi
447 | SSS-315 (E) | Supaul | f=os.khxat | e/; fo¦ky;] ekSu | Koshitech Devloper India Pvt.Ltd | [12 empty] | 1 | [5 empty] | Kosi
448 | SSS-316-1 | Supaul | fd'kuiqj | e/; fo¦ky;] deyngk | Dhiraj Kumar agarwal,Supaul | [14 empty] | 1 |  |  |  | Kosi
449 | SSS-317-1 | Supaul | fiijk | e/; fo¦ky;] clqyh | Madan Kumar Singh,Supaul | [14 empty] | 1 |  | Handover |  | Kosi
450 | SSS-318-1 | Supaul | jk?kksiqj | e/; fo¦ky;] jkeiqjdyk | M/s Durga Pratap Singh, Kidwaipuri, Patna | [5 empty] | 1 | [10 empty] | Land not available |  | Kosi
451 | SSS-318-2 | Supaul | jk?kksiqj | e/; fo¦ky; dkfj;kiÍh nsohiqj | M/s Durga Pratap Singh, Kidwaipuri, Patna | [12 empty] | 1 | [5 empty] | Kosi
452 | SSS-318-3 | Supaul | jk?kksiqj | e/; fo¦ky; gqykl | M/s Durga Pratap Singh, Kidwaipuri, Patna | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
453 | SSS-318-4 | Supaul | jk?kksiqj | e/; fo¦ky; ckSjkgk] fgUnh | M/s Durga Pratap Singh, Kidwaipuri, Patna | [5 empty] | 1 | [10 empty] | Land not available |  | Kosi
454 | SSS-318-5 | Supaul | jk?kksiqj | e/; fo¦ky;] eksfriqj | M/s Durga Pratap Singh, Kidwaipuri, Patna | [13 empty] | 1 |  |  |  |  | Kosi
455 | SSS-318-6 | Supaul | jk?kksiqj | jkeukFk e/; fo¦ky;] xkSliqj | M/s Durga Pratap Singh, Kidwaipuri, Patna | [13 empty] | 1 |  |  |  |  | Kosi
456 | SSS-319-1 | Supaul | ljk;x<+ | e/; fo¦ky;] fiijk[kqnZ | Kailash Prasad ydav,Supaul | [14 empty] | 1 |  |  |  | Kosi
457 | SSS-319-2 | Supaul | ljk;x<+ | e/; fo¦ky;] >Yyk Mqejh | Kailash Prasad ydav,Supaul | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
458 | SSS-320-1 | Supaul | ljk;x<+& HkifV;kgh | e/; fo¦ky;] ykyxat | Dhiraj Kumar agarwal,Supaul | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
459 | SSS-321-1 | Supaul | lqikSy | e/; fo¦ky;] cSjks | Ashok Kumar,Saharsa | [12 empty] | 1 | [5 empty] | Kosi
460 | SSS-321-2 | Supaul | lqikSy | dU;k e/; fo¦ky;] ckM+k | Ashok Kumar,Saharsa | [14 empty] | 1 |  |  |  | Kosi
461 | SSS-321-3 | Supaul | lqikSy | eqjyh euksgj e/; fo¦ky; cjSy | Ashok Kumar,Saharsa | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
462 | SSS-322-1 | Supaul | Nkrkiqj | e/; fo¦ky;] jrulkj | Satendra Kumar Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Kosi
463 | SSS-322-2 | Supaul | Nkrkiqj | e/; fo¦ky;] dVgh | Satendra Kumar Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Kosi
464 | SSS-322-3 | Supaul | Nkrkiqj | e/; fo¦ky;] fxfj/kjiÍh | Satendra Kumar Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Kosi
465 | SSS-322-4 | Supaul | Nkrkiqj | e/; fo¦ky;] egnhiqj | Satendra Kumar Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Kosi
466 | SSS-322-5 | Supaul | Nkrkiqj | e/; fo¦ky;] 'ks[kVksyk y{ehfu;ka | Satendra Kumar Construction Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Deleted School For N.I.T-45 |  | Kosi
467 | SSS-323-1 | Madhepura | dqekj[kaM | e/; fo¦ky;] csykjh | M/S Alam Construction, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
468 | SSS-323-2 | Madhepura | dqekj[kaM | e/; fo¦ky;] j?kqfu;k | M/S Alam Construction, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
469 | SSS-323-3 | Madhepura | dqekj[kaM | e/; fo¦ky; jhrk | M/S Alam Construction, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
470 | SSS-323-4 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] [kWwVgk jtsS | M/S Alam Construction, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
471 | SSS-323-5 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] bljk;u xksB | M/S Alam Construction, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
472 | SSS-323-6 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] lqUnjuxj ¼v0tk0½ | M/S Alam Construction, Madhepura | [12 empty] | 1 | [5 empty] | Kosi
473 | SSS-324-1 | Madhepura | eqjyhxat | e/; fo¦ky; frudksuek | Saliesh Kumar SIngh | [6 empty] | 1 | [11 empty] | Kosi
474 | SSS-324-2 | Madhepura | eqjyhxat | mRØfe.r e/; fo¦ky;] jtuh fefYyd | Saliesh Kumar SIngh | [10 empty] | 1 | [5 empty] | Very Poor work progress |  | Kosi
475 | SSS-325-1 | Madhepura | eqjyhxat | e/; fo¦ky;] jruiÍh] Hksykgh | M/S alam Construction works & Company, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
476 | SSS-325-2 | Madhepura | eqjyhxat | e/; fo¦ky;] thrkiqj | M/S alam Construction works & Company, Madhepura | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
477 | SSS-325-3 | Madhepura | eqjyhxat | e/; fo¦ky;] fnX?kh | M/S alam Construction works & Company, Madhepura | [13 empty] | 1 |  |  |  |  | Kosi
478 | SSS-326 (A) | Madhepura | fcgkjhxat | e/; fo¦ky;] dBkSfr;k | Flexicon Engineers And Planner Private Limited | [9 empty] | 1 | [8 empty] | Kosi
479 | SSS-326 (B) | Madhepura | fcgkjhxat | e/; fo¦ky;] y{ehiqj | Md Ikram Yasin | [12 empty] | 1 | [5 empty] | Kosi
480 | SSS-326 (C) | Madhepura | fcgkjhxat | mRØfer e/; fo¦ky;] jkexat | Madan Kumar Singh,Supaul/95721030516 | [14 empty] | 1 |  | Handover |  | Kosi
481 | SSS-327-1 | Madhepura | flags'oj | e/; fo¦ky;] rjgk MaMkjh | M/S alam Construction works & Company, Madhepura | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
482 | SSS-327-2 | Madhepura | flags'oj | e/; fo¦ky;] lcSyk | M/S alam Construction works & Company, Madhepura | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
483 | SSS-327-3 | Madhepura | flags'oj | mRØfer e/; fo¦ky;] ekuiqj | M/S alam Construction works & Company, Madhepura | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
484 | SSS-327-4 | Madhepura | flags'oj | e/; fo¦ky;] iVksjh | M/S alam Construction works & Company, Madhepura | [14 empty] | 1 |  | Inaugurated 2016 |  | Kosi
485 | SSS-328-1 | Madhepura | mnkfd'kquxat | dchj xaxk e/; fo¦ky;] chM+hj.kiky | Chandan Kumar Singh | [14 empty] | 1 |  |  |  | Kosi
486 | SSS-328-2 | Madhepura | mnkfd'kquxat | e/; fo¦ky;] eatkSjk | Chandan Kumar Singh | [14 empty] | 1 |  |  |  | Kosi
487 | SSS-329-1 | Madhepura | vkyeuxj | e/; fo¦ky;] fo"kiÍh | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [11 empty] | 1 |  |  |  | Kosi
488 | SSS-329-2 | Madhepura | vkyeuxj | e/; fo¦ky;] gfjgjiqj ctjkgk | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [10 empty] | 1 |  |  |  |  | Kosi
489 | SSS-329-3 | Madhepura | vkyeuxj | e/; fo¦ky;] difl;k | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [9 empty] | 1 | [5 empty] | Kosi
490 | SSS-330-1 | Madhepura | XokyikM+k | e/; fo¦ky;] 'kkgiqj | Shailesh Kumar Singh, Madhepura | [10 empty] | 1 | [7 empty] | Kosi
491 | SSS-330-2 | Madhepura | XokyikM+k | e/; fo¦ky;] VsekHksyk | Shailesh Kumar Singh, Madhepura | [6 empty] | 1 | [11 empty] | Kosi
492 | SSS-330-3 | Madhepura | XokyikM+k | e/; fo¦ky;] [kks[klh ckM+k] jkexat | Shailesh Kumar Singh, Madhepura | [12 empty] | 1 | [5 empty] | Kosi
493 | SSS-399-1 | Madhepura | eqjyhxat | e/; fo¦ky;] o``nkou | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED, 9431685933 | [14 empty] | 1 |  |  |  | Kosi
494 | SSS-399-2 | Madhepura | eqjyhxat | e/; fo¦ky;] ijekuUniqj | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED, 9431685933 | [14 empty] | 1 |  |  |  | Kosi
495 | SSS-439-1 | Supaul | lqikSy | e/; fo¦ky;] yksdgk | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9472103786 9199574775 | [10 empty] | 1 | [7 empty] | Kosi
496 | SSS-439-2 | Supaul | lqikSy | ckfydk e/; fo¦ky;] lqikSy | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9472103786 9199574775 | [5 empty] | 1 | [10 empty] | Land not available |  | Kosi
497 | SSS-440-1 | Supaul | fd'kuiqj | e/; fo¦ky;] czgecqyksd nqfc;kgh | DHIRAJ KUMAR AGRAWAL, 9771645678 | [14 empty] | 1 |  |  |  | Kosi
498 | SSS-359-1 | Supaul | fueZyh | e/; fo¦ky;] csyk Vksyk] nkseqgku | TRISHUL CONSTRUCTIONS, 8252940655 | [12 empty] | 1 | [5 empty] | Kosi
499 | SSS-360-1 | Supaul | lqikSy | e/; fo¦ky;] eYguh | Baba Hans Construction Pvt Ltd 9430407767 | [14 empty] | 1 |  |  |  | Kosi
500 | SSS-360-2 | Supaul | lqikSy | e/; fo¦ky;] clfoV~Vh | Baba Hans Construction Pvt Ltd 9430407767 | [13 empty] | 1 |  |  |  |  | Kosi
501 | SSS-361(A) | Supaul | ljk;x<+ | e/; fo¦ky;] cSlk | Adarsh Nirman Construction | [12 empty] | 1 | [5 empty] | Kosi
502 | SSS-361(B) | Supaul | ljk;x<+ | e/; fo¦ky;] eqjyh | Kailsh Prasad Yadav Consruction | [12 empty] | 1 | [5 empty] | Kosi
503 | SSS-362(A) | Supaul | ejkSuk | e/; fo¦ky;] ejkSuk | Ashok Kumar Yadav | [13 empty] | 1 |  |  |  |  | Kosi
504 | SSS-362(B) | Supaul | ejkSuk | e/; fo¦ky;] ljkstk csyk | GULAB DEVI,9472390207 | [13 empty] | 1 |  |  |  |  | Kosi
505 | SSS-363-1 | Supaul | fd'kuiqj | e/; fo¦ky;] rqykiV~Vh | MADHAV CONSTRUCTION | [14 empty] | 1 |  |  |  | Kosi
506 | SSS-73-1 | Purnea | /kenkgk | ukScr yky eŒfoŒ dqdjkSu&2 | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
507 | SSS-73-2 | Purnea | /kenkgk | e/; fo¦ky;] jaxiqjk | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
508 | SSS-73-3 | Purnea | /kenkgk | vkŒ e/; fo¦ky;] uhjiqj | M/S SATYANARAYAN SINGH 9431190410 | [13 empty] | 1 |  |  |  |  | Purnea
509 | SSS-74-1 | Purnea | chŒ dksBh | e/; fo¦ky;] xfgyLFkku | BIRENDRA KUMAR SINGH 9473440405 | [12 empty] | 1 | [5 empty] | Purnea
510 | SSS-74-2 | Purnea | chŒ dksBh | e/; fo¦ky;] fpduh iVjkgk | BIRENDRA KUMAR SINGH 9473440405 | [11 empty] | 1 | [6 empty] | Purnea
511 | SSS-74-3 | Purnea | chŒ dksBh | e/; fo¦ky;] xqykcVksy eYyMhgk | BIRENDRA KUMAR SINGH 9473440405 | [5 empty] | 1 | [10 empty] | Not Start. not included in contractor's aggrement |  | Purnea
512 | SSS-74-4 | Purnea | chŒ dksBh | e/; fo¦ky;] Hkrlkjk | BIRENDRA KUMAR SINGH 9473440405 | [13 empty] | 1 |  |  |  |  | Purnea
513 | SSS-74-5 | Purnea | chŒ dksBh | e/; fo¦ky;] lq[klsuk | BIRENDRA KUMAR SINGH 9473440405 | [9 empty] | 1 | [8 empty] | Purnea
514 | SSS-74-6 | Purnea | chŒ dksBh | e/; fo¦ky;] fuifu;k¡ | BIRENDRA KUMAR SINGH 9473440405 | [7 empty] | 1 | [10 empty] | Purnea
515 | SSS-74-7 | Purnea | chŒ dksBh | e/; fo¦ky;] lglkSy | BIRENDRA KUMAR SINGH 9473440405 | [5 empty] | 1 | [10 empty] | Not Start. Old hut to be demolished. |  | Purnea
516 | SSS-75-1 | Purnea | cueu[kh | e/; fo¦ky;] xaxSyh | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
517 | SSS-75-2 | Purnea | cueu[kh | e/; fo¦ky;] ft;uxaat e/; | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
518 | SSS-75-3 | Purnea | cueu[kh | e/; fo¦ky;] dk>h | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
519 | SSS-75-4 | Purnea | cueu[kh | e/; fo¦ky;] gfjiqjeknh | M/S SATYANARAYAN SINGH 9431190410 | [13 empty] | 1 |  |  | Work stopped due to water lodging |  | Purnea
520 | SSS-75-5 | Purnea | cueu[kh | e/; fo¦ky;] nsoksÙkj | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
521 | SSS-75-6 | Purnea | cueu[kh | e/; fo¦ky;] cksjkgh | M/S SATYANARAYAN SINGH 9431190410 | [14 empty] | 1 |  |  |  | Purnea
522 | SSS-75-7 | Purnea | cueu[kh | e/; fo¦ky;] jkeiqj fryd iwoZ | M/S SATYANARAYAN SINGH 9431190410 | [5 empty] | 1 | [10 empty] | Land not available ( upgradation of school is also cancelled by dist. administration) |  | Purnea
523 | SSS-76-1 | Purnea | iwf.kZ;k¡ iwoZ | e/; fo¦ky;] ykyxat | BIRENDRA KUMAR SINGH 9473440405 | [5 empty] | 1 | [10 empty] | Land litigation |  | Purnea
524 | SSS-77-1 | Purnea | Jhuxj | vkŒ e/; fo¦ky;] glSyh [kqWÎh | Hari Mohan Bishwas Hasanganj Katihar-9955713757 | [13 empty] | 1 |  |  | Debar notice issued to contractor & recommendation to debar sent to HQ vide EE ltr-3476/16(30.11.16) |  | Purnea
525 | SSS-78-1 | Araria | dqlkZdkaVk | mRØfer e/; fo¦ky;] fcduh | MD. Iftakar Alam Jokihat Araria-9431835133 | [14 empty] | 1 |  |  |  | Purnea
526 | SSS-78-2 | Araria | dqlkZdkaVk | mRØfer e/; fo¦ky;] gksfj;k | MD. Iftakar Alam Jokihat Araria-9431835133 | [14 empty] | 1 |  |  |  | Purnea
527 | SSS-79-1 | Araria | fldVh | e/; fo¦ky;] Msfu;k | M/S R.P Construction Rahikatoal Araria-9431412396 | [14 empty] | 1 |  |  |  | Purnea
528 | SSS-80-1 | Araria | Hkjxkek | mRØfer e/; fo¦ky;] fljfl;k dyk | Hari Mohan VishwasHasnganj Katihar-9955713757 | [13 empty] | 1 |  |  |  |  | Purnea
529 | SSS-81 (A) | Araria | iyklh | e/; fo¦ky;] neZxat | Md Iftakhar Alam | [14 empty] | 1 |  |  |  | Purnea
530 | SSS-81 (B) | Araria | iyklh | e/; fo¦ky; Qqyljk | Md Iftakhar Alam | [14 empty] | 1 |  |  |  | Purnea
531 | SSS-81 (C) | Araria | iyklh | e/; fo¦ky;] Mkyk | Suraj Traders | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
532 | SSS-82-1 | Araria | jkuhxat | e/; fo¦ky;] ykyiqj egqvk | M/S R.P Construction Rahikatoal Araria-9431412396 | [14 empty] | 1 |  |  |  | Purnea
533 | SSS-82-2 | Araria | jkuhxat | e/; fo¦ky;] cM+gkjk | M/S R.P Construction Rahikatoal Araria-9431412396 | [14 empty] | 1 |  |  |  | Purnea
534 | SSS-82-3 | Araria | jkuhxat | dU;k e/; fo¦ky;] iksfB;k | M/S R.P Construction Rahikatoal Araria-9431412396 | [13 empty] | 1 |  |  |  |  | Purnea
535 | SSS-84-1 | Araria | jkuhxat | e/; fo¦ky;] ekStgk | Hari Mohan Bishwas Hasanganj Katihar-9955713757 | [13 empty] | 1 |  |  |  |  | Purnea
536 | SSS-84-2 | Araria | jkuhxat | e/; fo¦ky;] e/kqyrk | Hari Mohan Bishwas Hasanganj Katihar-9955713757 | [13 empty] | 1 |  |  |  |  | Purnea
537 | SSS-85-1 | Araria | Qkjfclxat | e/; fo¦ky;] ijokgk gfjtu | M/S R.P Construction Rahikatoal Araria-9431412396 | [13 empty] | 1 |  |  |  |  | Purnea
538 | SSS-85-2 | Araria | Qkjfclxat | e/; fo¦ky;] clxM+k jkeiqj | M/S R.P Construction Rahikatoal Araria-9431412396 | [13 empty] | 1 |  |  |  |  | Purnea
539 | SSS-85-3 | Araria | Qkjfclxat | e/; fo¦ky;] ckjk | M/S R.P Construction Rahikatoal Araria-9431412396 | [14 empty] | 1 |  |  |  | Purnea
540 | SSS-85-4 | Araria | Qkjfclxat | e/; fo¦ky;] HkkxijHkkgk | M/S R.P Construction Rahikatoal Araria-9431412396 | [13 empty] | 1 |  |  |  |  | Purnea
541 | SSS-85-5 | Araria | Qkjfclxat | e/; fo¦ky;] lekSy | M/S R.P Construction Rahikatoal Araria-9431412396 | [13 empty] | 1 |  |  |  |  | Purnea
542 | SSS-86-1 | Araria | tksdhgkV | e/; fo¦ky;] nkseksguk 2 | MD. Iftakar Alam Jokihat Araria-9431835133 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
543 | SSS-87 (A) | Araria | ujirxat | e/; fo¦ky;] lkgscxat | Shailendra Kumar | [13 empty] | 1 |  |  |  |  | Purnea
544 | SSS-87 (B) | Araria | ujirxat | e/; fo¦ky;] MqejcUuk | Shailendra Kumar | [13 empty] | 1 |  |  |  |  | Purnea
545 | SSS-87 (C) | Araria | ujirxat | e/; fo¦ky;] x<+xkek | Shailendra Kumar | [5 empty] | 1 | [10 empty] | Land Dispute |  | Purnea
546 | SSS-87 (D) | Araria | ujirxat | e/; fo¦ky;] Hkokuhiqj | Shailendra Kumar | [13 empty] | 1 |  |  |  |  | Purnea
547 | SSS-88 (A) | Araria | vjfj;k | e/; fo¦ky;] csyokr | AKASH KUMAR | [5 empty] | 1 | [10 empty] | Land enchroched |  | Purnea
548 | SSS-88 (B) | Araria | vjfj;k | e/; fo¦ky;] dqfl;kjxkao | Suraj Traders | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
549 | SSS-88 (C) | Araria | vjfj;k | mRØfer e/; fo¦ky;] frjgqrfcêk | AKASH KUMAR | [5 empty] | 1 | [12 empty] | Purnea
550 | SSS-89-1 | Katihar | leSyh | e/; fo¦ky;] Nksgkj | Ashok Kumar Goushala- Katihar-9431096238 | [5 empty] | 1 | [10 empty] | Land not avialable |  | Purnea
551 | SSS-89-2 | Katihar | leSyh | e/; fo¦ky;] eygfj;k | Ashok Kumar Goushala- Katihar-9431096238 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
552 | SSS-90-1 | Katihar | dqlSyk | e/; fo¦ky;] dVfj;k | BIRENDRA KUMAR SINGH 9473440405 | [13 empty] | 1 |  |  |  |  | Purnea
553 | SSS-90-2 | Katihar | dqlSyk | e/; fo¦ky;] tjykgh | BIRENDRA KUMAR SINGH 9473440405 | [13 empty] | 1 |  |  |  |  | Purnea
554 | SSS-91-1 | Katihar | MaM[kksjk | e/; fo¦ky;] usigk | Pankaj Kumar Singh Gami Tola Katihar, Bihar-9431229327 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
555 | SSS-91-2 | Katihar | MaM[kksjk | e/; fo¦ky;] fVdSyh | Pankaj Kumar Singh Gami Tola Katihar, Bihar-9431229327 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
556 | SSS-92-1 | Kishanganj | Bkdqjxat | mRØfer e/; fo¦ky;] yks/kk | Birendra Kumar Singh | [10 empty] | 1 | [7 empty] | Purnea
557 | SSS-92-2 | Kishanganj | Bkdqjxat | e/; fo¦ky;] csgqynaxh | Birendra Kumar Singh | [9 empty] | 1 | [8 empty] | Purnea
558 | SSS-92-3 | Kishanganj | Bkdqjxat | mRØfer e/; fo¦ky;] iapxkNh | Birendra Kumar Singh | [9 empty] | 1 | [8 empty] | Purnea
559 | SSS-93 (A) | Kishanganj | cgknwjxat | mRØfer e/; fo¦ky;] ykSpk | Bholi Nath Roy | [13 empty] | 1 |  |  | 2nd floor Lintel lvl as per G+2 drawing |  | Purnea
560 | SSS-93 (B) | Kishanganj | cgknwjxat | mRØfer e/; fo¦ky;] eaMyVksyk Mksgj | Binod Yadav | [5 empty] | 1 | [10 empty] | Double Scheme |  | Purnea
561 | SSS-94-1 | Kishanganj | dkspk/kkeu | mRØfer e/; fo¦ky;] ckykuxj | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
562 | SSS-95-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] iuhlky | Sirajur Rahman Churipatti Road Kishanganj Bihar-9470866777 | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
563 | SSS-96-1 | Kishanganj | iksfB;k | e/; fo¦ky;] tkyqpkSd | BIRENDRA KUMAR SINGH 9473440405 | [8 empty] | 1 | [9 empty] | Purnea
564 | SSS-96-2 | Kishanganj | iksfB;k | mRØfer e/; fo¦ky;] lksukiqj | BIRENDRA KUMAR SINGH 9473440405 | [5 empty] | 1 | [10 empty] | Double Scheme |  | Purnea
565 | SSS-96-3 | Kishanganj | iksfB;k | e/; fo¦ky;] csyxkNh ohjiqj | BIRENDRA KUMAR SINGH 9473440405 | [10 empty] | 1 | [7 empty] | Purnea
566 | SSS-97 (A) | Kishanganj | Vs<+kxkN | mRØfer e/; fo¦ky;] vkfnoklh Vksyk Hkksjgk | Tender Process | [5 empty] | 1 | [10 empty] | Double Scheme |  | Purnea
567 | SSS-97 (B) | Kishanganj | Vs<+kxkN | e/; fo¦ky;] Hkkstiqj] cyok | DINESH KUMAR | [12 empty] | 1 | [5 empty] | Purnea
568 | SSS-389-1 | Katihar | dks<+k | e/; fo¦ky; f'ko yky Vksyk pkWih | MS Excellent | [14 empty] | 1 |  |  |  | Purnea
569 | SSS-390-1 | Katihar | Qydk | ckfydk e/; fo¦ky;] iksfB;k | M/S C S Construction | [14 empty] | 1 |  |  |  | Purnea
570 | SSS-404-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] gyeyk | Bholi Nath Ray | [8 empty] | 1 | [9 empty] | Purnea
571 | SSS-405-1 | Kishanganj | dkspk/kkeu | mRØfer e/; fo¦ky;] lkgiqj | BHOLI NATH ROY,7352520025 | [13 empty] | 1 |  |  |  |  | Purnea
572 | SSS-406-1 | Kishanganj | Vs<+kxkN | e/; fo¦ky;] >udh eqlgjh iqohZ | KRISHNA RANJAN KUMAR | [11 empty] | 1 | [6 empty] | Purnea
573 | SSS-407-1 | Kishanganj | iksfFkok | e/; fo¦ky;] Mkeyckjh | MD ANZAR ALAM,9431445928 | [10 empty] | 1 | [7 empty] | Purnea
574 | SSS-408-1 | Kishanganj | cgknqjxat | e/; fo¦ky;] HkkVkckjh | MD ANZAR ALAM,9431445928 | [13 empty] | 1 |  |  |  |  | Purnea
575 | SSS-416 (A) | Purnea | dlck | e/; fo¦ky;] lq/kqosyh | UMAKANT SINGH | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
576 | SSS-416 (B) | Purnea | dlck | e/; fo¦ky;] ft;uxat] xqjgh | MS Shining madhusudan cons. | [5 empty] | 1 | [10 empty] | Land not available |  | Purnea
577 | SSS-416 (C) | Purnea | dlck | e/; fo¦ky;] deyiqj] vejk] ykxu | MS Shining madhusudan cons. | [13 empty] | 1 |  |  |  |  | Purnea
578 | SSS-417-1 | Purnea | tykyx<+ | e/; fo¦ky;] lksjlksuh fctqfy;k | MS Excellent construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Purnea
579 | SSS-418-1 | Purnea | ok;lh | e/; fo¦ky;] e<+ok | UMAKANT SINGH | [14 empty] | 1 |  |  |  | Purnea
580 | SSS-419-1 | Purnea | Mx:vk | e/; fo¦ky;] egyckjh | UMAKANT SINGH | [14 empty] | 1 |  |  |  | Purnea
581 | SSS-420-1 | Purnea | iwf.kZ;k¡ ¼iwohZ½ | e/; fo¦ky;] csyok | UMAKANT SINGH | [12 empty] | 1 | [5 empty] | Purnea
582 | SSS-421-1 | Purnea | Hkokuhiqj | e/; fo¦ky;] lksunhi | Rajesh kumar sipahi tola purnea | [14 empty] | 1 |  |  |  | Purnea
583 | SSS-455-1 | Araria | jkuhxat | mRØfer e/; fo¦ky;] Hkokuhuxj | MS Vdhata Construction | [14 empty] | 1 |  |  |  | Purnea
584 | SSS-456-1 | Araria | tksdhgkV | mRØfer e/; fo¦ky;] ckjk bLrkecjkj | MD ARFIN,9006212706 | [14 empty] | 1 |  |  |  | Purnea
585 | S.S.S-357(A) | Purnea | /kenkgk | e/; fo¦ky;] la>k?kkV | RATNESH KUMAR RATNA,9334271195 | [5 empty] | 1 | [10 empty] | double scheme, cancelled |  | Purnea
586 | S.S.S-357(B) | Purnea | /kenkgk | e/; fo¦ky;] ehjxat | MS ALAM CONSTRUCTION WORKS & COMPANY, 9199574775 | [10 empty] | 1 | [7 empty] | Purnea
587 | S.S.S-357(C) | Purnea | /kenkgk | e/; fo¦ky;] xaxkjke] nexkM+k | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 | [9 empty] | 1 | [8 empty] | Purnea
588 | SSS-35-1 | Sitamarhi | :uh lSniqj | e/; fo¦ky;] egs'kk 1 | Akhilesh Kumar Chaudhary Sitamarhi-9431415700 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut East
589 | SSS-35-2 | Sitamarhi | :uh lSniqj | e/; fo¦ky;] oxkgh | Akhilesh Kumar Chaudhary Sitamarhi-9431415700 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut East
590 | SSS-36 (A) | Sitamarhi | cFkukgk | e/; fo¦ky;] gjcsy | Sharda Construction Patna-9431829462 | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
591 | SSS-36 (B) | Sitamarhi | cFkukgk | e/; fo¦ky;] jukSyh | Sharda Construction Patna-9431829462 | [10 empty] | 1 | [7 empty] | Tirhut East
592 | SSS-36 (C) | Sitamarhi | cFkukgk | e/; fo¦ky;] ;equk cjgh | Manoj Kumar | [14 empty] | 1 |  |  |  | Tirhut East
593 | SSS-36 (D) | Sitamarhi | cFkukgk | e/; fo¦ky;] gjiqj cygk | Sanjay Kumar, Belaganj | [10 empty] | 1 | [5 empty] | excavation |  | Tirhut East
594 | SSS-37-1 | Sitamarhi | cktiÍh | e/; fo¦ky;] clsiqj | Rajesh Kumar Sitamarhi-9931490405 | [14 empty] | 1 |  |  |  | Tirhut East
595 | SSS-38 (A) | Sitamarhi | csylaM | e/; fo¦ky;] Mqejk | Birendra Prasad Yadav | [8 empty] | 1 | [9 empty] | Tirhut East
596 | SSS-38 (B) | Sitamarhi | csylaM | e/; fo¦ky;] nekeh eB | Sadafal cons. Pvt. Ltd. | [10 empty] | 1 | [7 empty] | Tirhut East
597 | SSS-38 (C) | Sitamarhi | csylaM | e/; fo¦ky;] e/kdkSy | Retender | [14 empty] | 1 |  |  |  | Tirhut East
598 | SSS-39-1 | Sitamarhi | ijlkSuh | e/; fo¦ky;] /kuxsj | Amresh Kumar Dumra Sitamarhi-9525120333 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut East
599 | SSS-40 (A) | Sitamarhi | jhxk | e/; fo¦ky;] cqykdhiqj | Saroj Kumar | [13 empty] | 1 |  |  |  |  | Tirhut East
600 | SSS-40 (B) | Sitamarhi | jhxk | e/; fo¦ky;] mljfg;k | M/S Sheel Construction Sheohar | [14 empty] | 1 |  |  |  | Tirhut East
601 | SSS-40 (C) | Sitamarhi | jhxk | e/; fo¦ky;] nks?kjk | M/S Sheel Construction Sheohar Bihar-9430865502 | [14 empty] | 1 |  |  |  | Tirhut East
602 | SSS-40 (D) | Sitamarhi | jhxk | e/; fo¦ky;] ikSlk | Saroj Kumar | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
603 | SSS-41-1 | Sitamarhi | lksuo"kkZ | e/; fo¦ky;] clgh;k fgUnh | Sharda Construction Patna-9431829462 | [14 empty] | 1 |  |  |  | Tirhut East
604 | SSS-41-2 | Sitamarhi | lksuo"kkZ | e/; fo¦ky;] ejik dpkSj | Sharda Construction Patna-9431829462 | [14 empty] | 1 |  |  |  | Tirhut East
605 | SSS-42 (A) | Sitamarhi | lqjlaM | e/; fo¦ky;] dksfj;kgh | M/S Sheel Construction Sheohar Bihar-9473034622 | [5 empty] | 1 | [10 empty] | Not Start. Less Land |  | Tirhut East
606 | SSS-42 (B) | Sitamarhi | lqjlaM | e/; fo¦ky;] c[kjh | M/S Sheel Construction Sheohar Bihar-9473034622 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
607 | SSS-43-1 | Muzaffarpur | canjk | mRØfer e/; fo¦ky;] ?kksljkek dksBh | MS Jayshankar Kumar, Samastipur | [13 empty] | 1 |  |  |  |  | Tirhut East
608 | SSS-43-2 | Muzaffarpur | canjk | e/; fo¦ky;] cuxgh | MS Jayshankar Kumar, Samastipur | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
609 | SSS-43-3 | Muzaffarpur | canjk | e/; fo¦ky;] jruefu;k | MS Jayshankar Kumar, Samastipur | [13 empty] | 1 |  |  |  |  | Tirhut East
610 | SSS-43-4 | Muzaffarpur | canjk | mRØfer e/; fo¦ky;] caxjk | MS Jayshankar Kumar, Samastipur | [14 empty] | 1 |  |  |  | Tirhut East
611 | SSS-44-1 | Muzaffarpur | ckspgkW | e/; fo¦ky;] /kjHkjk | Ashok Kumar Singh Muzaffarpur-8521110001 | [13 empty] | 1 |  |  |  |  | Tirhut East
612 | SSS-45-1 | Muzaffarpur | ckspkgkW | e/; fo¦ky;] okftriqj | Ravi Jalan Patna City-9546109122 | [13 empty] | 1 |  |  |  |  | Tirhut East
613 | SSS-45-2 | Muzaffarpur | ckspkgkW | e/; fo¦ky;] vrgj | Ravi Jalan Patna City-9546109122 | [5 empty] | 1 | [10 empty] | Not started |  | Tirhut East
614 | SSS-46 (A) | Muzaffarpur | dkWVh | e/; fo¦ky;] cjfj;k | Dhanajay Kumar | Muzaffarpur | Bihar |  |  |  | 1 | [10 empty] | Land Dispute |  | Tirhut East
615 | SSS-46 (B) | Muzaffarpur | dkWVh | e/; fo¦ky;] eqLrQkiqj | Madav Construction | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
616 | SSS-46 (C) | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] e/kqcu | Anand Kumar | [13 empty] | 1 |  |  |  |  | Tirhut East
617 | SSS-46 (D) | Muzaffarpur | dkWVh | e/; fo¦ky;] diyiqjk | Sidhu Enterprises | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
618 | SSS-46 (E) | Muzaffarpur | dkWVh | e/; fo¦ky;] ';keiqj Hkkstk | M/S RANA CONSTRUCTION | [14 empty] | 1 |  |  |  | Tirhut East
619 | SSS-47-1 | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] dksfB;kiqj | Maa Tara Construction | [14 empty] | 1 |  | G+2 (SF Roof Level) |  | Tirhut East
620 | SSS-47-2 | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] jruiqjk | Maa Tara Construction | [14 empty] | 1 |  | F .F ROOF SLAB CASTED |  | Tirhut East
621 | SSS-48-1 | Muzaffarpur | dq<+uh | e/; fo¦ky;] caxjk | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
622 | SSS-48-2 | Muzaffarpur | dq<+uh | e/; fo¦ky;] rsfy;k | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
623 | SSS-48-3 | Muzaffarpur | dq<+uh | e/; fo¦ky;] djepUn jkeiqj cyjk | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
624 | SSS-48-4 | Muzaffarpur | dq<+uh | e/; fo¦ky;] Qrsgiqj | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
625 | SSS-48-5 | Muzaffarpur | dq<+uh | e/; fo¦ky;] p<+qvk | M/S Sanjay Construction Mahendru Patna-9431877189 | [13 empty] | 1 |  |  | Flooring , Sanitary in Progress Plaster Done |  | Tirhut East
626 | SSS-48-6 | Muzaffarpur | dq<+uh | e/; fo¦ky;] fd'kquiqj] e/kqcu | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Internal & external Plaster Just Started |  | Tirhut East
627 | SSS-48-7 | Muzaffarpur | dq<+uh | e/; fo¦ky;] vej[k | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Plaster Done Grill , Sanitary In Progress |  | Tirhut East
628 | SSS-48-8 | Muzaffarpur | dq<+uh | e/; fo¦ky;] efjpk | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Plaster , Flooring Done Grill , Sanitary In Progress |  | Tirhut East
629 | SSS-48-9 | Muzaffarpur | dq<+uh | e/; fo¦ky;] flykSV | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
630 | SSS-48-10 | Muzaffarpur | dq<+uh | e/; fo¦ky;] eksfjfuLd mnwZ | M/S Sanjay Construction Mahendru Patna-9431877189 | [14 empty] | 1 |  | Flooring , Putty in Progress Plaster Done |  | Tirhut East
631 | SSS-49-1 | Muzaffarpur | ehukiqj | e/; fo¦ky;] ed'kqniqj | Minni Devi Siwan 9162643061 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
632 | SSS-49-2 | Muzaffarpur | ehukiqj | e/; fo¦ky;] [kfjdk | Minni Devi Siwan 9162643061 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
633 | SSS-49-3 | Muzaffarpur | ehukiqj | e/; fo¦ky;] dksngfj;k | Minni Devi Siwan 9162643061 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
634 | SSS-49-4 | Muzaffarpur | ehukiqj | e/; fo¦ky;] flok;iÍh | Minni Devi Siwan 9162643061 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
635 | SSS-50-1 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] eksjlaMh | Devendra Kumar-Motipur Muzaffarpur-9473156515 | [14 empty] | 1 |  | Pianting electric plumbing Running Flooring Done |  | Tirhut East
636 | SSS-50-2 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] vatukdksV | Devendra Kumar-Motipur Muzaffarpur-9473156515 | [14 empty] | 1 |  | Brickwork above FFLL |  | Tirhut East
637 | SSS-50-3 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] /kqeuxj | Devendra Kumar-Motipur Muzaffarpur-9473156515 | [14 empty] | 1 |  | Pianting electric plumbing GF Flooring Running |  | Tirhut East
638 | SSS-51-1 | Muzaffarpur | eMou | mRØfer e/; fo¦ky;] xolkjk | Ravi Shekhar 8002497100 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut East
639 | SSS-51-2 | Muzaffarpur | eMou | mRØfer e/; fo¦ky;] cFkuk jke | Ravi Shekhar 8002497100 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut East
640 | SSS-52-1 | Muzaffarpur | eqjkSy | e/; fo¦ky;] cyqvk | Deam Eathcon Pvt. Ltd. 9431115629 | [13 empty] | 1 |  |  |  |  | Tirhut East
641 | SSS-52-2 | Muzaffarpur | eqjkSy | e/; fo¦ky;] fVVjk fo'kquiqj | Deam Eathcon Pvt. Ltd. 9431115629 | [13 empty] | 1 |  |  |  |  | Tirhut East
642 | SSS-52-3 | Muzaffarpur | eqjkSy | mRØfer e/; fo¦ky;] eq'kgjk ykSru | Deam Eathcon Pvt. Ltd. 9431115629 | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
643 | SSS-52-4 | Muzaffarpur | eqjkSy | e/; fo¦ky;] fo¦k>kai | Deam Eathcon Pvt. Ltd. 9431115629 | [13 empty] | 1 |  |  |  |  | Tirhut East
644 | SSS-53-1 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] idM+h LekbZy | Deam Eathcon Pvt. Ltd. 9431115629 | [14 empty] | 1 |  |  |  | Tirhut East
645 | SSS-53-2 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] [kcjk | Deam Eathcon Pvt. Ltd. 9431115629 | [5 empty] | 1 | [10 empty] | Not started |  | Tirhut East
646 | SSS-53-3 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] izgykniqj | Deam Eathcon Pvt. Ltd. 9431115629 | [14 empty] | 1 |  |  |  | Tirhut East
647 | SSS-53-4 | Muzaffarpur | eq'kgjh | mRØŒ e/; fo¦ky;] eqlgjh QkeZ | Deam Eathcon Pvt. Ltd. 9431115629 | [5 empty] | 1 | [10 empty] | Not started |  | Tirhut East
648 | SSS-54 (A) | Muzaffarpur | ik: | e/; fo¦ky;] jkepUnziqj | KAMESHWAR PD. SINGH | [14 empty] | 1 |  | Handover |  | Tirhut East
649 | SSS-54 (B) | Muzaffarpur | ik: | e/; fo¦ky;] lygiqj | Kumari Sindhu | [12 empty] | 1 | [5 empty] | Tirhut East
650 | SSS-54 (C) | Muzaffarpur | ik: | e/; fo¦ky;] l[kgjk | M/S Rana Cons. | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
651 | SSS-55-1 | Muzaffarpur | ldjk | e/; fo¦ky;] y{ehiqj | Mahesh Kumar Minapur Muzaffarpur-9931805726 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
652 | SSS-56 (A) | Muzaffarpur | ldjk | mRØfer e/; fo¦ky;] egenkiqj cuokjh | Sitesh Kumar Singh | [12 empty] | 1 | [5 empty] | Tirhut East
653 | SSS-56 (B) | Muzaffarpur | ldjk | e/; fo¦ky;] eFkqjkiqj] xksoZ/kuiqj | GAJENDRA PATEL | [10 empty] | 1 | [7 empty] | Tirhut East
654 | SSS-56 (C) | Muzaffarpur | ldjk | e/; fo¦ky;] xfu;kjh | Sanjay Kumar Jha | [12 empty] | 1 | [5 empty] | Tirhut East
655 | SSS-56 (D) | Muzaffarpur | ldjk | e/; fo¦ky;] eglh | Sitesh Kumar Singh | [13 empty] | 1 |  |  |  |  | Tirhut East
656 | SSS-56 (E) | Muzaffarpur | ldjk | e/; fo¦ky;] flejh | Pramod Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
657 | SSS-56 (F) | Muzaffarpur | ldjk | e/; fo¦ky;] gfjiqj d`".k | Sitesh Kumar Singh | [5 empty] | 1 | [10 empty] | Not Started. Land Problem , Letter Given To DPO |  | Tirhut East
658 | SSS-56 (G) | Muzaffarpur | ldjk | mRØfer e/; fo¦ky;] jfgeiqj jldk mnwZ | Sitesh Kumar Singh | [5 empty] | 1 | [10 empty] | Not Started. Land Problem , Letter Given To DPO |  | Tirhut East
659 | SSS-56 (H) | Muzaffarpur | ldjk | e/; fo¦ky;] ljeLriqj | AMIT KUMAR SINGH | [13 empty] | 1 |  |  |  |  | Tirhut East
660 | SSS-56 (I) | Muzaffarpur | ldjk | e/; fo¦ky;] ipMgh | Gajendra Patel, Vaishali | [14 empty] | 1 |  |  |  | Tirhut East
661 | SSS-57-1 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] oklqnso | Hari Shankar Prasad | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
662 | SSS-57-2 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] fo".kqiqj clSFkk | Hari Shankar Prasad | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut East
663 | SSS-57-3 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] xkSjhxkok | Hari Shankar Prasad | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut East
664 | SSS-57-4 | Muzaffarpur | ljS;k | e/; fo¦ky;] /kqch;kgh jked`".k | Hari Shankar Prasad | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
665 | SSS-58 (A) | Muzaffarpur | vkSjkb | e/; fo¦ky;] vkSjkb fgUnh | M/S Rana Construction | [13 empty] | 1 |  |  |  |  | Tirhut East
666 | SSS-58 (B) | Muzaffarpur | vkSjkb | e/; fo¦ky;] 'kaHkqrk | Maa Tara Construction | [13 empty] | 1 |  |  |  |  | Tirhut East
667 | SSS-58 (C) | Muzaffarpur | vkSjkb | e/; fo¦ky;] HkjFkqvk | M/S Rana Construction | [13 empty] | 1 |  |  | grill fitting |  | Tirhut East
668 | SSS-58 (D) | Muzaffarpur | vkSjkb | e/; fo¦ky;] HknbZ | MADHAV CONSTRUCTION | [10 empty] | 1 | [5 empty] | Work Stop |  | Tirhut East
669 | SSS-58 (E) | Muzaffarpur | vkSjkb | e/; fo¦ky;] veukSj | RAKESH RANJAN | [13 empty] | 1 |  |  |  |  | Tirhut East
670 | SSS-59-1 | Muzaffarpur | xk;?kkV | e/; fo¦ky; cq'kgjk eu | Keshav Kumar Keshri Bihar-7779830772 | [13 empty] | 1 |  |  |  |  | Tirhut East
671 | SSS-62-1 | Vaishali | egqvk | mRØfer e/; fo¦ky;] ijekuaniqj | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  |  |  | Tirhut East
672 | SSS-62-2 | Vaishali | egqvk | mRØfer e/; fo¦ky;] 'kkgiqj pdqEej | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  |  |  | Tirhut East
673 | SSS-62-3 | Vaishali | egqvk | mRØfer e/; fo¦ky;] gjiqj xaxkjke | Prem Pratap Ray 9852833505 | [5 empty] | 1 | [10 empty] | No Land DEO Letter To drop |  | Tirhut East
674 | SSS-62-4 | Vaishali | egqvk | jktdh; e/; fo¦ky;] pdmej | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
675 | SSS-62-5 | Vaishali | egqvk | mRØfer e/; fo¦ky;] idM+h | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  |  |  | Tirhut East
676 | SSS-63-1 | Vaishali | egukj | e/; fo¦ky; etfyliqj | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 | [14 empty] | 1 |  |  |  | Tirhut East
677 | SSS-64-1 | Vaishali | ikrsiqj | e/; fo¦ky;] ckftriqj] drkZj | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
678 | SSS-64-2 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] eksgEeniqj tqEeu | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
679 | SSS-64-3 | Vaishali | ikrsiqj | e/; fo¦ky;] igkM+iqj | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
680 | SSS-64-4 | Vaishali | ikrsiqj | e/; fo¦ky;] cfyxkWo | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
681 | SSS-65-1 | Vaishali | ikrsiqj | e/; fo¦ky;] cyk<+ | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
682 | SSS-65-2 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] ekSng pkrqj | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
683 | SSS-65-3 | Vaishali | ikrsiqj | e/; fo¦ky;] ikrsiqj | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
684 | SSS-65-4 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] iLrkjk | Hitech Construction and Developers Pvt. Ltd. 9470836333 | [13 empty] | 1 |  |  |  |  | Tirhut East
685 | SSS-66-1 | Vaishali | iVs<+h csylj | mRØfer e/; fo¦ky;] csylj gkV | Dilip Kumar Patepur Vaishali-8521072115 | [14 empty] | 1 |  |  |  | Tirhut East
686 | SSS-67-1 | Vaishali | jk?kksiqj | pdflaxkj e/; fo¦ky; | M/S Sanjay Construction Musllahpur Hat Mahendru Patna-9431877189 | [5 empty] | 1 | [10 empty] | Cancled |  | Tirhut East
687 | SSS-67-2 | Vaishali | jk?kksiqj | pkWniqjk e/; fo¦ky; | M/S Sanjay Construction Musllahpur Hat Mahendru Patna-9431877189 | [5 empty] | 1 | [10 empty] | Cancled |  | Tirhut East
688 | SSS-68-1 | Vaishali | jktkikdj | mRØfer e/; fo¦ky;] xkSliqj | Er. A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
689 | SSS-68-2 | Vaishali | jktkikdj | e/; fo¦ky; cu?kkM+k | Er. A.P. Construction Pvt.Ltd. Hajipur Vaishali-9431450146 | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
690 | SSS-69-1 | Vaishali | nsljh | mRØŒ e/; fo¦kŒ] eejstiqj dU;k | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 | [14 empty] | 1 |  |  |  | Tirhut East
691 | SSS-69-2 | Vaishali | nsljh | e/; fo¦ky;] mQjkSy | Binod Kumar Singh Basdeopur Chandal Vaishali-9931272442 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut East
692 | SSS-70-1 | Vaishali | oS'kkyh | e/; fo¦ky;] trdkSyh | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut East
693 | SSS-70-2 | Vaishali | oS'kkyh | e/; fo¦ky;] cjfV;k e>kSyh | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
694 | SSS-70-3 | Vaishali | oS'kkyh | e/; fo¦ky; pdvYgnkn ifjlj | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
695 | SSS-70-4 | Vaishali | oS'kkyh | mRØfer e/; fo¦ky;] gqlSuiqj | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
696 | SSS-70-5 | Vaishali | oS'kkyh | mRØfer e/; fo¦ky;] [ktqvrk | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
697 | SSS-70-6 | Vaishali | oS'kkyh | e/; fo¦ky;] nkmnuxj ifjlj | Satyendra Kumar & Co. Construction Pvt. Ltd. Mob.- 9308003925 | [14 empty] | 1 |  | Brickwork & Plinth Band |  | Tirhut East
698 | SSS-71-1 | Vaishali | tUnkgk | mRØfer e/; fo¦ky;] lksgjFkh | Ravindra Prasad Sharma jorpura Samastipur-9006504477 | [5 empty] | 1 | [10 empty] | Land in Pokhar |  | Tirhut East
699 | SSS-72-1 | Vaishali | ykyxat | mRØfer e/; fo¦ky;] txksMhg gfjtu | Gajendra Patel, Vaishali | [13 empty] | 1 |  |  | Brick work running |  | Tirhut East
700 | SSS-437-1 | Sitamarhi | बाजपट्टी | jktdh; e/; fo¦ky;] fuekgh | BIRENDRA KUMAR SINGH | [5 empty] | 1 | [10 empty] | Land Dispute |  | Tirhut East
701 | SSS-438-1 | Sitamarhi | Mqejk | e/; fo¦ky;] rkjknsoh] jathriqj | MUKESH KUMAR | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut East
702 | SSS-01-1 | East Champaran | pfd;k | mRØfer e/; fo¦ky;] [kSjh teqfu;k | Pristine Engicon Pvt. Ltd., Ranchi | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
703 | SSS-01-2 | East Champaran | pfd;k | mRØfer e/; fo¦ky;] cSfj;k | Pristine Engicon Pvt. Ltd., Ranchi | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
704 | SSS-01-3 | East Champaran | pfd;k | e/; fo¦ky;] jkedj.k idM+h | Pristine Engicon Pvt. Ltd., Ranchi | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
705 | SSS-02-1 | East Champaran | rqjdkSfy;k | e/; fo¦ky;] liêh | Sushil kumar Gayatri Nagar, Motihari-9430494360 | [13 empty] | 1 |  |  |  |  | Tirhut West
706 | SSS-02-2 | East Champaran | rqjdkSfy;k | mŒe/; fo¦kŒ Hkxr Vksyk] eksgCcr Nijk | Sushil kumar Gayatri Nagar, Motihari-9430494360 | [13 empty] | 1 |  |  |  |  | Tirhut West
707 | SSS-03-1 | East Champaran | dksVok | e/; fo¦ky;] jketh Vksyk | Munna Kumar Singh East Champaran Bihar-9097820489 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut West
708 | SSS-03-2 | East Champaran | dksVok | e/; fo¦ky;] iêh] ¼egkRek½ | Munna Kumar Singh East Champaran Bihar-9097820489 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut West
709 | SSS-03-3 | East Champaran | dksVok | mRØfer e/; fo¦ky;] djfj;k tkxhj | Munna Kumar Singh East Champaran Bihar-9097820489 | [14 empty] | 1 | Handover | Inaugurated 2015 |  | Tirhut West
710 | SSS-04-1 | East Champaran | idMh+n;ky | e/; fo¦ky;] jktsiqj] uoknk | Ravi Bhusan Singh, Alawalpur patna-9431083150 | [7 empty] | 1 | [10 empty] | Tirhut West
711 | SSS-04-2 | East Champaran | idMh+n;ky | e/; fo¦ky;] /kukSth | Ravi Bhusan Singh, Alawalpur patna-9431083150 | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
712 | SSS-05-1 | East Champaran | jkex<+ok | e/; fo¦ky;] eqjyk | Virendra Kumar Chaudhari, East Champaran Bihar- | [14 empty] | 1 |  | Handover |  | Tirhut West
713 | SSS-06-1 | East Champaran | gjlhnh | e/; fo¦ky;] mTtSu yksfg;kj | Smt.Radha Devi,East Champaran, Bihar-9471886673 | [13 empty] | 1 |  |  |  |  | Tirhut West
714 | SSS-07-1 | East Champaran | fiijkdksBh | mRØfer e/; fo¦ky;] gfFk;kgh | Sanjay Kumar Jha, East Champaran-9934244750 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
715 | SSS-08-1 | East Champaran | lqxkSyh | mRØfer e/; fo¦ky;] ';keiqj | Munna Kumar Singh -East Champaran-9097820489 | [13 empty] | 1 |  |  |  |  | Tirhut West
716 | SSS-09-1 | East Champaran | esglh | e/; fo¦ky;] e>kSfy;k | Keshav Kumar Keshri East Champaran-7779830772 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
717 | SSS-10-1 | East Champaran | fpjS;k | e/; fo¦ky;] gjkt?kkV | Sanjay Kumar Jha East Chaparan-9934244750 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
718 | SSS-11-1 | East Champaran | eksfrgkjh | mRØfer e/; fo¦ky;] ePNgkW | Keshav Kumar Keshri East Champaran-7779830772 | [14 empty] | 1 |  |  |  | Tirhut West
719 | SSS-12-1 | East Champaran | vjsjkt | e/; fo¦ky;] jeflfj;k¡ | KUNAL KISHOR MISHRA DUMRA KOTWA EAST CHAMPARAN | [13 empty] | 1 |  |  |  |  | Tirhut West
720 | SSS-12-2 | East Champaran | vjsjkt | e/; fo¦ky;] >[kjk | KUNAL KISHOR MISHRA DUMRA KOTWA EAST CHAMPARAN | [13 empty] | 1 |  |  |  |  | Tirhut West
721 | SSS-13-1 | East Champaran | <+kdk | e/; fo¦ky;] rsygkjk dyk | R.S.Construction Telharakala.East Champaran | [13 empty] | 1 |  |  |  |  | Tirhut West
722 | SSS-14-1 | East Champaran | vnkiqj | mRØfer e/; fo¦ky;] cjok | Vijay Kumar Singh Persouni East Champaran-9471296790 | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
723 | SSS-14-2 | East Champaran | vnkiqj | mRØfer e/; fo¦ky;] y{ehiqj | Vijay Kumar Singh Persouni East Champaran-9471296790 | [14 empty] | 1 |  |  |  | Tirhut West
724 | SSS-14-3 | East Champaran | vnkiqj | e/; fo¦ky;] Hkokuhiqj cktkj | Vijay Kumar Singh Persouni East Champaran-9471296790 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
725 | SSS-15-1 | East Champaran | igkjiqj | e/; fo¦ky;] jk;djfj;k | Alok Kumar Sangrampur East Champaran-9631044077 | [13 empty] | 1 |  |  |  |  | Tirhut West
726 | SSS-16-1 | East Champaran | Qsugjk | e/; fo¦ky;] fo'kquiqj clar | Vijay Kumar Singh Persouni, East Champaran-9471296790 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
727 | SSS-16-2 | East Champaran | Qsugjk | e/; fo¦ky; Vsolk | Vijay Kumar Singh Persouni, East Champaran-9471296790 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
728 | SSS-16-3 | East Champaran | Qsugjk | e/; fo¦ky;] ijlkSuh dksBh | Vijay Kumar Singh Persouni, East Champaran-9471296790 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
729 | SSS-17-1 | East Champaran | jDlkSy | e/; fo¦ky;] tksfd;kjh | Vijay Kumar Singh Persouni, East Champaran-9471296790 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
730 | SSS-18-1 | East Champaran | catfj;k | mRØfer e/; fo¦ky; xkSfj;k | DESHBANDHU KUMAR SINGH 7739855654 | [13 empty] | 1 |  |  |  |  | Tirhut West
731 | SSS-18-2 | East Champaran | catfj;k | mRØfer e/; fo¦ky;] vtxjok fgUnh | DESHBANDHU KUMAR SINGH 7739855654 | [5 empty] | 1 | [10 empty] | Not Start. Converted to Group No USSS176 |  | Tirhut West
732 | SSS-19-1 | East Champaran | dY;k.kiqj | e/; fo¦ky;] j?kqukFkiqj | Kiran Devi East Champaran Biha-9006524444 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
733 | SSS-20-1 | West Champaran | cxgk II | e/; fo¦ky;] egqvk | C. S. Construction Mob- 9473290979 | [13 empty] | 1 |  |  |  |  | Tirhut West
734 | SSS-20-2 | West Champaran | cxgk II | e/; fo¦ky;] cksjoy | C. S. Construction Mob- 9473290979 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
735 | SSS-20-3 | West Champaran | cxgk II | mRØfer e/; fo¦ky; csyok p[kuh | C. S. Construction Mob- 9473290979 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
736 | SSS-20-4 | West Champaran | cxgk II | mRØfer e/; fo¦ky;] ukSruok | C. S. Construction Mob- 9473290979 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
737 | SSS-20-5 | West Champaran | cxgk II | e/; fo¦ky;] fl/kko | C. S. Construction Mob- 9473290979 | [13 empty] | 1 |  |  |  |  | Tirhut West
738 | SSS-20-6 | West Champaran | cxgk II | mRØfer e/; fo¦ky;] feJkSSyh | C. S. Construction Mob- 9473290979 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
739 | SSS-20-7 | West Champaran | cxgk II | mRØfer e/; fo¦ky; jeofy;k | C. S. Construction Mob- 9473290979 | [13 empty] | 1 |  |  |  |  | Tirhut West
740 | SSS-20-8 | West Champaran | cxgk II | e/; fo¦ky;] egqvkj | C. S. Construction Mob- 9473290979 | [13 empty] | 1 |  |  |  |  | Tirhut West
741 | SSS-20-9 | West Champaran | cxgk II | mRØfer e/; fo¦ky; ePNjxkoka] | C. S. Construction Mob- 9473290979 | [13 empty] | 1 |  |  |  |  | Tirhut West
742 | SSS-21-1 | West Champaran | jkeuxj | mRØfer e/; fo¦ky; tqM+k idM+h | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
743 | SSS-21-2 | West Champaran | jkeuxj | mRØfer e/; fo¦ky; Mqejh | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
744 | SSS-21-3 | West Champaran | jkeuxj | e/; fo¦ky;] f'koiqj dkWyuh | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
745 | SSS-21-4 | West Champaran | jkeuxj | e/; fo¦ky;] chŒ,eŒlhŒ Qqydksy | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
746 | SSS-21-5 | West Champaran | jkeuxj | e/; fo¦ky;] Hkkoy | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
747 | SSS-21-6 | West Champaran | jkeuxj | e/; fo¦ky;] eqM+sjk | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
748 | SSS-21-7 | West Champaran | jkeuxj | e/; fo¦ky; cM+xks | Sabir Husain West Champaran Bihar-9430023820,9661948918 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
749 | SSS-22-1 | West Champaran | ea>kSfy;k | mRØfer e/; fo¦ky; cSBfu;k | M. K. Enterprises Mob- 9431212686 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
750 | SSS-22-2 | West Champaran | ea>kSfy;k | e/; fo¦ky;] efB;k o`r cSBfu;k | M. K. Enterprises Mob- 9431212686 | [14 empty] | 1 |  |  |  | Tirhut West
751 | SSS-22-3 | West Champaran | ea>kSfy;k | mRØfer e/; fo¦ky;] ijlk ckcw Vksyk | M. K. Enterprises Mob- 9431212686 | [14 empty] | 1 |  |  |  | Tirhut West
752 | SSS-22-4 | West Champaran | ea>kSfy;k | e/; fo¦ky;] lsuqvfj;k | M. K. Enterprises Mob- 9431212686 | [14 empty] | 1 |  |  |  | Tirhut West
753 | SSS-23 (A) | West Champaran | ujdfV;kxat | e/; fo¦ky;] euok ijlh | Anil Kumar Mishra | [14 empty] | 1 |  |  |  | Tirhut West
754 | SSS-23 (B) | West Champaran | ujdfV;kxat | mRØfer e/; fo¦ky;] cuofj;k | Raj Kishore Akela | [14 empty] | 1 |  |  |  | Tirhut West
755 | SSS-23 (C) | West Champaran | ujdfV;kxat | e/; fo¦ky;] jktiqj enku | Sanjay Kumar Jha | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
756 | SSS-23 (D) | West Champaran | ujdfV;kxat | mRØfer e/; fo¦ky; pxkSuk | Dhanajay Kumar | [13 empty] | 1 |  |  |  |  | Tirhut West
757 | SSS-24-1 | West Champaran | fHkrgk | e/; fo¦ky;] fcugh | MS Maa Bindyavashani Construction 9801696390 | [14 empty] | 1 |  |  |  | Tirhut West
758 | SSS-24-2 | West Champaran | fHkrgk | e/; fo¦ky;] [kSjok | MS Maa Bindyavashani Construction 9801696390 | [14 empty] | 1 |  |  |  | Tirhut West
759 | SSS-25 (A) | West Champaran | xkSukgk | e/; fo¦ky;] gkSnk Mqejk | Madhu Anand Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Tirhut West
760 | SSS-25 (B) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] fHkfrgjok | Sanjay Kumar Jha | [12 empty] | 1 | [5 empty] | Tirhut West
761 | SSS-25 (C) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] MjkSy | Madhu Anand Construction Pvt. Ltd. | [12 empty] | 1 | [5 empty] | Tirhut West
762 | SSS-25 (D) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] c[kjh | Abhishek Singh | [14 empty] | 1 |  |  |  | Tirhut West
763 | SSS-25 (E) | West Champaran | xkSukgk | e/; fo¦ky;] /kekSjk | Nagendra Prasad | [14 empty] | 1 |  |  |  | Tirhut West
764 | SSS-26-1 | West Champaran | ;ksxkiÍh | mRØfer e/; fo¦ky;] cklksiÍh | Rajesh Kumar | [14 empty] | 1 |  | Handover |  | Tirhut West
765 | SSS-26-2 | West Champaran | ;ksxkiÍh | mRØfer e/; fo¦ky;] nqf/kvok | Rajesh Kumar | [14 empty] | 1 |  |  |  | Tirhut West
766 | SSS-27-1 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] dksokgk | Shatrughan PrasadBettiah, W. Champaran-9431204259 | [13 empty] | 1 |  |  |  |  | Tirhut West
767 | SSS-27-2 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] ghjk ikdM+ | Shatrughan PrasadBettiah, W. Champaran-9431204259 | [14 empty] | 1 |  |  |  | Tirhut West
768 | SSS-27-3 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] HkjifV;k | Shatrughan PrasadBettiah, W. Champaran-9431204259 | [5 empty] | 1 | [10 empty] | Land Problem |  | Tirhut West
769 | SSS-27-4 | West Champaran | puifV;k | mRØfer e/; fo¦ky; lcs;k dkyk | Shatrughan PrasadBettiah, W. Champaran-9431204259 | [14 empty] | 1 |  |  |  | Tirhut West
770 | SSS-27-5 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] eksgNh lqXxk | Shatrughan PrasadBettiah, W. Champaran-9431204259 | [13 empty] | 1 |  |  |  |  | Tirhut West
771 | SSS-28-1 | West Champaran | cSfj;k | mŒe/; fo¦ky;] r/kokuUniqj y[kuh cktkj | Ravi Bhushan Singh-Patna,Bihar-9431083150 | [10 empty] | 1 | [7 empty] | Tirhut West
772 | SSS-28-2 | West Champaran | cSfj;k | mRØfer e/; fo¦ky; Kkuhth dk VksYkk | Ravi Bhushan Singh-Patna,Bihar-9431083150 | [5 empty] | 1 | [10 empty] | Not Start |  | Tirhut West
773 | SSS-28-3 | West Champaran | cSfj;k | mRØfer e/; fo¦ky; cyqvk jeiqjok | Ravi Bhushan Singh-Patna,Bihar-9431083150 | [5 empty] | 1 | [10 empty] | Land not available |  | Tirhut West
774 | SSS-29-1 | West Champaran | cxgk I | e/; fo¦ky;] pUnzgkW | Brijesh Kumar | [5 empty] | 1 | [10 empty] | Land not available |  | Tirhut West
775 | SSS-30-1 | West Champaran | ukSru | mRØfer e/; fo¦ky; fl;kjgh | Prem Pratap Ray 9852833505 | [13 empty] | 1 |  |  |  |  | Tirhut West
776 | SSS-30-2 | West Champaran | ukSru | vkn'kZ e/; fo¦ky;] eMqvkgkW | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
777 | SSS-30-3 | West Champaran | ukSru | e/; fo¦ky;] Mcfj;k | Prem Pratap Ray 9852833505 | [13 empty] | 1 |  |  |  |  | Tirhut West
778 | SSS-30-4 | West Champaran | ukSru | mRØfer e/; fo¦ky;] f'kojktiqj | Prem Pratap Ray 9852833505 | [7 empty] | 1 | [10 empty] | Tirhut West
779 | SSS-30-5 | West Champaran | ukSru | mRØfer e/; fo¦ky;] y{ehiqj nqcksfy;k | Prem Pratap Ray 9852833505 | [14 empty] | 1 |  | Inaugurated 2016 |  | Tirhut West
780 | SSS-31-1 | West Champaran | csfr;k | e/; fo¦ky;] flaXkkNkij | Sanjay Kumar Mishra West Champaran-9546215798 | [13 empty] | 1 |  |  |  |  | Tirhut West
781 | SSS-31-2 | West Champaran | csfr;k | e/; fo¦ky;] 'ks[kkSuk | Sanjay Kumar Mishra West Champaran-9546215798 | [13 empty] | 1 |  |  |  |  | Tirhut West
782 | SSS-32-1 | West Champaran | fldVk | e/; fo¦ky;] flfjfl;k | Asiana Contract Pvt.Ltd.Gopalganj-9431088485 | [5 empty] | 1 | [10 empty] | Not Start. Convert to SSSM21A |  | Tirhut West
783 | SSS-33-1 | West Champaran | e/kqcuh | e/; fo¦ky;] /kugk | BED BRAT PANDEY VILL-SONKHAR,P.O.+P.S.-RAMNAGAR,DIST.-WEST CHAMPARAN | [8 empty] | 1 | [9 empty] | Tirhut West
784 | SSS-33-2 | West Champaran | e/kqcuh | mRØfer e/; fo¦ky;] rudwgk | BED BRAT PANDEY VILL-SONKHAR,P.O.+P.S.-RAMNAGAR,DIST.-WEST CHAMPARAN | [13 empty] | 1 |  |  |  |  | Tirhut West
785 | SSS-34-1 | West Champaran | ykSfj;k | e/; fo¦ky;] cudVok | Radhey Krishna Construction | [14 empty] | 1 |  | Handover |  | Tirhut West
786 | SSS-60 (A) | Sheohar | rfj;kuh | e/; fo¦ky;] vkSjk | Sheel Construction | [14 empty] | 1 |  | Handover |  | Tirhut West
787 | SSS-60 (B) | Sheohar | rfj;kuh | e/; fo¦ky;] eqlgjh | DIBYESHWAR PRASAD | [13 empty] | 1 |  |  |  |  | Tirhut West
788 | SSS-60 (C) | Sheohar | rfj;kuh | e/; fo¦ky;] NrkSuh | Ramesh Shankar | [13 empty] | 1 |  |  |  |  | Tirhut West
789 | SSS-60 (D) | Sheohar | rfj;kuh | e/; fo¦ky;] exqjkgk | Sadafal Construction | [10 empty] | 1 | [7 empty] | Tirhut West
790 | SSS-61-1 | Sheohar | f'kogj | e/; fo¦ky;] lqanjiqj [kjkSuk | Sushil Kumar Brindavan Sheohar-9905176583 | [11 empty] | 1 | [6 empty] | Tirhut West
791 | SSS-409-1 | Sheohar | f'kogj | e/; fo¦ky; dVljh | Dolphin Contractors And Engineers Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Tirhut West
792 | SSS-411-1 | West Champaran | cxgk &1 | e/; fo¦ky;] cjxk¡o | Ravi Shekhar 8002497100 | [13 empty] | 1 |  |  |  |  | Tirhut West
793 | SSS-412-1 | West Champaran | cxgk &2 | mRØfer e/; fo¦ky;] Hksjhgjh dkWyksuh | RAVI SHEKHAR 8002497100 | [14 empty] | 1 |  |  |  | Tirhut West
794 | SSS-412-2 | West Champaran | cxgk &2 | mRØfer e/; fo¦ky;] ip:[kk | RAVI SHEKHAR 8002497100 | [11 empty] | 1 | [6 empty] | Tirhut West
795 | SSS-413-1 | West Champaran | ujdfV;kxat | e/; fo¦ky;] vtqvk lqxkSyh | RAVI SHEKHAR 8002497100 | [14 empty] | 1 |  |  |  | Tirhut West
796 | SSS-414-1 | West Champaran | ykSfj;k | mRØfer e/; fo¦ky;] ejfg;k | MS RADHEY KRISHNA CONSTRUCTION | [14 empty] | 1 |  |  |  | Tirhut West
797 | SSS-422-1 | East Champaran | jkex<+ok | mRØfer e/; fo¦ky;] f=os.kh | VANSHAJ CONSTRUCTION | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
798 | SSS-423-1 | East Champaran | eksfrgkjh | jktdh; e/; fo¦ky;] dVgk | HARIOM CONSTRUCTION | [5 empty] | 1 | [10 empty] | Land not available |  | Tirhut West
799 | SSS-424-1 | East Champaran | laxzkeiqj | mRØfer e/; fo¦ky;] bUnzxkNh uohu | SANTOSH PRASAD YADAV | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Tirhut West
800 | SSS-425-1 | East Champaran | dksVok | mRØfer e/; fo¦ky;] VdVdkiqj | VARUN KUMAR | [14 empty] | 1 |  |  |  | Tirhut West
801 | SSS-426-1 | East Champaran | e/kqcu | jktdh; e/; fo¦ky;] catfj;k | Mohamad Minhaj Ahmad | [7 empty] | 1 | [8 empty] | Land Not Registered land Reg. in progress |  | Tirhut West
802 | SSS-427-1 | East Champaran | <+kdk | mRØfer e/; fo¦ky;] Qqyofj;k | BHAWANI BUILDCON AND PROJECT PVT LTD | [10 empty] | 1 | [7 empty] | Tirhut West
803 | SSS-427-2 | East Champaran |  | e/; fo¦ky;] ipidM+h | BHAWANI BUILDCON AND PROJECT PVT LTD | [5 empty] | 1 | [10 empty] | Land not available |  | Tirhut West
804 | SSS-428-1 | East Champaran | ?kksM+klkgu | e/; fo¦ky;] iqjufg;k | BHAWANI BUILDCON AND PROJECT PVT LTD | [13 empty] | 1 |  |  |  |  | Tirhut West
805 | SSS-194-1 | Darbhanga | /ku';keiqj | e/; fo¦ky;] ?ku';keiqj | Ajay Kumar Pathak | [12 empty] | 1 | [5 empty] | Darbhanga
806 | SSS-195 (A) | Darbhanga | dq0LFkku | mRØfer e/; fo¦ky;] mljh | DHANAJAY KUMAR | [11 empty] | 1 | [6 empty] | Darbhanga
807 | SSS-195 (B) | Darbhanga | dq0LFkku | e/; fo¦ky;] gjkSyh | HARSH CONCRETE CONSTRUCTION | [10 empty] | 1 | [7 empty] | Darbhanga
808 | SSS-195 (C) | Darbhanga | dq0LFkku | e/; fo¦ky;] vkSjkgh | Amar Nath Jha | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
809 | SSS-195 (D) | Darbhanga | dq0LFkku | e/; fo¦ky;] gfjuxj | Amar Nath Jha | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
810 | SSS-195 (E) | Darbhanga | dq0LFkku | e/; fo¦ky;] ?kksjnkSj | Amar Nath Jha | [13 empty] | 1 |  |  |  |  | Darbhanga
811 | SSS-195 (F) | Darbhanga | dq0LFkku | e/; fo¦ky;] cjxkWo | Kanti Construction | [13 empty] | 1 |  |  |  |  | Darbhanga
812 | SSS-196 (A) | Darbhanga | fcjkSy | e/; fo¦ky;] f'kouxj | Vikash Anand Mahila | [13 empty] | 1 |  |  |  |  | Darbhanga
813 | SSS-196 (B) | Darbhanga | fcjkSy | e/; fo¦ky;] vEckfctqfy;k | Avinash Kumar | [13 empty] | 1 |  |  |  |  | Darbhanga
814 | SSS-196 (C) | Darbhanga | fcjkSy | e/; fo¦ky;] yngks | Avinash Kumar | [13 empty] | 1 |  |  |  |  | Darbhanga
815 | SSS-196 (D) | Darbhanga | fcjkSy | e/; fo¦ky;] lkgks | Avinash Kumar | [13 empty] | 1 |  |  |  |  | Darbhanga
816 | SSS-197-1 | Darbhanga | guqekuuxj | mRØfer e/; fo¦ky;] jkeiqj | Madhav Construction, Darbhanga | [14 empty] | 1 |  |  |  | Darbhanga
817 | SSS-198 (A) | Madhubani | ?kks?kjMhgk | e/; fo¦ky;] fpduk | Ajit Kumar | [14 empty] | 1 |  |  |  | Darbhanga
818 | SSS-198 (B) | Madhubani | ?kks?kjMhgk | mRØfer e/; fo¦ky;] dsoVuk | Ajit Kumar | [14 empty] | 1 |  |  |  | Darbhanga
819 | SSS-198 (C) | Madhubani | ?kks?kjMhgk | mRØefr e/; fo¦ky;] clqvkjk | Rajesh Kumar | [5 empty] | 1 | [10 empty] | stop by director education |  | Darbhanga
820 | SSS-199-1 | Madhubani | [kqVkSuk | e/; fo¦ky;] ugjh | Kailash Prasad Yadav Constructions Pvt. Ltd., SUPAUL | [5 empty] | 1 | [10 empty] | Land Dispute |  | Darbhanga
821 | SSS-199-2 | Madhubani | [kqVkSuk | e/; fo¦ky;] va/kkjou | Kailash Prasad Yadav Constructions Pvt. Ltd., SUPAUL | [7 empty] | 1 | [8 empty] | stop by director education |  | Darbhanga
822 | SSS-199-3 | Madhubani | [kqVkSuk | e/; fo¦ky;] fldfV;kgh | Kailash Prasad Yadav Constructions Pvt. Ltd., SUPAUL | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
823 | SSS-200 (A) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] dqlekj | Ajay Kumar Mandal | [14 empty] | 1 |  |  |  | Darbhanga
824 | SSS-200 (B) | Madhubani | [ktkSyh | e/; fo¦ky;] dlek ejkj | Rajesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
825 | SSS-200 (C) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] Nijk<+h | Ajay Kumar Mandal | [14 empty] | 1 |  |  |  | Darbhanga
826 | SSS-200 (D) | Madhubani | [ktkSyh | e/; fo¦ky;] jlhniqj | Ms Dayaram Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
827 | SSS-200 (E) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] bujok iwjc | Ms Dayaram Singh | [14 empty] | 1 |  |  |  | Darbhanga
828 | SSS-201-1 | Madhubani | >a>kjiqj | e/; fo¦ky;] flejk | Kailash Prasad Yadav, Supaul | [13 empty] | 1 |  |  |  |  | Darbhanga
829 | SSS-201-2 | Madhubani | >a>kjiqj | e/; fo¦ky;] flM+[kfj;k | Kailash Prasad Yadav, Supaul | [13 empty] | 1 |  |  |  |  | Darbhanga
830 | SSS-201-3 | Madhubani | >a>kjiqj | e/; fo¦ky;] vM+fj;k laxzke | Kailash Prasad Yadav, Supaul | [13 empty] | 1 |  |  |  |  | Darbhanga
831 | SSS-202-1 | Madhubani | ckcwcjgh | e/; fo¦ky;] dqYgfM+;k | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [10 empty] | 1 |  |  |  |  | Darbhanga
832 | SSS-202-2 | Madhubani | ckcwcjgh | e/; fo¦ky;] fodze'ksj | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [10 empty] | 1 |  |  |  |  | Darbhanga
833 | SSS-202-3 | Madhubani | ckcwcjgh | mRØfer e/; fo¦ky;] cyku'ksjiqjc | Avaneesh Enterprises Mob. - 9473282030 | Ghaziabad | UP | 9473282030 | [10 empty] | 1 |  |  |  |  | Darbhanga
834 | SSS-203 (A) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] dkSvkgk | Rohan Constuction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
835 | SSS-203 (B) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] pUnu dlsjk | Rajesh Kumar | [14 empty] | 1 |  |  |  | Darbhanga
836 | SSS-203 (C) | Madhubani | cklksiÍh | e/; fo¦ky;] xkSluxj | Ms Dayaram Singh | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
837 | SSS-203 (D) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] egFkkSaj | Madhav Construction, Darbhanga | [10 empty] | 1 | [7 empty] | Darbhanga
838 | SSS-203 (E) | Madhubani | cklksiÍh | e/; fo¦ky;] ?kksM+cadh | Rajesh Kumar | [14 empty] | 1 |  |  |  | Darbhanga
839 | SSS-204-1 | Madhubani | csuhiêh | e/; fo¦ky;] tjSy | Subodh kumar , Madhubani | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
840 | SSS-205 (A) | Madhubani | e/kokiqj | e/; fo¦ky;] iks[kjkSuh | Keshav Kumar | [10 empty] | 1 | [7 empty] | Darbhanga
841 | SSS-205 (B) | Madhubani | e/kokiqj | e/; fo¦ky;] fcgkjh | Rohan Constuction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Darbhanga
842 | SSS-205 (C) | Madhubani | e/kokiqj | mRØfer e/; fo¦ky;] vkSjk | Subodh kumar , Madhubani | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
843 | SSS-205 (D) | Madhubani | e/kokiqj | mRØfer e/; fo¦ky;] dsjck | A. B. Buildicon | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
844 | SSS-206 (A) | Madhubani | e/ksiqj | mRØfer e/; fo¦ky;] cdqvk | Beena Construction | Patna | Bihar | [8 empty] | 1 | [7 empty] | Darbhanga
845 | SSS-206 (B) | Madhubani | e/ksiqj | e/; fo¦ky;] }ky[k | Sharweshwar Kr. Ojha | [14 empty] | 1 |  |  |  | Darbhanga
846 | SSS-206 (C) | Madhubani | e/ksiqj | e/; fo¦ky;] Vsaxjkgk | Beena Construction Co | [14 empty] | 1 |  |  |  | Darbhanga
847 | SSS-206 (D) | Madhubani | e/ksiqj | mRØfer e/; fo¦ky;] ijcyiqj | Sharweshwar Kumar Ojha | [13 empty] | 1 |  |  |  |  | Darbhanga
848 | SSS-207-1 | Madhubani | gjyk[kh | mRØfer e/; fo¦ky;] jkeiqj | M/S Subodh kumar Singh, Saran | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
849 | SSS-208-1 | Madhubani | iaMkSy | e/; fo¦ky;] HkkSj | Rajesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
850 | SSS-208-2 | Madhubani | iaMkSy | e/; fo¦ky;] uogFk | Rajesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
851 | SSS-208-3 | Madhubani | iaMkSy | e/; fo¦ky;] Hkokuhiqj | Rajesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
852 | SSS-209 (A) | Madhubani | jfgdk | mRØfer e/; fo¦ky;] ekM+j | Bimalesh Kumar Construction Pvt. Ltd. | [14 empty] | 1 |  |  |  | Darbhanga
853 | SSS-209 (B) | Madhubani | jfgdk | e/; fo¦ky;] cfy;k | Bablu Kumar Singh, Patna | [14 empty] | 1 |  |  |  | Darbhanga
854 | SSS-209 (C) | Madhubani | jfgdk | e/; fo¦ky;] btjk | Amar Nath Jha | Darbhanga | Bihar | [10 empty] | 1 | [5 empty] | Darbhanga
855 | SSS-209 (D) | Madhubani | jfgdk | mRØfer e/; fo¦ky;] uhek | OM SHRI CONSTRUCTION | [13 empty] | 1 |  |  |  |  | Darbhanga
856 | SSS-210 (A) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] jgh iwjc | Bhawani Shankar Cons. | [14 empty] | 1 |  |  |  | Darbhanga
857 | SSS-210 (B) | Madhubani | jktuxj | e/; fo¦ky;] lqxkSuk iks[kj v0tk0 | JAI HIND BUILDCON INDIA PVT. LTD. | [12 empty] | 1 | [5 empty] | Darbhanga
858 | SSS-210 (C) | Madhubani | jktuxj | e/; fo¦ky;] flejh | Jai Hind Construction | [5 empty] | 1 | [10 empty] | Insufficient Land. (Required land 85'x55' avlaible land24'x18') |  | Darbhanga
859 | SSS-210 (D) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] cM+gkjk | Jai Hind Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
860 | SSS-210 (E) | Madhubani | jktuxj | e/; fo¦ky;] tgjeksgjk | Rajesh Kumar | [14 empty] | 1 |  |  |  | Darbhanga
861 | SSS-210 (F) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] jk/kksiqj | Rajesh Kumar | [14 empty] | 1 |  |  |  | Darbhanga
862 | SSS-211 (A) | Madhubani | Qqyijkl | e/; fo¦ky;] vekStk | Kiraye Baba Cons | [14 empty] | 1 |  |  |  | Darbhanga
863 | SSS-211 (B) | Madhubani | Qqyijkl | e/; fo¦ky;] egFkkSj [kqnZ | Manish Kumar | [12 empty] | 1 | [5 empty] | Darbhanga
864 | SSS-211 (C) | Madhubani | Qqyijkl | e/; fo¦ky;] fltkSfy;k] xksB | Bhawani Shankar Cons. | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
865 | SSS-212-1 | Madhubani | t;uxj | e/; fo¦ky;] dqok<+ | Rajesh Kumar | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
866 | SSS-213-1 | Madhubani | va/kjkBk<+h | e/; fo¦ky;] enuiêh | Kailash Prasad Yadav Constructions Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Darbhanga
867 | SSS-214 (A) | Madhubani | ykSdgh | e/; fo¦ky;] HkjQksM+h | Regal Construcion | [11 empty] | 1 | [6 empty] | Darbhanga
868 | SSS-214 (B) | Madhubani | ykSdgh | e/; fo¦ky;] ujsUnziqj | AJAY KUMAR MANDAL | [13 empty] | 1 |  |  |  |  | Darbhanga
869 | SSS-214 (C) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] dfj;kSr | RAJESH KUMAR | [14 empty] | 1 |  |  |  | Darbhanga
870 | SSS-214 (D) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] ujgh | RAGAL INFRATRADING PVT. LTD. | [10 empty] | 1 | [7 empty] | Darbhanga
871 | SSS-214 (E) | Madhubani | ykSdgh | e/; fo¦ky;] csygh dpujok | AJAY KUMAR MANDAL | [13 empty] | 1 |  |  |  |  | Darbhanga
872 | SSS-214 (F) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] dqjhou | Ajeet Kumar | [13 empty] | 1 |  |  |  |  | Darbhanga
873 | SSS-214 (G) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] Fk:vkjh | JUGNOO KUMAR | [14 empty] | 1 |  |  |  | Darbhanga
874 | SSS-215 (A) | Madhubani | ynfu;k¡ | e/; fo¦ky;] ,dgjh | ANNAPURNA CONSTRUCTION | [12 empty] | 1 | [5 empty] | Darbhanga
875 | SSS-215 (B) | Madhubani | ynfu;k¡ | mRØfer e/; fo¦ky;] Hkxorhiqj | ANNAPURNA CONSTRUCTION | [10 empty] | 1 | [7 empty] | Darbhanga
876 | SSS-215 (C) | Madhubani | ynfu;k¡ | e/; fo¦ky;] dqej[kr | ANNAPURNA CONSTRUCTION | [11 empty] | 1 | [6 empty] | Darbhanga
877 | SSS-215 (D) | Madhubani | ynfu;k¡ | e/; fo¦ky;] fla/ki ijlkgh | ANNAPURNA CONSTRUCTION | [13 empty] | 1 |  |  |  |  | Darbhanga
878 | SSS-216-1 | Samastipur | [kkuiqj | mRØfer e/; fo¦ky;] elhuk | Ray & Raj engineering Pvt.Ltd, Samastipur | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
879 | SSS-216-2 | Samastipur | [kkuiqj | mRØfer e/; fo¦ky;] cFkukgk | Ray & Raj engineering Pvt.Ltd, Samastipur | [5 empty] | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET |  | Darbhanga
880 | SSS-216-3 | Samastipur | [kkuiqj | e/; fo¦ky;] Hkkuiqj | Ray & Raj engineering Pvt.Ltd, Samastipur | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
881 | SSS-217-1 | Samastipur | dY;k.kiqj | mRØfer e/; fo¦ky;] /kksyh;kgh | Anil Kumar, Vaishali | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
882 | SSS-218-1 | Samastipur | eksjok | e/; fo¦ky; /keZiqj cans | Maruti Enterprises,Hajipur | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
883 | SSS-219-1 | Samastipur | f'kokthuxj | mRØfer e/; fo¦ky;] tUnkgk | Maruti Enterprises,Hajipur | [13 empty] | 1 |  |  | Inaugurated 2016 |  | Darbhanga
884 | SSS-220-1 | Samastipur | flaf?k;k | mRØfer e/; fo¦ky;] ijgV | Prakash Kumar, Muzaffarpur | [13 empty] | 1 |  |  |  |  | Darbhanga
885 | SSS-220-2 | Samastipur | flaf?k;k | mRØfer e/; fo¦ky;] uhjiqj Hkjfj;k | Prakash Kumar, Muzaffarpur | [13 empty] | 1 |  |  |  |  | Darbhanga
886 | SSS-221-1 | Samastipur | fo¦kifruxj | vkn'kZ jktdh; e/; fo¦ky;] dkaWpk | Vinod Kumar Singh, Samastipur | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
887 | SSS-221-2 | Samastipur | fo¦kifruxj | mRØfer e/; fo¦ky;] lksBxkek | Vinod Kumar Singh, Samastipur | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
888 | SSS-222-1 | Samastipur | foHkqrhiqj | e/; fo¦ky;] dY;k.kiqj | Chandra Prakash, 305, Patna | [5 empty] | 1 | [10 empty] | LOW LAND MORE THAN 10 FEET DEEP IN HALF PORTION AND ENCROCHMENT IN HALF PORTION |  | Darbhanga
889 | SSS-223-1 | Samastipur | gluiqj | mRØfer e/; fo¦ky;] nso?kk | Bablu Kumar Singh, Patna | [13 empty] | 1 |  |  |  |  | Darbhanga
890 | SSS-223-2 | Samastipur | gluiqj | mRØfer e/; fo¦ky;] gluiqj | Bablu Kumar Singh, Patna | [13 empty] | 1 |  |  |  |  | Darbhanga
891 | SSS-224-1 | Samastipur | jksljk | mRØfer e/; fo¦ky;] xksfoUniqj | Smt. Rita Devi, Hanuman Nagar | [13 empty] | 1 |  |  |  |  | Darbhanga
892 | SSS-225 (A) | Samastipur | jksljk | mRØfer e/; fo¦ky;] egqyh | Rita Devi | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
893 | SSS-225 (B) | Samastipur | jksljk | e/; fo¦ky;] iapxkek | Rita Devi | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
894 | SSS-225 (C) | Samastipur | jksljk | mRØfer e/; fo¦ky;] HkVksVj | Ray and Raj Cons. Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Darbhanga
895 | SSS-225 (D) | Samastipur | jksljk | mRØfer e/; fo¦ky;] ihV/kknksHkh | Rita Devi | [13 empty] | 1 |  |  |  |  | Darbhanga
896 | SSS-226-1 | Samastipur | leLrhiqj | e/; fo¦ky;] 'kaHkqiêh | Sudhakant enterprises Pvt. Ltd. Samastipur | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
897 | SSS-226-2 | Samastipur | leLrhiqj | mRØfer e/; fo¦ky;] ckftriqj | Sudhakant enterprises Pvt. Ltd. Samastipur | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
898 | SSS-226-3 | Samastipur | leLrhiqj | e/; fo¦ky; /kwjy[k | Sudhakant enterprises Pvt. Ltd. Samastipur | [5 empty] | 1 | [10 empty] | Land Dispute local |  | Darbhanga
899 | SSS-226-4 | Samastipur | leLrhiqj | mRØfer e/; fo¦ky;] flykSV | Sudhakant enterprises Pvt. Ltd. Samastipur | [5 empty] | 1 | [10 empty] | Land Dispute local |  | Darbhanga
900 | SSS-227-1 | Samastipur | ljk;jatu | mRØfer e/; fo¦ky;] jlyiqj | Vinod kumar Singh, Samastipur | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
901 | SSS-227-2 | Samastipur | ljk;jatu | jktdh; e/; fo¦ky;] vf[r;kjiqj | Vinod kumar Singh, Samastipur | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
902 | SSS-227-3 | Samastipur | ljk;jatu | mRØfer e/; fo¦ky;] ukSvkpd | Vinod kumar Singh, Samastipur | [14 empty] | 1 |  | Inaugurated 2015 |  | Darbhanga
903 | SSS-228-1 | Samastipur | mft;kjiqj | mRØfer e/; fo¦ky;] ijksfj;k | Arvind Kumar Singh, Samastipur | [14 empty] | 1 |  |  |  | Darbhanga
904 | SSS-229-1 | Samastipur | okfj"kuxj | mRØfer e/; fo¦ky;] gtiqjok | Satyendra Kumar Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
905 | SSS-355-1 | Madhubani | y[kukSj | e/; fo¦ky;] nhi | MAA VASUNDHARA CONSTRUCTION, 9006650591 | [13 empty] | 1 |  |  |  |  | Darbhanga
906 | SSS-398-1 | Madhubani | Qqyijkl | e/; fo¦ky;] lqfj;kgh | DADIALA ENTERPRISES,9835998444 | [12 empty] | 1 | [5 empty] | Darbhanga
907 | SSS-432-1 | Samastipur | ljk;jatu | e/; fo¦ky;] fe;kjh | SUDHAKANT ENTERPRISES PVT LTD, 9431208455 | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
908 | SSS-432-2 | Samastipur | ljk;jatu | e/; fo¦ky;] eqlkiqj | SUDHAKANT ENTERPRISES PVT LTD, 9431208455 | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
909 | SSS-433-1 | Samastipur | fo¦kifruxj | e/; fo¦ky;] 'ksjiqj | RENU DEVI, 8540807915 | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
910 | SSS-434-1 | Samastipur | uks[kk | e/; fo¦ky;] xqukÃ] clgh | Vipin Kumar Sahni, 9931468694 | [14 empty] | 1 |  | Inaugurated 2016 |  | Darbhanga
911 | SSS-435 (A) | Samastipur | foHkqfriqj | jktdh; e/; fo¦ky;] csylaMh] rkjk | Sudhakant Enterprises | [14 empty] | 1 |  |  |  | Darbhanga
912 | SSS-435 (B) | Samastipur | foHkqfriqj | e/; fo¦ky;] [kEgkj | Sudhakant Enterprises | [14 empty] | 1 |  |  |  | Darbhanga
913 | SSS-435 (C) | Samastipur | foHkqfriqj | jktdh; e/; fo¦ky;] ekukjk; Vksyk | Sudhakant Enterprises | [14 empty] | 1 |  |  |  | Darbhanga
914 | SSS-436-1 | Samastipur | nyflag ljk; | jktdh; e/; fo¦ky;] dejkm | Sudhakant Enterprises | [13 empty] | 1 |  |  |  |  | Darbhanga
915 | SSS-441-1 | Darbhanga | e.khxkNh | mRØfer e/; fo¦ky;] VVqvkj | SANJAY KUMAR, 8521954601 | [14 empty] | 1 |  |  |  | Darbhanga
916 | SSS-442-1 | Darbhanga | fcjkSy | mRØfer e/; fo¦ky;] fcjkSy vdcjiqj | CITY CREATION, 9386742763 | [14 empty] | 1 |  |  |  | Darbhanga
917 | SSS-442-2 | Darbhanga | fcjkSy | mRØfer e/; fo¦ky;] lksuiqj i?kkjh | CITY CREATION, 9386742763 | [13 empty] | 1 |  |  |  |  | Darbhanga
918 | SSS-443-1 | Darbhanga | ?ku';keiqj | mRØfer e/; fo¦ky;] t;nsoiV~~Vh | CITY CREATION, 9386742763 | [14 empty] | 1 |  |  |  | Darbhanga
919 | SSS-444-1 | Darbhanga | tkys | e/; fo¦ky;] eqjSBk | SANJAY KUMAR, 8521954601 | [13 empty] | 1 |  |  |  |  | Darbhanga
920 | SSS-331-1 | Saran | tykyiqj | e/; fo¦ky;] dksBs;kW | Ms Jagdamba buildcon Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
921 | SSS-331-2 | Saran | tykyiqj | e/; fo¦ky;] vuoy | Ms Jagdamba Buildcon Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
922 | SSS-332-1 | Saran | Nijk lnj | e/; fo¦ky;] clk<+h | Shiv Shankar Singh Construction Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Saran
923 | SSS-332-2 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] me/kk | Shiv Shankar Singh Construction Pvt. Ltd. | [13 empty] | 1 |  |  |  |  | Saran
924 | SSS-332-3 | Saran | Nijk lnj | dU;k e/; fo¦ky;] 'ksjiqj | Shiv Shankar Singh Construction Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Problem; 15' Depth. |  | Saran
925 | SSS-332-4 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] mn;iqjk | Shiv Shankar Singh Construction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
926 | SSS-332-5 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] cyou Vksyk | Shiv Shankar Singh Construction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
927 | SSS-333-1 | Saran | rjS;k | e/; fo¦ky;] gjiqj Qfjnu | Bajrangi Singh,chapra | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
928 | SSS-333-2 | Saran | rjS;k | e/; fo¦ky;] ljS;k clar | Bajrangi Singh,chapra | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
929 | SSS-334-1 | Saran | ,dek | mRØfer e/; fo¦ky;] xkSliqj | Shivasati Cons truction pvt ltd. Patliputra colony patna | [10 empty] | 1 | [7 empty] | Saran
930 | SSS-334-2 | Saran | ,dek | mRØfer e/; fo¦ky;] ukSru | Shivasati Cons truction pvt ltd. Patliputra colony patna | [5 empty] | 1 | [10 empty] | Land Problem |  | Saran
931 | SSS-335-1 | Saran | cfu;kiqj | mRØfer e/; fo¦ky;] djgh | Satrughan singh | [13 empty] | 1 |  |  |  |  | Saran
932 | SSS-335-2 | Saran | cfu;kiqj | mRØfer e/; fo¦ky;] fiiM+k | Satrughan singh | [12 empty] | 1 | [5 empty] | Saran
933 | SSS-336-1 | Saran | blqvkiqj | e/; fo¦ky;] fllokW | Sethi Construction, Chapra | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
934 | SSS-337-1 | Saran | ijlk | e/; fo¦ky;] HksYnh | Gaurav Construction, Muzaffarpur | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
935 | SSS-338-1 | Saran | e<+kSjk | e/; fo¦ky;] eqckjdiqj | Jitendra Kumar singh Gosi Amnour,Saran | [10 empty] | 1 | [7 empty] | Saran
936 | SSS-339-1 | Saran | Eklj[k | e/; fo¦ky;] xaMkeu | Er. A p Construction Pvt Ltd,Gopalgang | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Saran
937 | SSS-340-1 | Siwan | ip:[kh | mRØfer e/; fo¦ky;] MVokW | Shailcon Construction, Gopalgang | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Saran
938 | SSS-341-1 | Gopalganj | dVs;k | e/; fo¦ky;] /kjgjk esyk | Shailcon Construction, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
939 | SSS-341-2 | Gopalganj | dVs;k | mRØfer e/; fo¦ky;] idM+h Mhg | Shailcon Construction, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
940 | SSS-341-3 | Gopalganj | dVs;k | e/; fo¦ky;] jlkSrh | Shailcon Construction, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
941 | SSS-342-1 | Gopalganj | ek>kW | e/; fo¦ky;] rsfy;k ckW/k | Pawan Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
942 | SSS-342-2 | Gopalganj | ek>kW | mRØfer e/; fo¦ky;] e/kq ljs;k | Pawan Construction | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
943 | SSS-343-1 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] lksucjlk | Savitri technorats pvt ltd kaithwalia ward no. 7 gopalganj | [14 empty] | 1 |  |  |  | Saran
944 | SSS-343-2 | Gopalganj | cjkSyh | e/; fo¦ky;] dY;k.kiqj | Savitri technorats pvt ltd kaithwalia ward no. 7 gopalganj | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
945 | SSS-344-1 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] osylM | Asiana Contractor Pvt. Ltd.-9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
946 | SSS-344-2 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] [ktqfj;k ckyd | Asiana Contractor Pvt. Ltd.-9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
947 | SSS-344-3 | Gopalganj | cjkSyh | e/; fo¦ky;] ekMuiqj | Asiana Contractor Pvt. Ltd.-9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
948 | SSS-344-4 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] usmjh | Asiana Contractor Pvt. Ltd.-9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
949 | SSS-345-1 | Gopalganj | Hkksjs | e/; fo¦ky;] dqlgkW | Anand Mishra, Gopalgang | [13 empty] | 1 |  |  |  |  | Saran
950 | SSS-345-2 | Gopalganj | Hkksjs | mRØfer e/; fo¦ky;] egjknsmj | Anand Mishra, Gopalgang | [12 empty] | 1 | [5 empty] | Saran
951 | SSS-345-3 | Gopalganj | Hkksjs | e/; fo¦ky;] ftxuk nwcs | Anand Mishra, Gopalgang | [13 empty] | 1 |  |  |  |  | Saran
952 | SSS-345-4 | Gopalganj | Hkksjs | e/; fo¦ky;] fllbZ | Anand Mishra, Gopalgang | [13 empty] | 1 |  |  |  |  | Saran
953 | SSS-345-5 | Gopalganj | Hkksjs | e/; fo¦ky;] ykehpkSj | Anand Mishra, Gopalgang | [13 empty] | 1 |  |  |  |  | Saran
954 | SSS-345-6 | Gopalganj | Hkksjs | e/; fo¦ky;] oudVk tkxhjnkjh | Anand Mishra, Gopalgang | [13 empty] | 1 |  |  |  |  | Saran
955 | SSS-346-1 | Gopalganj | fl/kofy;k | mRØfer e/; fo¦ky;] oq/klh | NORTH BIHAR CONSTRUCTION | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
956 | SSS-346-2 | Gopalganj | fl/kofy;k | mRØfer e/; fo¦ky;] cqfp;k | NORTH BIHAR CONSTRUCTION | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
957 | SSS-346-3 | Gopalganj | fl/kofy;k | e/; fo¦ky;] >>okW | NORTH BIHAR CONSTRUCTION | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
958 | SSS-347-1 | Gopalganj | oSdq.Biqj | mRØfer e/; fo¦ky;] calrNkijk | Hariom construction vill-khaira po-jaihindtendua distt- Aurangabad | [14 empty] | 1 |  |  |  | Saran
959 | SSS-347-2 | Gopalganj | oSdq.Biqj | mRØfer e/; fo¦ky;] eMok | Hariom construction vill-khaira po-jaihindtendua distt- Aurangabad | [10 empty] | 1 | [7 empty] | Saran
960 | SSS-348-1 | Gopalganj | dqpk;dksV | mRØfer e/; fo¦ky;] HkkstNkij | Anand mishra, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
961 | SSS-348-2 | Gopalganj | dqpk;dksV | e/; fo¦ky;] fo'kEHkjiqj | Anand mishra, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
962 | SSS-348-3 | Gopalganj | dqpk;dksV | mRØfer e/; fo¦ky;] o`rHkkeh Vksyk | Anand mishra, Gopalgang | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
963 | SSS-349-1 | Gopalganj | xksikyxat | mRØfer e/; fo¦ky;] ekfudiqj dU;k | Sona Engicon Pvt Ltd, Gopalganj | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
964 | SSS-349-2 | Gopalganj | xksikyxat | mRØfer e/; fo¦ky;] [kSjfV;k jke uxj | Sona Engicon Pvt Ltd, Gopalganj | [13 empty] | 1 |  |  |  |  | Saran
965 | SSS-350-1 | Gopalganj | gFkqvk | e/; fo¦ky;] lsejko | Shiv Shankar Singh Construction Pvt. Ltd. | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
966 | SSS-350-2 | Gopalganj | gFkqvk | e/; fo¦ky;] pSuiqj | Shiv Shankar Singh Construction Pvt. Ltd. | [5 empty] | 1 | [10 empty] | Land Problem |  | Saran
967 | SSS-351-1 | Gopalganj | Qqyofj;k | mRØfer e/; fo¦ky;] exgkW | Kumar manash Construction, Gopalganj | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
968 | SSS-351-2 | Gopalganj | Qqyofj;k | e/; fo¦ky;] ekMhiqj | Kumar manash Construction, Gopalganj | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
969 | SSS-351-3 | Gopalganj | Qqyofj;k | mRØfer e/; fo¦ky;] laxzkeiqj xksiky | Kumar manash Construction, Gopalganj | [13 empty] | 1 |  |  |  |  | Saran
970 | SSS-352-1 | Gopalganj | mpdkxkWo | mRØfer e/; fo¦ky;] eqMk edlwniqj | Pawan Construction, Uchakagawn | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Saran
971 | SSS-353-1 | Gopalganj | iapnsojh | mRØfer e/; fo¦ky;] fiijgh | Anand mishra | [13 empty] | 1 |  |  |  |  | Saran
972 | SSS-354-1 | Gopalganj | fot;hiqj | e/; fo¦ky;] lqvjgkW gadkjiqj | Ashok construction vill+po- Chhitwana, Gopalganj | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
973 | SSS-466-1 | Gopalganj | cSdq.Biqj ¼cjkSyh½ | mRØfer e/; fo¦ky;] cyjk | North Bihar Construction Corporation , Gopalganj | [5 empty] | 1 | [10 empty] | Not Start. Short Land Not Sufficient In Size. |  | Saran
974 | SSS-466-2 | Gopalganj | cSdq.Biqj | e/; fo¦ky;] eqatk c[kjh | North Bihar Construction Corporation , Gopalganj | [13 empty] | 1 |  |  |  |  | Saran
975 | SSS-364-1 | Siwan | njkSyh | mRØfer e/; fo¦ky;] d`".kkikyh | ASIANA CONSTRACT PVT LTD 9431088485 | [5 empty] | 1 | [10 empty] | Land dispute |  | Saran
976 | SSS-364-2 | Siwan | njkSyh | e/; fo¦ky;] pdjh | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
977 | SSS-364-3 | Siwan | njkSyh | e/; fo¦ky;] gjukVkaM | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  |  |  | Saran
978 | SSS-364-4 | Siwan | njkSyh | mRØfer e/; fo¦ky;] Vmoka ijfl;ka | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
979 | SSS-365(A) | Siwan | njkSank | mRØfer e/; fo¦ky;]cSnkiqj | ASIANA CONSTRACT PVT LTD,9431081485 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Saran | added to 400 list
980 | SSS-365(B) | Siwan | njkSank | e/; fo¦ky;] idofy;k | ASIANA CONSTRACT PVT LTD,9431081485 | [14 empty] | 1 |  |  |  | Saran
981 | SSS-366-1 | Siwan | egkjktxat | e/; fo¦ky;] ek/kksijq | MS SHAILENDRA SHEKHAR MISHRA 9471004272 | [14 empty] | 1 |  |  |  | Saran
982 | SSS-367-1 | Siwan | Hkkxokuiqj gkV | mRØfer e/; fo¦ky;] ljk; iMkSyh | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
983 | SSS-367-2 | Siwan | Hkkxokuiqj gkV | e/; fo¦ky;] tqvkQj | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
984 | SSS-367-3 | Siwan | Hkkxokuiqj gkV | mRØfer e/; fo¦ky;][kfM+;k Vksyk | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 | Handover | Inaugurated 2016 |  | Saran
985 | SSS-368-1 | Siwan | xqBuh | e/; fo¦ky;] cdqykjh | AMIT KUMAR CHATURVEDI 7562033432 | [13 empty] | 1 |  |  |  |  | Saran
986 | SSS-368-2 | Siwan | xqBuh | e/; fo¦ky;] rkyh | AMIT KUMAR CHATURVEDI 7562033432 | [13 empty] | 1 |  |  |  |  | Saran
987 | SSS-369(A) | Siwan | j?kqukFkiqj | e/; fo¦ky;] fn?koyh;k | SUBHASH KUMAR SUBHASH,9934211227 | [5 empty] | 1 | [10 empty] | Land Problem. (Land In Progress By Dighwalia C.O.) |  | Saran
988 | SSS-369(B) | Siwan | j?kqukFkiqj | e/; fo¦ky;] uoknk | SIENN SECURITY PRIVATE LIMITED,9708011111 | [13 empty] | 1 |  |  |  |  | Saran
989 | SSS-370(A) | Siwan | fllou | e/; fo¦ky;] iM+jh | DURGA PRATAP SINGH,7781003700 | [13 empty] | 1 |  |  |  |  | Saran
990 | SSS-370(B) | Siwan | fllou | e/; fo¦ky;] Hkkxj | DURGA PRATAP SINGH, 7781003700 | [13 empty] | 1 |  |  |  |  | Saran
991 | SSS-371-1 | Siwan | thjknsbZ | e/; fo¦ky;] latyiqj | RENU DEVI 9771455967 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
992 | SSS-372-1 | Siwan | xksjs;kdksBh | mRØfer e/; fo¦ky;] e>ofy;k | ASIANA CONSTRACT PVT LTD 9431088485 | [14 empty] | 1 |  | Inaugurated 2016 |  | Saran
993 | SSS-373-1 | Siwan | ip:[kh | e/; fo¦ky;] orZofy;k | MD RAFIQUE, 8292149970 | [14 empty] | 1 |  |  |  | Saran
Total No. of Schools |  |  |  | 993 |  |  |  |  | 0 | 2 | 115 | 2 | 10 | 11 | 9 | 43 | 11 | 47 | 225 | 518
Note on E334: e/; fo¦ky; eksgCck*
Note on W646: LATE DUE TO CONTRACTOR