## Summary
BSEIDC, PATNA
Progress report for the construction of SSSM (2012-13) | [19 empty] | Date:-31.03.2015
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Physical Status | [7 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Not Start | In-Progress | Complete
[12 empty] | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA (EAST) | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna (East) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2 | PATNA (WEST) | Vinod Kumar Ranjan (9661863636) E.E., BSEIDC, Div.-Patna (West) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
4 | BHAGALPUR | Sanjeev Kumar (9199601788) , E.E. BSEIDC, Div.-Bhagalpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
5 | MUNGER | Surendra Kumar (9939599803), E.E. BSEIDC, Div.-Munger | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
6 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
7 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 46 | 66 | 7476.42 | 24 | 45 | 4855.91 | 1 | 8 | 7 | 4 | 3 | 0 | 0 | 1 | 20 | 24 | 0 | 362.78 |  | 1
8 | TIRHUT (EAST) | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
9 | TIRHUT (WEST) | Sunil Kumar Sinha, (8544126916), E.E. BSEIDC, Div.- Tirhut (West) | 12 | 12 | 1391.29 | 9 | 9 | 1042.94 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 22.61 |  | 0
10 | DARBHANGA | Pramod Kumar (9955128483) E.E. BSEIDC, Div.-Darbhanga | 11 | 13 | 1477.28 | 7 | 9 | 1022.64 | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 3 | 6 | 0 | 172.3 |  | 0
11 | SARAN | Uday Kumar Das, (9431821558) EE BSEIDC, Div.- Saran | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Total (SSSM) |  |  | 69 | 91 | 10344.99 | 40 | 63 | 6921.49 | 1 | 15 | 9 | 5 | 6 | 0 | 0 | 1 | 25 | 37 | 0 | 557.69 |  | 1

## Purnea
BSEIDC, PATNA
Progress report for the construction of SSSM (2012-13)
Name of Division :- PURNEA | [21 empty] | Date:-31.03.2015
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSSM-1 | dfVgkj | अमदाबाद | 1 | m0e0fo0 pkek | Umakant Singh,9431096239 |  |  | 342.51 |  |  | 15 ekg | [5 empty] | 1 |  |  |  |  | 91.56
|  |  | अमदाबाद | 2 | e0fo0 turkxksikyiqj | [12 empty] | 1
|  |  | अमदाबाद | 3 | e0fo0 ikjfn;kjk | [7 empty] | 1
2 | SSSM-2 | dfVgkj | आजमनगर | 1 | e0fo0 fldfV;k | BIRENDRA KUMAR SINGH,9473440405 |  |  | 343.75 |  |  | 15 ekg |  |  | 1 | [7 empty] | 33.03
|  |  | आजमनगर | 2 | m0e0fo0 csyjkgh | [12 empty] | 1
|  |  | आजमनगर | 3 | m0e0fo0 rs?kM+k | [7 empty] | 1
3 | SSSM-3(A) | dfVgkj | बारसोई | 1 | e0fo0 XokyVksyh | RANA BIRESH PRATAP SINGH,9430683578 |  |  | 115.71 |  |  | 15 ekg | 1
4 | SSSM-3(B) |  | बारसोई | 1 | e0fo0 [k#vk tehjk | Tender Process |  |  | 115.71 |  |  | 15 ekg
5 | SSSM-3(C) |  | बारसोई | 1 | m0e0fo0 Qqgkxk¡o | Tender Process |  |  | 115.71 |  |  | 15 ekg
6 | SSSM-4(A) | dfVgkj | बलरामपुर | 1 | e0fo0 efydiqj | MUKESH KUMAR,9431658565 |  |  | 115.34 |  |  | 15 ekg | 1
7 | SSSM-4(B) |  | बलरामपुर | 1 | e0fo0 Qrsgiqj | Tender Process |  |  | 115.34 |  |  | 15 ekg
8 | SSSM-4(C) |  | बलरामपुर | 1 | m0e0fo0 ckywxat fgUnh | Tender Process |  |  | 115.34 |  |  | 15 ekg
9 | SSSM-5 | dfVgkj | फलका | 1 | e0fo0 eks0 uxj jkt/kkuh | BIRENDRA KUMAR SINGH,9473440405 |  |  | 223.83 |  |  | 15 ekg | 1
|  |  | फलका | 2 | e0fo0 Hkjfl;k | [7 empty] | 1
10 | SSSM-6 | dfVgkj | कोढ़ा | 1 | vH;kl e0fo0 eqlkiqj | BIRENDRA KUMAR SINGH,9473440405 |  |  | 332.13 |  |  | 15 ekg |  |  |  |  | 1 | [5 empty] | 21.88
|  |  | कोढ़ा | 2 | e0fo0 [ksfj;k | [7 empty] | 1
|  |  | कोढ़ा | 3 | e0fo0 fn?kM+h | [7 empty] | 1
11 | SSSM-7 | dfVgkj | प्राणपुर | 1 | m0e0fo0 jkepUnziqj | PANKAJ KUMAR SINGH,9431229327 |  |  | 335.36 |  |  | 15 ekg | [8 empty] | 1
|  |  | प्राणपुर | 2 | e0fo0 egknsoiqj | [7 empty] | 1 | [9 empty] | 74.22
|  |  | प्राणपुर | 3 | e0fo0 cq) uxj | [11 empty] | 1
12 | SSSM-8 | dfVgkj | कटिहार | 1 | m0e0fo0 efu;k | PANKAJ KUMAR SINGH,9431229327 |  |  | 221.65 |  |  | 15 ekg | 1 | [9 empty] | 16.99
|  |  | कटिहार | 2 | e0fo0 cBSyh | [10 empty] | 1
13 | SSSM-9 | dfVgkj | मनसाही | 1 | jk0e0fo0 eajxh | BIRENDRA KUMAR SINGH,9473440405 |  |  | 222.46 |  |  | 15 ekg |  |  |  |  | 1 | [5 empty] | 21.69
|  |  | मनसाही | 2 | vk0e0fo0 jkuhirjk fla/k;k | [7 empty] | 1
14 | SSSM-10 | dfVgkj | बरारी | 1 | m0e0fo0 fxnjekjh | BIRENDRA KUMAR SINGH,9473440405 |  |  | 222.01 |  |  | 15 ekg |  |  |  | 1
|  |  | बरारी | 2 | e0fo0 Hk.Mkjry
15 | SSSM-11(A) | dfVgkj | मनिहारी | 1 | e0fo0 lqjkikjVky | MS EXCELLENT CONSTRUCTION,9472021967 |  |  | 112.5 |  |  | 15 ekg | 1
16 | SSSM-11(B) |  | मनिहारी | 1 | e0fo0 dkWVkdks'k | Tender Process |  |  | 112.5 |  |  | 15 ekg
17 | SSSM-12(A) | dfVgkj | कदवा | 1 | m0e0fo0 dpkSM+k iwoZ | Tender Process |  |  | 112.57 |  |  | 15 ekg
18 | SSSM-12(B) |  | कदवा | 1 | m0e0fo0 cSnk | Tender Process |  |  | 112.57 |  |  | 15 ekg
19 | SSSM-13(A) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 y[kukjs | Tender Process |  |  | 114 |  |  | 15 ekg
20 | SSSM-13(B) |  | अमौर | 1 | e0fo0 csydk | MD ARFIN,9006212706 |  |  | 114 |  |  | 15 ekg | 1 |  |  | 1
21 | SSSM-13(C) |  | अमौर | 1 | e0fo0 ckywVksyk] bLykeiqj | Tender Process |  |  | 114 |  |  | 15 ekg
22 | SSSM-14(A) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 etxkek | SANJEEV RANJAN SINHA, 9472063463 |  |  | 111.74 |  |  | 15 ekg | 1
23 | SSSM-14(B) |  | कसबा | 1 | e0fo0 yN.kiqj | Tender Process |  |  | 111.74 |  |  | 15 ekg
24 | SSSM-14(C) |  | कसबा | 1 | e0fo0 eksguh | Tender Process |  |  | 111.74 |  |  | 15 ekg
25 | SSSM-15(A) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 lkukiqj | Tender Process |  |  | 112.99 |  |  | 15 ekg
26 | SSSM-15(B) |  | बैसी | 1 | e0fo0 gjsjkeiqj | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED,9973239801 |  |  | 112.99 |  |  | 15 ekg | 1
27 | SSSM-15(C) |  | बैसी | 1 | e0fo0 pjS;k | Tender Process |  |  | 112.99 |  |  | 15 ekg
28 | SSSM-15(D) |  | बैसी | 1 | e0fo0 'kh'kckM+h | Tender Process |  |  | 112.99 |  |  | 15 ekg
29 | SSSM-15(E) |  | बैसी | 1 | e0fo0 p¡nokj | Tender Process |  |  | 112.99 |  |  | 15 ekg
30 | SSSM-15(F) |  | बैसी | 1 | e0fo0 uUnfu;k | Tender Process |  |  | 112.99 |  |  | 15 ekg
31 | SSSM-16(A) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 Mx#vk | HARIMOHAN BISHWAS,9955713757 |  |  | 112.25 |  |  | 15 ekg | 1
32 | SSSM-16(B) |  | डगरुआ | 1 | e0fo0 pkSiM+k cyqvk | Tender Process |  |  | 112.25 |  |  | 15 ekg
33 | SSSM-16(C) |  | डगरुआ | 1 | e0fo0 fl;kj[ke | Tender Process |  |  | 112.25 |  |  | 15 ekg
34 | SSSM-17 | iwf.kZ;k¡ | जलालगढ़ | 1 | e0fo0 efr;kjiqj | DILIP KUMAR,9631032543 '/ 9431666265 |  |  | 338.09 |  |  | 15 ekg |  |  |  | 1 | [6 empty] | 58.5
|  |  | जलालगढ़ | 2 | e0fo0 dBSyh | [11 empty] | 1
|  |  | जलालगढ़ | 3 | e0fo0 ,dEck | [9 empty] | 1
35 | SSSM-18 | iwf.kZ;k¡ | कृत्यानन्द नगर | 1 | e0fo0 iz[kaM dkWyuh | MS ALAM CONSTRUCTION WORKS AND COMPANY,9199574775 9472103786 |  |  | 333.26 |  |  | 15 ekg |  |  |  | 1 | [6 empty] | 21.07
|  |  | कृत्यानन्द नगर | 2 | e0fo0 izlkniqj csynkjh | [7 empty] | 1
|  |  | कृत्यानन्द नगर | 3 | e0fo0 dk>k x.ks'kiqj | [9 empty] | 1
36 | SSSM-19 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 1 | e0fo0 fiijk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 |  |  | 222.8 |  |  | 15 ekg |  |  |  | 1
|  |  | पूर्णियाँ इस्ट | 2 | e0fo0 egjktiqj | [9 empty] | 1
37 | SSSM-20 | iwf.kZ;k¡ | श्रीनगर | 1 | e0fo0 txSyh | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 |  |  | 224.28 |  |  | 15 ekg | 1
|  |  | श्रीनगर | 2 | e0fo0 xaxk Hkou [kks[kk | [9 empty] | 1
38 | SSSM-25 | vjfj;k | नरपतगंज | 1 | ,e0,l0 xks[kykiqj ch0,e0,l0 | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 |  |  | 353.03 |  |  | 15 ekg |  | 1 | [8 empty] | 23.84
|  |  | नरपतगंज | 2 | ,e0,l0 csyk fjQwth | [10 empty] | 1
|  |  | नरपतगंज | 3 | ,e0,l0 pUnk | [9 empty] | 1
39 | SSSM-26(A) | vjfj;k | रानीगंज | 1 | ,e0,l0 gjhnk,iqj | Tender Process |  |  | 114.05 |  |  | 15 ekg
40 | SSSM-26(B) |  | रानीगंज | 1 | ,e0,l0 ukjk;.kiqj | MD ARFIN, 9006212706 |  |  | 114.05 |  |  | 15 ekg | 1
41 | SSSM-26(C) |  | रानीगंज | 1 | ;w0,e0,l0 nqekfj;k ckyd | MD ARFIN, 9006212706 |  |  | 114.05 |  |  | 15 ekg |  |  | 1
42 | SSSM-27(A) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 vekSuk | KRISHNA RANJAN KUMAR,9939662452 |  |  | 116.06 |  |  | 15 ekg | 1
43 | SSSM-27(B) |  | फारबिसगंज | 1 | ,e0,l0 iq.kZnkgk | CHANDAN ABHISHEK,9431284224 |  |  | 116.06 |  |  | 15 ekg |  |  | 1
44 | SSSM-28(A) | vjfj;k | सिक्टी | 1 | ,e0,l0 xksjkxPN | Tender Process |  |  | 118.43 |  |  | 15 ekg
45 | SSSM-28(B) | vjfj;k | सिक्टी | 1 | ;w0,e0,l0 fnefg;k | Tender Process |  |  | 118.43 |  |  | 15 ekg
46 | SSSM-29 | vjfj;k | सिक्टी | 1 | ,e0,l0 ispkSyh | Tender Process |  |  | 114.93 |  |  | 15 ekg
Total No. of Schools |  |  |  | 66 |  |  |  |  | 7476.42 |  |  |  | 20 | 1 | 8 | 7 | 4 | 3 | 0 | 0 | 1 | 0 | 362.78

## Tirhut (West)
BSEIDC, PATNA
Progress report for the construction of SSSM (2012-13)
Name of Division :- TIRHUT (WEST) - East Champaran, West Champaran & Shivhar | [22 empty] | Date:-31.03.2015
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSSM-21(A) | if'pe pEikj.k | सिरिसिया | 1 | e0fo0 fljfl;k | KISHOR KUMAR,8298437834 |  |  | 115.98 |  |  | 15 ekg |  |  | 1
2 | SSSM-21(B) |  | बेहरा | 1 | e0fo0 >qedk mnwZ | MS SARASWATI COMPANY,9431491241 |  |  | 115.98 |  |  | 15 ekg | 1
3 | SSSM-21(C) |  | सूर्यपुर | 1 | mŒ ekŒ foŒ] Hkokuhiqj mnZw | MS SARASWATI COMPANY,9431491241 |  |  | 115.98 |  |  | 15 ekg |  |  | 1
4 | SSSM-22(A) | if'pe pEikj.k | तेलपुर | 1 | m0e0fo0 rsyiqj ckyd | Tender Process |  |  | 115.98 |  |  | 15 ekg
5 | SSSM-22(B) |  | देउरवा | 1 | e0fo0 nsmjok | Tender Process |  |  | 115.98 |  |  | 15 ekg
6 | SSSM-22(C) |  | धोबनी धर्मपुर | 1 | m0e0fo0 eqlgjh | SANJAY KUMAR MISHRA, 9546215798 |  |  | 115.98 |  |  | 15 ekg |  |  | 1
7 | SSSM-22(D) |  | मठिया | 1 | e0fo0 efB;k | AWADHESH SHUKLA, 9431203836 |  |  | 115.98 |  |  | 15 ekg |  |  | 1 | [7 empty] | 14.28
8 | SSSM-23(A) | if'pe pEikj.k | रखही | 1 | m0e0fo0 pEikj.k | SHAKAL DEO MISHRA,9006385958 |  |  | 115.55 |  |  | 15 ekg |  |  | 1
9 | SSSM-23(B) |  | शेरहवा | 1 | e0fo0 fllok cgqvjok | RAJ KISHORE AKELA,9430642227 |  |  | 115.55 |  |  | 15 ekg |  |  | 1 | [7 empty] | 8.33
10 | SSSM-23(C) |  | पुरैनिया हरसरी | 1 | m0e0fo0 dksbZjxkok | SANJAY KUMAR MISHRA,9546215798 |  |  | 115.55 |  |  | 15 ekg |  |  | 1
11 | SSSM-24(A) | if'pe pEikj.k | चैहटी | 1 | e0fo0 lkSdV | GYASUL AZAM, 9199932786 |  |  | 116.39 |  |  | 15 ekg | 1
12 | SSSM-24(B) |  | मधुरि | 1 | m0e0fo0 idqgok iwohZ | Tender Process |  |  | 116.39 |  |  | 15 ekg
Total No. of Schools |  |  |  | 12 |  |  |  |  | 1391.29 |  |  |  | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.61

## Darbhanga
BSEIDC, PATNA
Progress report for the construction of SSSM (2012-13)
Name of Division :- DARBHANGA | [22 empty] | Date:-31.03.2015
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of LOA | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
1 | SSSM-30 | njHkaxk | दरभंगा सदर | 1 | e0fo0 Bdqjfu;k¡ | RAJENDRA PRASAD, 8797539347 |  |  | 225.8 |  |  | 15 ekg | [5 empty] | 1 |  |  |  |  | 59.48
|  |  | दरभंगा सदर | 2 | e0fo0 da'kh | [10 empty] | 1
2 | SSSM-31 | njHkaxk | मनीगाछी | 1 | e0fo0 pdfpUrkef.kiqj | S K CONSTRUCTION AND COMPANY,9471006199 |  |  | 114.2 |  |  | 15 ekg | 1
3 | SSSM-32 | njHkaxk | अलीनगर | 1 | mnwZ e0fo0 vyhuxj | AJAY KUMAR PATHAK,9431034060 |  |  | 114.27 |  |  | 15 ekg |  |  |  |  | 1 | [5 empty] | 21.61
4 | SSSM-33 | njHkaxk | जाले | 1 | e0fo0 tgkxhj Vksy | SANJAY KUMAR, 8521954601 |  |  | 229.19 |  |  | 15 ekg | [5 empty] | 1 |  |  |  |  | 36.79
|  |  | जाले | 2 | e0fo0 vfg;kjh xksV | [7 empty] | 1
5 | SSSM-34(A) | njHkaxk | सिंहवाड़ा | 1 | e0fo0 jktks | BHUSAN KUMAR,9631681894 |  |  | 113.32 |  |  | 15 ekg |  |  |  | 1 | [6 empty] | 20.33
6 | SSSM-34(B) |  | सिंहवाड़ा | 1 | m0e0fo0 cgqvkjk | Tender Process |  |  | 113.32 |  |  | 15 ekg
7 | SSSM-34(C) |  | सिंहवाड़ा | 1 | m0e0fo0 xkSjhukFk czgeiqj | Tender Process |  |  | 113.32 |  |  | 15 ekg
8 | SSSM-35(A) | njHkaxk | केवटी | 1 | e0fo0 cjgh | OM SHREE CONSTRUCTION, 9934426934 |  |  | 112.93 |  |  | 15 ekg | 1
9 | SSSM-35(B) |  | केवटी | 1 | m0e0fo0 ykyxat | Rajesh Kumar, 9334374660 |  |  | 112.93 |  |  | 15 ekg | [5 empty] | 1 |  |  |  |  | 34.09
10 | SSSM-36 | njHkaxk | किरतपुर | 1 | e0fo0 fdjriqj | Tender Process |  |  | 113.75 |  |  | 15 ekg
11 | SSSM-37 | njHkaxk | गौराबौराम | 1 | e0fo0 ckSjke | Tender Process |  |  | 114.25 |  |  | 15 ekg
Total No. of Schools |  |  |  | 13 |  |  |  |  | 1477.28 |  |  |  | 3 | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 172.3

## Patna (East)
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- PATNA (EAST) - Patna, Nalanda & Bhojpur
Name & contact no. of EE : Satish Prasad (8987263065), AE (Patna & Nalanda):- S.Tiwari (9431495949), AE (Bhojpur):- Rama Shanker Prasad (9431492761)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1
2
| Total No. of Schools |  |  | #REF! |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Patna (West)
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- PATNA (WEST) - Buxar, Rohtas & Kaimur
Name & contact no. of EE : Vinod Kumar Ranjan (9661863636), AE (Buxar):- Atul Kr. Burnwal (9835658494) & AE (Rohtas & Kaimur):- Vijay Prasad Singh (9431041889)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Aggrement No & date | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[12 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[16 empty] | LL | RL | LL | RL
1
2
3
| Total No. of Schools |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Magadh
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- MAGADH
Name & contact no. of EE :- Rajiv Ranjan (9234271071), AE :- Mallu Singh (9835471249/ 9471211134), AE :- Helal Ahmad (9771081441), AE :- Benaik Prasad (9431420392)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency Address and Mobile No | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[14 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[18 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- BHAGALPUR
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar 9931487994
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Munger
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- MUNGER
Name & contact no. of EE :-Surendra Kumar (9939599803), Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Kosi
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- KOSI
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tirhut (East)
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- TIRHUT (EAST) - Vaishali, Muzaffarpur & Sitamarhi
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Name of Agency | Agency's Address & Mobile No. | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Saran
BSEIDC, PATNA
Progress Report for the construction of SSSM
Name of Division :- SARAN
Name & contact no. of EE :- Uday Kumar Das (9431821558), AE :-Maya prasad singh (9973106456), AE :- Rajiv Kr. (9934204444)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Agency's Address & Mobile No. | Advance Amount (in Lac) | Estimated Amount (in Lac) | Date of Aggrement | Date of start | Time of Completion | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks
[13 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[17 empty] | LL | RL | LL | RL
Total No. of Schools |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SSSM 2012-13 _list
1 | SSSM-3(A) | dfVgkj | 1 | e0fo0 XokyVksyh | 115.71 | 15 ekg | 1 | 1
2 | SSSM-3(B) |  | 1 | e0fo0 [k#vk tehjk | 115.71 | 15 ekg | 1 | 1
3 | SSSM-3(C) |  | 1 | m0e0fo0 Qqgkxk¡o | 115.71 | 15 ekg | 1 | 1
4 | SSSM-4(A) | dfVgkj | 1 | e0fo0 efydiqj | 115.34 | 15 ekg | 1 | 1
5 | SSSM-4(B) |  | 1 | e0fo0 Qrsgiqj | 115.34 | 15 ekg | 1 | 1
6 | SSSM-4(C) |  | 1 | m0e0fo0 ckywxat fgUnh | 115.34 | 15 ekg | 1 | 1
7 | SSSM-11(A) | dfVgkj | 1 | e0fo0 lqjkikjVky | 112.5 | 15 ekg | 1 | 1
8 | SSSM-11(B) |  | 1 | e0fo0 dkWVkdks'k | 112.5 | 15 ekg | 1 | 1
9 | SSSM-12(A) | dfVgkj | 1 | m0e0fo0 dpkSM+k iwoZ | 112.57 | 15 ekg | 1 | 1
10 | SSSM-12(B) |  | 1 | m0e0fo0 cSnk | 112.57 | 15 ekg | 1 | 1
11 | SSSM-13(A) | iwf.kZ;k¡ | 1 | e0fo0 y[kukjs | 114 | 15 ekg | 1 | 1
12 | SSSM-13(B) |  | 1 | e0fo0 csydk | 114 | 15 ekg | 1 | 1
13 | SSSM-13(C) |  | 1 | e0fo0 ckywVksyk] bLykeiqj | 114 | 15 ekg | 1 | 1
14 | SSSM-14(A) | iwf.kZ;k¡ | 1 | e0fo0 etxkek | 111.74 | 15 ekg | 1 | 1
15 | SSSM-14(B) |  | 1 | e0fo0 yN.kiqj | 111.74 | 15 ekg | 1 | 1
16 | SSSM-14(C) |  | 1 | e0fo0 eksguh | 111.74 | 15 ekg | 1 | 1
17 | SSSM-15(A) | iwf.kZ;k¡ | 1 | e0fo0 lkukiqj | 112.99 | 15 ekg | 1 | 1
18 | SSSM-15(B) |  | 1 | e0fo0 gjsjkeiqj | 112.99 | 15 ekg | 1 | 1
19 | SSSM-15(C) |  | 1 | e0fo0 pjS;k | 112.99 | 15 ekg | 1 | 1
20 | SSSM-15(D) |  | 1 | e0fo0 'kh'kckM+h | 112.99 | 15 ekg | 1 | 1
21 | SSSM-15(E) |  | 1 | e0fo0 p¡nokj | 112.99 | 15 ekg | 1 | 1
22 | SSSM-15(F) |  | 1 | e0fo0 uUnfu;k | 112.99 | 15 ekg | 1 | 1
23 | SSSM-16(A) | iwf.kZ;k¡ | 1 | e0fo0 Mx#vk | 112.25 | 15 ekg | 1 | 1
24 | SSSM-16(B) |  | 1 | e0fo0 pkSiM+k cyqvk | 112.25 | 15 ekg | 1 | 1
25 | SSSM-16(C) |  | 1 | e0fo0 fl;kj[ke | 112.25 |  | 1 | 1
26 | SSSM-21(A) | if'pe pEikj.k | 1 | e0fo0 fljfl;k | 115.98 | 15 ekg | 1 | 1
27 | SSSM-21(B) |  | 1 | e0fo0 >qedk mnwZ | 115.98 | 15 ekg | 1 | 1
28 | SSSM-21(C) |  | 1 | mŒ ekŒ foŒ] Hkokuhiqj mnZw | 115.98 | 15 ekg | 1 | 1
29 | SSSM-22(A) | if'pe pEikj.k | 1 | m0e0fo0 rsyiqj ckyd | 115.98 | 15 ekg | 1 | 1
30 | SSSM-22(B) |  | 1 | e0fo0 nsmjok | 115.98 | 15 ekg | 1 | 1
31 | SSSM-22(C) |  | 1 | m0e0fo0 eqlgjh | 115.98 | 15 ekg | 1 | 1
32 | SSSM-22(D) |  | 1 | e0fo0 efB;k | 115.98 |  | 1 | 1
33 | SSSM-23(A) | if'pe pEikj.k | 1 | m0e0fo0 pEikj.k | 115.55 | 15 ekg | 1 | 1
34 | SSSM-23(B) |  | 1 | e0fo0 fllok cgqvjok | 115.55 | 15 ekg | 1 | 1
35 | SSSM-23(C) |  | 1 | m0e0fo0 dksbZjxkok | 115.55 | 15 ekg | 1 | 1
36 | SSSM-24(A) | if'pe pEikj.k | 1 | e0fo0 lkSdV | 116.39 | 15 ekg | 1 | 1
37 | SSSM-24(B) |  | 1 | m0e0fo0 idqgok iwohZ | 116.39 | 15 ekg | 1 | 1
38 | SSSM-26(A) | vjfj;k | 1 | ,e0,l0 gjhnk,iqj | 114.05 | 15 ekg | 1 | 1
39 | SSSM-26(B) |  | 1 | ,e0,l0 ukjk;.kiqj | 114.05 | 15 ekg | 1 | 1
40 | SSSM-26(C) |  | 1 | ;w0,e0,l0 nqekfj;k ckyd | 114.05 | 15 ekg | 1 | 1
41 | SSSM-27(A) | vjfj;k | 1 | ,e0,l0 vekSuk | 116.06 | 15 ekg | 1 | 1
42 | SSSM-27(B) |  | 1 | ,e0,l0 iq.kZnkgk | 116.06 | 15 ekg | 1 | 1
43 | SSSM-28(A) | vjfj;k | 1 | ,e0,l0 xksjkxPN | 118.43 | 15 ekg | 1 | 1
44 | SSSM-28(B) | vjfj;k | 1 | ;w0,e0,l0 fnefg;k | 118.43 | 15 ekg | 1 | 1
45 | SSSM-29 | vjfj;k | 1 | ,e0,l0 ispkSyh | 114.93 | 15 ekg | 1 | 1
46 | SSSM-31 | njHkaxk | 1 | e0fo0 pdfpUrkef.kiqj | 114.2 | 15 ekg | 1 | 1
47 | SSSM-34(A) | njHkaxk | 1 | e0fo0 jktks | 113.32 | 15 ekg | 1 | 1
48 | SSSM-34(B) |  | 1 | m0e0fo0 cgqvkjk | 113.32 | 15 ekg | 1 | 1
49 | SSSM-34(C) |  | 1 | m0e0fo0 xkSjhukFk czgeiqj | 113.32 | 15 ekg | 1 | 1
50 | SSSM-35(A) | njHkaxk | 1 | e0fo0 cjgh | 112.93 | 15 ekg | 1 | 1
51 | SSSM-35(B) |  | 1 | m0e0fo0 ykyxat | 112.93 | 15 ekg | 1 | 1
52 | SSSM-37 | njHkaxk | 1 | e0fo0 ckSjke | 114.25 | 15 ekg | 1 | 1
53 | SSSM-1 | dfVgkj | 1 | m0e0fo0 pkek | 342.51 |  | 1 | 1
|  |  | 2 | e0fo0 turkxksikyiqj |  |  |  | 1
|  |  | 3 | e0fo0 ikjfn;kjk |  |  |  | 1
54 | SSSM-2 | dfVgkj | 1 | e0fo0 fldfV;k | 343.75 |  | 1 | 1
|  |  | 2 | m0e0fo0 csyjkgh |  |  |  | 1
|  |  | 3 | m0e0fo0 rs?kM+k |  |  |  | 1
55 | SSSM-5 | dfVgkj | 1 | e0fo0 eks0 uxj jkt/kkuh | 223.83 |  | 1 | 1
|  |  | 2 | e0fo0 Hkjfl;k |  |  | 0 | 1
56 | SSSM-6 | dfVgkj | 1 | vH;kl e0fo0 eqlkiqj | 332.13 |  | 1 | 1
|  |  | 2 | e0fo0 [ksfj;k |  |  | 0 | 1
|  |  | 3 | e0fo0 fn?kM+h |  |  | 0 | 1
57 | SSSM-7 | dfVgkj | 1 | m0e0fo0 jkepUnziqj | 335.36 |  | 1 | 1
|  |  | 2 | e0fo0 egknsoiqj |  |  | 0 | 1
|  |  | 3 | e0fo0 cq) uxj |  |  | 0 | 1
58 | SSSM-8 | dfVgkj | 1 | m0e0fo0 efu;k | 221.65 |  | 1 | 1
|  |  | 2 | e0fo0 cBSyh |  |  | 0 | 1
59 | SSSM-9 | dfVgkj | 1 | jk0e0fo0 eajxh | 222.46 |  | 1 | 1
|  |  | 2 | vk0e0fo0 jkuhirjk fla/k;k |  |  | 0 | 1
60 | SSSM-10 | dfVgkj | 1 | m0e0fo0 fxnjekjh | 222.01 |  | 1 | 1
|  |  | 2 | e0fo0 Hk.Mkjry |  |  | 0 | 1
61 | SSSM-17 | iwf.kZ;k¡ | 1 | e0fo0 efr;kjiqj | 338.09 |  | 1 | 1
|  |  | 2 | e0fo0 dBSyh |  |  | 0 | 1
|  |  | 3 | e0fo0 ,dEck |  |  | 0 | 1
62 | SSSM-18 | iwf.kZ;k¡ | 1 | e0fo0 iz[kaM dkWyuh | 333.26 |  | 1 | 1
|  |  | 2 | e0fo0 izlkniqj csynkjh |  |  | 0 | 1
|  |  | 3 | e0fo0 dk>k x.ks'kiqj |  |  | 0 | 1
63 | SSSM-19 | iwf.kZ;k¡ | 1 | e0fo0 fiijk | 222.8 |  | 1 | 1
|  |  | 2 | e0fo0 egjktiqj |  |  | 0 | 1
64 | SSSM-20 | iwf.kZ;k¡ | 1 | e0fo0 txSyh | 224.28 |  | 1 | 1
|  |  | 2 | e0fo0 xaxk Hkou [kks[kk |  |  | 0 | 1
65 | SSSM-25 | vjfj;k | 1 | ,e0,l0 xks[kykiqj ch0,e0,l0 | 353.03 |  | 1 | 1
|  |  | 2 | ,e0,l0 csyk fjQwth |  |  | 0 | 1
|  |  | 3 | ,e0,l0 pUnk |  |  | 0 | 1
66 | SSSM-30 | njHkaxk | 1 | e0fo0 Bdqjfu;k¡ | 225.8 |  | 1 | 1
|  |  | 2 | e0fo0 da'kh |  |  | 0 | 1
67 | SSSM-32 | njHkaxk | 1 | mnwZ e0fo0 vyhuxj | 114.27 |  | 1 | 1
68 | SSSM-33 | njHkaxk | 1 | e0fo0 tgkxhj Vksy | 229.19 |  | 1 | 1
|  |  | 2 | e0fo0 vfg;kjh xksV |  |  | 0 | 1
69 | SSSM-36 | njHkaxk | 1 | e0fo0 fdjriqj | 113.75 |  | 1 | 1
91