## SANIK SCHOOL
BSEIDC, PATNA
Progress Report For The Construction of Sanik School (Gopalganj)
Name & Contact No. of EE : Uday Kumar Das (9801575973), AE : Rajiv Kr. (9934204444), AE : Maya Prasad Singh (9973106456)
S.N. | Project | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [12 empty] | Fin. Exp. | Remarks
[8 empty] | LOA | Date of Aggrement | Time of Completion | Not Started | Lay-out | Foundation | PL | Ground Floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | ADMINISTRATION BUILDING (G+2) | Gopalganj | Kuchaikot | 1 | Sanik School | M/S Prakash Construction, Gyatri Mandir Road Kankarbagh | 2832.76 | ISSUED | 100 SBD OF 2012-13 (19.02.13) | 24 Months | [8 empty] | 1 |  |  | MB at Division; Bill Submitted.
2 | ACADEMIC BLOCK (G+2) |  |  | 1 | [14 empty] | 1
3 | HOSTEL BUILDING (G+2) |  |  | 1 | [14 empty] | 1
4 | CADET MESS (G+1) |  |  | 1 | [14 empty] | 1
5 | ELECTRICAL CONTROL ROOM (G.F.) |  |  | 1 | [14 empty] | 1
6 | EXTERNAL BOUNDARY WALL |  |  | 1 | [14 empty] | 1
7 | SITE DEVELOPMENT |  |  | 1 | [7 empty] | 1
8 | GATE WAY |  |  | 1 | [14 empty] | 1
| Total nos. of school |  |  | 8 |  |  | 2832.76 |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0