## List of USS (2)
BSEIDC Ltd. , Patna
Physical Status of USS (Central Fund) - 2009-10 & 2010-11
S.N. | Group No. | UDISE No. | Session | Division | Name of District | Name of Block | Name of School | Name of Agency |  | Date of Commencement | Physical Status | [9 empty] | Remarks | Date of Completion | Total Completion Cost
[11 empty] | Not Start | Layout | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[9 empty] | 2 | [5 empty] | LL | RL | LL | RL
1 | USS-1-1 |  | 2009-10 | Patna East | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | Uma Shankar & Co. Mob.- 9162544014 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4668583
2 | USS-1-2 |  | 2009-10 | Patna East | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | Uma Shankar & Co. Mob.- 9162544014 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4668583
3 | USS-1-3 |  | 2009-10 | Patna East | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | Uma Shankar & Co. Mob.- 9162544014 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4668582
4 | USS-1-4 |  | 2009-10 | Patna East | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | Uma Shankar & Co. Mob.- 9162544014 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4668582
5 | USS-2-1 |  | 2009-10 | Patna East | Nalanda | fxfj;d | eŒfoŒblqvk 9934451313 | Roy Engineers | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop
6 | USS-2-2 |  | 2009-10 | Patna East | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | Roy Engineers | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | Inaugurated | 15.07.2013 | 4254760
7 | USS-2-3 |  | 2009-10 | Patna East | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | Roy Engineers | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | Inaugurated | 15.07.2013 | 4254759
8 | USS-2-4 |  | 2009-10 | Patna East | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | Roy Engineers | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | Inaugurated | 15.07.2013 | 4254760
9 | USS-2-5 |  | 2009-10 | Patna East | Nalanda | uwjljk; | eŒfoŒdqUnh 9798241195 | Roy Engineers | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | 1 | [9 empty] | sufficient land not available, work not possible, Proposal for drop
10 | USS-3-1 |  | 2009-10 | Patna East | Patna | ck<+ | eŒfoŒngkSj 8804003367 | Bihar Sharif Construction Pvt. Ltd. Mob.- 9308021620 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | 1 | [9 empty] | Project Director Instruct to DEO to arrange land with corporation of local public work not possible, Proposal for drop
11 | USS-3-2 |  | 2009-10 | Patna East | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | Bihar Sharif Construction Pvt. Ltd. Mob.- 9308021620 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | Inaugurated | 13.02.2014 | 4838887
12 | USS-3-3 |  | 2009-10 | Patna East | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | Bihar Sharif Construction Pvt. Ltd. Mob.- 9308021620 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | Inaugurated | 13.02.2014 | 4838887
13 | USS-3-4 |  | 2009-10 | Patna East | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | Bihar Sharif Construction Pvt. Ltd. Mob.- 9308021620 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | Inaugurated | 13.02.2014 | 4838888
14 | USS-3-5 |  | 2009-10 | Patna East | Patna | [kq'k:iqj | mRØŒeŒfoŒfueZyhpd 9097610852 | Bihar Sharif Construction Pvt. Ltd. Mob.- 9308021620 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | 1 | [9 empty] | sufficient land not available work not possible, proposal for drop
15 | USS-4-1 |  | 2009-10 | Patna East | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | Vivek and Co. | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4892884
16 | USS-4-2 |  | 2009-10 | Patna East | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | Vivek and Co. | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | [9 empty] | 1 | Inaugurated | 30.05.2013 | 4892883
17 | USS-4-3 |  | 2009-10 | Patna East | Patna | ikyhxat | eŒfoŒHksM+gfj;k 9199997796 | Vivek and Co. | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | 1 | [9 empty] | dispute, work not possible, Proposal for drop
18 | USS-5-1 |  | 2009-10 | Patna East | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | Patliputra Construction | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | Inaugurated | 30.04.2014 | 3302602
19 | USS-5-2 |  | 2009-10 | Patna East | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | Malti Infrastructure Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | Inaugurated | 30.04.2014 | 3302602
20 | USS-5-3 |  | 2009-10 | Patna East | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | Malti Infrastructure Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | Inaugurated | 30.04.2014 | 3302601
21 | USS-5-4 |  | 2009-10 | Patna East | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | Malti Infrastructure Pvt. Ltd. | 138 dated 16.08.2011 | 328 F2 of 2014-15 Dt.-04.09.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 15.07.2015 | 3302601
22 | USS-6-1 |  | 2009-10 | Patna East | Bhojpur | ihjks | eŒfoŒrkj 8969213005 | B K Enterprises | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद |  | 1701676
23 | USS-6-2 |  | 2009-10 | Patna East | Bhojpur | ihjks | mRØŒeŒfoŒ nsopUnk 9386992853 | B K Enterprises | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद |  | 1701676
24 | USS-6-3 |  | 2009-10 | Patna East | Bhojpur | rjkjh | eŒfoŒ[kqVgk¡ 7631530412 | B K Enterprises | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | 1 | [9 empty] | low land available, work not possible
25 | USS-7-1 |  | 2009-10 | Patna East | Bhojpur | fcfg;k¡ | eŒfoŒ:nzuxj 9308401427 | B K Enterprises | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 | [8 empty] | 1 |  | काफी दिनों से कार्य बंद |  | 3082033
26 | USS-7-2 |  | 2009-10 | Patna East | Bhojpur | txnh'kiqj | eŒfoŒtaxynkok¡ 9931492812 | B K Enterprises | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद |  | 1541016
27 | USS-7-3 |  | 2009-10 | Patna East | Bhojpur | 'kkgiqj | eŒfoŒykyw Msjk 8873932298@9973022234 | B K Enterprises | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 |  |  |  |  | 1 | [5 empty] | काफी दिनों से कार्य बंद |  | 1348389
28 | USS-8-1 |  | 2009-10 | Patna East | Bhojpur | vfxvk¡o | eŒfoŒukjk;.kiqj 9852411014 | B K Enterprises | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 1495010
29 | USS-8-2 |  | 2009-10 | Patna East | Bhojpur | cM+gjk | eŒfoŒxqaMh 7739111542 | B K Enterprises | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [6 empty] | 1 |  |  |  | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 1681887
30 | USS-8-3 |  | 2009-10 | Patna East | Bhojpur | mnoUruxj | eŒfoŒds'kksiqj cdjh 9771242640 | B K Enterprises | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 |  |  | 1 | [7 empty] | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 747505
31 | USS-8-4 |  | 2009-10 | Patna East | Bhojpur | dksbyoj | mRØŒeŒfoŒ folquiqjk 9334151672 | B K Enterprises | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [8 empty] | 1 |  | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 2990020
32 | USS-101-1 |  | 2010-11 | Patna East | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | Roy Engineers | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | Inaugurated | 23.02.2016 | 4488550
33 | USS-101-2 |  | 2010-11 | Patna East | Nalanda | Ben | M.S. Akouna 9570951336 | Roy Engineers | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | Inaugurated | 23.02.2016 | 4488550
34 | USS-101-3 |  | 2010-11 | Patna East | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | Roy Engineers | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | Inaugurated | 23.02.2016 | 4488550
35 | USS-101-4 |  | 2010-11 | Patna East | Nalanda | Silao | Urdu.M.S. Barakar 9931004916 | Roy Engineers | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 |  |  |  |  | 1 | [5 empty] | Invalid list |  | 1570993
36 | USS-101-5 |  | 2010-11 | Patna East | Nalanda | Ben | M.S. Ramganj 9135849205 | Roy Engineers | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | Inaugurated | 23.02.2016 | 4488550
37 | USS-102-1 |  | 2010-11 | Patna East | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | Giridhar Gopal Murari | 138 dated 16.08.2011 | 321 F2 2014-15 Dt.-09.09.2014 | [9 empty] | 1 | Inaugurated | 21.05.2015 | 5009332
38 | USS-102-2 |  | 2010-11 | Patna East | Nalanda | Biharsarif | M.S. Majidpur 9570625433 | Arbind Prasad | 138 dated 16.08.2011 | 68 F2 2015-16 Dt.-22.05.2015 | [9 empty] | 1 |  | 25.08.2016 | 5072315
39 | USS-102-3 |  | 2010-11 | Patna East | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | Roy Engineers | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available, work not possible
40 | USS-102-4 |  | 2010-11 | Patna East | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | Krishna Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available, work not possible
41 | USS-102-5 |  | 2010-11 | Patna East | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | Prakash Construction | 138 dated 16.08.2011 | 423 F2 2014-15 Dt.-05.11.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 17.01.2016 | 5312880
42 | USS-102-6 |  | 2010-11 | Patna East | Nalanda | Sarmera | M.S.Singhaul 9934212058 | Rajnish Vats | 138 dated 16.08.2011 | 748 F2 2014-15 Dt.-13.03.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 | 17.01.2016 | 5298192
43 | USS-103-1 |  | 2010-11 | Patna East | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | Ram jee Prasad | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | Inaugurated | 30.09.2014 | 4799022
44 | USS-103-2 |  | 2010-11 | Patna East | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | Puja Engicone | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 |  | 1 | [8 empty] | E/W |  | 239954
45 | USS-103-3 |  | 2010-11 | Patna East | Nalanda | Islampur | M.S. Bargounw 9279149331 | Ram jee Prasad | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | Inaugurated | 30.09.2014 | 4799022
46 | USS-103-4 |  | 2010-11 | Patna East | Nalanda | Islampur | M.S. Banbag 9934487509 | Ram jee Prasad | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | Inaugurated | 30.09.2014 | 4799022
47 | USS-104-1 |  | 2010-11 | Patna East | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | Vikash Kumar Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Insufficient land. Scheme dropped
48 | USS-104-2 |  | 2010-11 | Patna East | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | Vikash Kumar Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Insufficient land. Scheme dropped
49 | USS-104-3 |  | 2010-11 | Patna East | Patna | Barh | U.M.S. Malahi 7250940590 | Vikash Kumar Singh | 138 dated 16.08.2011 | 213 SBD of 2013-14 Dt.-29.01.2014 | [9 empty] | 1 | Inaugurated | 25.10.2015 | 5307982
50 | USS-104-4 |  | 2010-11 | Patna East | Patna | Fatuha | M.S. Gabaspur 9955241716 | Vikash Kumar Singh | 138 dated 16.08.2011 | 213 SBD of 2013-14 Dt.-29.01.2014 | [9 empty] | 1 | Inaugurated | 25.10.2015 | 5307982
51 | USS-105-1 |  | 2010-11 | Patna East | Patna | Patna Sadar | M.S. Khokhna 9135334773 | Shristi Developers Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | Inaugurated | 10.04.2015 | 4890824
52 | USS-105-2 |  | 2010-11 | Patna East | Patna | Patna Sadar | M.S. Marchi 9430934711 | Shristi Developers Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | Inaugurated | 10.04.2015 | 4890824
53 | USS-105-3 |  | 2010-11 | Patna East | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | Shristi Developers Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | Inaugurated | 10.04.2015 | 4890824
54 | USS-105-4 |  | 2010-11 | Patna East | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | Shristi Developers Pvt. Ltd. | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | Inaugurated | 10.04.2015 | 4890823
55 | USS-106-1 |  | 2010-11 | Patna East | Patna | Bihta | M.S. Kateshar 7250695245 | Durga Electric | 138 dated 16.08.2011 |  | 1 | [9 empty] | Low Land about 12'-0", work not possible
56 | USS-106-2 |  | 2010-11 | Patna East | Patna | Bikram | M.S. Barah 8084301353 | Durga Electric | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not regitered to school, work not possible
57 | USS-106-3 |  | 2010-11 | Patna East | Patna | Bihta | M.S. Kanhauli 9386873458 | Durga Electric | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land dispute between School & college, work not possible
58 | USS-107-1 |  | 2010-11 | Patna East | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | Vijay kumar | 138 dated 16.08.2011 | 30 SBD of 2014-15 Dt.- | [9 empty] | 1 | Inaugurated | 15.07.2015 | 5006923
59 | USS-108-1 |  | 2010-11 | Patna East | Bhojpur | Agioan | M.S. Berath 09955434210 | Amrendra Kumar Singh | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | Inaugurated | 20.07.2015 | 5047383
60 | USS-108-2 |  | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | Amrendra Kumar Singh | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | Inaugurated | 20.07.2015 | 5047383
61 | USS-108-3 |  | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | Amrendra Kumar Singh | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | Inaugurated | 20.07.2015 | 5047383
62 | USS-108-4 |  | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | Amrendra Kumar Singh | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 |  | 20.07.2015 | 5047384
63 | USS-108-5 |  | 2010-11 | Patna East | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | Amrendra Kumar Singh | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | 1 | [9 empty] | Land not available, work not possible
64 | USS-109-1 |  | 2010-11 | Patna East | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | Narendra Kumar | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | Inaugurated |  | 5152143
65 | USS-109-2 |  | 2010-11 | Patna East | Bhojpur | Garhani | M.S. Kaup 9708602077 | Narendra Kumar | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [8 empty] | 1 |  |  |  | 4379325
66 | USS-109-3 |  | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | Narendra Kumar | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | Inaugurated |  | 5152143
67 | USS-109-4 |  | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | Narendra Kumar | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | Inaugurated |  | 5152143
68 | USS-109-5 |  | 2010-11 | Patna East | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | Narendra Kumar | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | Inaugurated |  | 5152143
69 | USS-110-1 |  | 2010-11 | Patna East | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | Rakesh Tiwari | 138 dated 16.08.2011 | 768 F2 of 2014-15 Dt.-18.03.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 | 10.07.16 | 4820859
70 | USS-110-2 |  | 2010-11 | Patna East | Bhojpur | Barhara | M.S. Pakri 9304856454 | Rakesh Tiwari | 138 dated 16.08.2011 | 775 F2 of 2014-15 Dt.-29.03.2015 | [7 empty] | 1 |  |  |  |  | 3392991
71 | USS-110-3 |  | 2010-11 | Patna East | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | Ritu Singh | 138 dated 16.08.2011 | 408 F2 of 2014-15 Dt.-27.10.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 25.04.16 | 5114266
72 | USS-110-4 |  | 2010-11 | Patna East | Bhojpur | Koilwar | M.S. Khesarhiyan 9973554537 | Ritu Singh | 138 dated 16.08.2011 | 156 F2 of 2015-16 Dt.-07.07.2015 | [7 empty] | 1 |  |  |  |  | 3633915
73 | USS-110-5 |  | 2010-11 | Patna East | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | Avnish Kumar | 138 dated 16.08.2011 | 311 F2 of 2015-16 Dt.-27.10.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 25.06.16 | 4604381
74 | USS-111-1 |  | 2010-11 | Patna East | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | Sudarshan Mahto | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | Inaugurated | 30.06.2014 | 5121966
75 | USS-111-2 |  | 2010-11 | Patna East | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | Sudarshan Mahto | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | Inaugurated | 30.06.2014 | 5121966
76 | USS-111-3 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | Sudarshan Mahto | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | Inaugurated | 30.06.2014 | 5121965
77 | USS-111-4 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | Sudarshan Mahto | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | Inaugurated | 30.06.2014 | 5121965
78 | USS-112-1 |  | 2010-11 | Patna East | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | Manoj Kumar | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [9 empty] | 1 | Inaugurated | 08.07.2015 | 5197311
79 | USS-112-2 |  | 2010-11 | Patna East | Bhojpur | Bihiyan | M.S. Kouriya 9431438960 | Manoj Kumar | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [7 empty] | 1 |  |  |  |  | 2858524
80 | USS-112-3 |  | 2010-11 | Patna East | Bhojpur | Shahpur | M.S. Jawainiya 8083447757 7677504269 | Manoj Kumar | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [5 empty] | 1 |  |  |  |  | Shuttering (DEBAR) |  | 2078924
81 | USS-112-4 |  | 2010-11 | Patna East | Bhojpur | Shahpur | M.S. Suhiya 9471919316 | Manoj Kumar | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [9 empty] | 1 |  |  | 5197311
82 | USS-113-1 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Gahruan 9472135231 9162748057 | Arvind Kumar | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 |  | 24.12.16 | 4953126
83 | USS-113-2 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Kurmuri 9576176655 | Arvind Kumar | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 |  | 24.12.16 | 4953126
84 | USS-113-3 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Tarari 9631136009 | Arvind Kumar | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 25.04.16 | 4953126
85 | USS-113-4 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | Arvind Kumar | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | Inaugurated | 09.05.15 | 4953125
86 | USS-113-5 |  | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Bagar 9801629878 | Arvind Kumar | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 |  | 24.12.16 | 4953125
87 | USS-114-1 |  | 2010-11 | Patna East | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | Maa khamakhya | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | 1 | [9 empty] | Dispute. Due to Court case & Land Dispute proposal for drop
88 | USS-114-2 |  | 2010-11 | Patna East | Bhojpur | Sahar | M.S. Baruhi 9199571702 | Maa khamakhya | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | Inaugurated | 08.05.2015 | 5103856
89 | USS-114-3 |  | 2010-11 | Patna East | Bhojpur | Ara | M.S. Basantpur 09308735308 | Maa khamakhya | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | Inaugurated | 08.05.2015 | 5103856
90 | USS-114-4 |  | 2010-11 | Patna East | Bhojpur | Sahar | M.S. Nawada 9934483628 | Maa khamakhya | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | Inaugurated | 08.05.2015 | 5103857
91 | USS-9-1 |  | 2009-10 | Patna West | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | Ramchhabila Rai | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | Inaugurated | 30.11.2013 | 4638139
92 | USS-9-2 |  | 2009-10 | Patna West | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | Ramchhabila Rai | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | Inaugurated | 30.11.2013 | 4638139
93 | USS-9-3 |  | 2009-10 | Patna West | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | Ramchhabila Rai | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | Inaugurated | 30.11.2013 | 4638139
94 | USS-9-4 |  | 2009-10 | Patna West | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | Ramchhabila Rai | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | Inaugurated | 30.11.2013 | 4638140
95 | USS-10-1 |  | 2009-10 | Patna West | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | Jai Mata Di Road Const. Pvt. Ltd. | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | Inaugurated |  | 4121306
96 | USS-10-2 |  | 2009-10 | Patna West | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | Jai Mata Di Road Const. Pvt. Ltd. | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | Inaugurated |  | 4121306
97 | USS-10-3 |  | 2009-10 | Patna West | Buxar | czg~eiqj | eŒfoŒegqvkj 7250949713 | Jai Mata Di Road Const. Pvt. Ltd. | 138 dated 16.08.2011 | 13.12.2011 | 1
98 | USS-10-4 |  | 2009-10 | Patna West | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | Jai Mata Di Road Const. Pvt. Ltd. | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | Inaugurated |  | 4121305
99 | USS-11-1 |  | 2009-10 | Patna West | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | Ajay kumar Singh 9934962360 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4247212
100 | USS-11-2 |  | 2009-10 | Patna West | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | Ajay kumar Singh 9934962360 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4247212
101 | USS-11-3 |  | 2009-10 | Patna West | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | Ajay kumar Singh 9934962360 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4247211
102 | USS-11-4 |  | 2009-10 | Patna West | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | Ajay kumar Singh 9934962360 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4247211
103 | USS-12-1 |  | 2009-10 | Patna West | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | Shiv Murat Bind 9934204800 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 05.02.2013 | 4067672
104 | USS-12-2 |  | 2009-10 | Patna West | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | Shiv Murat Bind 9934204800 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 05.02.2013 | 4067672
105 | USS-13-1 |  | 2009-10 | Patna West | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | Anita Singh Mob.- 9955710222/ 9934848051 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 4096220
106 | USS-13-2 |  | 2009-10 | Patna West | Rohtas | f'kolkxj | eŒfoŒxMqjk 9771022208 | Anita Singh Mob.- 9955710222/ 9934848051 | 138 dated 16.08.2011 | 16.1.2012 | 1 | [9 empty] | Foundation work stopped due to local disturbance (Inaugurated school campus sufficient land available & soil test also done Inaugurated schlInaugurated 16.07.2016 Campus but some local public want to construct this buildInaugurated 16.07.2016 Inaugurated other land wich is situated out of campus & no aproach road available & about 800 m(aproxInaugurated 16.07.2016) away from campus
107 | USS-13-3 |  | 2009-10 | Patna West | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | Anita Singh Mob.- 9955710222/ 9934848051 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | Inaugurated | 30.04.2013 | 4096220
108 | USS-13-4 |  | 2009-10 | Patna West | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | Anita Singh Mob.- 9955710222/ 9934848051 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | Inaugurated | 30.04.2013 | 4096219
109 | USS-14-1 |  | 2009-10 | Patna West | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | Bharat Infrastructure 9334125109 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4339127
110 | USS-14-2 |  | 2009-10 | Patna West | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | Bharat Infrastructure 9334125109 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4339127
111 | USS-14-3 |  | 2009-10 | Patna West | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | Bharat Infrastructure 9334125109 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4339127
112 | USS-14-4 |  | 2009-10 | Patna West | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | Bharat Infrastructure 9334125109 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | Inaugurated | 15.09.2013 | 4339127
113 | USS-115-1 |  | 2010-11 | Patna West | Buxar | Buxar | M.S.Nadanw 9234866577 9430015496 | Nithes Raj | 138 dated 16.08.2011 | 25.07.2014 | [8 empty] | 1 |  |  |  | 4228677
114 | USS-115-2 |  | 2010-11 | Patna West | Buxar | Buxar | M.S.Manjharia 9472951603 | Nithes Raj | 138 dated 16.08.2011 | 25.07.2014 | 1 | [9 empty] | No Way
115 | USS-115-3 |  | 2010-11 | Patna West | Buxar | Rajpur | M.S. Khiri 9470753325 | Nithes Raj | 138 dated 16.08.2011 | 25.07.2014 | [8 empty] | 1 |  |  |  | 4228677
116 | USS-115-4 |  | 2010-11 | Patna West | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | Nithes Raj | 138 dated 16.08.2011 | 25.07.2014 | 1 | [9 empty] | Land not available
117 | USS-116 (A) |  | 2010-11 | Patna West | Buxar | Dumraon | M.S.Nuaon 9939391144 | Bablu Kr. Singh | 138 dated 16.08.2011 | 10.10.2014 | [9 empty] | 1 |  | 19.01.2017 | 5423447
118 | USS-116 (B) |  | 2010-11 | Patna West | Buxar | Dumraon | M.S. Kanjharua 9955867071 | Shailendra Choubey | 138 dated 16.08.2011 | 09.10.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 5225721
119 | USS-116 (C) |  | 2010-11 | Patna West | Buxar | Dumraon | M.S. Mathila 9931890937 | Prem Prakash Singh | 138 dated 16.08.2011 | 13.07.2015 | [9 empty] | 1 |  | 27.02.2017 | 4796572
120 | USS-116 (D) |  | 2010-11 | Patna West | Buxar | Dumraon | M.S. Karuaj 9931281346 | Shailendra Choubey | 138 dated 16.08.2011 | 09.10.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 06.10.2015 | 5307275
121 | USS-116 (E) |  | 2010-11 | Patna West | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | Pawan Kr. Dubey | 138 dated 16.08.2011 | 05.11.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 25.01.2017 | 5023105
122 | USS-117 (A) |  | 2010-11 | Patna West | Buxar | Nawanagar | M.S.Pramanpur 9386827434 | Surbendra Kr. & Co. | 138 dated 16.08.2011 |  |  |  | 1
123 | USS-117 (B) |  | 2010-11 | Patna West | Buxar | Ithari | M.S. Barkagaon 8651239720 | Man Mardan Shukla | 138 dated 16.08.2011 | 12.09.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 17.02.2016 | 5659847
124 | USS-117 (C) |  | 2010-11 | Patna West | Buxar | Ithari | M.S. Harpur 9939590039 | Surbendra Kr. & Co. | 138 dated 16.08.2011 | 15.12.2014 | [9 empty] | 1 |  |  | 5102198
125 | USS-117 (D) |  | 2010-11 | Patna West | Buxar | Ithari | M.S. Basawan Kala 7739120173 | Pragati Construction | 138 dated 16.08.2011 | 27.08.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4993510
126 | USS-118-1 |  | 2010-11 | Patna West | Buxar | Simiri | M.S.Dhanpura 9199795834 | Ganga Enterprises | 138 dated 16.08.2011 |  | 1
127 | USS-118-2 |  | 2010-11 | Patna West | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 | Ganga Enterprises | 138 dated 16.08.2011 |  | 1
128 | USS-118-3 |  | 2010-11 | Patna West | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 | Ganga Enterprises | 138 dated 16.08.2011 |  | 1
129 | USS-119 (A) |  | 2010-11 | Patna West | Kaimur | Bhabhua | M.S.Miun | Sanjay Kumar Singh | 138 dated 16.08.2011 | 22.06.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 5685114
130 | USS-119 (B) |  | 2010-11 | Patna West | Kaimur | Bhabhua | M.S.Piliyan | Gupta Dham Construction | 138 dated 16.08.2011 | 03.09.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 5271310
131 | USS-119 (C) |  | 2010-11 | Patna West | Kaimur | Bhabhua | M.S. Mehsuan | Rajeev Ranjan | 138 dated 16.08.2011 | 20.06.2016 | [8 empty] | 1 |  |  |  | 3678107
132 | USS-119 (D) |  | 2010-11 | Patna West | Kaimur | Bhabhua | M.S. Mohan Darwan | Gupta Dham | 138 dated 16.08.2011 | 22.05.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 5762930
133 | USS-120 (A) |  | 2010-11 | Patna West | Kaimur | Ramgarh | M.S.Sijhua | Sudarshan Prasad | 138 dated 16.08.2011 | 30..03.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 | 28.09.2016 | 5940029
134 | USS-120 (B) |  | 2010-11 | Patna West | Kaimur | Ramgarh | M.S.Upari 9939613033 | Sanjay Kumar | 138 dated 16.08.2011 | 20.06.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 | 06.12.2016 | 5743457
135 | USS-120 (C) |  | 2010-11 | Patna West | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | Cancel | 138 dated 16.08.2011 |  | 1 | [9 empty] | Tender Process
136 | USS-120 (D) |  | 2010-11 | Patna West | Kaimur | Nuaon | M.S.Mushiyan 9546505256 | Kamal Technocrate Pvt. Ltd. | 138 dated 16.08.2011 | 16.03.2016 | [8 empty] | 1 |  |  | 12.03.2017 | 4349919
137 | USS-120 (E) |  | 2010-11 | Patna West | Kaimur | Durgawati | U.M.S Nuaon 9199361709 | Randhir Kumar | 138 dated 16.08.2011 | 20.01.2016 | [8 empty] | 1 |  |  |  | 3620620
138 | USS-121 (A) |  | 2010-11 | Patna West | Rohtas | Karakat | M.S.Dewmarkande 8969878557 | Gayatri Enterprises | 138 dated 16.08.2011 | 18.12.2014 | [9 empty] | 1 |  | 15.01.2017 | 4048863
139 | USS-121 (B) |  | 2010-11 | Patna West | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | Krishna Pratap Singh | 138 dated 16.08.2011 | 18.11.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.03.2016 | 5179420
140 | USS-121 (C) |  | 2010-11 | Patna West | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | Krishna Pratap Singh | 138 dated 16.08.2011 | 18.11.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.206 | 5077298
141 | USS-121 (D) |  | 2010-11 | Patna West | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | Anil Ray | 138 dated 16.08.2011 | 03.01.2015 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4957819
142 | USS-121 (E) |  | 2010-11 | Patna West | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | Kamal Technocrate Pvt. Ltd. | 138 dated 16.08.2011 | 11.08.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 10.08.2015 | 4978540
143 | USS-122-1 |  | 2010-11 | Patna West | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4672853
144 | USS-122-2 |  | 2010-11 | Patna West | Rohtas | Dinara | M.S.Sarwan ,8084920823 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 25.09.2016 | 4672853
145 | USS-122-3 |  | 2010-11 | Patna West | Rohtas | Dinara | M.S. Baliyan, 9931111475 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4672853
146 | USS-122-4 |  | 2010-11 | Patna West | Rohtas | Dinara | M.S. Bararhi, 9955083783 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4672853
147 | USS-122-5 |  | 2010-11 | Patna West | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | 1
148 | USS-122-6 |  | 2010-11 | Patna West | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | Vikash Kumar | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 27.09.2016 | 4672852
149 | USS-123-1 |  | 2010-11 | Patna West | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 07.09.2015 | 5067283
150 | USS-123-2 |  | 2010-11 | Patna West | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
151 | USS-123-3 |  | 2010-11 | Patna West | Rohtas | Kochas | M.S. Kuchila, 8002537247 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 07.09.2015 | 5067283
152 | USS-123-4 |  | 2010-11 | Patna West | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
153 | USS-123-5 |  | 2010-11 | Patna West | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
154 | USS-123-6 |  | 2010-11 | Patna West | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | Anita singh | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.03.2015 | 5067284
155 | USS-124-1 |  | 2010-11 | Patna West | Rohtas | Chenari | M.S. Ramgarh 9771746971 | Lallan Sukla | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
156 | USS-124-2 |  | 2010-11 | Patna West | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | Lallan Sukla | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
157 | USS-124-3 |  | 2010-11 | Patna West | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | Lallan Sukla | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
158 | USS-124-4 |  | 2010-11 | Patna West | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | Lallan Sukla | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 18.10.2016 | 4251956
159 | USS-124-5 |  | 2010-11 | Patna West | Rohtas | Sasaram | M.S. Akasi , 9204460486 | Lallan Sukla | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 18.10.2016 | 4251956
160 | USS-125-1 |  | 2010-11 | Patna West | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | S.A.B. Construction | 138 dated 16.08.2011 | 2.2.2013 | [9 empty] | 1 | Inaugurated |  | 4685702
161 | USS-28-1 |  | 2009-10 | Magadh | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2013 | 4100020
162 | USS-28-2 |  | 2009-10 | Magadh | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2013 | 4100020
163 | USS-28-3 |  | 2009-10 | Magadh | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 01.03.2013 | 4100021
164 | USS-28-4 |  | 2009-10 | Magadh | Jehanabad | jruhQjhniqj | mRØŒeŒfoŒyk[kkiqj 9934235714 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Dispute. Letter No.- BSEIDC/MAG/Ex/24/2014 Dt. 30.04.2014 Proposal for Drop. (Land not available)
165 | USS-29-1 |  | 2009-10 | Magadh | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | Anita Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.03.2015 | 4321597
166 | USS-29-2 |  | 2009-10 | Magadh | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | Anita Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 08.03.2016 | 4321597
167 | USS-29-3 |  | 2009-10 | Magadh | Aurangabad | jQhxat | eŒfoŒ[kjks[kj 9006027690 | Anita Singh | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4321596
168 | USS-29-4 |  | 2009-10 | Magadh | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | Anita Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4321596
169 | USS-30-1 |  | 2009-10 | Magadh | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 19.03.2015 | 4177823
170 | USS-30-2 |  | 2009-10 | Magadh | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 01.04.2014 | 4177823
171 | USS-30-3 |  | 2009-10 | Magadh | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.11.2014 | 4177823
172 | USS-30-4 |  | 2009-10 | Magadh | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | Baijnath Nirman India Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.11.2014 | 4177823
173 | USS-31-1 |  | 2009-10 | Magadh | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | Him Shikha Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.12.2014 | 4160193
174 | USS-31-2 |  | 2009-10 | Magadh | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | Him Shikha Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 23.12.2014 | 4160193
175 | USS-31-3 |  | 2009-10 | Magadh | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | Him Shikha Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 23.12.2014 | 4160193
176 | USS-32-1 |  | 2009-10 | Magadh | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 | Waris Buildicon Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 12.04.2016 | 4031017
177 | USS-32-2 |  | 2009-10 | Magadh | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | Waris Buildicon Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2013 | 4031017
178 | USS-32-3 |  | 2009-10 | Magadh | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | Waris Buildicon Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 09.04.2014 | 4031017
179 | USS-32-4 |  | 2009-10 | Magadh | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | Waris Buildicon Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 27.01.2016 | 4031016
180 | USS-33-1 |  | 2009-10 | Magadh | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | Mithlesh Kumar Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2015 | 4256723
181 | USS-33-2 |  | 2009-10 | Magadh | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | Mithlesh Kumar Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2015 | 4256723
182 | USS-33-3 |  | 2009-10 | Magadh | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | Mithlesh Kumar Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2015 | 4256723
183 | USS-33-4 |  | 2009-10 | Magadh | Gaya | cthjxat | eŒfoŒikys 9955418354 | Mithlesh Kumar Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2015 | 4256723
184 | USS-34 A-1 |  | 2009-10 | Magadh | Gaya | ckjkpV~Vh | mRØŒeŒfoŒ/kuxbZ 9931313425 | Er. Ashok Kr. Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Approach road unavailable
185 | USS-34 A-2 |  | 2009-10 | Magadh | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | Er. Ashok Kr. Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.08.2015 | 4501315
186 | USS-34 A-3 |  | 2009-10 | Magadh | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | Er. Ashok Kr. Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.08.2015 | 4501314
187 | USS-34 B-1 |  | 2009-10 | Magadh | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.11.2014 | 5095977
188 | USS-34 B-2 |  | 2009-10 | Magadh | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.11.2014 | 5095977
189 | USS-35-1 |  | 2009-10 | Magadh | Nawada | uoknk | eŒfoŒiVok ljk; 9006212577 | Dhanpat Prasad | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 3020152
190 | USS-35-2 |  | 2009-10 | Magadh | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | Dhanpat Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4314503
191 | USS-35-3 |  | 2009-10 | Magadh | Nawada | jksg 1 | mRØŒeŒfoŒf'k[kjiqj 9661237533 | Dhanpat Prasad | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 3020152
192 | USS-35-4 |  | 2009-10 | Magadh | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | Dhanpat Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4314503
193 | USS-36-1 |  | 2009-10 | Magadh | Nawada | vdcjiqj | eŒfoŒrs;kj | Sujay Bhan Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Approach road unavailable
194 | USS-36-2 |  | 2009-10 | Magadh | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | Sujay Bhan Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.03.2015 | 4200953
195 | USS-36-3 |  | 2009-10 | Magadh | Nawada | fljnyk | eŒfoŒlka< 9771960601 | Sujay Bhan Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.03.2015 | 4200953
196 | USS-143-1 |  | 2010-11 | Magadh | Jehanabad | Kako | M.S.Kajisarai 9934814478 | Kaushlendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.11.2013 | 4901494
197 | USS-143-2 |  | 2010-11 | Magadh | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | Kaushlendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.11.2013 | 4901494
198 | USS-143-3 |  | 2010-11 | Magadh | Jehanabad | Kako | M.S.Pinzour 9931803275 | Kaushlendra Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Insufficient Land
199 | USS-143-4 |  | 2010-11 | Magadh | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | Kaushlendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.11.2013 | 4901495
200 | USS-144 (A) |  | 2010-11 | Magadh | Jehanabad | Hulasganj | M.S.Vira, 9771693433 | Kaushlendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4413483
201 | USS-144 (B) |  | 2010-11 | Magadh | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | Bhupesh Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Not started
202 | USS-144 (C) |  | 2010-11 | Magadh | Jehanabad | Jehanabad | M.S.Bazartali, 9955297199 | Pandooi Construction Company | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3462361
203 | USS-145-1 |  | 2010-11 | Magadh | Nawada | Nawada | U.M.S. Jhunathi, 9631172127 | Pramod Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3712006
204 | USS-145-2 |  | 2010-11 | Magadh | Nawada | Akbarpur | U.M.S. Derma, 9931232692 | Pramod Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3712006
205 | USS-145-3 |  | 2010-11 | Magadh | Nawada | Akbarpur | M.S. Kuhaila, 9771085197 | Pramod Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4367066
206 | USS-145-4 |  | 2010-11 | Magadh | Nawada | Akbarpur | M.S. Paharpur, 9771672098 | Pramod Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3712006
207 | USS-145-5 |  | 2010-11 | Magadh | Nawada | Nawada | M.S. Wermi, 9708857028 | Pramod Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
208 | USS-146 (A) |  | 2010-11 | Magadh | Nawada | Govindpur | M.S. Rampur, 9771867218 | Surendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  | 07.07.2016 | 5197671
209 | USS-146 (B) |  | 2010-11 | Magadh | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | Awadh Kishore Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5154654
210 | USS-146 (C) |  | 2010-11 | Magadh | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | Kiran Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.06.2015 | 5222945
211 | USS-146 (D) |  | 2010-11 | Magadh | Nawada | Pakribarawan | M.S. Ukaorah | Khalid Aziz Siddique | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4821920
212 | USS-146 (E) |  | 2010-11 | Magadh | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | Tender Process | 138 dated 16.08.2011 |  | 1 | [9 empty] | Retender
213 | USS-147-1 |  | 2010-11 | Magadh | Nawada | Narhat | M.S. Khanwa, 9905846666 | Kumar Saroj | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4480450
214 | USS-147-2 |  | 2010-11 | Magadh | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | Kumar Saroj | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4480451
215 | USS-148-1 |  | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Moratala, 9934282506 | C. S. Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3556262
216 | USS-148-2 |  | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | C. S. Construction | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 2091921
217 | USS-148-3 |  | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Bataspur, 9470447309 | C. S. Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3556262
218 | USS-148-4 |  | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 | C. S. Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Not start. Insufficient Land
219 | USS-149 (A) |  | 2010-11 | Magadh | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5148020
220 | USS-149 (B) |  | 2010-11 | Magadh | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 13.05.2016 | 5008684
221 | USS-149 (C) |  | 2010-11 | Magadh | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 18.02.2016 | 4989238
222 | USS-149 (D) |  | 2010-11 | Magadh | Gaya | Imamganj | M.S. Naudiha, 9135294703, 8235212693 | Koela Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 10.03.2016 | 5059171
223 | USS-149 (E) |  | 2010-11 | Magadh | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | Sanju Kumari | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 20.07.2015 | 5380074
224 | USS-150 (A) |  | 2010-11 | Magadh | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | Shyam Bihari Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 31.01.2016 | 4714441
225 | USS-150 (B) |  | 2010-11 | Magadh | Gaya | Tekari | M.S. Urdu Bishnupur, 9771128251, 9135850031 | Mithlesh Kr. Singh | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3925878
226 | USS-150 (C) |  | 2010-11 | Magadh | Gaya | Konch | M.S. Goribigha, 9939408167 | Bishwanath Kumar Bharti | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4384516
227 | USS-150 (D) |  | 2010-11 | Magadh | Gaya | Konch | M.S. Ahiyarpur, 9934008030 | Mithlesh Kr. Singh | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4548801
228 | USS-151-1 |  | 2010-11 | Magadh | Gaya | Bathani | Basic M.S. Radui, 7654409634 | Roy Engineers Mob-9431011395 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.12.2014 | 4727421.9967
229 | USS-151-2 |  | 2010-11 | Magadh | Gaya | Bathani | M.S. Karubigha, 9934427661 | Roy Engineers Mob-9431011395 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.12.2014 | 4727423
230 | USS-151-3 |  | 2010-11 | Magadh | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | Roy Engineers Mob-9431011395 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.12.2014 | 4727423
231 | USS-152-1 |  | 2010-11 | Magadh | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | Sanjeet kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.08.2015 | 4436714
232 | USS-152-2 |  | 2010-11 | Magadh | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | Sanjeet kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4436714
233 | USS-152-3 |  | 2010-11 | Magadh | Gaya | Fatehpur | M.S. Khajuri, 8969107991 | Sanjeet kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4436714
234 | USS-152-4 |  | 2010-11 | Magadh | Gaya | Fatehpur | M.S. Nagwa, 9798270089 | Sanjeet kumar | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3771211
235 | USS-152-5 |  | 2010-11 | Magadh | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | Sanjeet kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.08.2015 | 4436714
236 | USS-152-6 |  | 2010-11 | Magadh | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | Sanjeet kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 13.08.2015 | 4436714
237 | USS-153 (A) |  | 2010-11 | Magadh | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | Koela Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4947507
238 | USS-153 (B) |  | 2010-11 | Magadh | Gaya | Guraru | M.S. Manjhar, 9572789270 | Mithlesh Kr. Singh | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 3746778
239 | USS-153 (C) |  | 2010-11 | Magadh | Gaya | Amas | M.S. Baliyari, 9570551566, 8294856371, 8051934469 | Keola Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 2281952
240 | USS-153 (D) |  | 2010-11 | Magadh | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | Rajeev Ranjan | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
241 | USS-154-1 |  | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | Mateshwari Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.02.2015 | 5132054
242 | USS-154-2 |  | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | Mateshwari Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.02.2015 | 5132054
243 | USS-154-3 |  | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | Mateshwari Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available. (PROPOSED FOR DROP)
244 | USS-154-4 |  | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | Mateshwari Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.01.2015 | 5132053
245 | USS-154-5 |  | 2010-11 | Magadh | Aurangabad | Deo | M.S. Vijouli, 9801123435 | Mateshwari Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.02.2015 | 5132053
246 | USS-155-1 |  | 2010-11 | Magadh | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | Raj Mangal Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 13.12.2014 | 4953704
247 | USS-155-2 |  | 2010-11 | Magadh | Aurangabad | Obra | M.S. Ratwar, 9931418907 | Raj Mangal Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.12.2014 | 4953705
248 | USS-155-3 |  | 2010-11 | Magadh | Aurangabad | Obra | M.S. Tejpur, 9973299799 | Raj Mangal Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available. (PROPOSED FOR DROP.- LETTER NO.BSEIDC/MAG/EX/377/2015 DATED- 28/09/2015)
249 | USS-155-4 |  | 2010-11 | Magadh | Aurangabad | Obra | M.S. Karsawan, 9470488343 | Raj Mangal Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.12.2014 | 4953704
250 | USS-156-1 |  | 2010-11 | Magadh | Aurangabad | Haspura | M.S. Piru, 9135064392 | Mateshwari Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Encrochment
251 | USS-156-2 |  | 2010-11 | Magadh | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | Mateshwari Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
252 | USS-156-3 |  | 2010-11 | Magadh | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | Mateshwari Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4930998
253 | USS-157 (A) |  | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | Kamdeo Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 25.08.2015 | 5204445
254 | USS-157 (B) |  | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Pogar, 9973150471 | Maa Sharda Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3231282
255 | USS-157 (C) |  | 2010-11 | Magadh | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | Sambhu Saran Singh | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 08.09.2015 | 5226367
256 | USS-157 (D) |  | 2010-11 | Magadh | Aurangabad | Madanpur | M.S. Saliya, 9955803641 | Maa Sharda Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2514834
257 | USS-157 (E) |  | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Danai, 9097351245 | Ms Manglam Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 2936509
258 | USS-20-1 |  | 2009-10 | Munger | Munger | gosyh [kM+xiqj | eŒfoŒj?kqukFkiqj | D P Maheshwari Construction India Pvt. Ltd. Mob.- 9162255747 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Problem
259 | USS-20-2 |  | 2009-10 | Munger | Munger | eqaxsj lnj | eŒfoŒVhdkjkeiqj 9431612789 | D P Maheshwari Construction India Pvt. Ltd. Mob.- 9162255747 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Problem
260 | USS-20-3 |  | 2009-10 | Munger | Munger | /kjgjk | eŒfoŒegjuk 9504681361@9852445511 | D P Maheshwari Construction India Pvt. Ltd. Mob.- 9162255747 | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 1491139
261 | USS-21-1 |  | 2009-10 | Munger | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | Arbind Prasad Mob.- 9431258802/ 8757503857 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.03.2013 | 4282252
262 | USS-22-1 |  | 2009-10 | Munger | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | Rajendra Kumar 9939195777 / 9473044777 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 2014-03-01 | 4451460
263 | USS-22-2 |  | 2009-10 | Munger | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | Rajendra Kumar 9939195777 / 9473044777 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 22.07.2014 | 4451460
264 | USS-22-3 |  | 2009-10 | Munger | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | Rajendra Kumar 9939195777 / 9473044777 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 22.07.2014 | 4451460
265 | USS-23-1 |  | 2009-10 | Munger | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | Lal Rupak Kumar Singh 9576391000/ 8809977286 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 26.08.2014 | 4514149
266 | USS-23-2 |  | 2009-10 | Munger | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | Lal Rupak Kumar Singh 9576391000/ 8809977286 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 26.08.2014 | 4514149
267 | USS-23-3 |  | 2009-10 | Munger | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | Lal Rupak Kumar Singh 9576391000/ 8809977286 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 26.08.2014 | 4514149
268 | USS-23-4 |  | 2009-10 | Munger | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | Lal Rupak Kumar Singh 9576391000/ 8809977286 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 26.08.2014 | 4514150
269 | USS-24-1 |  | 2009-10 | Munger | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | Ray & Raj Engineering Pvt. Ltd. 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.05.2013 | 4810561
270 | USS-24-2 |  | 2009-10 | Munger | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | Ray & Raj Engineering Pvt. Ltd. 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.05.2013 | 4810561
271 | USS-24-3 |  | 2009-10 | Munger | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | Ray & Raj Engineering Pvt. Ltd. 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 16.06.2013 | 4810562
272 | USS-25-1 |  | 2009-10 | Munger | Begusarai | cfy;k | eŒfoŒelwnuiqj 9955252445 | Brij Deo Singh 9430885959 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | Roof Casted , work stopped after R.C. , due to land dispute |  | 2219305
273 | USS-25-2 |  | 2009-10 | Munger | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | Brij Deo Singh 9430885959 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4931792
274 | USS-25-3 |  | 2009-10 | Munger | Begusarai | lkgsciqj deky | eŒfoŒfo".kqiqj vkgksd 9534757293 | Brij Deo Singh 9430885959 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
275 | USS-26-1 |  | 2009-10 | Munger | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | Daya Ram Singh Mob.- 9801031299 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 16.07.2013 | 4780393
276 | USS-26-2 |  | 2009-10 | Munger | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | Daya Ram Singh Mob.- 9801031299 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.07.2013 | 4780393
277 | USS-27-1 |  | 2009-10 | Munger | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | Rajendra Singh Const. Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4920833
278 | USS-27-2 |  | 2009-10 | Munger | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | Rajendra Singh Const. Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4920833
279 | USS-27-3 |  | 2009-10 | Munger | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | Rajendra Singh Const. Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4920833
280 | USS-27-4 |  | 2009-10 | Munger | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | Rajendra Singh Const. Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4920833
281 | USS-27-5 |  | 2009-10 | Munger | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | Rajendra Singh Const. Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4920832
282 | USS-132-1 |  | 2010-11 | Munger | Sheikhpura | Barbigha | M.S.Keuti | Arbind Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.01.2015 | 4825065
283 | USS-132-2 |  | 2010-11 | Munger | Sheikhpura | SheKhpura | M.S.Lodipur | Arbind Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.01.2015 | 4825065
284 | USS-132-3 |  | 2010-11 | Munger | Sheikhpura | Chewara | M.S.Lahana | Arbind Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.01.2015 | 4825065
285 | USS-132-4 |  | 2010-11 | Munger | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | Arbind Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.01.2015 | 4825065
286 | USS-132-5 |  | 2010-11 | Munger | Sheikhpura | Ariari | M.S.Husainawad | Arbind Prasad | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.01.2015 | 4825065
287 | USS-133(A) |  | 2010-11 | Munger | Lakhisarai | Barahiya | M.S.Pali 9546977875 | Rajnis Vats | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 04.02.2016 | 5172716
288 | USS-133(B) |  | 2010-11 | Munger | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | Rajnis Vats | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land dispute
289 | USS-133(C) |  | 2010-11 | Munger | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | Manglam Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available. Dropped
290 | USS-133(D) |  | 2010-11 | Munger | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | Ashok Kumar, Sheikpura | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 05.07.2015 | 5314780
291 | USS-133(E) |  | 2010-11 | Munger | Lakhisarai | Suryagarha | U.M.S. Lahasaurwa 9631695175, 8434346388 | Ibha Devi, Kamleshwar Sthan, Ward No.-11, Mokama, Patna | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 2615151
292 | USS-133(F) |  | 2010-11 | Munger | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | Ram Naresh Sharma | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5278158
293 | USS-134-1 |  | 2010-11 | Munger | Jamui | Sono | M.S.Buijhayt 09631584296 | A. K. Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 2651801
294 | USS-135-1 |  | 2010-11 | Munger | Munger | Asarganj | M.S.Chakhand 9135065232 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4857416.9967
295 | USS-135-2 |  | 2010-11 | Munger | Munger | Asarganj | M.S. Beran 9204931976 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4857418
296 | USS-135-3 |  | 2010-11 | Munger | Munger | Tarapur | M.S. Mahamadpur 9709507263 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4857418
297 | USS-136-1 |  | 2010-11 | Munger | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5300308
298 | USS-136-2 |  | 2010-11 | Munger | Munger | Sangrampur | M.S.Khapra 9934832035 | Rajendra Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
299 | USS-136-3 |  | 2010-11 | Munger | Munger | Sangrampur | M.S.Katiyari 9199782900 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5300308
300 | USS-137-1 |  | 2010-11 | Munger | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | B. S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4878010
301 | USS-137-2 |  | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | B. S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4878010
302 | USS-137-3 |  | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | B. S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4878011
303 | USS-137-4 |  | 2010-11 | Munger | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | B. S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4878011
304 | USS-137-5 |  | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | B. S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4878011
305 | USS-138-1 |  | 2010-11 | Munger | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | Ambey Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
306 | USS-138-2 |  | 2010-11 | Munger | Begusarai | Begusarai | M.S.Bharra 9204202640 | Ambey Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3658867
307 | USS-138-3 |  | 2010-11 | Munger | Begusarai | Begusarai | M.S.Babasudebpur 9934708295, 88777402400 | Ambey Construction | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1951395
308 | USS-138-4 |  | 2010-11 | Munger | Begusarai | Matihani | M.S.Richiyahi Nayartol 9973647476, 9608273410 | Ambey Construction | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1951395
309 | USS-138-5 |  | 2010-11 | Munger | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | Ambey Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
310 | USS-139-1 |  | 2010-11 | Munger | Begusarai | Bachhawara | M.S.Dadupur 9801471859 | Ray & Raj Engineering Pvt. Ltd. Mob.- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4578151
311 | USS-139-2 |  | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | Ray & Raj Engineering Pvt. Ltd. Mob.- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4578151
312 | USS-139-3 |  | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | Ray & Raj Engineering Pvt. Ltd. Mob.- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4578151
313 | USS-139-4 |  | 2010-11 | Munger | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | Ray & Raj Engineering Pvt. Ltd. Mob.- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4578151
314 | USS-139-5 |  | 2010-11 | Munger | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | Ray & Raj Engineering Pvt. Ltd. Mob.- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4578152
315 | USS-140-1 |  | 2010-11 | Munger | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | Ray & Raj Engineering Pvt. Ltd. Mob.-9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4799563
316 | USS-140-2 |  | 2010-11 | Munger | Begusarai | Dandari | M.S.Katarmala 9709640304 | Ray & Raj Engineering Pvt. Ltd. Mob.-9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4799563
317 | USS-140-3 |  | 2010-11 | Munger | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | Ray & Raj Engineering Pvt. Ltd. Mob.-9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4799563
318 | USS-141 (A) |  | 2010-11 | Munger | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 | Ambey Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5738627
319 | USS-141 (B) |  | 2010-11 | Munger | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 | Ambey Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5322965
320 | USS-141 (C) |  | 2010-11 | Munger | Khagaria | Khagaria | M.S.Nanku Mandal Tola 9955646986 | Ambey Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land dispute in court
321 | USS-141 (D) |  | 2010-11 | Munger | Khagaria | Khagaria | M.S.Mathar 9771388437 | Regal Infratrading Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 28.03.2016 | 6084753
322 | USS-142-1 |  | 2010-11 | Munger | Khagaria | Beldaur | M.S.Kainjari 7549429234 | Rajendra Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
323 | USS-142-2 |  | 2010-11 | Munger | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5121092
324 | USS-142-3 |  | 2010-11 | Munger | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | Rajendra Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.03.2015 | 5121092
325 | USS-15-1 |  | 2009-10 | Bhagalpur | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4515294
326 | USS-15-2 |  | 2009-10 | Bhagalpur | Bhagalpur | Sultanganj | MS Udadih 9801583582 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4515295
327 | USS-15-3 |  | 2009-10 | Bhagalpur | Bhagalpur | NathNagar | MS Ajmeribariya 8969037136 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | SLOW WORK( 2ND DEBAR LETTER ISSUED)(STOPPED FROM MARCH 2014() |  | 1806117
328 | USS-15-4 |  | 2009-10 | Bhagalpur | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4515295
329 | USS-16-1 |  | 2009-10 | Bhagalpur | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4242445
330 | USS-16-2 |  | 2009-10 | Bhagalpur | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4242445
331 | USS-16-3 |  | 2009-10 | Bhagalpur | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4242445
332 | USS-16-4 |  | 2009-10 | Bhagalpur | Bhagalpur | Goradih | MS Garhotiya 9931865594 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4242446
333 | USS-17-1 |  | 2009-10 | Bhagalpur | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.09.2013 | 4862662
334 | USS-17-2 |  | 2009-10 | Bhagalpur | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.09.2013 | 4862662
335 | USS-17-3 |  | 2009-10 | Bhagalpur | Bhagalpur | Bihpur | MS Kaharour 9934602158 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Droped, Land not available
336 | USS-17-4 |  | 2009-10 | Bhagalpur | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.09.2013 | 4862662
337 | USS-18-1 |  | 2009-10 | Bhagalpur | Banka | Barahat | MS Saharna 9431689507/ | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 01.07.2014 | 4242879
338 | USS-18-2 |  | 2009-10 | Bhagalpur | Banka | Bounsi | MS Bishanpur 9006554728 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 04.12.2014 | 4242879
339 | USS-18-3 |  | 2009-10 | Bhagalpur | Banka | Dhouriya | MS Bhatuachak 9955916141 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.03.2014 | 4242879
340 | USS-18-4 |  | 2009-10 | Bhagalpur | Banka | Rajoun | MS Majhgay 9771243197 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.10.2014 | 4242879
341 | USS-19-1 |  | 2009-10 | Bhagalpur | Banka | Amarpur | MS Bhadariya 9939749402 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 3530044
342 | USS-19-2 |  | 2009-10 | Bhagalpur | Banka | Chandan | UMS Asudha-Mukunda 9199722081 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [9 empty] | 1 |  | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353542
343 | USS-19-3 |  | 2009-10 | Bhagalpur | Banka | Katoriya | MS Bhorsar 9304136524 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [9 empty] | 1 |  | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353542
344 | USS-19-4 |  | 2009-10 | Bhagalpur | Banka | Belhar | UMS Nagel 9934928705 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [9 empty] | 1 |  | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353541
345 | USS-19-5 |  | 2009-10 | Bhagalpur | Banka | Shambhuganj | MS Rajghat 9199067916 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [9 empty] | 1 |  | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353541
346 | USS-126 (A) |  | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S.Basudeopur Bhaluya 9801295281 | Dinesh Yadav | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 5429502
347 | USS-126 (B) |  | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Handover |  | 4917175
348 | USS-126 (C) |  | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Handover |  | 5052732
349 | USS-126 (D) |  | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Saur 9430428851 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 |  | 24.12.2016 | 4942059
350 | USS-127 (A) |  | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | [10 empty] | 1 |  | 21.01.2017 | 3789711
351 | USS-127 (B) |  | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | [6 empty] | 1
352 | USS-127 (C) |  | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5240787
353 | USS-127 (D) |  | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Ekchari Diyara 9507752647, 9934426205 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | [10 empty] | 1 |  | 10.02.2017 | 5630115
354 | USS-127 (E) |  | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4882446
355 | USS-128 (A) |  | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Birnaugha 9955198006 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 |  | 26.01.2017 | 5048149
356 | USS-128 (B) |  | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 28.12.2015 | 5401431
357 | USS-128 (C) |  | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5023873
358 | USS-128 (D) |  | 2010-11 | Bhagalpur | Bhagalpur | Sabaur | Govt. M.S.Kurpat 9204660635, 9931729153 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | LETTER FOR DEBAR TO C.E. |  | 2719586
359 | USS-129 (A) |  | 2010-11 | Bhagalpur | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | LAND GIVEN BY PRINCIPAL ON 19-12-16. |  | 1743984
360 | USS-129 (B) |  | 2010-11 | Bhagalpur | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5619506
361 | USS-130-1 |  | 2010-11 | Bhagalpur | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.04.2014 | 5277527
362 | USS-130-2 |  | 2010-11 | Bhagalpur | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.04.2014 | 5277528
363 | USS-130-3 |  | 2010-11 | Bhagalpur | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.04.2014 | 5277528
364 | USS-130-4 |  | 2010-11 | Bhagalpur | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.04.2014 | 5277528
365 | USS-130-5 |  | 2010-11 | Bhagalpur | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.04.2014 | 5277528
366 | USS-131-1 |  | 2010-11 | Bhagalpur | Banka | Amarpur | M.S.Surihari 9931727384 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | [9 empty] | 1 |  | LETTER FOR DEBAR TO C.E. |  | 4156210
367 | USS-131-2 |  | 2010-11 | Bhagalpur | Banka | Belhar | M.S.Hatiyadadha 8521126388 | Shankar Sharan Singh Mob.- 9934724833 | 138 dated 16.08.2011 | [9 empty] | 1 |  | LETTER FOR DEBAR TO C.E. |  | 4156210
368 | USS-131-3 |  | 2010-11 | Bhagalpur | Banka | Dhoraiya | U.M.S.Jharkha 9934883358 | Shankar Sharan Singh Mob.- 9934724833 | 138 dated 16.08.2011 | [9 empty] | 1 |  | LETTER FOR DEBAR TO C.E. |  | 4156210
369 | USS-71-1 |  | 2009-10 | Kosi | Madhepura | Madhepura | M/S Bharahi Bazar 9852057904 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Dispute
370 | USS-71-2 |  | 2009-10 | Kosi | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5044198
371 | USS-71-3 |  | 2009-10 | Kosi | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5044198
372 | USS-71-4 |  | 2009-10 | Kosi | Madhepura | Sigheshwar | M/S Singyon 9430633497 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5044198
373 | USS-72-1 |  | 2009-10 | Kosi | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5078932
374 | USS-72-2 |  | 2009-10 | Kosi | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5078932
375 | USS-72-3 |  | 2009-10 | Kosi | Madhepura | Alamnagar | M/S Bargaon 9939489984 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.06.2015 | 5078933
376 | USS-73-1 |  | 2009-10 | Kosi | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5274930
377 | USS-73-2 |  | 2009-10 | Kosi | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5274930
378 | USS-73-3 |  | 2009-10 | Kosi | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.12.2014 | 5274931
379 | USS-74-1 |  | 2009-10 | Kosi | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 3967262
380 | USS-74-2 |  | 2009-10 | Kosi | Saharsa | Simri Bakhtiyarpur | M/S Ghoghsam 9471654377 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | Work Stopped |  | 991816
381 | USS-74-3 |  | 2009-10 | Kosi | Saharsa | Mahishi | M/S Jhara 9430696742 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 3967263
382 | USS-75-1 |  | 2009-10 | Kosi | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.05.2014 | 5418531
383 | USS-75-2 |  | 2009-10 | Kosi | Supaul | Chatapur | M/S Madhubani 9631295927 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.05.2014 | 5418531
384 | USS-75-3 |  | 2009-10 | Kosi | Supaul | Marauna | M/S Parikoch 9931662963 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.05.2014 | 5418531
385 | USS-75-4 |  | 2009-10 | Kosi | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.05.2014 | 5418530
386 | USS-76-1 |  | 2009-10 | Kosi | Supaul | Kishanpur | M/S Phulwaria 8298274284 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.05.2014 | 4984565
387 | USS-76-2 |  | 2009-10 | Kosi | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.05.2014 | 4984565
388 | USS-76-3 |  | 2009-10 | Kosi | Supaul | Supaul | M/S Kariho 9430029088 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.05.2014 | 4984565
389 | USS-76-4 |  | 2009-10 | Kosi | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.05.2014 | 4984564
390 | USS-199C |  | 2010-11 | Kosi | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | Dinesh Yadav | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 19.12.2015 | 5055354
391 | USS-199D-1 |  | 2010-11 | Kosi | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5460744
392 | USS-199 D-2 |  | 2010-11 | Kosi | Madhepura | Singheshwar | Middle School Barhari 9661376885 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.01.2015 | 5460745
393 | USS-199D-3 |  | 2010-11 | Kosi | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
394 | USS-77-1 | 10072000701 | 2009-10 | Purnea | Araria | Bhargama | उत्क्र॰म॰वि॰रहड़िया | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | Inaugurated | 2015-06-02 | 5194053
395 | USS-77-2 | 10071301902 | 2009-10 | Purnea | Araria | Raniganj | बालिका म॰वि॰गुणवती 9771105449 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | Inaugurated | 2015-03-03 | 5194053
396 | USS-77-3 | 10071304802 | 2009-10 | Purnea | Araria | Raniganj | म॰वि॰परमानंदपुर | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | Inaugurated | 23/04/2015 | 5194053
397 | USS-77-4 | 10071901901 | 2009-10 | Purnea | Araria | Narpatganj | म॰वि॰नोनिया टोला चकला | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | Inaugurated | 2015-12-08 | 5194051
398 | USS-78-1 | 10071809001 | 2009-10 | Purnea | Araria | Farbisganj | म॰वि॰मधुबनी 9661601762 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | Inaugurated | 22/08/2015 | 6300438
399 | USS-78-2 | 10071809401 | 2009-10 | Purnea | Araria | Farbisganj | म॰वि॰टेढ़ी मुसहरी | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | Inaugurated | 14/01/2015 | 6300438
400 | USS-78-3 | 10071206001 | 2009-10 | Purnea | Araria | Araria | म॰वि॰पैकटोला | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | Inaugurated | 14/01/2015 | 6300438
401 | USS-78-4 | 10071203201 | 2009-10 | Purnea | Araria | Araria | म॰वि॰बाँसबाड़ी 9430264342 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | Inaugurated | 2015-08-03 | 6300437
402 | USS-79-1 | 10071701201 | 2009-10 | Purnea | Araria | Kursakanta | म॰वि॰कपारफोड़ा | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | Inaugurated | 28/02/2014 | 5571632
403 | USS-79-2 | 10071501001 | 2009-10 | Purnea | Araria | Sikti | म॰वि॰सोहागमाड़ों | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | Inaugurated | 28/02/2014 | 5571632
404 | USS-79-3 | 10071406401 | 2009-10 | Purnea | Araria | Jokihat | म॰वि॰भूना 9570679546 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | 1 | [9 empty] | May be Drop. Final bill
405 | USS-79-4 | 10071606801 | 2009-10 | Purnea | Araria | Palasi | म॰वि॰रूपैल मधैल | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | Inaugurated | 28/02/2014 | 5571632
406 | USS-80-1 | 10082500101 | 2009-10 | Purnea | Kishanganj | Dighalbank | म॰वि॰हरवाडंगा | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | Inaugurated |  | 5148963
407 | USS-80-2 | 10082405002 | 2009-10 | Purnea | Kishanganj | Thakurganj | म॰वि॰जंगलभीटा | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | Inaugurated |  | 5148963
408 | USS-80-3 | 10082705601 | 2009-10 | Purnea | Kishanganj | Kochadhaman | म॰वि॰धनपुरा 9470868499 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | Inaugurated |  | 5148963
409 | USS-80-4 | 10082304401 | 2009-10 | Purnea | Kishanganj | Pothiya | म॰वि॰हरिपोखर क्रांतिगाछ 9430677962 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | Inaugurated |  | 5148963
410 | USS-80-5 | 10082601401 | 2009-10 | Purnea | Kishanganj | Bahadurganj | म॰वि॰हरिभाषा 9471834254 | Md. Shafique Alam Mob. - 9431259842 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | Inaugurated |  | 5148964
411 | USS-81-1 | 10090605201 | 2009-10 | Purnea | Purnea | K Nagar | आदर्श म॰वि॰परोरा 9631003614 | Shankar Sharan Singh Mob.- 9934724833 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated | 19/12/2014 | 4622720
412 | USS-81-2 | 10090904503 | 2009-10 | Purnea | Purnea | Kasba | उत्क्र॰ म॰ वि॰ कदवा 9006717685/9162698638 | Shankar Sharan Singh Mob.- 9934724833 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated | 2015-12-09 | 4622720
413 | USS-81-3 | 10091400301 | 2009-10 | Purnea | Purnea | Dagrua | म॰वि॰मोहम्मदपुर 8877902279/9852305617 | Shankar Sharan Singh Mob.- 9934724833 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated |  | 4622719
414 | USS-82-1 | 10091100601 | 2009-10 | Purnea | Purnea | Dhamdaha | आदर्श म॰वि॰विशनपुर 8002692294 | Shankar Sharan Singh Mob. - 9934724833 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated | 31.07.2014 | 4586049
415 | USS-82-2 | 10091008201 | 2009-10 | Purnea | Purnea | Bhawanipur | म॰वि॰ब्रह्मज्ञानी 9931249419 | Shankar Sharan Singh Mob. - 9934724833 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated | 31.07.2014 | 4586049
416 | USS-82-3 | 10090800503 | 2009-10 | Purnea | Purnea | Rupauli | म॰वि॰लालगंज 9934565697 | Shankar Sharan Singh Mob. - 9934724833 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated 16.07.2016 | 31.07.2014 | 4586049
417 | USS-82-4 | 10090700101 | 2009-10 | Purnea | Purnea | Banmankhi | म॰वि॰जानकी नगर हाट 9430675018 | Shankar Sharan Singh Mob. - 9934724833 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | Inaugurated | 31.07.2014 | 4586048
418 | USS-83-1 | 10090200101 | 2009-10 | Purnea | Purnea | Vayasi | म॰वि॰आसजा मबैया 9931676786 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | Avaibility Of land after one year,Contractor not interested in work now
419 | USS-83-2 | 10090300401 | 2009-10 | Purnea | Purnea | Amaur | म॰वि॰मच्छट्टा 9470487168/9934622591 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | Avaibility Of land after one year,Contractor not interested in work now
420 | USS-83-3 | 10090105101 | 2009-10 | Purnea | Purnea | Vaisa | म॰वि॰मालोपाड़ा 9939083102 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | Avaibility Of land after one year,Contractor not interested in work now
421 | USS-84-1 | 10100908601 | 2009-10 | Purnea | Katihar | Balrampur | म॰वि॰झलझली 9434962404/8986444230 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | No Land, Proposal for Drop
422 | USS-84-2 | 10101104501 | 2009-10 | Purnea | Katihar | Barsoi | म॰ वि॰ बसलगांव 9126846409 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | Inaugurated | 14/07/2014 | 5113164
423 | USS-84-3 | 10101107001 | 2009-10 | Purnea | Katihar | Barsoi | म॰ वि॰ ढट्ठा 9471674809 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | Inaugurated | 2014-02-07 | 5113164
424 | USS-84-4 | 10101201201 | 2009-10 | Purnea | Katihar | Ajamnagar | म॰ वि॰ जलकी 9470423557/ 8877799621 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | Inaugurated | 2014-12-07 | 5113165
425 | USS-85-1 | 10100602003 | 2009-10 | Purnea | Katihar | Barari | म॰वि॰बकिया सुखाय 9572154446 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | Land not available (E.E letter No.-731/14-15 Dt.28.10.14)
426 | USS-85-2 | 10101600701 | 2009-10 | Purnea | Katihar | Manihari | म॰वि॰पटनी नारायणपुर 9430970158 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | Inaugurated |  | 4987532
427 | USS-85-3 | 10100801202 | 2009-10 | Purnea | Katihar | Phalka | म॰वि॰झगरूचक 0431668067 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 |  | 28/09/2015 | 4987532
428 | USS-85-4 | 10100400902 | 2009-10 | Purnea | Katihar | Kodha | म॰वि॰शिशिया 9431625914 | Bala Ji Construction Mob. - 9006169540 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 |  |  | 4987532
429 | USS-86-1 | 10101503001 | 2009-10 | Purnea | Katihar | Ahamdabad | म॰वि॰दिल्ली दिवानगंज 9431667161/7631741488 | Umakant Singh Mob. - 9431229132 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | May be Drop
430 | USS-86-2 | 10101025401 | 2009-10 | Purnea | Katihar | Kadwa | म॰वि॰आशयानी 8986509086 | Umakant Singh Mob. - 9431229132 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | Inaugurated | 15/06/2013 | 4952737
431 | USS-86-3 | 10101003801 | 2009-10 | Purnea | Katihar | Kadwa | म॰वि॰चौकी 9470208190 | Umakant Singh Mob. - 9431229132 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | May be Drop
432 | USS-194-1 | 10090308501 | 2010-11 | Purnea | Purnea | Amaur | U. M. S. Bagdar 9939096309 | Shining Madhusudan Construction | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | Inaugurated | 01.08.2015 | 5267661
433 | USS-194-2 | 10090605401 | 2010-11 | Purnea | Purnea | K. Nagar | M S Gauasi 9473124829 | Shining Madhusudan Construction | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
434 | USS-194-3 | 10090400901 | 2010-11 | Purnea | Purnea | Purnia East | M S Maranga 9939732346 | Shining Madhusudan Construction | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
435 | USS-194-4 | 10090208201 | 2010-11 | Purnea | Purnea | Rupauli | M. S. Bairiya 9434821065 | Shining Madhusudan Construction | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
436 | USS-195-1 | 10101503101 | 2010-11 | Purnea | Katihar | Amdabad | M. S. Laxmipur Daiwa 7549854721 | Anil Kumar Singh | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3937720
437 | USS-195-2 | 10101602701 | 2010-11 | Purnea | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 | Anil Kumar Singh | 138 dated 16.08.2011 |  | 1 | [9 empty] | Not start. Agreement not done
438 | USS-195-3 | 10101402001 | 2010-11 | Purnea | Katihar | Mansahi | Middle School Mohanpur 9472890120 | Anil Kumar Singh | 138 dated 16.08.2011 | 15-F2 2016-17 (26.4.16) | [8 empty] | 1 |  |  |  | 5018863
439 | USS-196(A) | 10101303001 | 2010-11 | Purnea | Katihar | Pranpur | Middle School Kast Hawar 8809776384 9162325809 | Birendra Kumar Singh, Katihar | 138 dated 16.08.2011 | 525F₂ of 14-15 (16.12.14) | [5 empty] | 1 | [6 empty] | 1627604
440 | USS-196(B) | 10101207601 | 2010-11 | Purnea | Katihar | Ajamnagar | Middle School Arihana 8809322797 | Birendra Kr. Singh, Katihar | 138 dated 16.08.2011 | 184F₂ of 15-16 (06.08.15) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 4749252
441 | USS-196(C) | 10101206701 | 2010-11 | Purnea | Katihar | Ajamnagar | Middle School Dhena Baghchhala 9801372634 | Birendra Kumar Singh, Katihar | 138 dated 16.08.2011 | 535F₂ of 14-15 (17.12.14) | [8 empty] | 1 |  |  |  | 4692608
442 | USS-196(D) | 10101303101 | 2010-11 | Purnea | Katihar | Pranpur | Middle School Ghanhar Vighocha 9939688768 | Birendra Kumar Singh, Katihar | 138 dated 16.08.2011 | 505F₂ of 14-15 (12.12.14) | [8 empty] | 1 |  |  |  | 3827150
443 | USS-197(A) | 10101100301 | 2010-11 | Purnea | Katihar | Barsoi | Middle School Barsoi Ghat 9431626189 | Birendra Kumar Singh, Katihar | 138 dated 16.08.2011 | 185F₂ of 15-16 (06.08.15) | [8 empty] | 1 |  |  |  | 4773701
444 | USS-197(B) | 10100201502 | 2010-11 | Purnea | Katihar | Dhankhora | Middle School Durgasthan Dhankhora 9431869787 | Santosh Kumar, Katihar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available |  | 0
445 | USS-197(C) | 10100402302 | 2010-11 | Purnea | Katihar | Kodha | Middle School Marwa Najrachowki 9006363823 | Santosh Kumar, Katihar | 138 dated 16.08.2011 | 183F₂ of 15-16 (06.08.15) | [8 empty] | 1 |  |  |  | 5270370
446 | USS-197(D) | 10101000701 | 2010-11 | Purnea | Katihar | Kadwa | Dukhi Ram Middle School Chandpur 9709755452 | Birendra Kumar Singh, Katihar | 138 dated 16.08.2011 | 506F₂ of 14-15 (12.12.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 5492010
447 | USS-198-1 | 10100600505 | 2010-11 | Purnea | Katihar | Brari | Middle School Laxmipur | Prem Prakash, At-Khutahara,PO+PS- Kursakanta, Dist.-Arariya 9931935213 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Tender Process |  | 0
448 | USS-198-2 | 10100601802 | 2010-11 | Purnea | Katihar | Brari | Middle School Anarkali | Prem Prakash, At-Khutahara,PO+PS- Kursakanta, Dist.-Arariya 9931935213 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Tender Process |  | 0
449 | USS-198-3 | 10100300302 | 2010-11 | Purnea | Katihar | Hasanganj | Middle School Hasanganj | Prem Prakash, At-Khutahara,PO+PS- Kursakanta, Dist.-Arariya 9931935213 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Tender Process |  | 0
450 | USS-198-4 | 10100800101 | 2010-11 | Purnea | Katihar | Phalka | Middle School Morsanda | Narayan Mandal, Vill.-Barari, Dist.-Katihar 854 104 | 138 dated 16.08.2011 | 366-F2 2015-16 (19.01.16) | [8 empty] | 1 |  |  |  | 6071767
451 | USS-198-5 | 10100700301 | 2010-11 | Purnea | Katihar | Sameli | Middle School Dumar | Narayan Mandal, Vill.-Barari, Dist.-Katihar 854 104 | 138 dated 16.08.2011 | 367-F2 2015-16 (19.01.16) | [8 empty] | 1 |  |  |  | 5837001
452 | USS-199A (A) | 10071801204 | 2010-11 | Purnea | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | Pramod Kumar, Araria | 138 dated 16.08.2011 | 544F₂ of 14-15 (20.12.14) | [9 empty] | 1 | Inaugurated 16.07.2016 | 25/08/2015 | 5712968
453 | USS-199A (B) | 10071801402 | 2010-11 | Purnea | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | Pramod Kumar, Araria | 138 dated 16.08.2011 | 545F₂ of 14-15 (20.12.14) | [9 empty] | 1 | Inaugurated 16.07.2016 | 2015-06-10 | 5617717
454 | USS-199A (C) | 10071905003 | 2010-11 | Purnea | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | Pramod Kumar, Araria | 138 dated 16.08.2011 | 546F₂ of 14-15 (20.12.14) | [9 empty] | 1 | Inaugurated 16.07.2016 | 2015-05-12 | 5144190
455 | USS-199A (D) | 10071900701 | 2010-11 | Purnea | Araria | Narpatganj | Middle School Achra 9801296055 | Pramod Kumar, Araria | 138 dated 16.08.2011 | 547F₂ of 14-15 (20.12.14) | [9 empty] | 1 | Inaugurated 16.07.2016 | 20/08/2015 | 6042836
456 | USS-199 B-1 | 10071400601 | 2010-11 | Purnea | Araria | Jokihat | Middle School Jhanpur 9471219710 | MD. Iftakhar Alam | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | Inaugurated | 04.07.2014 | 5678199.0033
457 | USS-199 B-2 | 10071302802 | 2010-11 | Purnea | Araria | Raniganj | Middle School Kosikapur 9199673607 | MD. Iftakhar Alam | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | Inaugurated | 04.07.2014 | 5678199.0033
458 | USS-199 B-3 | 10071801402 | 2010-11 | Purnea | Araria | Araria | Middle School Araria Basti 9661185784 | MD. Iftakhar Alam | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | Inaugurated | 04.07.2014 | 5678200.0033
459 | USS-46-1 |  | 2009-10 | Tirhut East | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | Sadafal Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 5603319
460 | USS-46-2 |  | 2009-10 | Tirhut East | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | Sadafal Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 5603319
461 | USS-46-3 |  | 2009-10 | Tirhut East | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 | Sadafal Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 5603319
462 | USS-46-4 |  | 2009-10 | Tirhut East | Sitamarhi | csylaM | eŒ foŒ] ipukSj | Sadafal Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 5603320
463 | USS-47-1 |  | 2009-10 | Tirhut East | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | Malti Singh Darbhanga Mob. - 8969355977 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.12.2013 | 5074450
464 | USS-47-2 |  | 2009-10 | Tirhut East | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | Malti Singh Darbhanga Mob. - 8969355977 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.12.2013 | 5074450
465 | USS-47-3 |  | 2009-10 | Tirhut East | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | Malti Singh Darbhanga Mob. - 8969355977 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.12.2013 | 5074450
466 | USS-47-4 |  | 2009-10 | Tirhut East | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | Malti Singh Darbhanga Mob. - 8969355977 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.12.2013 | 5074450
467 | USS-47-5 |  | 2009-10 | Tirhut East | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | Malti Singh Darbhanga Mob. - 8969355977 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.12.2013 | 5074449
468 | USS-48-1 |  | 2009-10 | Tirhut East | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.09.2013 | 4685120
469 | USS-48-2 |  | 2009-10 | Tirhut East | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.09.2013 | 4685120
470 | USS-48-3 |  | 2009-10 | Tirhut East | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.09.2013 | 4685120
471 | USS-48-4 |  | 2009-10 | Tirhut East | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.09.2013 | 4685120
472 | USS-49-1 |  | 2009-10 | Tirhut East | Muzaffarpur | dkaVh | eŒ foŒJ`axkj 8809637605 | Ramji Prasad Mob. - 9334489874 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land problem
473 | USS-49-2 |  | 2009-10 | Tirhut East | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | Ramji Prasad Mob. - 9334489874 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.06.2013 | 4608913
474 | USS-49-3 |  | 2009-10 | Tirhut East | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | Ramji Prasad Mob. - 9334489874 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.06.2013 | 4608913
475 | USS-50-1 |  | 2009-10 | Tirhut East | Muzaffarpur | ik: | eŒ foŒ] HkkstiV~Vh 9931888752 | Diamond ConstructionMob. - 9471299381 | 138 dated 16.08.2011 | [5 empty] | 1 | [7 empty] | 973939
476 | USS-50-2 |  | 2009-10 | Tirhut East | Muzaffarpur | ik: | eŒ foŒ] pkaniqj 9801265669 | Diamond ConstructionMob. - 9471299381 | 138 dated 16.08.2011 | [5 empty] | 1 | [7 empty] | 973939
477 | USS-50-3 |  | 2009-10 | Tirhut East | Muzaffarpur | lkgscxat | eŒ foŒ] 'kkgiqj iV~Vh 9801128043 | Diamond ConstructionMob. - 9471299381 | 138 dated 16.08.2011 | [5 empty] | 1 | [7 empty] | 973939
478 | USS-50-4 |  | 2009-10 | Tirhut East | Muzaffarpur | ljS;k | eŒ foŒ] xksjhxkekMhg 9431615151 | Diamond ConstructionMob. - 9471299381 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1460910
479 | USS-51-1 |  | 2009-10 | Tirhut East | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.12.2013 | 4626431
480 | USS-51-2 |  | 2009-10 | Tirhut East | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.12.2013 | 4626431
481 | USS-51-3 |  | 2009-10 | Tirhut East | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | Mother India Pvt. Ltd. Mob. - 9431018204 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.12.2013 | 4626432
482 | USS-52-1 |  | 2009-10 | Tirhut East | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | Man Mardan Shukla Construction Pvt. Ltd. Mob. - 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.12.2014 | 4596083
483 | USS-52-2 |  | 2009-10 | Tirhut East | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | Man Mardan Shukla Construction Pvt. Ltd. Mob. - 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.12.2014 | 4596083
484 | USS-52-3 |  | 2009-10 | Tirhut East | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | Man Mardan Shukla Construction Pvt. Ltd. Mob. - 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.12.2014 | 4596083
485 | USS-52-4 |  | 2009-10 | Tirhut East | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | Man Mardan Shukla Construction Pvt. Ltd. Mob. - 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.12.2014 | 4596083
486 | USS-53-1 |  | 2009-10 | Tirhut East | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | Man Mardan Shukla Construction Pvt. Ltd. Ph: 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 4445041
487 | USS-53-2 |  | 2009-10 | Tirhut East | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | Man Mardan Shukla Construction Pvt. Ltd. Ph: 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 4445041
488 | USS-53-3 |  | 2009-10 | Tirhut East | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | Man Mardan Shukla Construction Pvt. Ltd. Ph: 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 4445041
489 | USS-53-4 |  | 2009-10 | Tirhut East | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | Man Mardan Shukla Construction Pvt. Ltd. Ph: 9431013056 / 9507328440 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2016 | 4445042
490 | USS-54-1 |  | 2009-10 | Tirhut East | Vaishali | jktkikdj | eŒ foŒ] csydqaMk 7677785326 | Aditi Annanya Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Dispute
491 | USS-54-2 |  | 2009-10 | Tirhut East | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | Aditi Annanya Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 08.09.2013 | 3981333
492 | USS-54-3 |  | 2009-10 | Tirhut East | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 | Aditi Annanya Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  | 08.09.2013 | 3981333
493 | USS-162 (A) |  | 2010-11 | Tirhut East | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | Malti Infrastructure Pvt. Ltd. Patna | 138 dated 16.08.2011 | [10 empty] | 1 | handover | 18.06.2016 | 5777282
494 | USS-162 (B) |  | 2010-11 | Tirhut East | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | Dilip Kumar Mishra, Sitamarhi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 20.04.2015 | 5842495
495 | USS-162 (C) |  | 2010-11 | Tirhut East | Sitamarhi | Suppi | M. S. Aktha 9470821881 | Ramesh Shankar, Shivhar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.06.2015 | 5986289
496 | USS-162 (D) |  | 2010-11 | Tirhut East | Sitamarhi | Riga | M. S. Ramnagara 9570781314 | Krishna Nandan Jha, Sitamarhi | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | brick work above GF in progess |  | 3111750
497 | USS-162 (E) |  | 2010-11 | Tirhut East | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | Avinash Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 28.03.2016 | 6291219
498 | USS-162 (F) |  | 2010-11 | Tirhut East | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | Bharti Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 24.01.2016 | 5710520
499 | USS-163 (A) |  | 2010-11 | Tirhut East | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | Dilip Kumar Sharma | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 05.08.2015 | 6050689
500 | USS-163 (B) |  | 2010-11 | Tirhut East | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | Dilip Kumar Mishra | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 23.04.2015 | 5966644
501 | USS-163 (C) |  | 2010-11 | Tirhut East | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | Dilip Kumar Mishra | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2015 | 5830496
502 | USS-163 (D) |  | 2010-11 | Tirhut East | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | Pawan-Pawan Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 6078789
503 | USS-164-1 |  | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5117276.0033
504 | USS-164-2 |  | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5117276.0033
505 | USS-164-3 |  | 2010-11 | Tirhut East | Vaishali | Bhagwanpur | M. S. Askaranpur | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5117277.0033
506 | USS-164-4 |  | 2010-11 | Tirhut East | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
507 | USS-164-5 |  | 2010-11 | Tirhut East | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
508 | USS-165-1 |  | 2010-11 | Tirhut East | Vaishali | Jandaha | U. M.S. Shahpur Rohuya 9934414222 | Samrat Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2701700
509 | USS-165-2 |  | 2010-11 | Tirhut East | Vaishali | Jandaha | M. S, Mahhisaur 9661844106 | Samrat Construction | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 1964873
510 | USS-165-3 |  | 2010-11 | Tirhut East | Vaishali | Sahadei Bujurg | M.S, Toimath 9939693675 | Samrat Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2701700
511 | USS-165-4 |  | 2010-11 | Tirhut East | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 | Samrat Construction | 138 dated 16.08.2011 |  | 1 | [9 empty] | Insufficient Land
512 | USS-165-5 |  | 2010-11 | Tirhut East | Vaishali | Jandaha | M.S, Bijrauti 9973922533 | Samrat Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4175356
513 | USS-166 (A) |  | 2010-11 | Tirhut East | Vaishali | Raghopur | M. S,Tersiya 9631970772 | Avnish Kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4732483
514 | USS-166 (B) |  | 2010-11 | Tirhut East | Vaishali | Raghopur | M.S,Paharpur 7654539556 | Macro Ranjan Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 29.01.2016 | 5520473
515 | USS-166 (C) |  | 2010-11 | Tirhut East | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | Ashutosh Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land dispute |  | 0
516 | USS-166 (D) |  | 2010-11 | Tirhut East | Vaishali | Desari | M. S, Bhikhanpura 9973319373 | Amrendra Kumar, Vaishali | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 2067830
517 | USS-166 (E) |  | 2010-11 | Tirhut East | Vaishali | Rajapakar | M. S, Makhadumpur Pokhraira 9934478747 | Amrendra Kumar, Vaishali | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4974260
518 | USS-167-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.04.2015 | 5160919
519 | USS-167-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.04.2015 | 5160919
520 | USS-167-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.04.2015 | 5160920
521 | USS-167-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.04.2015 | 5160920
522 | USS-167-5 |  | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | Man Mardan Shukla Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.04.2015 | 5160920
523 | USS-168-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.03.2016 | 5390321
524 | USS-168-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.03.2016 | 5390321
525 | USS-168-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.03.2016 | 5390322
526 | USS-168-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.03.2016 | 5390322
527 | USS-169-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.11.2014 | 5518665
528 | USS-169-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.11.2014 | 5518665
529 | USS-169-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.11.2014 | 5518665
530 | USS-169-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.11.2014 | 5518665
531 | USS-169-5 |  | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | Minni Devi | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.11.2014 | 5518668
532 | USS-170-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | Rama Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5007288
533 | USS-170-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | Rama Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 14.12.2015 | 5007288
534 | USS-170-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | Rama Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 11.08.2015 | 5007288
535 | USS-170-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | Rama Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 5007288
536 | USS-170-5 |  | 2010-11 | Tirhut East | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | Rama Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 01.08.2015 | 5007289
537 | USS-171-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | RANA Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.09.2015 | 4729150
538 | USS-171-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | RANA Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 25.03.2016 | 4729150
539 | USS-171-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | RANA Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 4729150
540 | USS-171-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | RANA Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 25.03.2016 | 4729150
541 | USS-171-5 |  | 2010-11 | Tirhut East | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | RANA Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 |  | 4729151
542 | USS-172-1 |  | 2010-11 | Tirhut East | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | Rakesh Ranjan, Muzaffarpur | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.04.2015 | 5225504
543 | USS-172-2 |  | 2010-11 | Tirhut East | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | Rakesh Ranjan, Muzaffarpur | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.04.2015 | 5225504
544 | USS-172-3 |  | 2010-11 | Tirhut East | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | Rakesh Ranjan, Muzaffarpur | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.04.2015 | 5225504
545 | USS-172-4 |  | 2010-11 | Tirhut East | Muzaffarpur | Mushhari | M. S, Dronpur | Rakesh Ranjan, Muzaffarpur | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.04.2015 | 5225504
546 | USS-172-5 |  | 2010-11 | Tirhut East | Muzaffarpur | Muraul | M. S, Pilkhi | Rakesh Ranjan, Muzaffarpur | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.04.2015 | 5225506
547 | USS-37-1 |  | 2009-10 | Tirhut West | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | Prem Pratap Ray 9386878517/ 9852833505 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.04.2014 | 4919560
548 | USS-37-2 |  | 2009-10 | Tirhut West | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | Prem Pratap Ray 9386878517/ 9852833505 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.04.2014 | 4919560
549 | USS-37-3 |  | 2009-10 | Tirhut West | West Champaran | Bairiya | M.S. Bathna 9431466192 | Prem Pratap Ray 9386878517/ 9852833505 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.04.2014 | 4919560
550 | USS-37-4 |  | 2009-10 | Tirhut West | West Champaran | Nautan | M.S. Mangalpur 9430691686 | Prem Pratap Ray 9386878517/ 9852833505 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.04.2014 | 4919560
551 | USS-38-1 |  | 2009-10 | Tirhut West | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | Sarswati Company 9431491214 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5024180
552 | USS-38-2 |  | 2009-10 | Tirhut West | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | Sarswati Company 9431491214 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5024180
553 | USS-38-3 |  | 2009-10 | Tirhut West | West Champaran | Lauriya | M.S.Dhobani 9430571439 | Sarswati Company 9431491214 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5024180
554 | USS-38-4 |  | 2009-10 | Tirhut West | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | Sarswati Company 9431491214 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5024180
555 | USS-39-1 |  | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Tajpur 8986956152 | Amit Kr. Rai Mob. - 9934056756/ 9470249005 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4847286
556 | USS-39-2 |  | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Sukhlahi 9546120109 | Amit Kr. Rai Mob. - 9934056756/ 9470249005 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4847286
557 | USS-39-3 |  | 2009-10 | Tirhut West | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | Amit Kr. Rai Mob. - 9934056756/ 9470249005 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4847286
558 | USS-40-1 |  | 2009-10 | Tirhut West | West Champaran | Narkatiaganj | M.S. Shomgarh 9470256119 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1378817
559 | USS-40-2 |  | 2009-10 | Tirhut West | West Champaran | Yogapatti | M.S. Kohra 9934686513 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1378817
560 | USS-40-3 |  | 2009-10 | Tirhut West | West Champaran | Ramnagar | M.S. Sher Hawa Don 9470860764 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 |  |  |  |  | 1 | [8 empty] | 766009
561 | USS-41-1 |  | 2009-10 | Tirhut West | East Champaran | Motihari | M.S. Jamla 9934828027 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3338944
562 | USS-41-2 |  | 2009-10 | Tirhut West | East Champaran | Banjariya | M.S. Kukurjari 9708975580 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 2504208
563 | USS-41-3 |  | 2009-10 | Tirhut West | East Champaran | Turkauliya | M.S. Vishnupurwa 9801485906 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 3338944
564 | USS-41-4 |  | 2009-10 | Tirhut West | East Champaran | Chiraiya | M.S. Parewa 9386155278 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [5 empty] | 1 | [7 empty] | 1878158
565 | USS-42-1 |  | 2009-10 | Tirhut West | East Champaran | Areraj | M.S. Radhiya 9576399366 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4586954
566 | USS-42-2 |  | 2009-10 | Tirhut West | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4586954
567 | USS-42-3 |  | 2009-10 | Tirhut West | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4586954
568 | USS-42-4 |  | 2009-10 | Tirhut West | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4586954
569 | USS-43-1 |  | 2009-10 | Tirhut West | East Champaran | Raxaul | M.S. Gonha 9470284937 | Jagdamba Construction, 9470606400 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1636359
570 | USS-43-2 |  | 2009-10 | Tirhut West | East Champaran | Sugauli | M.S. Muswa 9471878742 | Jagdamba Construction, 9470606400 | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 1999994
571 | USS-43-3 |  | 2009-10 | Tirhut West | East Champaran | Aadapur | M.S. Beldarwa 9771769291 / 9472911484 | Jagdamba Construction, 9470606400 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1636361
572 | USS-43-4 |  | 2009-10 | Tirhut West | East Champaran | Chhauradano | M.S. Pakariya Urdu 9470233197 | Jagdamba Construction, 9470606400 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
573 | USS-44-1 |  | 2009-10 | Tirhut West | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | Ashiyana Contract Pvt. Ltd. Mob. - 9431088485 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.05.2014 | 4216292
574 | USS-44-2 |  | 2009-10 | Tirhut West | East Champaran | kalyanpur | M.S. Mandhwa Urdu 9939516692 | Ashiyana Contract Pvt. Ltd. Mob. - 9431088485 | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
575 | USS-44-3 |  | 2009-10 | Tirhut West | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | Ashiyana Contract Pvt. Ltd. Mob. - 9431088485 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4216292
576 | USS-44-4 |  | 2009-10 | Tirhut West | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | Ashiyana Contract Pvt. Ltd. Mob. - 9431088485 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 30.04.2104 | 4216292
577 | USS-44-5 |  | 2009-10 | Tirhut West | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | Ashiyana Contract Pvt. Ltd. Mob. - 9431088485 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.04.2014 | 4216291
578 | USS-45-1 |  | 2009-10 | Tirhut West | East Champaran | Dhaka | M.S. Chandanbara Urdu 9931213480 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1504367
579 | USS-45-2 |  | 2009-10 | Tirhut West | East Champaran | Patahi | M.S. Betauna 9708717133 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 | [5 empty] | 1 | [7 empty] | 1002911
580 | USS-45-3 |  | 2009-10 | Tirhut West | East Champaran | Madhuban | M.S. Gurmiya | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 |  |  |  |  | 1 | [8 empty] | 668607
581 | USS-45-4 |  | 2009-10 | Tirhut West | East Champaran | Ghorasahan | M.S. Laxmipur Laukhan 9431652891 | Diamond Construction Mob. - 9471299381 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2005823
582 | USS-158-1 |  | 2010-11 | Tirhut West | East Champaran | Turkauliya | M.S. Belwa Ray 9430645457 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4727390.0033
583 | USS-158-2 |  | 2010-11 | Tirhut West | East Champaran | Turkauliya | M.S. Jaishinghpur 9430209305 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4727390.0033
584 | USS-158-3 |  | 2010-11 | Tirhut West | East Champaran | Motihari | M.S. Basantpur 9576483588 | Ranjeet Kumar 9470235016 | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4727391.0033
585 | USS-159-1 |  | 2010-11 | Tirhut West | East Champaran | Pakridayal | M.S. Sishani 9934715029 | C.S. Construction, Gayatri Nagar, Motihari. | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4948335
586 | USS-159-2 |  | 2010-11 | Tirhut West | East Champaran | chaaiya | M.S. Madhubani 9430565177 | C.S. Construction, Gayatri Nagar, Motihari. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
587 | USS-159-3 |  | 2010-11 | Tirhut West | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 | C.S. Construction, Gayatri Nagar, Motihari. | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4948335
588 | USS-159-4 |  | 2010-11 | Tirhut West | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | C.S. Construction, Gayatri Nagar, Motihari. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4948335
589 | USS-159-5 |  | 2010-11 | Tirhut West | East Champaran | Ghorasahan | M.S. Samanpur 9939403946 | C.S. Construction, Gayatri Nagar, Motihari. | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 1979334
590 | USS-160-1 |  | 2010-11 | Tirhut West | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 | C.S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5589516
591 | USS-160-2 |  | 2010-11 | Tirhut West | West Champaran | Narkatiyaganj | Govt.M.S. Bhadiharwa 8986137181 | C.S. Construction | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 4751088
592 | USS-160-3 |  | 2010-11 | Tirhut West | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | C.S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5589516
593 | USS-160-4 |  | 2010-11 | Tirhut West | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 | C.S. Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5589517
594 | USS-160-5 |  | 2010-11 | Tirhut West | West Champaran | Nautan | M.S.Sansariya 8757124792 | C.S. Construction | 138 dated 16.08.2011 |  | 1
595 | USS-161-1 |  | 2010-11 | Tirhut West | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 | Shushil kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5002626
596 | USS-161-2 |  | 2010-11 | Tirhut West | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 | Shushil kumar | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5002626
597 | USS-61-1 |  | 2009-10 | Darbhanga | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 13.03.2015 | 5079714
598 | USS-61-2 |  | 2009-10 | Darbhanga | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 13.03.2015 | 5079714
599 | USS-61-3 |  | 2009-10 | Darbhanga | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 13.03.2015 | 5079713
600 | USS-62-1 |  | 2009-10 | Darbhanga | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4944280
601 | USS-62-2 |  | 2009-10 | Darbhanga | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4944280
602 | USS-62-3 |  | 2009-10 | Darbhanga | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | Hariom Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.05.2015 | 4944279
603 | USS-63-1 |  | 2009-10 | Darbhanga | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.04.2014 | 4819201
604 | USS-63-2 |  | 2009-10 | Darbhanga | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.04.2014 | 4819201
605 | USS-63-3 |  | 2009-10 | Darbhanga | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 24.04.2014 | 4819201
606 | USS-64-1 |  | 2009-10 | Darbhanga | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.05.2013 | 5098590
607 | USS-64-2 |  | 2009-10 | Darbhanga | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.05.2013 | 5098590
608 | USS-64-3 |  | 2009-10 | Darbhanga | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.05.2013 | 5098590
609 | USS-64-4 |  | 2009-10 | Darbhanga | Darbhanga | rkjMhg | mRØŒeŒfoŒ rkjMhg 9934870957 | Siemens Construction Corporation | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x62' available land 27'x25' | 17.05.2013
610 | USS-65-1 |  | 2009-10 | Darbhanga | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.08.2015 | 4908351
611 | USS-65-2 |  | 2009-10 | Darbhanga | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.08.2015 | 4908351
612 | USS-65-3 |  | 2009-10 | Darbhanga | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.08.2015 | 4908350
613 | USS-66-1 |  | 2009-10 | Darbhanga | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2014 | 4795082
614 | USS-66-2 |  | 2009-10 | Darbhanga | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2014 | 4795082
615 | USS-66-3 |  | 2009-10 | Darbhanga | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.07.2014 | 4795083
616 | USS-67-1 |  | 2009-10 | Darbhanga | Samastipur | iVksjh | eŒfoŒ]njok 8757084952 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x67' available land 17'x15'
617 | USS-67-2 |  | 2009-10 | Darbhanga | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2014 | 4856296
618 | USS-67-3 |  | 2009-10 | Darbhanga | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2014 | 4856296
619 | USS-67-4 |  | 2009-10 | Darbhanga | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2014 | 4856296
620 | USS-67-5 |  | 2009-10 | Darbhanga | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2014 | 4856296
621 | USS-68-1 |  | 2009-10 | Darbhanga | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623765
622 | USS-68-2 |  | 2009-10 | Darbhanga | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | Ray and Raj Engineering Pvt. Ltd. Mob- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623765
623 | USS-68-3 |  | 2009-10 | Darbhanga | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | Ray and Raj Engineering Pvt. Ltd. Mob- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623765
624 | USS-68-4 |  | 2009-10 | Darbhanga | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqj etjfg;k 9955507715 | Ray and Raj Engineering Pvt. Ltd. Mob- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623765
625 | USS-68-5 |  | 2009-10 | Darbhanga | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | Ray and Raj Engineering Pvt. Ltd. Mob- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623765
626 | USS-68-6 |  | 2009-10 | Darbhanga | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | Ray and Raj Engineering Pvt. Ltd. Mob- 9430047216 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.12.2013 | 4623763
627 | USS-69-1 |  | 2009-10 | Darbhanga | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | Sudhakant Enterprises Pvt. Ltd. Mob. - 9931640405 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.04.2014 | 4554745
628 | USS-69-2 |  | 2009-10 | Darbhanga | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | Sudhakant Enterprises Pvt. Ltd. Mob. - 9931640405 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.04.2014 | 4554745
629 | USS-69-3 |  | 2009-10 | Darbhanga | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | Sudhakant Enterprises Pvt. Ltd. Mob. - 9931640405 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.04.2014 | 4554745
630 | USS-69-4 |  | 2009-10 | Darbhanga | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | Sudhakant Enterprises Pvt. Ltd. Mob. - 9931640405 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 29.04.2014 | 4554746
631 | USS-70-1 |  | 2009-10 | Darbhanga | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | Rajendra Singh Construction Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2013 | 4925292
632 | USS-70-2 |  | 2009-10 | Darbhanga | Samastipur | iwlk | eŒfoŒ]efYydkSj | Rajendra Singh Construction Pvt. Ltd. Mob. - 9931996161 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 31.03.2013 | 4925292
633 | USS-187-1 |  | 2010-11 | Darbhanga | Madhubani | Babu Barhi | M. S. Barhara | Avaneesh Enterprises Mob. - 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 3349144
634 | USS-187-2 |  | 2010-11 | Darbhanga | Madhubani | Lakhanpur | M. S. Belaucha | Avaneesh Enterprises Mob. - 9473282030 | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x67' available land20'x15'
635 | USS-187-3 |  | 2010-11 | Darbhanga | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | Avaneesh Enterprises Mob. - 9473282030 | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x67' available land17'x15'
636 | USS-187-4 |  | 2010-11 | Darbhanga | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 | Avaneesh Enterprises Mob. - 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 3940170
637 | USS-187-5 |  | 2010-11 | Darbhanga | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 | Avaneesh Enterprises Mob. - 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 3940170
638 | USS-188-1 |  | 2010-11 | Darbhanga | Madhubani | Banipatti | M. S.Ganguli 9431629001 | Narendra Prasad Singh | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | AGREEMENT NOT DONE (CONTRACTOR REFUSED)
639 | USS-188-2 |  | 2010-11 | Darbhanga | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 | Narendra Prasad Singh | 138 dated 16.08.2011 |  | 1
640 | USS-188-3 |  | 2010-11 | Darbhanga | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 | Narendra Prasad Singh | 138 dated 16.08.2011 | [5 empty] | 1
641 | USS-189-1 |  | 2010-11 | Darbhanga | Samastipur | Shivajinagar | M. S. Shripur Bhataura | Arvind Kumar | 138 dated 16.08.2011 | [9 empty] | 1 |  |  |  | 5860814
642 | USS-189-2 |  | 2010-11 | Darbhanga | Samastipur | Vibhutipur | U. M. S, Mustafapur | Arvind Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | Low land more than 15'
643 | USS-190-1 |  | 2010-11 | Darbhanga | Darbhanga | Kusheshwarsthan E | U. M. S, Barniya 7870017996 | Madhav Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2228155
644 | USS-190-2 |  | 2010-11 | Darbhanga | Darbhanga | Kusheshwarsthan W | U. M. S, Sihariya 8969431987 | Madhav Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2228156
645 | USS-191-1 |  | 2010-11 | Darbhanga | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | Rajesh Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x67' available land 27'x25'
646 | USS-191-2 |  | 2010-11 | Darbhanga | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | Rajesh Kumar | 138 dated 16.08.2011 |  | 1 | [9 empty] | LAND DISPUTE
647 | USS-191-3 |  | 2010-11 | Darbhanga | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | Rajesh Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.03.2015 | 5366524
648 | USS-191-4 |  | 2010-11 | Darbhanga | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | Rajesh Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.03.2015 | 5366524
649 | USS-191-5 |  | 2010-11 | Darbhanga | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | Rajesh Kumar | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 25.03.2015 | 5366524
650 | USS-192 A |  | 2010-11 | Darbhanga | Darbhanga | Bahadurpur | M. S, Daing 9199229540 | Madhav Construction | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 4933184
651 | USS-192 B |  | 2010-11 | Darbhanga | Darbhanga | Biraul | M. S, Koilajan 9939650547 | Madhav Construction | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 1715613
652 | USS-192 C |  | 2010-11 | Darbhanga | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | Raam Pukar Yadav | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 09.05.2016 | 5843829
653 | USS-192 D |  | 2010-11 | Darbhanga | Darbhanga | Biraul | U. M. S, Balha 7631905606 | Raam Pukar Yadav | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | 08.05.2016 | 5789262
654 | USS-193-1 |  | 2010-11 | Darbhanga | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | Kailash Prasad Yadav Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.05.2015 | 5330421.9967
655 | USS-193-2 |  | 2010-11 | Darbhanga | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | Kailash Prasad Yadav Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.05.2015
656 | USS-193-3 |  | 2010-11 | Darbhanga | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | Kailash Prasad Yadav Construction Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | required land 68'x67' available land 16'x14' |  | 5330422.9967
657 | USS-193-4 |  | 2010-11 | Darbhanga | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | Kailash Prasad Yadav Construction Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.05.2015 | 5330422.9967
658 | USS-55-1 |  | 2009-10 | Saran | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.02.2014 | 4616434
659 | USS-55-2 |  | 2009-10 | Saran | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.02.2014 | 4616434
660 | USS-55-3 |  | 2009-10 | Saran | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.02.2014 | 4616434
661 | USS-55-4 |  | 2009-10 | Saran | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.02.2014 | 4616433
662 | USS-56-1 |  | 2009-10 | Saran | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.02.2014 | 4635997
663 | USS-56-2 |  | 2009-10 | Saran | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 15.06.2014 | 4635997
664 | USS-56-3 |  | 2009-10 | Saran | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 12.02.2014 | 4635997
665 | USS-56-4 |  | 2009-10 | Saran | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.03.2014 | 4635998
666 | USS-57-1 |  | 2009-10 | Saran | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | Shiv Shankar Singh Construction Pvt. Ltd. Mob.- 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4561491
667 | USS-57-2 |  | 2009-10 | Saran | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | Shiv Shankar Singh Construction Pvt. Ltd. Mob.- 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4561491
668 | USS-57-3 |  | 2009-10 | Saran | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | Shiv Shankar Singh Construction Pvt. Ltd. Mob.- 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4561490
669 | USS-57-4 |  | 2009-10 | Saran | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | Shiv Shankar Singh Construction Pvt. Ltd. Mob.- 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4561490
670 | USS-58-1 |  | 2009-10 | Saran | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4575371
671 | USS-58-2 |  | 2009-10 | Saran | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 17.02.2014 | 4575371
672 | USS-58-3 |  | 2009-10 | Saran | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.03.2014 | 4575371
673 | USS-58-4 |  | 2009-10 | Saran | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4575371
674 | USS-58-5 |  | 2009-10 | Saran | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | Shiv Shankar Singh Construction Pvt. Ltd. Mob. - 9431217515 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4575372
675 | USS-59-1 |  | 2009-10 | Saran | Saran | Masharrakha | M. School, Dum Dumma, Mob.: 9006658111 | Nitish Raj Mob.- 9470607184 / 9572239242 | 138 dated 16.08.2011 | [7 empty] | 1 | [5 empty] | 2360886
676 | USS-59-2 |  | 2009-10 | Saran | Saran | Panapur | U. M. School, Panapur, Mob.: 9199453564 | Nitish Raj Mob.- 9470607184 / 9572239242 | 138 dated 16.08.2011 | [6 empty] | 1 | [6 empty] | 2164145
677 | USS-59-3 |  | 2009-10 | Saran | Saran | Tarraiyan | M. School, Parauna Balak, Mob.: 9931139238 | Nitish Raj Mob.- 9470607184 / 9572239242 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2360886
678 | USS-59-4 |  | 2009-10 | Saran | Saran | Jalalpur | M. School, Nawadah, Mob.: 9431630231 | Nitish Raj Mob.- 9470607184 / 9572239242 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2360887
679 | USS-60-1 |  | 2009-10 | Saran | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | Kishore Construction Mob.- 9473059195 / 9546578888 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4026418
680 | USS-60-2 |  | 2009-10 | Saran | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | Kishore Construction Mob.- 9473059195 / 9546578888 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.10.2014 | 4026418
681 | USS-60-3 |  | 2009-10 | Saran | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | Kishore Construction Mob.- 9473059195 / 9546578888 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4026418
682 | USS-60-4 |  | 2009-10 | Saran | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | Kishore Construction Mob.- 9473059195 / 9546578888 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4026419
683 | USS-60-5 |  | 2009-10 | Saran | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | Kishore Construction Mob.- 9473059195 / 9546578888 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4026419
684 | USS-173 (A) |  | 2010-11 | Saran | Siwan | Husainganj | M. S, Hata Tola Chhata 9546660912 | Star Construction & Co., Siwan | 138 dated 16.08.2011 | [8 empty] | 1 |  |  |  |  | 2213013
685 | USS-173 (B) |  | 2010-11 | Saran | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | Bighnahanta Construction Pvt. Ltd., Patna | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5638394
686 | USS-174-1 |  | 2010-11 | Saran | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 07.04.2014 | 5339023
687 | USS-174-2 |  | 2010-11 | Saran | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5339023
688 | USS-174-3 |  | 2010-11 | Saran | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 02.09.2014 | 5339023
689 | USS-174-4 |  | 2010-11 | Saran | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 19.05.2014 | 5339023
690 | USS-175-1 |  | 2010-11 | Saran | Siwan | Siswan | M. S, Gyaspur 8809341191 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Hand Over | 30.05.2014 | 5221031
691 | USS-175-2 |  | 2010-11 | Saran | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 27.01.2014 | 5221031
692 | USS-175-3 |  | 2010-11 | Saran | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 28.01.2014 | 5221031
693 | USS-175-4 |  | 2010-11 | Saran | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5221032
694 | USS-176-1 |  | 2010-11 | Saran | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5141045.0033
695 | USS-176-2 |  | 2010-11 | Saran | Siwan | Gudhani | M. S, Belauri 8809165382 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5141045.0033
696 | USS-176-3 |  | 2010-11 | Saran | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5141046.0033
697 | USS-177-1 |  | 2010-11 | Saran | Saran | Dariyapur | Middle School, Saraiya 9431647901 | Aditi Annanya Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4160095
698 | USS-177-2 |  | 2010-11 | Saran | Saran | Dariyapur | Middle School, Bhongha 9006298659 | Aditi Annanya Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4160095
699 | USS-177-3 |  | 2010-11 | Saran | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | Aditi Annanya Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4160095
700 | USS-177-4 |  | 2010-11 | Saran | Saran | Dighwara | Middle School, Malkhachak 9135336330 | Aditi Annanya Construction | 138 dated 16.08.2011 |  |  | 1 | [10 empty] | 208005
701 | USS-178-1 |  | 2010-11 | Saran | Saran | Sonpur | Middle School, Shikharpur 9631221348 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5293479
702 | USS-179-1 |  | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Basahi Urdu | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4500184
703 | USS-179-2 |  | 2010-11 | Saran | Saran | Ekma | Middle School, Bhodasa | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4500184
704 | USS-179-3 |  | 2010-11 | Saran | Saran | Ekma | Middle School, Betbaniya 8294839353 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4500184
705 | USS-179-4 |  | 2010-11 | Saran | Saran | Ekma | Middle School, Eksar 9572740280 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4500185
706 | USS-179-5 |  | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 4500185
707 | USS-181-1 |  | 2010-11 | Saran | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | Hariom Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5015920
708 | USS-182-1 |  | 2010-11 | Saran | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.10.2014 | 5018410.9967
709 | USS-182-2 |  | 2010-11 | Saran | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5018411.9967
710 | USS-182-3 |  | 2010-11 | Saran | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | Kishore Construction | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5018411.9967
711 | USS-183-1 |  | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 16.03.2015 | 5236618
712 | USS-183-2 |  | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 18.06.2015 | 5236618
713 | USS-183-3 |  | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | Siemens Construction Corporation | 138 dated 16.08.2011 |  | 1 | [9 empty] | Low Land
714 | USS-183-4 |  | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | Siemens Construction Corporation | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 14.03.2015 | 5236618
715 | USS-184-1 |  | 2010-11 | Saran | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 08.05.2014 | 5364757.9967
716 | USS-184-2 |  | 2010-11 | Saran | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 03.05.2014 | 5364758.9967
717 | USS-184-3 |  | 2010-11 | Saran | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 05.08.2014 | 5364758.9967
718 | USS-184-4 |  | 2010-11 | Saran | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Not Available
719 | USS-185-1 |  | 2010-11 | Saran | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5271801
720 | USS-185-2 |  | 2010-11 | Saran | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Problem
721 | USS-185-3 |  | 2010-11 | Saran | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated |  | 5271802
722 | USS-185-4 |  | 2010-11 | Saran | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | Burnwala Contract Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land Problem
723 | USS-186-1 |  | 2010-11 | Saran | Gopalganj | Hathua | U. M. S, Satai 8757888461 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.01.2015 | 5243983.9967
724 | USS-186-2 |  | 2010-11 | Saran | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | 10.01.2015 | 5243984.9967
725 | USS-186-3 |  | 2010-11 | Saran | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 |  | 1 | [9 empty] | Land not available
726 | USS-186-4 |  | 2010-11 | Saran | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | Shiv Shankar Singh Contract Pvt. Ltd. | 138 dated 16.08.2011 | [10 empty] | 1 |  |  | 5243984.9967
| Total No. of Schools-RMSA (USS) | [5 empty] | 726 |  |  |  | 87 | 2 | 2 | 4 | 8 | 20 | 9 | 16 | 49 | 529
Note on V49: Group will closed due dely in land availability.
Note on B64: ACCORD. TO 475 USS-108-1
Note on H355: Gurudev Const.
Note on H358: Gurudev Const.
Note on B720: List from 161 & 250 ing list

## Sheet3
Session | 2010-11
Row Labels | Completed
Araria | 7
Aurangabad | 10
Banka
Begusarai | 8
Bhagalpur | 16
Bhojpur | 25
Buxar | 8
Darbhanga | 9
East Champaran | 3
Gaya | 17
Gopalganj | 11
Jamui
Jehanabad | 4
Kaimur | 5
Katihar | 2
Khagaria | 5
Lakhisarai | 3
Madhepura | 2
Madhubani | 3
Munger | 10
Muzaffarpur | 29
Nalanda | 11
Nawada | 6
Patna | 7
Purnea | 4
Rohtas | 22
Saharsa | 1
Samastipur
Saran | 13
Sheikhpura | 5
Sheohar | 2
Sitamarhi | 9
Siwan | 12
Vaishali | 5
West Champaran | 3
Grand Total | 277

## Sheet4
Count of Date of Completion | Column Labels
Row Labels | 2009-10 | 2010-11 | Grand Total
Bhagalpur | 8 | 6 | 14
Banka | 1 |  | 1
Bhagalpur | 7 | 6 | 13
Darbhanga |  | 4 | 4
Darbhanga |  | 1 | 1
Madhubani |  | 3 | 3
Kosi | 4 | 1 | 5
Madhepura | 2 | 1 | 3
Saharsa | 2 |  | 2
Magadh | 4 | 12 | 16
Aurangabad | 2 | 1 | 3
Gaya |  | 6 | 6
Jehanabad |  | 1 | 1
Nawada | 2 | 4 | 6
Munger | 1 | 22 | 23
Begusarai | 1 | 8 | 9
Khagaria |  | 3 | 3
Lakhisarai |  | 1 | 1
Munger |  | 10 | 10
Patna East |  | 5 | 5
Bhojpur |  | 5 | 5
Patna West | 3 | 8 | 11
Buxar | 3 | 2 | 5
Kaimur |  | 1 | 1
Rohtas |  | 5 | 5
Purnea | 8 | 2 | 10
Katihar | 2 | 2 | 4
Kishanganj | 5 |  | 5
Purnea | 1 |  | 1
Saran | 11 | 21 | 32
Gopalganj |  | 3 | 3
Saran | 4 | 12 | 16
Siwan | 7 | 6 | 13
Tirhut East |  | 7 | 7
Muzaffarpur |  | 3 | 3
Vaishali |  | 4 | 4
Tirhut West | 12 | 8 | 20
East Champaran | 5 | 3 | 8
Sheohar |  | 2 | 2
West Champaran | 7 | 3 | 10
Grand Total | 51 | 96 | 147

## Sheet1
BSEIDC Ltd., Patna
USS 2009-10 & 2010-11 (Pending list for Completion Certificate)
S.N. | SL. NO. | Group No. | Session | Division | Name of District | Name of Block | Name of School | Remarks | Date of Completion | Total Completion Cost
1 | 1 | USS-109-1 | 2010-11 | Patna East | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | Inaugurated |  | 5152143
2 | 2 | USS-109-3 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | Inaugurated |  | 5152143
3 | 3 | USS-109-4 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | Inaugurated |  | 5152143
4 | 4 | USS-109-5 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | Inaugurated |  | 5152143
5 | 5 | USS-112-4 | 2010-11 | Patna East | Bhojpur | Shahpur | M.S. Suhiya 9471919316 |  |  | 5197311
6 | 1 | USS-10-1 | 2009-10 | Patna West | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | Inaugurated |  | 4121306
7 | 2 | USS-10-2 | 2009-10 | Patna West | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | Inaugurated |  | 4121306
8 | 3 | USS-10-4 | 2009-10 | Patna West | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | Inaugurated |  | 4121305
9 | 4 | USS-117 (C) | 2010-11 | Patna West | Buxar | Ithari | M.S. Harpur 9939590039 |  |  | 5102198
10 | 5 | USS-117 (D) | 2010-11 | Patna West | Buxar | Ithari | M.S. Basawan Kala 7739120173 | Inaugurated 16.07.2016 |  | 4993510
11 | 6 | USS-119 (A) | 2010-11 | Patna West | Kaimur | Bhabhua | M.S.Miun | Inaugurated 16.07.2016 |  | 5685114
12 | 7 | USS-121 (D) | 2010-11 | Patna West | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | Inaugurated 16.07.2016 |  | 4957819
13 | 8 | USS-122-1 | 2010-11 | Patna West | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | Inaugurated 16.07.2016 |  | 4672853
14 | 9 | USS-122-3 | 2010-11 | Patna West | Rohtas | Dinara | M.S. Baliyan, 9931111475 | Inaugurated 16.07.2016 |  | 4672853
15 | 10 | USS-122-4 | 2010-11 | Patna West | Rohtas | Dinara | M.S. Bararhi, 9955083783 | Inaugurated 16.07.2016 |  | 4672853
16 | 11 | USS-125-1 | 2010-11 | Patna West | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | Inaugurated |  | 4685702
17 | 1 | USS-29-3 | 2009-10 | Magadh | Aurangabad | jQhxat | eŒfoŒ[kjks[kj 9006027690 |  |  | 4321596
18 | 2 | USS-29-4 | 2009-10 | Magadh | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | Inaugurated |  | 4321596
19 | 3 | USS-35-2 | 2009-10 | Magadh | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | Inaugurated |  | 4314503
20 | 4 | USS-35-4 | 2009-10 | Magadh | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | Inaugurated 16.07.2016 |  | 4314503
21 | 5 | USS-144 (A) | 2010-11 | Magadh | Jehanabad | Hulasganj | M.S.Vira, 9771693433 |  |  | 4413483
22 | 6 | USS-146 (B) | 2010-11 | Magadh | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | Inaugurated 16.07.2016 |  | 5154654
23 | 7 | USS-146 (D) | 2010-11 | Magadh | Nawada | Pakribarawan | M.S. Ukaorah | Inaugurated 16.07.2016 |  | 4821920
24 | 8 | USS-147-1 | 2010-11 | Magadh | Nawada | Narhat | M.S. Khanwa, 9905846666 | Inaugurated 16.07.2016 |  | 4480450
25 | 9 | USS-147-2 | 2010-11 | Magadh | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | Inaugurated 16.07.2016 |  | 4480451
26 | 10 | USS-149 (A) | 2010-11 | Magadh | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 |  |  | 5148020
27 | 11 | USS-150 (C) | 2010-11 | Magadh | Gaya | Konch | M.S. Goribigha, 9939408167 |  |  | 4384516
28 | 12 | USS-152-2 | 2010-11 | Magadh | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | Inaugurated |  | 4436714
29 | 13 | USS-152-3 | 2010-11 | Magadh | Gaya | Fatehpur | M.S. Khajuri, 8969107991 |  |  | 4436714
30 | 14 | USS-153 (A) | 2010-11 | Magadh | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | Inaugurated 16.07.2016 |  | 4947507
31 | 15 | USS-153 (B) | 2010-11 | Magadh | Gaya | Guraru | M.S. Manjhar, 9572789270 |  |  | 3746778
32 | 16 | USS-156-3 | 2010-11 | Magadh | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | Inaugurated |  | 4930998
33 | 1 | USS-25-2 | 2009-10 | Munger | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | Inaugurated |  | 4931792
34 | 2 | USS-133(F) | 2010-11 | Munger | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | Inaugurated 16.07.2016 |  | 5278158
35 | 3 | USS-135-1 | 2010-11 | Munger | Munger | Asarganj | M.S.Chakhand 9135065232 | Inaugurated |  | 4857416.9967
36 | 4 | USS-135-2 | 2010-11 | Munger | Munger | Asarganj | M.S. Beran 9204931976 | Inaugurated |  | 4857418
37 | 5 | USS-135-3 | 2010-11 | Munger | Munger | Tarapur | M.S. Mahamadpur 9709507263 |  |  | 4857418
38 | 6 | USS-136-1 | 2010-11 | Munger | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | Inaugurated |  | 5300308
39 | 7 | USS-136-3 | 2010-11 | Munger | Munger | Sangrampur | M.S.Katiyari 9199782900 | Inaugurated |  | 5300308
40 | 8 | USS-137-1 | 2010-11 | Munger | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | Inaugurated |  | 4878010
41 | 9 | USS-137-2 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | Inaugurated |  | 4878010
42 | 10 | USS-137-3 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | Inaugurated |  | 4878011
43 | 11 | USS-137-4 | 2010-11 | Munger | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | Inaugurated |  | 4878011
44 | 12 | USS-137-5 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | Inaugurated |  | 4878011
45 | 13 | USS-139-1 | 2010-11 | Munger | Begusarai | Bachhawara | M.S.Dadupur 9801471859 |  |  | 4578151
46 | 14 | USS-139-2 | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | Inaugurated |  | 4578151
47 | 15 | USS-139-3 | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | Inaugurated |  | 4578151
48 | 16 | USS-139-4 | 2010-11 | Munger | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | Inaugurated |  | 4578151
49 | 17 | USS-139-5 | 2010-11 | Munger | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | Inaugurated |  | 4578152
50 | 18 | USS-140-1 | 2010-11 | Munger | Begusarai | Garhpura | M.S.Kuddhar 9955509070 |  |  | 4799563
51 | 19 | USS-140-2 | 2010-11 | Munger | Begusarai | Dandari | M.S.Katarmala 9709640304 |  |  | 4799563
52 | 20 | USS-140-3 | 2010-11 | Munger | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | Inaugurated |  | 4799563
53 | 21 | USS-141 (A) | 2010-11 | Munger | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 |  |  | 5738627
54 | 22 | USS-141 (B) | 2010-11 | Munger | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 |  |  | 5322965
55 | 23 | USS-142-2 | 2010-11 | Munger | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | Inaugurated |  | 5121092
56 | 1 | USS-15-1 | 2009-10 | Bhagalpur | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | Inaugurated |  | 4515294
57 | 2 | USS-15-2 | 2009-10 | Bhagalpur | Bhagalpur | Sultanganj | MS Udadih 9801583582 | Inaugurated |  | 4515295
58 | 3 | USS-15-4 | 2009-10 | Bhagalpur | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | Inaugurated |  | 4515295
59 | 4 | USS-16-1 | 2009-10 | Bhagalpur | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | Inaugurated |  | 4242445
60 | 5 | USS-16-2 | 2009-10 | Bhagalpur | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | Inaugurated |  | 4242445
61 | 6 | USS-16-3 | 2009-10 | Bhagalpur | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | Inaugurated |  | 4242445
62 | 7 | USS-16-4 | 2009-10 | Bhagalpur | Bhagalpur | Goradih | MS Garhotiya 9931865594 | Inaugurated |  | 4242446
63 | 8 | USS-19-1 | 2009-10 | Bhagalpur | Banka | Amarpur | MS Bhadariya 9939749402 | Inaugurated |  | 3530044
64 | 9 | USS-126 (B) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | Handover |  | 4917175
65 | 10 | USS-126 (C) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | Handover |  | 5052732
66 | 11 | USS-127 (C) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | Inaugurated |  | 5240787
67 | 12 | USS-127 (E) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | Inaugurated 16.07.2016 |  | 4882446
68 | 13 | USS-128 (C) | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | Inaugurated 16.07.2016 |  | 5023873
69 | 14 | USS-129 (B) | 2010-11 | Bhagalpur | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | Inaugurated 16.07.2016 |  | 5619506
70 | 1 | USS-72-1 | 2009-10 | Kosi | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | Inaugurated 16.07.2016 |  | 5078932
71 | 2 | USS-72-2 | 2009-10 | Kosi | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | Inaugurated 16.07.2016 |  | 5078932
72 | 3 | USS-74-1 | 2009-10 | Kosi | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | Inaugurated 16.07.2016 |  | 3967262
73 | 4 | USS-74-3 | 2009-10 | Kosi | Saharsa | Mahishi | M/S Jhara 9430696742 | Inaugurated 16.07.2016 |  | 3967263
74 | 5 | USS-199D-1 | 2010-11 | Kosi | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | Inaugurated 16.07.2016 |  | 5460744
75 | 1 | USS-80-1 | 2009-10 | Purnea | Kishanganj | Dighalbank | म॰वि॰हरवाडंगा | Inaugurated |  | 5148963
76 | 2 | USS-80-2 | 2009-10 | Purnea | Kishanganj | Thakurganj | म॰वि॰जंगलभीटा | Inaugurated |  | 5148963
77 | 3 | USS-80-3 | 2009-10 | Purnea | Kishanganj | Kochadhaman | म॰वि॰धनपुरा 9470868499 | Inaugurated |  | 5148963
78 | 4 | USS-80-4 | 2009-10 | Purnea | Kishanganj | Pothiya | म॰वि॰हरिपोखर क्रांतिगाछ 9430677962 | Inaugurated |  | 5148963
79 | 5 | USS-80-5 | 2009-10 | Purnea | Kishanganj | Bahadurganj | म॰वि॰हरिभाषा 9471834254 | Inaugurated |  | 5148964
80 | 6 | USS-81-3 | 2009-10 | Purnea | Purnea | Dagrua | म॰वि॰मोहम्मदपुर 8877902279/9852305617 | Inaugurated |  | 4622719
81 | 7 | USS-85-2 | 2009-10 | Purnea | Katihar | Manihari | म॰वि॰पटनी नारायणपुर 9430970158 | Inaugurated |  | 4987532
82 | 8 | USS-85-4 | 2009-10 | Purnea | Katihar | Kodha | म॰वि॰शिशिया 9431625914 |  |  | 4987532
83 | 9 | USS-196(B) | 2010-11 | Purnea | Katihar | Ajamnagar | Middle School Arihana 8809322797 | Inaugurated 16.07.2016 |  | 4749252
84 | 10 | USS-197(D) | 2010-11 | Purnea | Katihar | Kadwa | Dukhi Ram Middle School Chandpur 9709755452 | Inaugurated 16.07.2016 |  | 5492010
85 | 1 | USS-164-1 | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | Inaugurated |  | 5117276.0033
86 | 2 | USS-164-2 | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | Inaugurated |  | 5117276.0033
87 | 3 | USS-164-3 | 2010-11 | Tirhut East | Vaishali | Bhagwanpur | M. S. Askaranpur |  |  | 5117277.0033
88 | 4 | USS-166 (A) | 2010-11 | Tirhut East | Vaishali | Raghopur | M. S,Tersiya 9631970772 |  |  | 4732483
89 | 5 | USS-170-1 | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | Inaugurated |  | 5007288
90 | 6 | USS-170-4 | 2010-11 | Tirhut East | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | Inaugurated 16.07.2016 |  | 5007288
91 | 7 | USS-171-5 | 2010-11 | Tirhut East | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | Inaugurated 16.07.2016 |  | 4729151
92 | 1 | USS-38-1 | 2009-10 | Tirhut West | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | Inaugurated |  | 5024180
93 | 2 | USS-38-2 | 2009-10 | Tirhut West | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | Inaugurated |  | 5024180
94 | 3 | USS-38-3 | 2009-10 | Tirhut West | West Champaran | Lauriya | M.S.Dhobani 9430571439 | Inaugurated |  | 5024180
95 | 4 | USS-38-4 | 2009-10 | Tirhut West | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | Inaugurated |  | 5024180
96 | 5 | USS-39-1 | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Tajpur 8986956152 | Inaugurated |  | 4847286
97 | 6 | USS-39-2 | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Sukhlahi 9546120109 |  |  | 4847286
98 | 7 | USS-39-3 | 2009-10 | Tirhut West | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | Inaugurated |  | 4847286
99 | 8 | USS-42-1 | 2009-10 | Tirhut West | East Champaran | Areraj | M.S. Radhiya 9576399366 | Inaugurated |  | 4586954
100 | 9 | USS-42-2 | 2009-10 | Tirhut West | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | Inaugurated |  | 4586954
101 | 10 | USS-42-3 | 2009-10 | Tirhut West | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | Inaugurated |  | 4586954
102 | 11 | USS-42-4 | 2009-10 | Tirhut West | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | Inaugurated |  | 4586954
103 | 12 | USS-44-3 | 2009-10 | Tirhut West | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | Inaugurated |  | 4216292
104 | 13 | USS-159-1 | 2010-11 | Tirhut West | East Champaran | Pakridayal | M.S. Sishani 9934715029 |  |  | 4948335
105 | 14 | USS-159-3 | 2010-11 | Tirhut West | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 |  |  | 4948335
106 | 15 | USS-159-4 | 2010-11 | Tirhut West | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | Inaugurated |  | 4948335
107 | 16 | USS-160-1 | 2010-11 | Tirhut West | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 |  |  | 5589516
108 | 17 | USS-160-3 | 2010-11 | Tirhut West | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | Inaugurated |  | 5589516
109 | 18 | USS-160-4 | 2010-11 | Tirhut West | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 |  |  | 5589517
110 | 19 | USS-161-1 | 2010-11 | Tirhut West | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 |  |  | 5002626
111 | 20 | USS-161-2 | 2010-11 | Tirhut West | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 |  |  | 5002626
112 | 1 | USS-187-1 | 2010-11 | Darbhanga | Madhubani | Babu Barhi | M. S. Barhara |  |  | 3349144
113 | 2 | USS-187-4 | 2010-11 | Darbhanga | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 |  |  | 3940170
114 | 3 | USS-187-5 | 2010-11 | Darbhanga | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 |  |  | 3940170
115 | 4 | USS-192 A | 2010-11 | Darbhanga | Darbhanga | Bahadurpur | M. S, Daing 9199229540 |  |  | 4933184
116 | 1 | USS-57-1 | 2009-10 | Saran | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | Inaugurated |  | 4561491
117 | 2 | USS-57-2 | 2009-10 | Saran | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | Inaugurated |  | 4561491
118 | 3 | USS-57-3 | 2009-10 | Saran | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | Inaugurated |  | 4561490
119 | 4 | USS-57-4 | 2009-10 | Saran | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | Inaugurated |  | 4561490
120 | 5 | USS-58-1 | 2009-10 | Saran | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | Inaugurated |  | 4575371
121 | 6 | USS-58-4 | 2009-10 | Saran | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | Inaugurated |  | 4575371
122 | 7 | USS-58-5 | 2009-10 | Saran | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | Inaugurated |  | 4575372
123 | 8 | USS-60-1 | 2009-10 | Saran | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | Inaugurated |  | 4026418
124 | 9 | USS-60-3 | 2009-10 | Saran | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | Inaugurated |  | 4026418
125 | 10 | USS-60-4 | 2009-10 | Saran | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | Inaugurated |  | 4026419
126 | 11 | USS-60-5 | 2009-10 | Saran | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | Inaugurated |  | 4026419
127 | 12 | USS-173 (B) | 2010-11 | Saran | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | Inaugurated |  | 5638394
128 | 13 | USS-174-2 | 2010-11 | Saran | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 |  |  | 5339023
129 | 14 | USS-175-4 | 2010-11 | Saran | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | Inaugurated |  | 5221032
130 | 15 | USS-176-1 | 2010-11 | Saran | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | Inaugurated |  | 5141045.0033
131 | 16 | USS-176-2 | 2010-11 | Saran | Siwan | Gudhani | M. S, Belauri 8809165382 | Inaugurated |  | 5141045.0033
132 | 17 | USS-176-3 | 2010-11 | Saran | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | Inaugurated |  | 5141046.0033
133 | 18 | USS-177-1 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Saraiya 9431647901 | Inaugurated |  | 4160095
134 | 19 | USS-177-2 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Bhongha 9006298659 | Inaugurated |  | 4160095
135 | 20 | USS-177-3 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | Inaugurated |  | 4160095
136 | 21 | USS-178-1 | 2010-11 | Saran | Saran | Sonpur | Middle School, Shikharpur 9631221348 | Inaugurated |  | 5293479
137 | 22 | USS-179-1 | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Basahi Urdu | Inaugurated |  | 4500184
138 | 23 | USS-179-2 | 2010-11 | Saran | Saran | Ekma | Middle School, Bhodasa | Inaugurated |  | 4500184
139 | 24 | USS-179-3 | 2010-11 | Saran | Saran | Ekma | Middle School, Betbaniya 8294839353 | Inaugurated |  | 4500184
140 | 25 | USS-179-4 | 2010-11 | Saran | Saran | Ekma | Middle School, Eksar 9572740280 | Inaugurated |  | 4500185
141 | 26 | USS-179-5 | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | Inaugurated |  | 4500185
142 | 27 | USS-181-1 | 2010-11 | Saran | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | Inaugurated |  | 5015920
143 | 28 | USS-182-2 | 2010-11 | Saran | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | Inaugurated |  | 5018411.9967
144 | 29 | USS-182-3 | 2010-11 | Saran | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | Inaugurated |  | 5018411.9967
145 | 30 | USS-185-1 | 2010-11 | Saran | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | Inaugurated |  | 5271801
146 | 31 | USS-185-3 | 2010-11 | Saran | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | Inaugurated |  | 5271802
147 | 32 | USS-186-4 | 2010-11 | Saran | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 |  |  | 5243984.9967

## Sheet2
USS 2009-10 & 2010-11
[13 empty] | Grd floor |  | 1st Floor
S.N. | Group No. | UDISE No. | Name of District | Name of Block | Name of School | Name of Agency | 2 | Date of Commencement | Not Start | Layout | Foundation | PL | LL | RL | LL | RL | Finishing | Complete | Remarks | Division | Session | Date of Completion | Total Completion Cost
56 | USS-15-1 |  | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4515294
57 | USS-15-2 |  | Bhagalpur | Sultanganj | MS Udadih 9801583582 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4515295
58 | USS-15-4 |  | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4515295
59 | USS-16-1 |  | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4242445
60 | USS-16-2 |  | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4242445
61 | USS-16-3 |  | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4242445
62 | USS-16-4 |  | Bhagalpur | Goradih | MS Garhotiya 9931865594 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 4242446
63 | USS-19-1 |  | Banka | Amarpur | MS Bhadariya 9939749402 | K. D. Company Mob.- 9431497838 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2009-10 |  | 3530044
64 | USS-126 (B) |  | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Handover | Bhagalpur | 2010-11 |  | 4917175
65 | USS-126 (C) |  | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | Avaneesh Enterprises Mob.- 9473282030 | 138 dated 16.08.2011 | [10 empty] | 1 | Handover | Bhagalpur | 2010-11 |  | 5052732
66 | USS-127 (C) |  | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | Raj Kishore Singh Mob. - 9431412396 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated | Bhagalpur | 2010-11 |  | 5240787
67 | USS-127 (E) |  | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | Bhagalpur | 2010-11 |  | 4882446
68 | USS-128 (C) |  | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | MD. IFTEKHAR ALAM | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | Bhagalpur | 2010-11 |  | 5023873
69 | USS-129 (B) |  | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | Iftakhar Alam Mob. - 9431835133 / 9934724033 | 138 dated 16.08.2011 | [10 empty] | 1 | Inaugurated 16.07.2016 | Bhagalpur | 2010-11 |  | 5619506

## Sheet5
BSEIDC Ltd., Patna
Pending list of division wise Completion Date
S. NO. | Division=> District Name | USS 2009-10 | USS 2010-11 | Pending total No. of Schools's Completion Date
1 | Bhagalpur | 8 | 6 | 14
| Banka | 1 | 0 | 1
| Bhagalpur | 7 | 6 | 13
2 | Darbhanga | 0 | 4 | 4
| Darbhanga | 0 | 1 | 1
| Madhubani | 0 | 3 | 3
3 | Kosi | 4 | 1 | 5
| Madhepura | 2 | 1 | 3
| Saharsa | 2 | 0 | 2
4 | Magadh | 4 | 12 | 16
| Aurangabad | 2 | 1 | 3
| Gaya | 0 | 6 | 6
| Jehanabad | 0 | 1 | 1
| Nawada | 2 | 4 | 6
5 | Munger | 1 | 22 | 23
| Begusarai | 1 | 8 | 9
| Khagaria | 0 | 3 | 3
| Lakhisarai | 0 | 1 | 1
| Munger | 0 | 10 | 10
6 | Patna East | 0 | 5 | 5
| Bhojpur | 0 | 5 | 5
7 | Patna West | 3 | 8 | 11
| Buxar | 3 | 2 | 5
| Kaimur | 0 | 1 | 1
| Rohtas | 0 | 5 | 5
8 | Purnea | 8 | 2 | 10
| Katihar | 2 | 2 | 4
| Kishanganj | 5 | 0 | 5
| Purnea | 1 | 0 | 1
9 | Saran | 11 | 21 | 32
| Gopalganj | 0 | 3 | 3
| Saran | 4 | 12 | 16
| Siwan | 7 | 6 | 13
10 | Tirhut East | 0 | 7 | 7
| Muzaffarpur | 0 | 3 | 3
| Vaishali | 0 | 4 | 4
11 | Tirhut West | 12 | 8 | 20
| East Champaran | 5 | 3 | 8
| Sheohar | 0 | 2 | 2
| West Champaran | 7 | 3 | 10
GRAND TOTAL |  | 51 | 96 | 147

## Sheet7
Column Labels
| 2009-10 |  |  |  | 2010-11 |  |  |  | Total Not Started | Total In Progress | Total Completed | Total Total Completion Cost (in Rs.)
Row Labels | Not Started | In Progress | Completed | Total Completion Cost (in Rs.) | Not Started | In Progress | Completed | Total Completion Cost (in Rs.)
Bhagalpur | 1 | 5 | 15 | 80825494 |  | 7 | 16 | 104297325 | 1 | 12 | 31 | 185122819
Darbhanga | 2 | 0 | 34 | 164172989 | 7 | 6 | 12 | 71919336.99 | 9 | 6 | 46 | 236092325.99
Kosi | 1 | 1 | 19 | 96732905 | 1 | 0 | 3 | 15976843 | 2 | 1 | 22 | 112709748
Magadh | 3 | 2 | 30 | 134195076 | 10 | 15 | 37 | 230351817.9967 | 13 | 17 | 67 | 364546893.9967
Munger | 3 | 2 | 19 | 92932099 | 7 | 5 | 31 | 166960483.9967 | 10 | 7 | 50 | 259892582.9967
Patna East | 6 | 9 | 16 | 85240656 | 9 | 7 | 43 | 232682085 | 15 | 16 | 59 | 317922741
Patna West | 2 | 0 | 20 | 85685831 | 7 | 6 | 35 | 193995903 | 9 | 6 | 55 | 279681734
Purnea | 8 | 0 | 30 | 155904853 | 5 | 9 | 13 | 111920999.01 | 13 | 9 | 43 | 267825852.01
Saran |  | 4 | 22 | 107511438 | 5 | 2 | 36 | 184148292.98 | 5 | 6 | 58 | 291659730.98
Tirhut East | 2 | 4 | 28 | 138133016 | 4 | 7 | 43 | 250605603.01 | 6 | 11 | 71 | 388738619.01
Tirhut West | 2 | 14 | 19 | 114568120 | 2 | 5 | 8 | 62531399.01 | 4 | 19 | 27 | 177099519.01
Grand Total | 30 | 41 | 252 | 1255902477 | 57 | 69 | 277 | 1625390088.9933 | 87 | 110 | 529 | 2881292565.9933

## List of USS (3)
S. No. | Group | Session | Division | Name of District | Name of Block | Name of School | Sanc Order No. | Date of Commencement | Not Start | Layout | Foundation | PL | GF-LL | GF-RL | FF-LL | FF-RL | Finishing | Complete | Inprogress | Remarks | Date of Completion | Total Completion Cost
1 | USS-1-1 | 2009-10 | Patna East | Nalanda | p.Mh | eŒfoŒlwedk 9931607862 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4668583
2 | USS-1-2 | 2009-10 | Patna East | Nalanda | bLykeiqj | eŒfoŒenkjxat 9631262679 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4668583
3 | USS-1-3 | 2009-10 | Patna East | Nalanda | fgylk | eŒfoŒvdcjiqj 9470085363 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4668582
4 | USS-1-4 | 2009-10 | Patna East | Nalanda | fcgkj 'kjhQ | eŒfoŒflaxFkq 9204881769 | 138 dated 16.08.2011 | 13 SBD of 2011-12 Dt.-14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4668582
5 | USS-2-1 | 2009-10 | Patna East | Nalanda | fxfj;d | eŒfoŒblqvk 9934451313 | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | 1 | [9 empty] | 0 | sufficient land not available, work not possible, Proposal for drop
6 | USS-2-2 | 2009-10 | Patna East | Nalanda | drjhljk; | eŒfoŒxkso/kZu fcxgk 9006335967@8434590969 | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.07.2013 | 4254760
7 | USS-2-3 | 2009-10 | Patna East | Nalanda | jktxhj | eŒfoŒygqvkj 9798642205@9504394778 | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.07.2013 | 4254759
8 | USS-2-4 | 2009-10 | Patna East | Nalanda | flyko | eŒfoŒujgj fcxgk 8002186727 | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.07.2013 | 4254760
9 | USS-2-5 | 2009-10 | Patna East | Nalanda | uwjljk; | eŒfoŒdqUnh 9798241195 | 138 dated 16.08.2011 | 08 SBD of 2011-12 Dt.-13.12.2011 | 1 | [9 empty] | 0 | sufficient land not available, work not possible, Proposal for drop
10 | USS-3-1 | 2009-10 | Patna East | Patna | ck<+ | eŒfoŒngkSj 8804003367 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | 1 | [9 empty] | 0 | Project Director Instruct to DEO to arrange land with corporation of local public work not possible, Proposal for drop
11 | USS-3-2 | 2009-10 | Patna East | Patna | ck<+ | eŒfoŒeqckjdiqj 9631978359 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | 0 | Inaugurated | 13.02.2014 | 4838887
12 | USS-3-3 | 2009-10 | Patna East | Patna | Qrqgk¡ | eŒfoŒMqejh 8521893444 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | 0 | Inaugurated | 13.02.2014 | 4838887
13 | USS-3-4 | 2009-10 | Patna East | Patna | Qrqgk¡ | mRØŒeŒfoŒip:f[k;k 9801459905 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | [9 empty] | 1 | 0 | Inaugurated | 13.02.2014 | 4838888
14 | USS-3-5 | 2009-10 | Patna East | Patna | [kq'k:iqj | mRØŒeŒfoŒfueZyhpd 9097610852 | 138 dated 16.08.2011 | 18 SBD of 2011-12 Dt.-26.11.2011 | 1 | [9 empty] | 0 | sufficient land not available work not possible, proposal for drop
15 | USS-4-1 | 2009-10 | Patna East | Patna | nkukiqj | eŒfoŒvdhyiqj 9835490244 | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4892884
16 | USS-4-2 | 2009-10 | Patna East | Patna | ukScriqj | eŒfoŒvgqvkjk 9939680617 | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4892883
17 | USS-4-3 | 2009-10 | Patna East | Patna | ikyhxat | eŒfoŒHksM+gfj;k 9199997796 | 138 dated 16.08.2011 | 15 SBD 0f 2011-12 Dt.-15.12.2011 | 1 | [9 empty] | 0 | dispute, work not possible, Proposal for drop
18 | USS-5-1 | 2009-10 | Patna East | Patna | /ku:vk | eŒfoŒdkslqr 9973270948@9974270948 | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2014 | 3302602
19 | USS-5-2 | 2009-10 | Patna East | Patna | elkS<+h | eŒfoŒNkrk 8084994281 | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2014 | 3302602
20 | USS-5-3 | 2009-10 | Patna East | Patna | lairpd | eŒfoŒyadk dNqvkjk 9162137790 | 138 dated 16.08.2011 | 19 SBD of 2011-12 Dt.-26.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2014 | 3302601
21 | USS-5-4 | 2009-10 | Patna East | Patna | iquiqu | eŒfoŒdY;k.kiqj 9507549063 | 138 dated 16.08.2011 | 328 F2 of 2014-15 Dt.-04.09.14 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 15.07.2015 | 3302601
22 | USS-6-1 | 2009-10 | Patna East | Bhojpur | ihjks | eŒfoŒrkj 8969213005 | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | 1 | काफी दिनों से कार्य बंद |  | 1701676
23 | USS-6-2 | 2009-10 | Patna East | Bhojpur | ihjks | mRØŒeŒfoŒ nsopUnk 9386992853 | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | 1 | काफी दिनों से कार्य बंद |  | 1701676
24 | USS-6-3 | 2009-10 | Patna East | Bhojpur | rjkjh | eŒfoŒ[kqVgk¡ 7631530412 | 138 dated 16.08.2011 | 41 SBD of 2011-12 Dt.-14.3.2012 | 1 | [9 empty] | 0 | low land available, work not possible
25 | USS-7-1 | 2009-10 | Patna East | Bhojpur | fcfg;k¡ | eŒfoŒ:nzuxj 9308401427 | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 | [8 empty] | 1 |  | 1 | काफी दिनों से कार्य बंद |  | 3082033
26 | USS-7-2 | 2009-10 | Patna East | Bhojpur | txnh'kiqj | eŒfoŒtaxynkok¡ 9931492812 | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 | [5 empty] | 1 |  |  |  |  | 1 | काफी दिनों से कार्य बंद |  | 1541016
27 | USS-7-3 | 2009-10 | Patna East | Bhojpur | 'kkgiqj | eŒfoŒykyw Msjk 8873932298@9973022234 | 138 dated 16.08.2011 | 42 SBD of 2011-12 Dt.-14.30.2012 |  |  |  |  | 1 | [5 empty] | 1 | काफी दिनों से कार्य बंद |  | 1348389
28 | USS-8-1 | 2009-10 | Patna East | Bhojpur | vfxvk¡o | eŒfoŒukjk;.kiqj 9852411014 | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [5 empty] | 1 |  |  |  |  | 1 | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 1495010
29 | USS-8-2 | 2009-10 | Patna East | Bhojpur | cM+gjk | eŒfoŒxqaMh 7739111542 | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [6 empty] | 1 |  |  |  | 1 | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 1681887
30 | USS-8-3 | 2009-10 | Patna East | Bhojpur | mnoUruxj | eŒfoŒds'kksiqj cdjh 9771242640 | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 |  |  | 1 | [7 empty] | 1 | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 747505
31 | USS-8-4 | 2009-10 | Patna East | Bhojpur | dksbyoj | mRØŒeŒfoŒ folquiqjk 9334151672 | 138 dated 16.08.2011 | 43 SBD of 2011-12 Dt.-14.3.2012 | [8 empty] | 1 |  | 1 | काफी दिनों से कार्य बंद (एकरारनामा विखंडित एवं पत्रांक 441/12.08.16 द्वारा अंतिम मापी मुख्यालय को समर्पित) |  | 2990020
32 | USS-101-1 | 2010-11 | Patna East | Nalanda | Katrisarai | M.S. Bhagwanpur 9939987297 | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | 0 | Inaugurated | 23.02.2016 | 4488550
33 | USS-101-2 | 2010-11 | Patna East | Nalanda | Ben | M.S. Akouna 9570951336 | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | 0 | Inaugurated | 23.02.2016 | 4488550
34 | USS-101-3 | 2010-11 | Patna East | Nalanda | Giriyak | M.S. Sakuchi Sarai 9631154626 | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | 0 | Inaugurated | 23.02.2016 | 4488550
35 | USS-101-4 | 2010-11 | Patna East | Nalanda | Silao | Urdu.M.S. Barakar 9931004916 | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 |  |  |  |  | 1 | [5 empty] | 1 | Invalid list |  | 1570993
36 | USS-101-5 | 2010-11 | Patna East | Nalanda | Ben | M.S. Ramganj 9135849205 | 138 dated 16.08.2011 | 26 SBD of 2012-13 Dt.-14.5.2013 | [9 empty] | 1 | 0 | Inaugurated | 23.02.2016 | 4488550
37 | USS-102-1 | 2010-11 | Patna East | Nalanda | Biharsarif | M.S. Mahanandpur 7352573660 | 138 dated 16.08.2011 | 321 F2 2014-15 Dt.-09.09.2014 | [9 empty] | 1 | 0 | Inaugurated | 21.05.2015 | 5009332
38 | USS-102-2 | 2010-11 | Patna East | Nalanda | Biharsarif | M.S. Majidpur 9570625433 | 138 dated 16.08.2011 | 68 F2 2015-16 Dt.-22.05.2015 | [9 empty] | 1 | 0 |  | 25.08.2016 | 5072315
39 | USS-102-3 | 2010-11 | Patna East | Nalanda | Chandi | M.S. Dariya Bigha 9931236900 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available, work not possible
40 | USS-102-4 | 2010-11 | Patna East | Nalanda | Chandi | Urdu.M.S. Baisa 9939043903 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available, work not possible
41 | USS-102-5 | 2010-11 | Patna East | Nalanda | Noorsarai | M.S. Michaiganj Sakroura 9973050555 | 138 dated 16.08.2011 | 423 F2 2014-15 Dt.-05.11.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 17.01.2016 | 5312880
42 | USS-102-6 | 2010-11 | Patna East | Nalanda | Sarmera | M.S.Singhaul 9934212058 | 138 dated 16.08.2011 | 748 F2 2014-15 Dt.-13.03.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 17.01.2016 | 5298192
43 | USS-103-1 | 2010-11 | Patna East | Nalanda | Parwalpur | M.S. Bawukhana 8434655776 | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.09.2014 | 4799022
44 | USS-103-2 | 2010-11 | Patna East | Nalanda | Hilsa | M.S. Rasai Bigha 9934593683 | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 |  | 1 | [8 empty] | 1 | E/W |  | 239954
45 | USS-103-3 | 2010-11 | Patna East | Nalanda | Islampur | M.S. Bargounw 9279149331 | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.09.2014 | 4799022
46 | USS-103-4 | 2010-11 | Patna East | Nalanda | Islampur | M.S. Banbag 9934487509 | 138 dated 16.08.2011 | 43 SBD of 2013-14 Dt.-03.07.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.09.2014 | 4799022
47 | USS-104-1 | 2010-11 | Patna East | Patna | Khushrupur | M.S. Jagmal Bigha 9771442400 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Insufficient land. Scheme dropped
48 | USS-104-2 | 2010-11 | Patna East | Patna | Khushrupur | U.M.S. Arrai Benipur 9135748584 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Insufficient land. Scheme dropped
49 | USS-104-3 | 2010-11 | Patna East | Patna | Barh | U.M.S. Malahi 7250940590 | 138 dated 16.08.2011 | 213 SBD of 2013-14 Dt.-29.01.2014 | [9 empty] | 1 | 0 | Inaugurated | 25.10.2015 | 5307982
50 | USS-104-4 | 2010-11 | Patna East | Patna | Fatuha | M.S. Gabaspur 9955241716 | 138 dated 16.08.2011 | 213 SBD of 2013-14 Dt.-29.01.2014 | [9 empty] | 1 | 0 | Inaugurated | 25.10.2015 | 5307982
51 | USS-105-1 | 2010-11 | Patna East | Patna | Patna Sadar | M.S. Khokhna 9135334773 | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | 0 | Inaugurated | 10.04.2015 | 4890824
52 | USS-105-2 | 2010-11 | Patna East | Patna | Patna Sadar | M.S. Marchi 9430934711 | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | 0 | Inaugurated | 10.04.2015 | 4890824
53 | USS-105-3 | 2010-11 | Patna East | Patna | Punpun | Urdu.M.S. Painarghat 9546616297, 9572202274 | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | 0 | Inaugurated | 10.04.2015 | 4890824
54 | USS-105-4 | 2010-11 | Patna East | Patna | Phulwarisarif | M.S. Kurthoul 9431817223 | 138 dated 16.08.2011 | 19 SBD of 2013-14 Dt.-03.05.2013 | [9 empty] | 1 | 0 | Inaugurated | 10.04.2015 | 4890823
55 | USS-106-1 | 2010-11 | Patna East | Patna | Bihta | M.S. Kateshar 7250695245 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Low Land about 12'-0", work not possible
56 | USS-106-2 | 2010-11 | Patna East | Patna | Bikram | M.S. Barah 8084301353 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not regitered to school, work not possible
57 | USS-106-3 | 2010-11 | Patna East | Patna | Bihta | M.S. Kanhauli 9386873458 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land dispute between School & college, work not possible
58 | USS-107-1 | 2010-11 | Patna East | Patna | Dhanrua | M.S. Gawaspur Tubhara 8298503210 | 138 dated 16.08.2011 | 30 SBD of 2014-15 Dt.- | [9 empty] | 1 | 0 | Inaugurated | 15.07.2015 | 5006923
59 | USS-108-1 | 2010-11 | Patna East | Bhojpur | Agioan | M.S. Berath 09955434210 | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 20.07.2015 | 5047383
60 | USS-108-2 | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Mukundpur 9525995189 9931418305 | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 20.07.2015 | 5047383
61 | USS-108-3 | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Kumhaila 8294303061 | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 20.07.2015 | 5047383
62 | USS-108-4 | 2010-11 | Patna East | Bhojpur | Charpokhari | M.S. Sonbarsa 9771517920 | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | [9 empty] | 1 | 0 |  | 20.07.2015 | 5047384
63 | USS-108-5 | 2010-11 | Patna East | Bhojpur | Agioan | M.S. Lasarhi 9661399087 | 138 dated 16.08.2011 | 81 SBD 2012-13 Dt.-05.01.2013 | 1 | [9 empty] | 0 | Land not available, work not possible
64 | USS-109-1 | 2010-11 | Patna East | Bhojpur | Garhani | M.S. Aslan Bahadurpur 8092200406 | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | 0 | Inaugurated |  | 5152143
65 | USS-109-2 | 2010-11 | Patna East | Bhojpur | Garhani | M.S. Kaup 9708602077 | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [8 empty] | 1 |  | 1 |  |  | 4379325
66 | USS-109-3 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Karisath 9934636023 | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | 0 | Inaugurated |  | 5152143
67 | USS-109-4 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | M.S. Nawada Ben 9472456455 | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | 0 | Inaugurated |  | 5152143
68 | USS-109-5 | 2010-11 | Patna East | Bhojpur | Udawant Nagar | U.M.S. Chaurai 993900732 | 138 dated 16.08.2011 | 91 SBD of 2012-13 Dt.-23.01.2013 | [9 empty] | 1 | 0 | Inaugurated |  | 5152143
69 | USS-110-1 | 2010-11 | Patna East | Bhojpur | Barhara | U.M.S. Shaligram Singh Ka Tola 8409626973 | 138 dated 16.08.2011 | 768 F2 of 2014-15 Dt.-18.03.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 10.07.16 | 4820859
70 | USS-110-2 | 2010-11 | Patna East | Bhojpur | Barhara | M.S. Pakri 9304856454 | 138 dated 16.08.2011 | 775 F2 of 2014-15 Dt.-29.03.2015 | [7 empty] | 1 |  |  | 1 |  |  | 3392991
71 | USS-110-3 | 2010-11 | Patna East | Bhojpur | Barhara | Govt.M.S. Bakhorapur 9570469585 | 138 dated 16.08.2011 | 408 F2 of 2014-15 Dt.-27.10.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.04.16 | 5114266
72 | USS-110-4 | 2010-11 | Patna East | Bhojpur | Koilwar | M.S. Khesarhiyan 9973554537 | 138 dated 16.08.2011 | 156 F2 of 2015-16 Dt.-07.07.2015 | [7 empty] | 1 |  |  | 1 |  |  | 3633915
73 | USS-110-5 | 2010-11 | Patna East | Bhojpur | Koilwar | M.S. Khangaown 9631265664 | 138 dated 16.08.2011 | 311 F2 of 2015-16 Dt.-27.10.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.06.16 | 4604381
74 | USS-111-1 | 2010-11 | Patna East | Bhojpur | Jagdishpur | M.S.Kakila 8083448999 | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.06.2014 | 5121966
75 | USS-111-2 | 2010-11 | Patna East | Bhojpur | Jagdishpur | U.M.S. Isarhi 9973041304 | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.06.2014 | 5121966
76 | USS-111-3 | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Jethwar 9006698116/9931037637 | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.06.2014 | 5121965
77 | USS-111-4 | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Chakiya 9572477211 9934218390 | 138 dated 16.08.2011 | 87 SBD of 2012-13Dt.-16.01.2013 | [9 empty] | 1 | 0 | Inaugurated | 30.06.2014 | 5121965
78 | USS-112-1 | 2010-11 | Patna East | Bhojpur | Bihiyan | M.S. Sikariya 8873764301 | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [9 empty] | 1 | 0 | Inaugurated | 08.07.2015 | 5197311
79 | USS-112-2 | 2010-11 | Patna East | Bhojpur | Bihiyan | M.S. Kouriya 9431438960 | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [7 empty] | 1 |  |  | 1 |  |  | 2858524
80 | USS-112-3 | 2010-11 | Patna East | Bhojpur | Shahpur | M.S. Jawainiya 8083447757 7677504269 | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [5 empty] | 1 |  |  |  |  | 1 | Shuttering (DEBAR) |  | 2078924
81 | USS-112-4 | 2010-11 | Patna East | Bhojpur | Shahpur | M.S. Suhiya 9471919316 | 138 dated 16.08.2011 | 118 SBD of 2013-14 Dt.-01.10.2013 | [9 empty] | 1 | 0 |  |  | 5197311
82 | USS-113-1 | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Gahruan 9472135231 9162748057 | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | 0 |  | 24.12.16 | 4953126
83 | USS-113-2 | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Kurmuri 9576176655 | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | 0 |  | 24.12.16 | 4953126
84 | USS-113-3 | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Tarari 9631136009 | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.04.16 | 4953126
85 | USS-113-4 | 2010-11 | Patna East | Bhojpur | Tarari | M.S. Kartha 8757442408 9546312131 | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | 0 | Inaugurated | 09.05.15 | 4953125
86 | USS-113-5 | 2010-11 | Patna East | Bhojpur | Tarari | M.S.Bagar 9801629878 | 138 dated 16.08.2011 | 46 SBD of 13-14 Dt.-6.7.2013 | [9 empty] | 1 | 0 |  | 24.12.16 | 4953125
87 | USS-114-1 | 2010-11 | Patna East | Bhojpur | Sandesh | U.M.S.Nasratpur 9334673203 | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | 1 | [9 empty] | 0 | Dispute. Due to Court case & Land Dispute proposal for drop
88 | USS-114-2 | 2010-11 | Patna East | Bhojpur | Sahar | M.S. Baruhi 9199571702 | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | 0 | Inaugurated | 08.05.2015 | 5103856
89 | USS-114-3 | 2010-11 | Patna East | Bhojpur | Ara | M.S. Basantpur 09308735308 | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | 0 | Inaugurated | 08.05.2015 | 5103856
90 | USS-114-4 | 2010-11 | Patna East | Bhojpur | Sahar | M.S. Nawada 9934483628 | 138 dated 16.08.2011 | 45 SBD of 13-14 Dt.-5.7.2013 | [9 empty] | 1 | 0 | Inaugurated | 08.05.2015 | 5103857
91 | USS-9-1 | 2009-10 | Patna West | Buxar | cDlj | eŒfoŒd`riqjk 9576622685 | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.11.2013 | 4638139
92 | USS-9-2 | 2009-10 | Patna West | Buxar | pkSlk | eŒfoŒcukjiqj 8873946373 | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.11.2013 | 4638139
93 | USS-9-3 | 2009-10 | Patna West | Buxar | jktiqj | eŒfoŒjlsu 9006272320 | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.11.2013 | 4638139
94 | USS-9-4 | 2009-10 | Patna West | Buxar | bVkM+h | eŒfoŒcSdqUBiqj 9931755863 | 138 dated 16.08.2011 | 9.4.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.11.2013 | 4638140
95 | USS-10-1 | 2009-10 | Patna West | Buxar | Mqejk¡o | eŒfoŒiqjkuk Hkkstiqj 9771052120 | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | 0 | Inaugurated |  | 4121306
96 | USS-10-2 | 2009-10 | Patna West | Buxar | flejh | eŒfoŒ<+dkbZp 9934519481 | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | 0 | Inaugurated |  | 4121306
97 | USS-10-3 | 2009-10 | Patna West | Buxar | czg~eiqj | eŒfoŒegqvkj 7250949713 | 138 dated 16.08.2011 | 13.12.2011 | 1 | [9 empty] | 0
98 | USS-10-4 | 2009-10 | Patna West | Buxar | ukokuxj | eŒfoŒ/kuc[kjk 9771286504 | 138 dated 16.08.2011 | 13.12.2011 | [9 empty] | 1 | 0 | Inaugurated |  | 4121305
99 | USS-11-1 | 2009-10 | Patna West | Kaimur | dqnjk | eŒfoŒvojS;k 9973613935 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4247212
100 | USS-11-2 | 2009-10 | Patna West | Kaimur | eksgfu;k¡ | eŒfoŒdVjkdyk 9006263731 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4247212
101 | USS-11-3 | 2009-10 | Patna West | Kaimur | jkex<+ | mRØŒeŒfoŒ dykuh 9771939746@9934838921 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4247211
102 | USS-11-4 | 2009-10 | Patna West | Kaimur | nqxkZorh | eŒfoŒnqxkZorh 9430340748@9955221828 | 138 dated 16.08.2011 | 17.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4247211
103 | USS-12-1 | 2009-10 | Patna West | Kaimur | HkHkqvk | eŒfoŒdqM+klu 9031437647 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 05.02.2013 | 4067672
104 | USS-12-2 | 2009-10 | Patna West | Kaimur | pSuiqj | eŒfoŒdasok 9430026932 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 05.02.2013 | 4067672
105 | USS-13-1 | 2009-10 | Patna West | Rohtas | djxgj | eŒfoŒrksjuh 9631253327 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 4096220
106 | USS-13-2 | 2009-10 | Patna West | Rohtas | f'kolkxj | eŒfoŒxMqjk 9771022208 | 138 dated 16.08.2011 | 16.1.2012 | 1 | [9 empty] | 0 | Foundation work stopped due to local disturbance (Inaugurated school campus sufficient land available & soil test also done Inaugurated schlInaugurated 16.07.2016 Campus but some local public want to construct this buildInaugurated 16.07.2016 Inaugurated other land wich is situated out of campus & no aproach road available & about 800 m(aproxInaugurated 16.07.2016) away from campus
107 | USS-13-3 | 2009-10 | Patna West | Rohtas | lklkjke | eŒfoŒfldfj;k 9431464894 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2013 | 4096220
108 | USS-13-4 | 2009-10 | Patna West | Rohtas | dkspl | eŒfoŒegqvkjh 9661222301 | 138 dated 16.08.2011 | 16.1.2012 | [9 empty] | 1 | 0 | Inaugurated | 30.04.2013 | 4096219
109 | USS-14-1 | 2009-10 | Patna West | Rohtas | fMgjh | eŒfoŒxaxkSyh 7352200057 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4339127
110 | USS-14-2 | 2009-10 | Patna West | Rohtas | fnukjk | eŒfoŒljuk 9771634397 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4339127
111 | USS-14-3 | 2009-10 | Patna West | Rohtas | dkjkdkV | eŒfoŒeksguiqj 9801296392 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4339127
112 | USS-14-4 | 2009-10 | Patna West | Rohtas | uks[kk | eŒfoŒ?kksjfMgk 9801894133 | 138 dated 16.08.2011 | 14.12.2011 | [9 empty] | 1 | 0 | Inaugurated | 15.09.2013 | 4339127
113 | USS-115-1 | 2010-11 | Patna West | Buxar | Buxar | M.S.Nadanw 9234866577 9430015496 | 138 dated 16.08.2011 | 25.07.2014 | [8 empty] | 1 |  | 1 |  |  | 4228677
114 | USS-115-2 | 2010-11 | Patna West | Buxar | Buxar | M.S.Manjharia 9472951603 | 138 dated 16.08.2011 | 25.07.2014 | 1 | [9 empty] | 0 | No Way
115 | USS-115-3 | 2010-11 | Patna West | Buxar | Rajpur | M.S. Khiri 9470753325 | 138 dated 16.08.2011 | 25.07.2014 | [8 empty] | 1 |  | 1 |  |  | 4228677
116 | USS-115-4 | 2010-11 | Patna West | Buxar | Rajpur | Urdu M.S. Banni 9973105344 | 138 dated 16.08.2011 | 25.07.2014 | 1 | [9 empty] | 0 | Land not available
117 | USS-116 (A) | 2010-11 | Patna West | Buxar | Dumraon | M.S.Nuaon 9939391144 | 138 dated 16.08.2011 | 10.10.2014 | [9 empty] | 1 | 0 |  | 19.01.2017 | 5423447
118 | USS-116 (B) | 2010-11 | Patna West | Buxar | Dumraon | M.S. Kanjharua 9955867071 | 138 dated 16.08.2011 | 09.10.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 5225721
119 | USS-116 (C) | 2010-11 | Patna West | Buxar | Dumraon | M.S. Mathila 9931890937 | 138 dated 16.08.2011 | 13.07.2015 | [9 empty] | 1 | 0 |  | 27.02.2017 | 4796572
120 | USS-116 (D) | 2010-11 | Patna West | Buxar | Dumraon | M.S. Karuaj 9931281346 | 138 dated 16.08.2011 | 09.10.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 06.10.2015 | 5307275
121 | USS-116 (E) | 2010-11 | Patna West | Buxar | Dumraon | M.S. Rampur Mathiya 9798067177 | 138 dated 16.08.2011 | 05.11.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.01.2017 | 5023105
122 | USS-117 (A) | 2010-11 | Patna West | Buxar | Nawanagar | M.S.Pramanpur 9386827434 | 138 dated 16.08.2011 |  |  |  | 1 | [7 empty] | 1
123 | USS-117 (B) | 2010-11 | Patna West | Buxar | Ithari | M.S. Barkagaon 8651239720 | 138 dated 16.08.2011 | 12.09.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 17.02.2016 | 5659847
124 | USS-117 (C) | 2010-11 | Patna West | Buxar | Ithari | M.S. Harpur 9939590039 | 138 dated 16.08.2011 | 15.12.2014 | [9 empty] | 1 | 0 |  |  | 5102198
125 | USS-117 (D) | 2010-11 | Patna West | Buxar | Ithari | M.S. Basawan Kala 7739120173 | 138 dated 16.08.2011 | 27.08.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4993510
126 | USS-118-1 | 2010-11 | Patna West | Buxar | Simiri | M.S.Dhanpura 9199795834 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0
127 | USS-118-2 | 2010-11 | Patna West | Buxar | Simiri | M.S. Barka Singhnpura 9934740004 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0
128 | USS-118-3 | 2010-11 | Patna West | Buxar | Simiri | M.S. Kharha Tarnh 9199359782 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0
129 | USS-119 (A) | 2010-11 | Patna West | Kaimur | Bhabhua | M.S.Miun | 138 dated 16.08.2011 | 22.06.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5685114
130 | USS-119 (B) | 2010-11 | Patna West | Kaimur | Bhabhua | M.S.Piliyan | 138 dated 16.08.2011 | 03.09.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 5271310
131 | USS-119 (C) | 2010-11 | Patna West | Kaimur | Bhabhua | M.S. Mehsuan | 138 dated 16.08.2011 | 20.06.2016 | [8 empty] | 1 |  | 1 |  |  | 3678107
132 | USS-119 (D) | 2010-11 | Patna West | Kaimur | Bhabhua | M.S. Mohan Darwan | 138 dated 16.08.2011 | 22.05.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 5762930
133 | USS-120 (A) | 2010-11 | Patna West | Kaimur | Ramgarh | M.S.Sijhua | 138 dated 16.08.2011 | 30..03.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 28.09.2016 | 5940029
134 | USS-120 (B) | 2010-11 | Patna West | Kaimur | Ramgarh | M.S.Upari 9939613033 | 138 dated 16.08.2011 | 20.06.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 06.12.2016 | 5743457
135 | USS-120 (C) | 2010-11 | Patna West | Kaimur | Nuaon | Govt. Basic School Kari Ram Akhili | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Tender Process
136 | USS-120 (D) | 2010-11 | Patna West | Kaimur | Nuaon | M.S.Mushiyan 9546505256 | 138 dated 16.08.2011 | 16.03.2016 | [8 empty] | 1 |  | 1 |  | 12.03.2017 | 4349919
137 | USS-120 (E) | 2010-11 | Patna West | Kaimur | Durgawati | U.M.S Nuaon 9199361709 | 138 dated 16.08.2011 | 20.01.2016 | [8 empty] | 1 |  | 1 |  |  | 3620620
138 | USS-121 (A) | 2010-11 | Patna West | Rohtas | Karakat | M.S.Dewmarkande 8969878557 | 138 dated 16.08.2011 | 18.12.2014 | [9 empty] | 1 | 0 |  | 15.01.2017 | 4048863
139 | USS-121 (B) | 2010-11 | Patna West | Rohtas | Karakat | Girl's M.S.Motha 9162106111 | 138 dated 16.08.2011 | 18.11.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.03.2016 | 5179420
140 | USS-121 (C) | 2010-11 | Patna West | Rohtas | Nasriganj | M.S. Paiga9955477596, 9905271092 | 138 dated 16.08.2011 | 18.11.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.206 | 5077298
141 | USS-121 (D) | 2010-11 | Patna West | Rohtas | Nasriganj | M.S. Pawani 9473321921, 8298414859 | 138 dated 16.08.2011 | 03.01.2015 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4957819
142 | USS-121 (E) | 2010-11 | Patna West | Rohtas | Akorhigola | M.S.Chhapra 9934757484 | 138 dated 16.08.2011 | 11.08.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 10.08.2015 | 4978540
143 | USS-122-1 | 2010-11 | Patna West | Rohtas | Surajpura | Govt.M.S.Agrair Khurd, 9430254440 | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4672853
144 | USS-122-2 | 2010-11 | Patna West | Rohtas | Dinara | M.S.Sarwan ,8084920823 | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.09.2016 | 4672853
145 | USS-122-3 | 2010-11 | Patna West | Rohtas | Dinara | M.S. Baliyan, 9931111475 | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4672853
146 | USS-122-4 | 2010-11 | Patna West | Rohtas | Dinara | M.S. Bararhi, 9955083783 | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4672853
147 | USS-122-5 | 2010-11 | Patna West | Rohtas | Bikramganj | M.S. Jamorhi, 9955952582 | 138 dated 16.08.2011 | 13.01.2014 | 1 | [9 empty] | 0
148 | USS-122-6 | 2010-11 | Patna West | Rohtas | Bikramganj | M.S. Dhusiyankala ,08521032016 | 138 dated 16.08.2011 | 13.01.2014 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 27.09.2016 | 4672852
149 | USS-123-1 | 2010-11 | Patna West | Rohtas | Kochas | M.S.Balthari 09162543647, 09473245646 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 07.09.2015 | 5067283
150 | USS-123-2 | 2010-11 | Patna West | Rohtas | Kochas | M.S. Ubadhi, 8002578689 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
151 | USS-123-3 | 2010-11 | Patna West | Rohtas | Kochas | M.S. Kuchila, 8002537247 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 07.09.2015 | 5067283
152 | USS-123-4 | 2010-11 | Patna West | Rohtas | Kargahar | U.M.S. Goghara, 9931721820 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
153 | USS-123-5 | 2010-11 | Patna West | Rohtas | Kargahar | M.S. Khanethi, 9631193620 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.03.2015 | 5067283
154 | USS-123-6 | 2010-11 | Patna West | Rohtas | Kargahar | M.S. Rampur Naresh, 9801892595 | 138 dated 16.08.2011 | 29.8.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.03.2015 | 5067284
155 | USS-124-1 | 2010-11 | Patna West | Rohtas | Chenari | M.S. Ramgarh 9771746971 | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
156 | USS-124-2 | 2010-11 | Patna West | Rohtas | Chenari | M.S. Chandrakaithi, 9934281842 | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
157 | USS-124-3 | 2010-11 | Patna West | Rohtas | Sheosagar | M.S. Alampur, 9572407040 | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.10.2016 | 4251957
158 | USS-124-4 | 2010-11 | Patna West | Rohtas | Sheosagar | M.S. Sonhar 9006103550 | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.10.2016 | 4251956
159 | USS-124-5 | 2010-11 | Patna West | Rohtas | Sasaram | M.S. Akasi , 9204460486 | 138 dated 16.08.2011 | 26.7.2013 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.10.2016 | 4251956
160 | USS-125-1 | 2010-11 | Patna West | Rohtas | Nouhatta | M.S. Anndichak, 8002169557 | 138 dated 16.08.2011 | 2.2.2013 | [9 empty] | 1 | 0 | Inaugurated |  | 4685702
161 | USS-28-1 | 2009-10 | Magadh | Jehanabad | tgkukckn | eŒfoŒveSu 9473327625 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2013 | 4100020
162 | USS-28-2 | 2009-10 | Magadh | Jehanabad | dkdks | eŒfoŒHknljk 9006927848 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2013 | 4100020
163 | USS-28-3 | 2009-10 | Magadh | Jehanabad | e[knqeiqj | eŒfoŒdksgjk 9162155024 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 01.03.2013 | 4100021
164 | USS-28-4 | 2009-10 | Magadh | Jehanabad | jruhQjhniqj | mRØŒeŒfoŒyk[kkiqj 9934235714 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Dispute. Letter No.- BSEIDC/MAG/Ex/24/2014 Dt. 30.04.2014 Proposal for Drop. (Land not available)
165 | USS-29-1 | 2009-10 | Magadh | Aurangabad | nso | eŒfoŒcs<+uh 9631266207 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.03.2015 | 4321597
166 | USS-29-2 | 2009-10 | Magadh | Aurangabad | enuiqj | eŒfoŒfijok¡ 9934340488 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 08.03.2016 | 4321597
167 | USS-29-3 | 2009-10 | Magadh | Aurangabad | jQhxat | eŒfoŒ[kjks[kj 9006027690 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4321596
168 | USS-29-4 | 2009-10 | Magadh | Aurangabad | xksg | eŒfoŒcktkj oekZ 9939868217 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4321596
169 | USS-30-1 | 2009-10 | Magadh | Aurangabad | vkscjk | eŒfoŒ'kadjiqj 7739690373 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 19.03.2015 | 4177823
170 | USS-30-2 | 2009-10 | Magadh | Aurangabad | nkmnuxj | eŒfoŒteqvkok¡ 9801563600 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 01.04.2014 | 4177823
171 | USS-30-3 | 2009-10 | Magadh | Aurangabad | nkmnuxj | eŒfoŒpkSjh 9934434990 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.11.2014 | 4177823
172 | USS-30-4 | 2009-10 | Magadh | Aurangabad | gliqjk | eŒfoŒdksbyok¡ 9135312996 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.11.2014 | 4177823
173 | USS-31-1 | 2009-10 | Magadh | Aurangabad | dqVqEck | eŒfoŒfjfl;i 9955874942 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.12.2014 | 4160193
174 | USS-31-2 | 2009-10 | Magadh | Aurangabad | uohuxj | eŒfoŒiM+fj;k 9931622753 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 23.12.2014 | 4160193
175 | USS-31-3 | 2009-10 | Magadh | Aurangabad | ok:.k | eŒfoŒikSFkq 9471060433 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 23.12.2014 | 4160193
176 | USS-32-1 | 2009-10 | Magadh | Gaya | cks/k x;k | eŒfoŒchjgqr 9934480418 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 12.04.2016 | 4031017
177 | USS-32-2 | 2009-10 | Magadh | Gaya | uxj fuxe | eŒfoŒpwjh 9199466924 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2013 | 4031017
178 | USS-32-3 | 2009-10 | Magadh | Gaya | osykxat | mRØŒeŒfoŒve>j 9931835374 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 09.04.2014 | 4031017
179 | USS-32-4 | 2009-10 | Magadh | Gaya | fVdkjh | eŒfoŒrkik Qrsgiqj 9430070517 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 27.01.2016 | 4031016
180 | USS-33-1 | 2009-10 | Magadh | Gaya | MksHkh | eŒfoŒihjklhu 9473140628 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2015 | 4256723
181 | USS-33-2 | 2009-10 | Magadh | Gaya | dksp | eŒfoŒfnX?kh 9576852929 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2015 | 4256723
182 | USS-33-3 | 2009-10 | Magadh | Gaya | f[ktjljk; | eŒfoŒvkneiqj 9771084118 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2015 | 4256723
183 | USS-33-4 | 2009-10 | Magadh | Gaya | cthjxat | eŒfoŒikys 9955418354 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2015 | 4256723
184 | USS-34 A-1 | 2009-10 | Magadh | Gaya | ckjkpV~Vh | mRØŒeŒfoŒ/kuxbZ 9931313425 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Approach road unavailable
185 | USS-34 A-2 | 2009-10 | Magadh | Gaya | Qrsgiqj | eŒfoŒckiwxzke 9934840966 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.08.2015 | 4501315
186 | USS-34 A-3 | 2009-10 | Magadh | Gaya | eksguiqj | eŒfoŒvedksyk 9955837262 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.08.2015 | 4501314
187 | USS-34 B-1 | 2009-10 | Magadh | Gaya | xq:vk | eŒfoŒpk¡lh 9006129640 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.11.2014 | 5095977
188 | USS-34 B-2 | 2009-10 | Magadh | Gaya | bekexat | mRØŒeŒfoŒ]dksBh 9931625800 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.11.2014 | 5095977
189 | USS-35-1 | 2009-10 | Magadh | Nawada | uoknk | eŒfoŒiVok ljk; 9006212577 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 3020152
190 | USS-35-2 | 2009-10 | Magadh | Nawada | idjhojkok¡ | eŒfoŒxqyuh 995563436 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4314503
191 | USS-35-3 | 2009-10 | Magadh | Nawada | jksg 1 | mRØŒeŒfoŒf'k[kjiqj 9661237533 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 3020152
192 | USS-35-4 | 2009-10 | Magadh | Nawada | okfjlyhxat | mRØŒeŒfoŒelwnk 9708007113 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4314503
193 | USS-36-1 | 2009-10 | Magadh | Nawada | vdcjiqj | eŒfoŒrs;kj | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Approach road unavailable
194 | USS-36-2 | 2009-10 | Magadh | Nawada | jtkSyh | mRØŒeŒfoŒ]ckjkVk¡M loS;k | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.03.2015 | 4200953
195 | USS-36-3 | 2009-10 | Magadh | Nawada | fljnyk | eŒfoŒlka< 9771960601 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.03.2015 | 4200953
196 | USS-143-1 | 2010-11 | Magadh | Jehanabad | Kako | M.S.Kajisarai 9934814478 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.11.2013 | 4901494
197 | USS-143-2 | 2010-11 | Magadh | Jehanabad | Kako | M.S.Dedhsaiya, 9955836404 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.11.2013 | 4901494
198 | USS-143-3 | 2010-11 | Magadh | Jehanabad | Kako | M.S.Pinzour 9931803275 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Insufficient Land
199 | USS-143-4 | 2010-11 | Magadh | Jehanabad | Modanganj | M.S.Jalalpur , 9939911087 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.11.2013 | 4901495
200 | USS-144 (A) | 2010-11 | Magadh | Jehanabad | Hulasganj | M.S.Vira, 9771693433 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4413483
201 | USS-144 (B) | 2010-11 | Magadh | Jehanabad | Makhdumpur | M.S.Akbarpur, 9934858600 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Not started
202 | USS-144 (C) | 2010-11 | Magadh | Jehanabad | Jehanabad | M.S.Bazartali, 9955297199 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3462361
203 | USS-145-1 | 2010-11 | Magadh | Nawada | Nawada | U.M.S. Jhunathi, 9631172127 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3712006
204 | USS-145-2 | 2010-11 | Magadh | Nawada | Akbarpur | U.M.S. Derma, 9931232692 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3712006
205 | USS-145-3 | 2010-11 | Magadh | Nawada | Akbarpur | M.S. Kuhaila, 9771085197 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4367066
206 | USS-145-4 | 2010-11 | Magadh | Nawada | Akbarpur | M.S. Paharpur, 9771672098 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3712006
207 | USS-145-5 | 2010-11 | Magadh | Nawada | Nawada | M.S. Wermi, 9708857028 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
208 | USS-146 (A) | 2010-11 | Magadh | Nawada | Govindpur | M.S. Rampur, 9771867218 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 07.07.2016 | 5197671
209 | USS-146 (B) | 2010-11 | Magadh | Nawada | Roh 3 | M.S. Wara panday, 9931630318 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5154654
210 | USS-146 (C) | 2010-11 | Magadh | Nawada | Pakribarawan | M.S. Deodha, 8578046529 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.06.2015 | 5222945
211 | USS-146 (D) | 2010-11 | Magadh | Nawada | Pakribarawan | M.S. Ukaorah | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4821920
212 | USS-146 (E) | 2010-11 | Magadh | Nawada | Kashichak | U.M.S. Vishbnathpur , 9386540972 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Retender
213 | USS-147-1 | 2010-11 | Magadh | Nawada | Narhat | M.S. Khanwa, 9905846666 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4480450
214 | USS-147-2 | 2010-11 | Magadh | Nawada | Hasua | Adarsh M.S. Bhadsaini, 9939018688 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4480451
215 | USS-148-1 | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Moratala, 9934282506 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3556262
216 | USS-148-2 | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Titoiya, 9934672899 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 2091921
217 | USS-148-3 | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Bataspur, 9470447309 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3556262
218 | USS-148-4 | 2010-11 | Magadh | Gaya | Bodh Gaya | M.S. Gapha Kala, 9934972678 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Not start. Insufficient Land
219 | USS-149 (A) | 2010-11 | Magadh | Gaya | Dumariya | M.S. Bhangiya, 9472443151 9801769544 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5148020
220 | USS-149 (B) | 2010-11 | Magadh | Gaya | Imamganj | M.S. Karsan Kala, 9199768865, 9199061230 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 13.05.2016 | 5008684
221 | USS-149 (C) | 2010-11 | Magadh | Gaya | Imamganj | M.S. Salaiya, 9471093249, 8969123151 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 18.02.2016 | 4989238
222 | USS-149 (D) | 2010-11 | Magadh | Gaya | Imamganj | M.S. Naudiha, 9135294703, 8235212693 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 10.03.2016 | 5059171
223 | USS-149 (E) | 2010-11 | Magadh | Gaya | Imamganj | M.S. Mjiyarpur Bahera, 9801672105, 8092670699 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 20.07.2015 | 5380074
224 | USS-150 (A) | 2010-11 | Magadh | Gaya | Belaganj | M.S. Chirala, 9934883794, 9199681520 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 31.01.2016 | 4714441
225 | USS-150 (B) | 2010-11 | Magadh | Gaya | Tekari | M.S. Urdu Bishnupur, 9771128251, 9135850031 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3925878
226 | USS-150 (C) | 2010-11 | Magadh | Gaya | Konch | M.S. Goribigha, 9939408167 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4384516
227 | USS-150 (D) | 2010-11 | Magadh | Gaya | Konch | M.S. Ahiyarpur, 9934008030 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4548801
228 | USS-151-1 | 2010-11 | Magadh | Gaya | Bathani | Basic M.S. Radui, 7654409634 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.12.2014 | 4727421.9967
229 | USS-151-2 | 2010-11 | Magadh | Gaya | Bathani | M.S. Karubigha, 9934427661 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.12.2014 | 4727423
230 | USS-151-3 | 2010-11 | Magadh | Gaya | Khizarsarai | M.S. Sonas, 9931434932 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.12.2014 | 4727423
231 | USS-152-1 | 2010-11 | Magadh | Gaya | Tankauppa | M.S.Utalibara, 9934434061 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.08.2015 | 4436714
232 | USS-152-2 | 2010-11 | Magadh | Gaya | Tankauppa | M.S. Gajadharpur, 9934063626 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4436714
233 | USS-152-3 | 2010-11 | Magadh | Gaya | Fatehpur | M.S. Khajuri, 8969107991 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4436714
234 | USS-152-4 | 2010-11 | Magadh | Gaya | Fatehpur | M.S. Nagwa, 9798270089 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3771211
235 | USS-152-5 | 2010-11 | Magadh | Gaya | Manpur | M.S. Sadikpur, 9955056070, 9801212926 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.08.2015 | 4436714
236 | USS-152-6 | 2010-11 | Magadh | Gaya | Manpur | M.S. Kaiya, 9771196567, 7277124934 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 13.08.2015 | 4436714
237 | USS-153 (A) | 2010-11 | Magadh | Gaya | Barachatty | U.M.S. Barawadih, 9631852939 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4947507
238 | USS-153 (B) | 2010-11 | Magadh | Gaya | Guraru | M.S. Manjhar, 9572789270 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 3746778
239 | USS-153 (C) | 2010-11 | Magadh | Gaya | Amas | M.S. Baliyari, 9570551566, 8294856371, 8051934469 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 2281952
240 | USS-153 (D) | 2010-11 | Magadh | Gaya | Sherghatty | M.S. Naknuppa, 9431289085 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
241 | USS-154-1 | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Mahsu, 9631400107 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.02.2015 | 5132054
242 | USS-154-2 | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Chintaman Bigha, 9199013498 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.02.2015 | 5132054
243 | USS-154-3 | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Darmi, 9955519885, 9931921788 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available. (PROPOSED FOR DROP)
244 | USS-154-4 | 2010-11 | Magadh | Aurangabad | Kutumba | M.S. Jhakri, 7654545570, 9162783589 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.01.2015 | 5132053
245 | USS-154-5 | 2010-11 | Magadh | Aurangabad | Deo | M.S. Vijouli, 9801123435 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.02.2015 | 5132053
246 | USS-155-1 | 2010-11 | Magadh | Aurangabad | Barun | M.S. Tahal Amba, 9931428989 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 13.12.2014 | 4953704
247 | USS-155-2 | 2010-11 | Magadh | Aurangabad | Obra | M.S. Ratwar, 9931418907 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.12.2014 | 4953705
248 | USS-155-3 | 2010-11 | Magadh | Aurangabad | Obra | M.S. Tejpur, 9973299799 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available. (PROPOSED FOR DROP.- LETTER NO.BSEIDC/MAG/EX/377/2015 DATED- 28/09/2015)
249 | USS-155-4 | 2010-11 | Magadh | Aurangabad | Obra | M.S. Karsawan, 9470488343 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.12.2014 | 4953704
250 | USS-156-1 | 2010-11 | Magadh | Aurangabad | Haspura | M.S. Piru, 9135064392 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Encrochment
251 | USS-156-2 | 2010-11 | Magadh | Aurangabad | Haspura | M.S. Sriwanbhatt, 9939023445 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
252 | USS-156-3 | 2010-11 | Magadh | Aurangabad | Daudnagar | M.S. Belwan, 9162117681, 9934238032 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4930998
253 | USS-157 (A) | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Badhopur, 9955270100 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.08.2015 | 5204445
254 | USS-157 (B) | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Pogar, 9973150471 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3231282
255 | USS-157 (C) | 2010-11 | Magadh | Aurangabad | Madanpur | M.S. Judahi, 9931892284 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 08.09.2015 | 5226367
256 | USS-157 (D) | 2010-11 | Magadh | Aurangabad | Madanpur | M.S. Saliya, 9955803641 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2514834
257 | USS-157 (E) | 2010-11 | Magadh | Aurangabad | Raphiganj | M.S. Danai, 9097351245 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 2936509
258 | USS-20-1 | 2009-10 | Munger | Munger | gosyh [kM+xiqj | eŒfoŒj?kqukFkiqj | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Problem
259 | USS-20-2 | 2009-10 | Munger | Munger | eqaxsj lnj | eŒfoŒVhdkjkeiqj 9431612789 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Problem
260 | USS-20-3 | 2009-10 | Munger | Munger | /kjgjk | eŒfoŒegjuk 9504681361@9852445511 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 1491139
261 | USS-21-1 | 2009-10 | Munger | Sheikhpura | 'ks[kiqjk | eŒfoŒckn'kkgiqj 9709066149 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.03.2013 | 4282252
262 | USS-22-1 | 2009-10 | Munger | Jamui | pdkbZ | eŒfoŒnqyeiqj 9973390953@9661984491 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 2014-03-01 | 4451460
263 | USS-22-2 | 2009-10 | Munger | Jamui | >k>k | eŒfoŒf'ko eafnj cfy;kMhg 9934566478 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 22.07.2014 | 4451460
264 | USS-22-3 | 2009-10 | Munger | Jamui | lksuks | eŒfoŒiSjk efVgkuk 9801576608 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 22.07.2014 | 4451460
265 | USS-23-1 | 2009-10 | Munger | Jamui | teqbZ | mRØŒeŒfoŒ HkkVpd 9430818763 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 26.08.2014 | 4514149
266 | USS-23-2 | 2009-10 | Munger | Jamui | y{ehiqj | eŒfoŒgjyk 9162733763@9006655639 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 26.08.2014 | 4514149
267 | USS-23-3 | 2009-10 | Munger | Jamui | [kSjk | mRØŒeŒfoŒ ck/kk[kkWM++ 9955740414 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 26.08.2014 | 4514149
268 | USS-23-4 | 2009-10 | Munger | Jamui | bZŒ vyhxat | eŒfoŒfetkZxat 8292659272 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 26.08.2014 | 4514150
269 | USS-24-1 | 2009-10 | Munger | Begusarai | cNokM+k | eŒfoŒQrsg 9570919206 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4810561
270 | USS-24-2 | 2009-10 | Munger | Begusarai | Hkxokuiqj | eŒfoŒeksf[r;kjiqj 9934441250 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.05.2013 | 4810561
271 | USS-24-3 | 2009-10 | Munger | Begusarai | psfj;k cfj;kjiqj | eŒfoŒldjoklk 9939576953 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 16.06.2013 | 4810562
272 | USS-25-1 | 2009-10 | Munger | Begusarai | cfy;k | eŒfoŒelwnuiqj 9955252445 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 | Roof Casted , work stopped after R.C. , due to land dispute |  | 2219305
273 | USS-25-2 | 2009-10 | Munger | Begusarai | rs?kjk | eŒfoŒxkSjk&1 9973170370 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4931792
274 | USS-25-3 | 2009-10 | Munger | Begusarai | lkgsciqj deky | eŒfoŒfo".kqiqj vkgksd 9534757293 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
275 | USS-26-1 | 2009-10 | Munger | Begusarai | cjkSuh | eŒfoŒcFkkSyh 9801572247@9534334080 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 16.07.2013 | 4780393
276 | USS-26-2 | 2009-10 | Munger | Begusarai | efVgkuh | eŒfoŒtxriqjk 9939465778 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.07.2013 | 4780393
277 | USS-27-1 | 2009-10 | Munger | Khagaria | ijoÙkk | eŒfoŒdjuk 9939629342@9006237936 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4920833
278 | USS-27-2 | 2009-10 | Munger | Khagaria | vykSyh | eŒfoŒes?kkSuk 9534870633 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4920833
279 | USS-27-3 | 2009-10 | Munger | Khagaria | pkSFke | eŒfoŒigkM+pd 9431651745 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4920833
280 | USS-27-4 | 2009-10 | Munger | Khagaria | xksxjh | eŒfoŒidjSy 9955068112 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4920833
281 | USS-27-5 | 2009-10 | Munger | Khagaria | [kxfM+;k | eŒfoŒeksjdkgh Fkkuk 9534404397 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4920832
282 | USS-132-1 | 2010-11 | Munger | Sheikhpura | Barbigha | M.S.Keuti | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.01.2015 | 4825065
283 | USS-132-2 | 2010-11 | Munger | Sheikhpura | SheKhpura | M.S.Lodipur | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.01.2015 | 4825065
284 | USS-132-3 | 2010-11 | Munger | Sheikhpura | Chewara | M.S.Lahana | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.01.2015 | 4825065
285 | USS-132-4 | 2010-11 | Munger | Sheikhpura | Ghat Kushumbha | M.S.Bamghat | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.01.2015 | 4825065
286 | USS-132-5 | 2010-11 | Munger | Sheikhpura | Ariari | M.S.Husainawad | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.01.2015 | 4825065
287 | USS-133(A) | 2010-11 | Munger | Lakhisarai | Barahiya | M.S.Pali 9546977875 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 04.02.2016 | 5172716
288 | USS-133(B) | 2010-11 | Munger | Lakhisarai | Barahiya | M.S.Lal Diyara 9097688412 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land dispute
289 | USS-133(C) | 2010-11 | Munger | Lakhisarai | Halsi | M.S. Geruapursanda 8084044144 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available. Dropped
290 | USS-133(D) | 2010-11 | Munger | Lakhisarai | Lakhisarai | U.M.S. Kachhiyana 9934788038, 9199110418 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 05.07.2015 | 5314780
291 | USS-133(E) | 2010-11 | Munger | Lakhisarai | Suryagarha | U.M.S. Lahasaurwa 9631695175, 8434346388 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 2615151
292 | USS-133(F) | 2010-11 | Munger | Lakhisarai | Pipariya | M.S. Pawai 9263032826 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5278158
293 | USS-134-1 | 2010-11 | Munger | Jamui | Sono | M.S.Buijhayt 09631584296 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 2651801
294 | USS-135-1 | 2010-11 | Munger | Munger | Asarganj | M.S.Chakhand 9135065232 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4857416.9967
295 | USS-135-2 | 2010-11 | Munger | Munger | Asarganj | M.S. Beran 9204931976 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4857418
296 | USS-135-3 | 2010-11 | Munger | Munger | Tarapur | M.S. Mahamadpur 9709507263 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4857418
297 | USS-136-1 | 2010-11 | Munger | Munger | Sangrampur | M.S.Bhikhdih 9006793477 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5300308
298 | USS-136-2 | 2010-11 | Munger | Munger | Sangrampur | M.S.Khapra 9934832035 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
299 | USS-136-3 | 2010-11 | Munger | Munger | Sangrampur | M.S.Katiyari 9199782900 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5300308
300 | USS-137-1 | 2010-11 | Munger | Munger | Bariyarpur | M.S.Ratanpur 9430453475 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4878010
301 | USS-137-2 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Jamuhat 8051879837 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4878010
302 | USS-137-3 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Gangata 8544287260 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4878011
303 | USS-137-4 | 2010-11 | Munger | Munger | Haweli Khadagpur | U.M.Gangata More 9471899589 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4878011
304 | USS-137-5 | 2010-11 | Munger | Munger | Haweli Khadagpur | M.S.Chhoti Manjhagoya 9470400961, 9934017811 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4878011
305 | USS-138-1 | 2010-11 | Munger | Begusarai | Mansurchak | M.S.Chhabilapur 9771848155 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
306 | USS-138-2 | 2010-11 | Munger | Begusarai | Begusarai | M.S.Bharra 9204202640 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3658867
307 | USS-138-3 | 2010-11 | Munger | Begusarai | Begusarai | M.S.Babasudebpur 9934708295, 88777402400 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1951395
308 | USS-138-4 | 2010-11 | Munger | Begusarai | Matihani | M.S.Richiyahi Nayartol 9973647476, 9608273410 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1951395
309 | USS-138-5 | 2010-11 | Munger | Begusarai | Sahebpur Kamal | M.S.Rajoura 9709067460 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
310 | USS-139-1 | 2010-11 | Munger | Begusarai | Bachhawara | M.S.Dadupur 9801471859 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4578151
311 | USS-139-2 | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Pansalla 9939728107 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4578151
312 | USS-139-3 | 2010-11 | Munger | Begusarai | Chhaurahi | M.S.Sihama 9973149590 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4578151
313 | USS-139-4 | 2010-11 | Munger | Begusarai | Khodawantpur | M.S.Begampur 9631129256 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4578151
314 | USS-139-5 | 2010-11 | Munger | Begusarai | Nawakothi | M.S.Rajakpur 9667863543 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4578152
315 | USS-140-1 | 2010-11 | Munger | Begusarai | Garhpura | M.S.Kuddhar 9955509070 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4799563
316 | USS-140-2 | 2010-11 | Munger | Begusarai | Dandari | M.S.Katarmala 9709640304 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4799563
317 | USS-140-3 | 2010-11 | Munger | Begusarai | Bakhari | M.S.Ghaghara 9570665862 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4799563
318 | USS-141 (A) | 2010-11 | Munger | Khagaria | Alauli | M.S.Shumbha Ghat 8969741611 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5738627
319 | USS-141 (B) | 2010-11 | Munger | Khagaria | Alauli | M.S.Khairi Khutaha 9471283095 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5322965
320 | USS-141 (C) | 2010-11 | Munger | Khagaria | Khagaria | M.S.Nanku Mandal Tola 9955646986 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land dispute in court
321 | USS-141 (D) | 2010-11 | Munger | Khagaria | Khagaria | M.S.Mathar 9771388437 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 28.03.2016 | 6084753
322 | USS-142-1 | 2010-11 | Munger | Khagaria | Beldaur | M.S.Kainjari 7549429234 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
323 | USS-142-2 | 2010-11 | Munger | Khagaria | Beldaur | M.S.Khairi Kurbani 9631652583 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5121092
324 | USS-142-3 | 2010-11 | Munger | Khagaria | Parbatta | M.S.Timapur Lagar 8877288448 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.03.2015 | 5121092
325 | USS-15-1 | 2009-10 | Bhagalpur | Bhagalpur | Shahkund | MS Dindayalpur 8809672417 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4515294
326 | USS-15-2 | 2009-10 | Bhagalpur | Bhagalpur | Sultanganj | MS Udadih 9801583582 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4515295
327 | USS-15-3 | 2009-10 | Bhagalpur | Bhagalpur | NathNagar | MS Ajmeribariya 8969037136 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 | SLOW WORK( 2ND DEBAR LETTER ISSUED)(STOPPED FROM MARCH 2014() |  | 1806117
328 | USS-15-4 | 2009-10 | Bhagalpur | Bhagalpur | Jagdishpur | MS Mohammadpur 9279216759 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4515295
329 | USS-16-1 | 2009-10 | Bhagalpur | Bhagalpur | Sanhola | MS Madarganj 9955488107/ | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4242445
330 | USS-16-2 | 2009-10 | Bhagalpur | Bhagalpur | Pirpainti | MS Dilouri 9801095027 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4242445
331 | USS-16-3 | 2009-10 | Bhagalpur | Bhagalpur | Kahalgaon | MS Pannuchak 9279457160 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4242445
332 | USS-16-4 | 2009-10 | Bhagalpur | Bhagalpur | Goradih | MS Garhotiya 9931865594 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4242446
333 | USS-17-1 | 2009-10 | Bhagalpur | Bhagalpur | Sabaur | MS Shivaydih 9973394344 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.09.2013 | 4862662
334 | USS-17-2 | 2009-10 | Bhagalpur | Bhagalpur | Kharik | MS Dadpur 8051625862/ 2 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.09.2013 | 4862662
335 | USS-17-3 | 2009-10 | Bhagalpur | Bhagalpur | Bihpur | MS Kaharour 9934602158 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Droped, Land not available
336 | USS-17-4 | 2009-10 | Bhagalpur | Bhagalpur | Ismailpur | MS Laxmipur 9546492998 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.09.2013 | 4862662
337 | USS-18-1 | 2009-10 | Bhagalpur | Banka | Barahat | MS Saharna 9431689507/ | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 01.07.2014 | 4242879
338 | USS-18-2 | 2009-10 | Bhagalpur | Banka | Bounsi | MS Bishanpur 9006554728 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 04.12.2014 | 4242879
339 | USS-18-3 | 2009-10 | Bhagalpur | Banka | Dhouriya | MS Bhatuachak 9955916141 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.03.2014 | 4242879
340 | USS-18-4 | 2009-10 | Bhagalpur | Banka | Rajoun | MS Majhgay 9771243197 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.10.2014 | 4242879
341 | USS-19-1 | 2009-10 | Bhagalpur | Banka | Amarpur | MS Bhadariya 9939749402 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 3530044
342 | USS-19-2 | 2009-10 | Bhagalpur | Banka | Chandan | UMS Asudha-Mukunda 9199722081 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353542
343 | USS-19-3 | 2009-10 | Bhagalpur | Banka | Katoriya | MS Bhorsar 9304136524 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353542
344 | USS-19-4 | 2009-10 | Bhagalpur | Banka | Belhar | UMS Nagel 9934928705 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353541
345 | USS-19-5 | 2009-10 | Bhagalpur | Banka | Shambhuganj | MS Rajghat 9199067916 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | DEBAR ON DATED 31.3.2016.2ND LETTER FOR RECINED TO C.E. |  | 3353541
346 | USS-126 (A) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S.Basudeopur Bhaluya 9801295281 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 5429502
347 | USS-126 (B) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Maheshmunda 8987170031 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Handover |  | 4917175
348 | USS-126 (C) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Ekdara 9961316463 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Handover |  | 5052732
349 | USS-126 (D) | 2010-11 | Bhagalpur | Bhagalpur | Kahalgaon | M.S. Saur 9430428851 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 24.12.2016 | 4942059
350 | USS-127 (A) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Mahuadhih 9955027709, 7549131650 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 21.01.2017 | 3789711
351 | USS-127 (B) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S. Maultola, 9534766339 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1
352 | USS-127 (C) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Mahadeo Tikar 9973648394 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5240787
353 | USS-127 (D) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Ekchari Diyara 9507752647, 9934426205 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 10.02.2017 | 5630115
354 | USS-127 (E) | 2010-11 | Bhagalpur | Bhagalpur | Pirpainti | M.S.Lakshmipur 7549681618 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4882446
355 | USS-128 (A) | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Birnaugha 9955198006 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 26.01.2017 | 5048149
356 | USS-128 (B) | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Agarpur 9931629228 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 28.12.2015 | 5401431
357 | USS-128 (C) | 2010-11 | Bhagalpur | Bhagalpur | Goradih | M.S.Danda Bazar 9801648849 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5023873
358 | USS-128 (D) | 2010-11 | Bhagalpur | Bhagalpur | Sabaur | Govt. M.S.Kurpat 9204660635, 9931729153 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 | LETTER FOR DEBAR TO C.E. |  | 2719586
359 | USS-129 (A) | 2010-11 | Bhagalpur | Bhagalpur | Rangrachauk | M.S.Murli 9534523062 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 | LAND GIVEN BY PRINCIPAL ON 19-12-16. |  | 1743984
360 | USS-129 (B) | 2010-11 | Bhagalpur | Bhagalpur | Gopalpur | M.S.Kelendi Nagar 9801016695 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5619506
361 | USS-130-1 | 2010-11 | Bhagalpur | Bhagalpur | Nath Nagar | M.S.Fathehpur 9199519165 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.04.2014 | 5277527
362 | USS-130-2 | 2010-11 | Bhagalpur | Bhagalpur | Shahkund | M.S.Bakchapar 9939070704 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.04.2014 | 5277528
363 | USS-130-3 | 2010-11 | Bhagalpur | Bhagalpur | Shahkund | M.S.Khaira 9931326337 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.04.2014 | 5277528
364 | USS-130-4 | 2010-11 | Bhagalpur | Bhagalpur | Sultanganj | M.S.Abharatanpur 9939267569 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.04.2014 | 5277528
365 | USS-130-5 | 2010-11 | Bhagalpur | Bhagalpur | Sultanganj | M.S.Kiranpur 9801149910 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.04.2014 | 5277528
366 | USS-131-1 | 2010-11 | Bhagalpur | Banka | Amarpur | M.S.Surihari 9931727384 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | LETTER FOR DEBAR TO C.E. |  | 4156210
367 | USS-131-2 | 2010-11 | Bhagalpur | Banka | Belhar | M.S.Hatiyadadha 8521126388 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | LETTER FOR DEBAR TO C.E. |  | 4156210
368 | USS-131-3 | 2010-11 | Bhagalpur | Banka | Dhoraiya | U.M.S.Jharkha 9934883358 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 | LETTER FOR DEBAR TO C.E. |  | 4156210
369 | USS-71-1 | 2009-10 | Kosi | Madhepura | Madhepura | M/S Bharahi Bazar 9852057904 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Dispute
370 | USS-71-2 | 2009-10 | Kosi | Madhepura | Murliganj | M/S Parsha Navtol 9973625392 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5044198
371 | USS-71-3 | 2009-10 | Kosi | Madhepura | Kumarkhand | M/S Karuvaili 9771194253 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5044198
372 | USS-71-4 | 2009-10 | Kosi | Madhepura | Sigheshwar | M/S Singyon 9430633497 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5044198
373 | USS-72-1 | 2009-10 | Kosi | Madhepura | Uda kishunganj | M/S Barataini 9631850096 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5078932
374 | USS-72-2 | 2009-10 | Kosi | Madhepura | Chausa | Lalji M/S Laua Lagan 8969228737 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5078932
375 | USS-72-3 | 2009-10 | Kosi | Madhepura | Alamnagar | M/S Bargaon 9939489984 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.06.2015 | 5078933
376 | USS-73-1 | 2009-10 | Kosi | Saharsa | Saur Bazar | M/S Khajuri 9472653157 9430632563 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5274930
377 | USS-73-2 | 2009-10 | Kosi | Saharsa | Navhatta | M/S Kedalpatti 9939942137 8987203752 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5274930
378 | USS-73-3 | 2009-10 | Kosi | Saharsa | Sonbarsa | M/S Pachlakh 7549317375 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.12.2014 | 5274931
379 | USS-74-1 | 2009-10 | Kosi | Saharsa | Salkhua | M/S Pipra Bageva 9905964384 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 3967262
380 | USS-74-2 | 2009-10 | Kosi | Saharsa | Simri Bakhtiyarpur | M/S Ghoghsam 9471654377 | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | 1 | Work Stopped |  | 991816
381 | USS-74-3 | 2009-10 | Kosi | Saharsa | Mahishi | M/S Jhara 9430696742 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 3967263
382 | USS-75-1 | 2009-10 | Kosi | Supaul | Basantpur | M/S Balbhadrapur 9472034607 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.05.2014 | 5418531
383 | USS-75-2 | 2009-10 | Kosi | Supaul | Chatapur | M/S Madhubani 9631295927 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.05.2014 | 5418531
384 | USS-75-3 | 2009-10 | Kosi | Supaul | Marauna | M/S Parikoch 9931662963 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.05.2014 | 5418531
385 | USS-75-4 | 2009-10 | Kosi | Supaul | Raghopur | Lakhi Chand Sahu M/S Hariraha 9470047275 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.05.2014 | 5418530
386 | USS-76-1 | 2009-10 | Kosi | Supaul | Kishanpur | M/S Phulwaria 8298274284 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.05.2014 | 4984565
387 | USS-76-2 | 2009-10 | Kosi | Supaul | Pipra | M/S Ramnagar 9472335572 9570603091 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.05.2014 | 4984565
388 | USS-76-3 | 2009-10 | Kosi | Supaul | Supaul | M/S Kariho 9430029088 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.05.2014 | 4984565
389 | USS-76-4 | 2009-10 | Kosi | Supaul | Triveniganj | M/S Kumiyahi 8986062906 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.05.2014 | 4984564
390 | USS-199C | 2010-11 | Kosi | Saharsa | Banma Ithari | Middle School Ithari 8084243454 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 19.12.2015 | 5055354
391 | USS-199D-1 | 2010-11 | Kosi | Madhepura | Ghailarh | Middle School Chiknotwa 9430942006 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5460744
392 | USS-199 D-2 | 2010-11 | Kosi | Madhepura | Singheshwar | Middle School Barhari 9661376885 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.01.2015 | 5460745
393 | USS-199D-3 | 2010-11 | Kosi | Madhepura | Kumarkhand | Middle School Rahta 9631460084 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
394 | USS-77-1 | 2009-10 | Purnea | Araria | Bhargama | उत्क्र॰म॰वि॰रहड़िया | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | 0 | Inaugurated | 2015-06-02 | 5194053
395 | USS-77-2 | 2009-10 | Purnea | Araria | Raniganj | बालिका म॰वि॰गुणवती 9771105449 | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | 0 | Inaugurated | 2015-03-03 | 5194053
396 | USS-77-3 | 2009-10 | Purnea | Araria | Raniganj | म॰वि॰परमानंदपुर | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | 0 | Inaugurated | 23/04/2015 | 5194053
397 | USS-77-4 | 2009-10 | Purnea | Araria | Narpatganj | म॰वि॰नोनिया टोला चकला | 138 dated 16.08.2011 | 44SBD OF 2012-13 Dt. 24.07.12 | [9 empty] | 1 | 0 | Inaugurated | 2015-12-08 | 5194051
398 | USS-78-1 | 2009-10 | Purnea | Araria | Farbisganj | म॰वि॰मधुबनी 9661601762 | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | 0 | Inaugurated | 22/08/2015 | 6300438
399 | USS-78-2 | 2009-10 | Purnea | Araria | Farbisganj | म॰वि॰टेढ़ी मुसहरी | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | 0 | Inaugurated | 14/01/2015 | 6300438
400 | USS-78-3 | 2009-10 | Purnea | Araria | Araria | म॰वि॰पैकटोला | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | 0 | Inaugurated | 14/01/2015 | 6300438
401 | USS-78-4 | 2009-10 | Purnea | Araria | Araria | म॰वि॰बाँसबाड़ी 9430264342 | 138 dated 16.08.2011 | 207SBD OF 2013-14 Dt. 15.01.14 | [9 empty] | 1 | 0 | Inaugurated | 2015-08-03 | 6300437
402 | USS-79-1 | 2009-10 | Purnea | Araria | Kursakanta | म॰वि॰कपारफोड़ा | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | 0 | Inaugurated | 28/02/2014 | 5571632
403 | USS-79-2 | 2009-10 | Purnea | Araria | Sikti | म॰वि॰सोहागमाड़ों | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | 0 | Inaugurated | 28/02/2014 | 5571632
404 | USS-79-3 | 2009-10 | Purnea | Araria | Jokihat | म॰वि॰भूना 9570679546 | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | 1 | [9 empty] | 0 | May be Drop. Final bill
405 | USS-79-4 | 2009-10 | Purnea | Araria | Palasi | म॰वि॰रूपैल मधैल | 138 dated 16.08.2011 | 56SBD OF 2012-13Dt. 10.10.12 | [9 empty] | 1 | 0 | Inaugurated | 28/02/2014 | 5571632
406 | USS-80-1 | 2009-10 | Purnea | Kishanganj | Dighalbank | म॰वि॰हरवाडंगा | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | 0 | Inaugurated |  | 5148963
407 | USS-80-2 | 2009-10 | Purnea | Kishanganj | Thakurganj | म॰वि॰जंगलभीटा | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | 0 | Inaugurated |  | 5148963
408 | USS-80-3 | 2009-10 | Purnea | Kishanganj | Kochadhaman | म॰वि॰धनपुरा 9470868499 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | 0 | Inaugurated |  | 5148963
409 | USS-80-4 | 2009-10 | Purnea | Kishanganj | Pothiya | म॰वि॰हरिपोखर क्रांतिगाछ 9430677962 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | 0 | Inaugurated |  | 5148963
410 | USS-80-5 | 2009-10 | Purnea | Kishanganj | Bahadurganj | म॰वि॰हरिभाषा 9471834254 | 138 dated 16.08.2011 | 4 SBD OF 2012-13 Dt. 09.04.12 | [9 empty] | 1 | 0 | Inaugurated |  | 5148964
411 | USS-81-1 | 2009-10 | Purnea | Purnea | K Nagar | आदर्श म॰वि॰परोरा 9631003614 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated | 19/12/2014 | 4622720
412 | USS-81-2 | 2009-10 | Purnea | Purnea | Kasba | उत्क्र॰ म॰ वि॰ कदवा 9006717685/9162698638 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated | 2015-12-09 | 4622720
413 | USS-81-3 | 2009-10 | Purnea | Purnea | Dagrua | म॰वि॰मोहम्मदपुर 8877902279/9852305617 | 138 dated 16.08.2011 | 28 SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated |  | 4622719
414 | USS-82-1 | 2009-10 | Purnea | Purnea | Dhamdaha | आदर्श म॰वि॰विशनपुर 8002692294 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated | 31.07.2014 | 4586049
415 | USS-82-2 | 2009-10 | Purnea | Purnea | Bhawanipur | म॰वि॰ब्रह्मज्ञानी 9931249419 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated | 31.07.2014 | 4586049
416 | USS-82-3 | 2009-10 | Purnea | Purnea | Rupauli | म॰वि॰लालगंज 9934565697 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 31.07.2014 | 4586049
417 | USS-82-4 | 2009-10 | Purnea | Purnea | Banmankhi | म॰वि॰जानकी नगर हाट 9430675018 | 138 dated 16.08.2011 | 29SBD OF 2012-13 Dt. 25.05.12 | [9 empty] | 1 | 0 | Inaugurated | 31.07.2014 | 4586048
418 | USS-83-1 | 2009-10 | Purnea | Purnea | Vayasi | म॰वि॰आसजा मबैया 9931676786 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | Avaibility Of land after one year,Contractor not interested in work now
419 | USS-83-2 | 2009-10 | Purnea | Purnea | Amaur | म॰वि॰मच्छट्टा 9470487168/9934622591 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | Avaibility Of land after one year,Contractor not interested in work now
420 | USS-83-3 | 2009-10 | Purnea | Purnea | Vaisa | म॰वि॰मालोपाड़ा 9939083102 | 138 dated 16.08.2011 | 51SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | Avaibility Of land after one year,Contractor not interested in work now
421 | USS-84-1 | 2009-10 | Purnea | Katihar | Balrampur | म॰वि॰झलझली 9434962404/8986444230 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | No Land, Proposal for Drop
422 | USS-84-2 | 2009-10 | Purnea | Katihar | Barsoi | म॰ वि॰ बसलगांव 9126846409 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 | Inaugurated | 14/07/2014 | 5113164
423 | USS-84-3 | 2009-10 | Purnea | Katihar | Barsoi | म॰ वि॰ ढट्ठा 9471674809 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 | Inaugurated | 2014-02-07 | 5113164
424 | USS-84-4 | 2009-10 | Purnea | Katihar | Ajamnagar | म॰ वि॰ जलकी 9470423557/ 8877799621 | 138 dated 16.08.2011 | 52SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 | Inaugurated | 2014-12-07 | 5113165
425 | USS-85-1 | 2009-10 | Purnea | Katihar | Barari | म॰वि॰बकिया सुखाय 9572154446 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | Land not available (E.E letter No.-731/14-15 Dt.28.10.14)
426 | USS-85-2 | 2009-10 | Purnea | Katihar | Manihari | म॰वि॰पटनी नारायणपुर 9430970158 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 | Inaugurated |  | 4987532
427 | USS-85-3 | 2009-10 | Purnea | Katihar | Phalka | म॰वि॰झगरूचक 0431668067 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 |  | 28/09/2015 | 4987532
428 | USS-85-4 | 2009-10 | Purnea | Katihar | Kodha | म॰वि॰शिशिया 9431625914 | 138 dated 16.08.2011 | 53SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 |  |  | 4987532
429 | USS-86-1 | 2009-10 | Purnea | Katihar | Ahamdabad | म॰वि॰दिल्ली दिवानगंज 9431667161/7631741488 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | May be Drop
430 | USS-86-2 | 2009-10 | Purnea | Katihar | Kadwa | म॰वि॰आशयानी 8986509086 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | [9 empty] | 1 | 0 | Inaugurated | 15/06/2013 | 4952737
431 | USS-86-3 | 2009-10 | Purnea | Katihar | Kadwa | म॰वि॰चौकी 9470208190 | 138 dated 16.08.2011 | 11SBD OF 2012-13 Dt. 28.09.12 | 1 | [9 empty] | 0 | May be Drop
432 | USS-194-1 | 2010-11 | Purnea | Purnea | Amaur | U. M. S. Bagdar 9939096309 | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | 0 | Inaugurated | 01.08.2015 | 5267661
433 | USS-194-2 | 2010-11 | Purnea | Purnea | K. Nagar | M S Gauasi 9473124829 | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
434 | USS-194-3 | 2010-11 | Purnea | Purnea | Purnia East | M S Maranga 9939732346 | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
435 | USS-194-4 | 2010-11 | Purnea | Purnea | Rupauli | M. S. Bairiya 9434821065 | 138 dated 16.08.2011 | 156 SBD OF 2013-14 Dt. 25.11.13 | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 01.08.2015 | 5267661
436 | USS-195-1 | 2010-11 | Purnea | Katihar | Amdabad | M. S. Laxmipur Daiwa 7549854721 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3937720
437 | USS-195-2 | 2010-11 | Purnea | Katihar | Manihari | Middle School Mirjapur 8084519254 941640318 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Not start. Agreement not done
438 | USS-195-3 | 2010-11 | Purnea | Katihar | Mansahi | Middle School Mohanpur 9472890120 | 138 dated 16.08.2011 | 15-F2 2016-17 (26.4.16) | [8 empty] | 1 |  | 1 |  |  | 5018863
439 | USS-196(A) | 2010-11 | Purnea | Katihar | Pranpur | Middle School Kast Hawar 8809776384 9162325809 | 138 dated 16.08.2011 | 525F₂ of 14-15 (16.12.14) | [5 empty] | 1 |  |  |  |  | 1 |  |  | 1627604
440 | USS-196(B) | 2010-11 | Purnea | Katihar | Ajamnagar | Middle School Arihana 8809322797 | 138 dated 16.08.2011 | 184F₂ of 15-16 (06.08.15) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4749252
441 | USS-196(C) | 2010-11 | Purnea | Katihar | Ajamnagar | Middle School Dhena Baghchhala 9801372634 | 138 dated 16.08.2011 | 535F₂ of 14-15 (17.12.14) | [8 empty] | 1 |  | 1 |  |  | 4692608
442 | USS-196(D) | 2010-11 | Purnea | Katihar | Pranpur | Middle School Ghanhar Vighocha 9939688768 | 138 dated 16.08.2011 | 505F₂ of 14-15 (12.12.14) | [8 empty] | 1 |  | 1 |  |  | 3827150
443 | USS-197(A) | 2010-11 | Purnea | Katihar | Barsoi | Middle School Barsoi Ghat 9431626189 | 138 dated 16.08.2011 | 185F₂ of 15-16 (06.08.15) | [8 empty] | 1 |  | 1 |  |  | 4773701
444 | USS-197(B) | 2010-11 | Purnea | Katihar | Dhankhora | Middle School Durgasthan Dhankhora 9431869787 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available |  | 0
445 | USS-197(C) | 2010-11 | Purnea | Katihar | Kodha | Middle School Marwa Najrachowki 9006363823 | 138 dated 16.08.2011 | 183F₂ of 15-16 (06.08.15) | [8 empty] | 1 |  | 1 |  |  | 5270370
446 | USS-197(D) | 2010-11 | Purnea | Katihar | Kadwa | Dukhi Ram Middle School Chandpur 9709755452 | 138 dated 16.08.2011 | 506F₂ of 14-15 (12.12.14) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5492010
447 | USS-198-1 | 2010-11 | Purnea | Katihar | Brari | Middle School Laxmipur | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Tender Process |  | 0
448 | USS-198-2 | 2010-11 | Purnea | Katihar | Brari | Middle School Anarkali | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Tender Process |  | 0
449 | USS-198-3 | 2010-11 | Purnea | Katihar | Hasanganj | Middle School Hasanganj | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Tender Process |  | 0
450 | USS-198-4 | 2010-11 | Purnea | Katihar | Phalka | Middle School Morsanda | 138 dated 16.08.2011 | 366-F2 2015-16 (19.01.16) | [8 empty] | 1 |  | 1 |  |  | 6071767
451 | USS-198-5 | 2010-11 | Purnea | Katihar | Sameli | Middle School Dumar | 138 dated 16.08.2011 | 367-F2 2015-16 (19.01.16) | [8 empty] | 1 |  | 1 |  |  | 5837001
452 | USS-199A (A) | 2010-11 | Purnea | Araria | Forbesganj | Adarsh Middle School Mirjapur 9430521363, 9006224356 | 138 dated 16.08.2011 | 544F₂ of 14-15 (20.12.14) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25/08/2015 | 5712968
453 | USS-199A (B) | 2010-11 | Purnea | Araria | Forbesganj | Middle School Hingna Aurahi 9771866450 | 138 dated 16.08.2011 | 545F₂ of 14-15 (20.12.14) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 2015-06-10 | 5617717
454 | USS-199A (C) | 2010-11 | Purnea | Araria | Narpatganj | Middle School Khabdah Dumriya 9661102737 | 138 dated 16.08.2011 | 546F₂ of 14-15 (20.12.14) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 2015-05-12 | 5144190
455 | USS-199A (D) | 2010-11 | Purnea | Araria | Narpatganj | Middle School Achra 9801296055 | 138 dated 16.08.2011 | 547F₂ of 14-15 (20.12.14) | [9 empty] | 1 | 0 | Inaugurated 16.07.2016 | 20/08/2015 | 6042836
456 | USS-199 B-1 | 2010-11 | Purnea | Araria | Jokihat | Middle School Jhanpur 9471219710 | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | 0 | Inaugurated | 04.07.2014 | 5678199.0033
457 | USS-199 B-2 | 2010-11 | Purnea | Araria | Raniganj | Middle School Kosikapur 9199673607 | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | 0 | Inaugurated | 04.07.2014 | 5678199.0033
458 | USS-199 B-3 | 2010-11 | Purnea | Araria | Araria | Middle School Araria Basti 9661185784 | 138 dated 16.08.2011 | 34 SBD OF 2013-14 (28.05.13) | [9 empty] | 1 | 0 | Inaugurated | 04.07.2014 | 5678200.0033
459 | USS-46-1 | 2009-10 | Tirhut East | Sheohar | rfj;kuh | eŒ foŒ] xaxk /kjeiqj 9097081921@8804009312 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 5603319
460 | USS-46-2 | 2009-10 | Tirhut East | Sitamarhi | :Uuh lSniqj | eŒ foŒ] cyqvk 9771099254 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 5603319
461 | USS-46-3 | 2009-10 | Tirhut East | Sitamarhi | :Uuh lSniqj | eŒ foŒ] FkqEek 9472379528 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 5603319
462 | USS-46-4 | 2009-10 | Tirhut East | Sitamarhi | csylaM | eŒ foŒ] ipukSj | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 5603320
463 | USS-47-1 | 2009-10 | Tirhut East | Sitamarhi | jhxk | eŒ foŒ] ;ksxokuk 9534893264 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.12.2013 | 5074450
464 | USS-47-2 | 2009-10 | Tirhut East | Sitamarhi | cFkukgk | eŒ foŒ] fMgBh 9973981418 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.12.2013 | 5074450
465 | USS-47-3 | 2009-10 | Tirhut East | Sitamarhi | ukuiqj | eŒ foŒ] cÙkjk 9931668054 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.12.2013 | 5074450
466 | USS-47-4 | 2009-10 | Tirhut East | Sitamarhi | ukuiqj | eŒ foŒ] dksbyh ¼Boys½ 8877302381 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.12.2013 | 5074450
467 | USS-47-5 | 2009-10 | Tirhut East | Sitamarhi | lksucjlk | eŒ foŒ] bVgjok 9546578977 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.12.2013 | 5074449
468 | USS-48-1 | 2009-10 | Tirhut East | Muzaffarpur | vkSjkbZ | eŒ foŒ] cSaxuk 7209905677 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.09.2013 | 4685120
469 | USS-48-2 | 2009-10 | Tirhut East | Muzaffarpur | ckspgk¡ | eŒ foŒ] f'kojkg e>kSfy;k 9931991492 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.09.2013 | 4685120
470 | USS-48-3 | 2009-10 | Tirhut East | Muzaffarpur | xk; ?kkV | eŒ foŒ] iqjkuUgdkj 8434666123@8434057271 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.09.2013 | 4685120
471 | USS-48-4 | 2009-10 | Tirhut East | Muzaffarpur | dVjk | eŒ foŒ] cq/kdkjk 9934016332 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.09.2013 | 4685120
472 | USS-49-1 | 2009-10 | Tirhut East | Muzaffarpur | dkaVh | eŒ foŒJ`axkj 8809637605 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land problem
473 | USS-49-2 | 2009-10 | Tirhut East | Muzaffarpur | eM+ou | eŒ foŒ] jsiqjk 8252129824 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.06.2013 | 4608913
474 | USS-49-3 | 2009-10 | Tirhut East | Muzaffarpur | ehukiqj | eŒ foŒ] tkfeu efB;k 9934619525 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.06.2013 | 4608913
475 | USS-50-1 | 2009-10 | Tirhut East | Muzaffarpur | ik: | eŒ foŒ] HkkstiV~Vh 9931888752 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1 |  |  | 973939
476 | USS-50-2 | 2009-10 | Tirhut East | Muzaffarpur | ik: | eŒ foŒ] pkaniqj 9801265669 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1 |  |  | 973939
477 | USS-50-3 | 2009-10 | Tirhut East | Muzaffarpur | lkgscxat | eŒ foŒ] 'kkgiqj iV~Vh 9801128043 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1 |  |  | 973939
478 | USS-50-4 | 2009-10 | Tirhut East | Muzaffarpur | ljS;k | eŒ foŒ] xksjhxkekMhg 9431615151 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1460910
479 | USS-51-1 | 2009-10 | Tirhut East | Muzaffarpur | ldjk | eŒ foŒ] ckth cqtqxZ 9572907300 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.12.2013 | 4626431
480 | USS-51-2 | 2009-10 | Tirhut East | Muzaffarpur | eq'kgjh | eŒ foŒ] fn?kM+k 9430051489@9304110351 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.12.2013 | 4626431
481 | USS-51-3 | 2009-10 | Tirhut East | Muzaffarpur | eksrhiqj | eŒ foŒ] ckjthMhg 9934895236 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.12.2013 | 4626432
482 | USS-52-1 | 2009-10 | Tirhut East | Vaishali | lgnsbZ cqtqxZ | eŒ foŒ]jkeiqj dqEgjdksy 9934974677 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.12.2014 | 4596083
483 | USS-52-2 | 2009-10 | Tirhut East | Vaishali | egukj | eŒ foŒ deyk dU;k] djukSrh 8002747546 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.12.2014 | 4596083
484 | USS-52-3 | 2009-10 | Tirhut East | Vaishali | tUnkgk | eŒ foŒ] jlqyiqj 8651291731 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.12.2014 | 4596083
485 | USS-52-4 | 2009-10 | Tirhut East | Vaishali | fonqiqj | eŒ foŒ] tqM+kouiqj xksikyiqj 8292960800 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.12.2014 | 4596083
486 | USS-53-1 | 2009-10 | Tirhut East | Vaishali | gkthiqj | eŒ foŒ] yksek 9470638549 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 4445041
487 | USS-53-2 | 2009-10 | Tirhut East | Vaishali | gkthiqj | eŒ foŒ] dqrqciqj 9905099533 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 4445041
488 | USS-53-3 | 2009-10 | Tirhut East | Vaishali | ykyxat | eŒ foŒ] xqjfe;k 8651626851 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 4445041
489 | USS-53-4 | 2009-10 | Tirhut East | Vaishali | xksjkSy | eŒ foŒ] Bhdgk¡ 9431254109 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2016 | 4445042
490 | USS-54-1 | 2009-10 | Tirhut East | Vaishali | jktkikdj | eŒ foŒ] csydqaMk 7677785326 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Dispute
491 | USS-54-2 | 2009-10 | Tirhut East | Vaishali | ikrsiqj | eŒ foŒ] vQtyiqj iqjSuk 9006341864 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 08.09.2013 | 3981333
492 | USS-54-3 | 2009-10 | Tirhut East | Vaishali | jk?kksiqj | eŒ foŒ] ohjiqj 9931458401 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  | 08.09.2013 | 3981333
493 | USS-162 (A) | 2010-11 | Tirhut East | Sitamarhi | Bathnaha | M.S.Belahi Jairam 9973134925 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | handover | 18.06.2016 | 5777282
494 | USS-162 (B) | 2010-11 | Tirhut East | Sitamarhi | Parsauni | M. S. Jisara 9931684677 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 20.04.2015 | 5842495
495 | USS-162 (C) | 2010-11 | Tirhut East | Sitamarhi | Suppi | M. S. Aktha 9470821881 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.06.2015 | 5986289
496 | USS-162 (D) | 2010-11 | Tirhut East | Sitamarhi | Riga | M. S. Ramnagara 9570781314 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 | brick work above GF in progess |  | 3111750
497 | USS-162 (E) | 2010-11 | Tirhut East | Sitamarhi | Parihar | M. S. Sirsiya Bazar 8102085348, 7654040371 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 28.03.2016 | 6291219
498 | USS-162 (F) | 2010-11 | Tirhut East | Sitamarhi | Dumri | M. S. Pakri Sanakarit 8294843032 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 24.01.2016 | 5710520
499 | USS-163 (A) | 2010-11 | Tirhut East | Sitamarhi | Runni Saidpur | M. S. Dhanukhi 9006835850 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 05.08.2015 | 6050689
500 | USS-163 (B) | 2010-11 | Tirhut East | Sitamarhi | Pupri | M. S. Maulanagar 9608713501 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 23.04.2015 | 5966644
501 | USS-163 (C) | 2010-11 | Tirhut East | Sitamarhi | Sursand | M. S. Bhitta Bazar 8271527471 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2015 | 5830496
502 | USS-163 (D) | 2010-11 | Tirhut East | Sitamarhi | Bokhara | M. S. Chakauti 8986347412 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 6078789
503 | USS-164-1 | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Paramanandpur 9939709788 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5117276.0033
504 | USS-164-2 | 2010-11 | Tirhut East | Vaishali | Lalganj | M. S. Sathiyauta 9939770494 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5117276.0033
505 | USS-164-3 | 2010-11 | Tirhut East | Vaishali | Bhagwanpur | M. S. Askaranpur | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5117277.0033
506 | USS-164-4 | 2010-11 | Tirhut East | Vaishali | Bhagwanpur | M. S. Kutubpur 9534509369 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
507 | USS-164-5 | 2010-11 | Tirhut East | Vaishali | Lalganj | U.M.S. Basanta 9934417163 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
508 | USS-165-1 | 2010-11 | Tirhut East | Vaishali | Jandaha | U. M.S. Shahpur Rohuya 9934414222 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2701700
509 | USS-165-2 | 2010-11 | Tirhut East | Vaishali | Jandaha | M. S, Mahhisaur 9661844106 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 1964873
510 | USS-165-3 | 2010-11 | Tirhut East | Vaishali | Sahadei Bujurg | M.S, Toimath 9939693675 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2701700
511 | USS-165-4 | 2010-11 | Tirhut East | Vaishali | Sahadei Bujurg | M.S, Nayaganj 9934912623 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Insufficient Land
512 | USS-165-5 | 2010-11 | Tirhut East | Vaishali | Jandaha | M.S, Bijrauti 9973922533 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4175356
513 | USS-166 (A) | 2010-11 | Tirhut East | Vaishali | Raghopur | M. S,Tersiya 9631970772 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4732483
514 | USS-166 (B) | 2010-11 | Tirhut East | Vaishali | Raghopur | M.S,Paharpur 7654539556 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 29.01.2016 | 5520473
515 | USS-166 (C) | 2010-11 | Tirhut East | Vaishali | Bidupur | M. S, Mohanpur Kajipatti 9199314551 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land dispute |  | 0
516 | USS-166 (D) | 2010-11 | Tirhut East | Vaishali | Desari | M. S, Bhikhanpura 9973319373 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2067830
517 | USS-166 (E) | 2010-11 | Tirhut East | Vaishali | Rajapakar | M. S, Makhadumpur Pokhraira 9934478747 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4974260
518 | USS-167-1 | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Chhitrauli 9934656924 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.04.2015 | 5160919
519 | USS-167-2 | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | U. M.S, Drohiratan 9801136261 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.04.2015 | 5160919
520 | USS-167-3 | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Jhitki 9934019395 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.04.2015 | 5160920
521 | USS-167-4 | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Dariyapur Kefen 8051703323 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.04.2015 | 5160920
522 | USS-167-5 | 2010-11 | Tirhut East | Muzaffarpur | Kurhani | M. S, Balbhadrapur 8809991008 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.04.2015 | 5160920
523 | USS-168-1 | 2010-11 | Tirhut East | Muzaffarpur | Paroo | M. S, Lalu Chapra 9934760982 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.03.2016 | 5390321
524 | USS-168-2 | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M. S, Bhagwanpur Kashi 8084360691 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.03.2016 | 5390321
525 | USS-168-3 | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M.S ,Rajwara 9934809051 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.03.2016 | 5390322
526 | USS-168-4 | 2010-11 | Tirhut East | Muzaffarpur | Sahebganj | M. S, Jitachhapra 9939926195 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.03.2016 | 5390322
527 | USS-169-1 | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Bendra 9939297191 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.11.2014 | 5518665
528 | USS-169-2 | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Sakriman 9006863747 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.11.2014 | 5518665
529 | USS-169-3 | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Keshopur 9135823204 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.11.2014 | 5518665
530 | USS-169-4 | 2010-11 | Tirhut East | Muzaffarpur | Sakra | M. S. Munni Baingari 9955660204 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.11.2014 | 5518665
531 | USS-169-5 | 2010-11 | Tirhut East | Muzaffarpur | Bandra | M. S, Cachhahi 8757974704 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.11.2014 | 5518668
532 | USS-170-1 | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Semra 9771240801, 9835814768 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5007288
533 | USS-170-2 | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Mahamada 9934659092 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 14.12.2015 | 5007288
534 | USS-170-3 | 2010-11 | Tirhut East | Muzaffarpur | Motipur | M. S, Nakta 9430864377 , 8235157414 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 11.08.2015 | 5007288
535 | USS-170-4 | 2010-11 | Tirhut East | Muzaffarpur | Minapur | M. S, Ranikhaira 9430864835, 9934203612 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 5007288
536 | USS-170-5 | 2010-11 | Tirhut East | Muzaffarpur | Minapur | M. S,Rampur Ratan, 430865561, 9798455140 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 01.08.2015 | 5007289
537 | USS-171-1 | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S, Kothiya 9973191481 9931842980 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.09.2015 | 4729150
538 | USS-171-2 | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S,Balaur Bhatgama 8434895543, 8434868088 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.03.2016 | 4729150
539 | USS-171-3 | 2010-11 | Tirhut East | Muzaffarpur | Gaighat | M. S,Dahila 9973658759 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 30.04.2016 | 4729150
540 | USS-171-4 | 2010-11 | Tirhut East | Muzaffarpur | Katra | M. S, Bakhari 9631173639 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 25.03.2016 | 4729150
541 | USS-171-5 | 2010-11 | Tirhut East | Muzaffarpur | Bochahan | Middle, Kefen 9162802550 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 |  | 4729151
542 | USS-172-1 | 2010-11 | Tirhut East | Muzaffarpur | Aurai | M. S, Chahuta 9973925814 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.04.2015 | 5225504
543 | USS-172-2 | 2010-11 | Tirhut East | Muzaffarpur | Aurai | M. S, Rajkhand 9431806467 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.04.2015 | 5225504
544 | USS-172-3 | 2010-11 | Tirhut East | Muzaffarpur | Marwan | M S, Bishunpur 9471621233, 9939934993 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.04.2015 | 5225504
545 | USS-172-4 | 2010-11 | Tirhut East | Muzaffarpur | Mushhari | M. S, Dronpur | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.04.2015 | 5225504
546 | USS-172-5 | 2010-11 | Tirhut East | Muzaffarpur | Muraul | M. S, Pilkhi | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.04.2015 | 5225506
547 | USS-37-1 | 2009-10 | Tirhut West | West Champaran | Manjhauliya | M.S.Aharwar Shekh 9470655463 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.04.2014 | 4919560
548 | USS-37-2 | 2009-10 | Tirhut West | West Champaran | Manjhauliya | M.S. Parsa Bahuarwa 9470859628 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.04.2014 | 4919560
549 | USS-37-3 | 2009-10 | Tirhut West | West Champaran | Bairiya | M.S. Bathna 9431466192 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.04.2014 | 4919560
550 | USS-37-4 | 2009-10 | Tirhut West | West Champaran | Nautan | M.S. Mangalpur 9430691686 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.04.2014 | 4919560
551 | USS-38-1 | 2009-10 | Tirhut West | West Champaran | Bagha-1 | M.S.Kolhua Chautarwa 9430668747 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5024180
552 | USS-38-2 | 2009-10 | Tirhut West | West Champaran | Bagha-2 | M.S. Rampurwa 9572454264 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5024180
553 | USS-38-3 | 2009-10 | Tirhut West | West Champaran | Lauriya | M.S.Dhobani 9430571439 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5024180
554 | USS-38-4 | 2009-10 | Tirhut West | West Champaran | Gaunaha | Govt Girls M.S. Gaunaha 9430421378 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5024180
555 | USS-39-1 | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Tajpur 8986956152 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4847286
556 | USS-39-2 | 2009-10 | Tirhut West | West Champaran | Mainatand | M.S. Sukhlahi 9546120109 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4847286
557 | USS-39-3 | 2009-10 | Tirhut West | West Champaran | Sikta | M.S. Baishkhwa 9955233530 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4847286
558 | USS-40-1 | 2009-10 | Tirhut West | West Champaran | Narkatiaganj | M.S. Shomgarh 9470256119 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1378817
559 | USS-40-2 | 2009-10 | Tirhut West | West Champaran | Yogapatti | M.S. Kohra 9934686513 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1378817
560 | USS-40-3 | 2009-10 | Tirhut West | West Champaran | Ramnagar | M.S. Sher Hawa Don 9470860764 | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | 1 |  |  | 766009
561 | USS-41-1 | 2009-10 | Tirhut West | East Champaran | Motihari | M.S. Jamla 9934828027 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3338944
562 | USS-41-2 | 2009-10 | Tirhut West | East Champaran | Banjariya | M.S. Kukurjari 9708975580 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 2504208
563 | USS-41-3 | 2009-10 | Tirhut West | East Champaran | Turkauliya | M.S. Vishnupurwa 9801485906 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 3338944
564 | USS-41-4 | 2009-10 | Tirhut West | East Champaran | Chiraiya | M.S. Parewa 9386155278 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1 |  |  | 1878158
565 | USS-42-1 | 2009-10 | Tirhut West | East Champaran | Areraj | M.S. Radhiya 9576399366 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4586954
566 | USS-42-2 | 2009-10 | Tirhut West | East Champaran | Sangrampur | M.S. Shyampur 8969622208 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4586954
567 | USS-42-3 | 2009-10 | Tirhut West | East Champaran | Harsidhi | M.S. Ghivadhar 8298836365 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4586954
568 | USS-42-4 | 2009-10 | Tirhut West | East Champaran | Kotwa | M.S. Ahirauliya 9546303762 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4586954
569 | USS-43-1 | 2009-10 | Tirhut West | East Champaran | Raxaul | M.S. Gonha 9470284937 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1636359
570 | USS-43-2 | 2009-10 | Tirhut West | East Champaran | Sugauli | M.S. Muswa 9471878742 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 1999994
571 | USS-43-3 | 2009-10 | Tirhut West | East Champaran | Aadapur | M.S. Beldarwa 9771769291 / 9472911484 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1636361
572 | USS-43-4 | 2009-10 | Tirhut West | East Champaran | Chhauradano | M.S. Pakariya Urdu 9470233197 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
573 | USS-44-1 | 2009-10 | Tirhut West | East Champaran | Chakiya | M.S. Chintamanpur 9546123872 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.05.2014 | 4216292
574 | USS-44-2 | 2009-10 | Tirhut West | East Champaran | kalyanpur | M.S. Mandhwa Urdu 9939516692 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
575 | USS-44-3 | 2009-10 | Tirhut West | East Champaran | Kesariya | M.S. Sundarpur 9006381049 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4216292
576 | USS-44-4 | 2009-10 | Tirhut West | East Champaran | Mehshi | M.S. Jhitkahiya 9162250321 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 30.04.2104 | 4216292
577 | USS-44-5 | 2009-10 | Tirhut West | East Champaran | Paharpur | M.S. Siswa Bazar 8809296371 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.04.2014 | 4216291
578 | USS-45-1 | 2009-10 | Tirhut West | East Champaran | Dhaka | M.S. Chandanbara Urdu 9931213480 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1504367
579 | USS-45-2 | 2009-10 | Tirhut West | East Champaran | Patahi | M.S. Betauna 9708717133 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1 |  |  | 1002911
580 | USS-45-3 | 2009-10 | Tirhut West | East Champaran | Madhuban | M.S. Gurmiya | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | 1 |  |  | 668607
581 | USS-45-4 | 2009-10 | Tirhut West | East Champaran | Ghorasahan | M.S. Laxmipur Laukhan 9431652891 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2005823
582 | USS-158-1 | 2010-11 | Tirhut West | East Champaran | Turkauliya | M.S. Belwa Ray 9430645457 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4727390.0033
583 | USS-158-2 | 2010-11 | Tirhut West | East Champaran | Turkauliya | M.S. Jaishinghpur 9430209305 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4727390.0033
584 | USS-158-3 | 2010-11 | Tirhut West | East Champaran | Motihari | M.S. Basantpur 9576483588 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4727391.0033
585 | USS-159-1 | 2010-11 | Tirhut West | East Champaran | Pakridayal | M.S. Sishani 9934715029 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4948335
586 | USS-159-2 | 2010-11 | Tirhut West | East Champaran | chaaiya | M.S. Madhubani 9430565177 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
587 | USS-159-3 | 2010-11 | Tirhut West | East Champaran | Tetariya | M.S. Maniyarpur 9471297810 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4948335
588 | USS-159-4 | 2010-11 | Tirhut West | East Champaran | Piprakothi | M.S. Jhakracolony 9431270018 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4948335
589 | USS-159-5 | 2010-11 | Tirhut West | East Champaran | Ghorasahan | M.S. Samanpur 9939403946 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1979334
590 | USS-160-1 | 2010-11 | Tirhut West | West Champaran | Lauriya | Govt.M.S. Phulwariya 9431674559 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5589516
591 | USS-160-2 | 2010-11 | Tirhut West | West Champaran | Narkatiyaganj | Govt.M.S. Bhadiharwa 8986137181 | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 4751088
592 | USS-160-3 | 2010-11 | Tirhut West | West Champaran | Mainatand | Govt.M.S. Damrapur 9572125416 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5589516
593 | USS-160-4 | 2010-11 | Tirhut West | West Champaran | Madhubani | M.S.Pakri Ahawa Khothwa 08002571785 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5589517
594 | USS-160-5 | 2010-11 | Tirhut West | West Champaran | Nautan | M.S.Sansariya 8757124792 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0
595 | USS-161-1 | 2010-11 | Tirhut West | Sheohar | Purnhiya | M.S.Basant Jagivan 9430526421 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5002626
596 | USS-161-2 | 2010-11 | Tirhut West | Sheohar | Dumri Katsari | M.S.Phulkaha 9631003475 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5002626
597 | USS-61-1 | 2009-10 | Darbhanga | Madhubani | ?kks?kjMhgk | eŒ foŒ] xax}kj 9934407620 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 13.03.2015 | 5079714
598 | USS-61-2 | 2009-10 | Darbhanga | Madhubani | >a>kjiqj | eŒ foŒ]ykSguk 9430835195 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 13.03.2015 | 5079714
599 | USS-61-3 | 2009-10 | Darbhanga | Madhubani | ykSdgh | eŒ foŒ] dyqvkgh 9572025500 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 13.03.2015 | 5079713
600 | USS-62-1 | 2009-10 | Darbhanga | Madhubani | t;uxj | eŒ foŒflyukFk cjgh 9572618953 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4944280
601 | USS-62-2 | 2009-10 | Darbhanga | Madhubani | i.MkSy | eŒ foŒ] 'kkgiqj 9973048002 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4944280
602 | USS-62-3 | 2009-10 | Darbhanga | Madhubani | jktuxj | eŒ foŒ] eaxjkSuh 9931643145 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.05.2015 | 4944279
603 | USS-63-1 | 2009-10 | Darbhanga | Darbhanga | guqeku uxj | eŒfoŒ]Fkyokjk 9771791978 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.04.2014 | 4819201
604 | USS-63-2 | 2009-10 | Darbhanga | Darbhanga | cgsM+h | eŒfoŒ fctqfy;k 9939521323 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.04.2014 | 4819201
605 | USS-63-3 | 2009-10 | Darbhanga | Darbhanga | cgknqjiqj | mRØŒeŒfoŒ dejkSyh 9801391631 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 24.04.2014 | 4819201
606 | USS-64-1 | 2009-10 | Darbhanga | Darbhanga | ?ku';keiqj | eŒfoŒ]rqekSy 9939754496 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.05.2013 | 5098590
607 | USS-64-2 | 2009-10 | Darbhanga | Darbhanga | csuhiqj | mRØŒeŒfoŒ jf<+;ke 9770623526 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.05.2013 | 5098590
608 | USS-64-3 | 2009-10 | Darbhanga | Darbhanga | euhxkNh | mRØŒeŒfoŒ jk?kksiqj M;ks<+h 8651054266 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.05.2013 | 5098590
609 | USS-64-4 | 2009-10 | Darbhanga | Darbhanga | rkjMhg | mRØŒeŒfoŒ rkjMhg 9934870957 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x62' available land 27'x25' | 17.05.2013
610 | USS-65-1 | 2009-10 | Darbhanga | Darbhanga | dq'ks'oj LFkku iwŒ | mRØŒeŒfoŒ egknso eB 9973391579 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.08.2015 | 4908351
611 | USS-65-2 | 2009-10 | Darbhanga | Darbhanga | dq'ks'oj LFkku iŒ | mRØŒeŒfoŒ e/kqcu 7870017880@9570802231 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.08.2015 | 4908351
612 | USS-65-3 | 2009-10 | Darbhanga | Darbhanga | fojkSy | eŒfoŒ]iVfu;k¡ 9771113614 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.08.2015 | 4908350
613 | USS-66-1 | 2009-10 | Darbhanga | Darbhanga | fal?kokM+k | mRØŒeŒfoŒ e/kqiqj 9934911481 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2014 | 4795082
614 | USS-66-2 | 2009-10 | Darbhanga | Darbhanga | dsoVh | eŒfoŒ]dks;yk LFkku 9905459110 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2014 | 4795082
615 | USS-66-3 | 2009-10 | Darbhanga | Darbhanga | njHkaxk xzkeh.k | mRØŒeŒfoŒ cygk 9570479967 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.07.2014 | 4795083
616 | USS-67-1 | 2009-10 | Darbhanga | Samastipur | iVksjh | eŒfoŒ]njok 8757084952 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x67' available land 17'x15'
617 | USS-67-2 | 2009-10 | Darbhanga | Samastipur | nyflag ljk; | eŒfoŒ]ekyiqj 9934140121 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2014 | 4856296
618 | USS-67-3 | 2009-10 | Darbhanga | Samastipur | eksfgmÌhu uxj | eŒfoŒ]fcUn ckspgk 9939988449 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2014 | 4856296
619 | USS-67-4 | 2009-10 | Darbhanga | Samastipur | fo¦kifr uxj | mRØŒeŒfoŒ flejh ¼dU;k½ 9931656978 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2014 | 4856296
620 | USS-67-5 | 2009-10 | Darbhanga | Samastipur | eksfgmÌhu uxj | eŒfoŒ]efu;kj 7549600801 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2014 | 4856296
621 | USS-68-1 | 2009-10 | Darbhanga | Samastipur | foHkwfriqj | eŒfoŒ]nsljh 9939816100 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623765
622 | USS-68-2 | 2009-10 | Darbhanga | Samastipur | fcFkku | eŒfoŒ]NsNuh 9934979521 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623765
623 | USS-68-3 | 2009-10 | Darbhanga | Samastipur | gluiqj | mRØŒeŒfoŒ egqyh 9801690551 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623765
624 | USS-68-4 | 2009-10 | Darbhanga | Samastipur | f'kokth uxj | eŒfoŒ]Jhiqj etjfg;k 9955507715 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623765
625 | USS-68-5 | 2009-10 | Darbhanga | Samastipur | foHkwfriqj | eŒfoŒ]irSfy;k 9973163333 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623765
626 | USS-68-6 | 2009-10 | Darbhanga | Samastipur | f'kokth uxj | eŒfoŒ]jkuhiêh 9955989162 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.12.2013 | 4623763
627 | USS-69-1 | 2009-10 | Darbhanga | Samastipur | dY;k.kiqj | eŒfoŒ]eksjokjk 9162249115 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.04.2014 | 4554745
628 | USS-69-2 | 2009-10 | Darbhanga | Samastipur | leLrhiqj | eŒfoŒ][kksM+h 9263781760 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.04.2014 | 4554745
629 | USS-69-3 | 2009-10 | Darbhanga | Samastipur | mft;kiqj | eŒfoŒ]vaxkj ?kkV 9204971619 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.04.2014 | 4554745
630 | USS-69-4 | 2009-10 | Darbhanga | Samastipur | mft;kiqj | eŒfoŒdksjc)k] irSyh 9263731315 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 29.04.2014 | 4554746
631 | USS-70-1 | 2009-10 | Darbhanga | Samastipur | eksjok | eŒfoŒ iq:"kksreiqj 9973123260 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2013 | 4925292
632 | USS-70-2 | 2009-10 | Darbhanga | Samastipur | iwlk | eŒfoŒ]efYydkSj | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 31.03.2013 | 4925292
633 | USS-187-1 | 2010-11 | Darbhanga | Madhubani | Babu Barhi | M. S. Barhara | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 3349144
634 | USS-187-2 | 2010-11 | Darbhanga | Madhubani | Lakhanpur | M. S. Belaucha | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x67' available land20'x15'
635 | USS-187-3 | 2010-11 | Darbhanga | Madhubani | Jaynagar | Middle School, Dhaniyapatti 9931037199 9661794550 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x67' available land17'x15'
636 | USS-187-4 | 2010-11 | Darbhanga | Madhubani | Rajnagar | Govt. M S, Kewalpatti 9430032594 8051418065 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 3940170
637 | USS-187-5 | 2010-11 | Darbhanga | Madhubani | Khutauna | Middle School, Malin Belha 9572178379 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 3940170
638 | USS-188-1 | 2010-11 | Darbhanga | Madhubani | Banipatti | M. S.Ganguli 9431629001 | 138 dated 16.08.2011 |  |  |  |  | 1 | [6 empty] | 1 | AGREEMENT NOT DONE (CONTRACTOR REFUSED)
639 | USS-188-2 | 2010-11 | Darbhanga | Madhubani | Kaluahi | M. S.Kalikapur 9973900631 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0
640 | USS-188-3 | 2010-11 | Darbhanga | Madhubani | Bisfi | M. S.Singhaso 9162249674 8051935537 | 138 dated 16.08.2011 | [5 empty] | 1 | [5 empty] | 1
641 | USS-189-1 | 2010-11 | Darbhanga | Samastipur | Shivajinagar | M. S. Shripur Bhataura | 138 dated 16.08.2011 | [9 empty] | 1 |  | 1 |  |  | 5860814
642 | USS-189-2 | 2010-11 | Darbhanga | Samastipur | Vibhutipur | U. M. S, Mustafapur | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Low land more than 15'
643 | USS-190-1 | 2010-11 | Darbhanga | Darbhanga | Kusheshwarsthan E | U. M. S, Barniya 7870017996 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2228155
644 | USS-190-2 | 2010-11 | Darbhanga | Darbhanga | Kusheshwarsthan W | U. M. S, Sihariya 8969431987 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2228156
645 | USS-191-1 | 2010-11 | Darbhanga | Darbhanga | Manigachhi | U. M. S, Dahaura 9431405480 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x67' available land 27'x25'
646 | USS-191-2 | 2010-11 | Darbhanga | Darbhanga | Kewati | M. S, Koila Majhigama 9304020023 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | LAND DISPUTE
647 | USS-191-3 | 2010-11 | Darbhanga | Darbhanga | Kewati | M B D J D M S Pachadi 9708287712 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.03.2015 | 5366524
648 | USS-191-4 | 2010-11 | Darbhanga | Darbhanga | Singheshwar | M. S .Sanhapur 9801444701 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.03.2015 | 5366524
649 | USS-191-5 | 2010-11 | Darbhanga | Darbhanga | Singheshwar | U. M. S, Katka 9473151051 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 25.03.2015 | 5366524
650 | USS-192 A | 2010-11 | Darbhanga | Darbhanga | Bahadurpur | M. S, Daing 9199229540 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 4933184
651 | USS-192 B | 2010-11 | Darbhanga | Darbhanga | Biraul | M. S, Koilajan 9939650547 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 1715613
652 | USS-192 C | 2010-11 | Darbhanga | Darbhanga | Benipur | U. M. S, Ramouli 9931745776 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 09.05.2016 | 5843829
653 | USS-192 D | 2010-11 | Darbhanga | Darbhanga | Biraul | U. M. S, Balha 7631905606 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated 16.07.2016 | 08.05.2016 | 5789262
654 | USS-193-1 | 2010-11 | Darbhanga | Darbhanga | Alinagar | U M S, Jayantipur 9431691474 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.05.2015 | 5330421.9967
655 | USS-193-2 | 2010-11 | Darbhanga | Darbhanga | Alinagar | U.M S, Garaul Chakka 9430640027 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.05.2015
656 | USS-193-3 | 2010-11 | Darbhanga | Darbhanga | Alinagar | U. M. S, Rampur Uday 9546520079 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | required land 68'x67' available land 16'x14' |  | 5330422.9967
657 | USS-193-4 | 2010-11 | Darbhanga | Darbhanga | Hanuman Nagar | M. S, Tarlahi 9608648110 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.05.2015 | 5330422.9967
658 | USS-55-1 | 2009-10 | Saran | Gopalganj | Baikunthapur | M. School, Deokulli, Mob.: 9708861129 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.02.2014 | 4616434
659 | USS-55-2 | 2009-10 | Saran | Gopalganj | Baikunthapur | M. School, Maharani, Mob.:9199443900 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.02.2014 | 4616434
660 | USS-55-3 | 2009-10 | Saran | Gopalganj | Kuchayakot | M. School, Mahuaba, Hindi, Mob.: 9430055420/9162622220 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.02.2014 | 4616434
661 | USS-55-4 | 2009-10 | Saran | Gopalganj | Singhawalia | U. M. School, Dumaria East, Mob.: 9955648224 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.02.2014 | 4616433
662 | USS-56-1 | 2009-10 | Saran | Gopalganj | Bhore | M. School, Shivarajpur, Mob.: 9973200939 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.02.2014 | 4635997
663 | USS-56-2 | 2009-10 | Saran | Gopalganj | Kattaya | M. School, Rudrapur, Mob.: 9628550100 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 15.06.2014 | 4635997
664 | USS-56-3 | 2009-10 | Saran | Gopalganj | Kuchayakot | M. School, Purkhaus, Mob.: 9955647418 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 12.02.2014 | 4635997
665 | USS-56-4 | 2009-10 | Saran | Gopalganj | Vijayipur | M. School, Mathaulli, Mob.: 9838674751 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.03.2014 | 4635998
666 | USS-57-1 | 2009-10 | Saran | Siwan | Badahardiya | M. School, Hathigaya, Mob.: 9771334715 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4561491
667 | USS-57-2 | 2009-10 | Saran | Siwan | Siwan Sadar | M. School, Chanauri, Mob.: 9006388052 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4561491
668 | USS-57-3 | 2009-10 | Saran | Siwan | Aundar | M. School, Bairawaun, Mob.: 9934499146 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4561490
669 | USS-57-4 | 2009-10 | Saran | Siwan | Hussainganj | M. School, Bardharam, Mob.: 9801700327 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4561490
670 | USS-58-1 | 2009-10 | Saran | Siwan | Raghunathpur | M. School, Karshar, Mob.: 9631444459 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4575371
671 | USS-58-2 | 2009-10 | Saran | Siwan | Guddhani | U. M. School, Bangardha, Mob.: 9801180809 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 17.02.2014 | 4575371
672 | USS-58-3 | 2009-10 | Saran | Siwan | Daraulli | M. School, Dumarhar Bujurga, Mob.: 9199854822 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.03.2014 | 4575371
673 | USS-58-4 | 2009-10 | Saran | Siwan | Mairwa | M. School, Kabirpur, Mob.: 9801620606 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4575371
674 | USS-58-5 | 2009-10 | Saran | Siwan | Sisawan | M. School, Ramgarha, Mob.: 9973555208 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4575372
675 | USS-59-1 | 2009-10 | Saran | Saran | Masharrakha | M. School, Dum Dumma, Mob.: 9006658111 | 138 dated 16.08.2011 | [7 empty] | 1 |  |  |  | 1 |  |  | 2360886
676 | USS-59-2 | 2009-10 | Saran | Saran | Panapur | U. M. School, Panapur, Mob.: 9199453564 | 138 dated 16.08.2011 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2164145
677 | USS-59-3 | 2009-10 | Saran | Saran | Tarraiyan | M. School, Parauna Balak, Mob.: 9931139238 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2360886
678 | USS-59-4 | 2009-10 | Saran | Saran | Jalalpur | M. School, Nawadah, Mob.: 9431630231 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2360887
679 | USS-60-1 | 2009-10 | Saran | Saran | Chhapra Sadar | U. M. School, Chakia, Mob.: 9852100257/9128630531 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4026418
680 | USS-60-2 | 2009-10 | Saran | Saran | Manjhi | M. School, Dumari, Mob.: 8083701946/8757054210 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.10.2014 | 4026418
681 | USS-60-3 | 2009-10 | Saran | Saran | Parsa | M. School, Badraholpur, Mob.: 9199413413 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4026418
682 | USS-60-4 | 2009-10 | Saran | Saran | Maker | M. School, Hussanpur, Mob.: 8969809826 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4026419
683 | USS-60-5 | 2009-10 | Saran | Saran | Ekma | M. School, Devapura, Mob.: 9934276159 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4026419
684 | USS-173 (A) | 2010-11 | Saran | Siwan | Husainganj | M. S, Hata Tola Chhata 9546660912 | 138 dated 16.08.2011 | [8 empty] | 1 |  |  | 1 |  |  | 2213013
685 | USS-173 (B) | 2010-11 | Saran | Siwan | Raghunathpur | M. S, Kandhauli 9934615203 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5638394
686 | USS-174-1 | 2010-11 | Saran | Siwan | Goriya Kothi | M. S, Agayan 9931238480 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 07.04.2014 | 5339023
687 | USS-174-2 | 2010-11 | Saran | Siwan | Mahrajganj | U. M. S, Shahpur 9934425050 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5339023
688 | USS-174-3 | 2010-11 | Saran | Siwan | Mahrajganj | U M S, Balui(Boys) 9430845490 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 02.09.2014 | 5339023
689 | USS-174-4 | 2010-11 | Saran | Siwan | Basantpur | U M S, Shekhpura (Urdu) 9431051956 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 19.05.2014 | 5339023
690 | USS-175-1 | 2010-11 | Saran | Siwan | Siswan | M. S, Gyaspur 8809341191 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Hand Over | 30.05.2014 | 5221031
691 | USS-175-2 | 2010-11 | Saran | Siwan | Siwan Sadar | U. M. S, Sarawe 9931980061 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 27.01.2014 | 5221031
692 | USS-175-3 | 2010-11 | Saran | Siwan | Siwan Sadar | M. S, Sarsar 9430206854 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 28.01.2014 | 5221031
693 | USS-175-4 | 2010-11 | Saran | Siwan | Siwan Sadar | M. S, Baletha 9973162074 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5221032
694 | USS-176-1 | 2010-11 | Saran | Siwan | Andar | M. S, Pateji Bahadur 9939697369 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5141045.0033
695 | USS-176-2 | 2010-11 | Saran | Siwan | Gudhani | M. S, Belauri 8809165382 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5141045.0033
696 | USS-176-3 | 2010-11 | Saran | Siwan | Andar | M. S, Bangra Ujjain 9955673604 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5141046.0033
697 | USS-177-1 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Saraiya 9431647901 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4160095
698 | USS-177-2 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Bhongha 9006298659 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4160095
699 | USS-177-3 | 2010-11 | Saran | Saran | Dariyapur | Middle School, Barka Baniya 8434756046 9934920997 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4160095
700 | USS-177-4 | 2010-11 | Saran | Saran | Dighwara | Middle School, Malkhachak 9135336330 | 138 dated 16.08.2011 |  |  | 1 | [8 empty] | 1 |  |  | 208005
701 | USS-178-1 | 2010-11 | Saran | Saran | Sonpur | Middle School, Shikharpur 9631221348 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5293479
702 | USS-179-1 | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Basahi Urdu | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4500184
703 | USS-179-2 | 2010-11 | Saran | Saran | Ekma | Middle School, Bhodasa | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4500184
704 | USS-179-3 | 2010-11 | Saran | Saran | Ekma | Middle School, Betbaniya 8294839353 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4500184
705 | USS-179-4 | 2010-11 | Saran | Saran | Ekma | Middle School, Eksar 9572740280 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4500185
706 | USS-179-5 | 2010-11 | Saran | Saran | Lahaladpur | Middle School, Mirjapur Murarpur 9955645700 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 4500185
707 | USS-181-1 | 2010-11 | Saran | Saran | Riwilganj | Middle School, Shekhpura 9162298688 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5015920
708 | USS-182-1 | 2010-11 | Saran | Saran | Parsa | Middle School, Bankarwa Mau 8757804020 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.10.2014 | 5018410.9967
709 | USS-182-2 | 2010-11 | Saran | Saran | Garkha | Upgraded Middle School, Itwa 09401585033 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5018411.9967
710 | USS-182-3 | 2010-11 | Saran | Saran | Madhaura | Upgraded Middle S, Nethua 8809143641 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5018411.9967
711 | USS-183-1 | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Barnaya Rajaram 9801382670 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 16.03.2015 | 5236618
712 | USS-183-2 | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Chhatarpati 09695415475 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 18.06.2015 | 5236618
713 | USS-183-3 | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Balthari 9973181137 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Low Land
714 | USS-183-4 | 2010-11 | Saran | Gopalganj | Kuchaikot | Middle School, Mateya 9771369553 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 14.03.2015 | 5236618
715 | USS-184-1 | 2010-11 | Saran | Gopalganj | Baikunthpur | Middle School, Chamanpura 9708223803 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 08.05.2014 | 5364757.9967
716 | USS-184-2 | 2010-11 | Saran | Gopalganj | Baikunthpur | Middle School, Gandhua 9097163144 9631026226 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 03.05.2014 | 5364758.9967
717 | USS-184-3 | 2010-11 | Saran | Gopalganj | Baikunthpur | Upgraded Middle School,Banaura 9661229932 9835052184 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 05.08.2014 | 5364758.9967
718 | USS-184-4 | 2010-11 | Saran | Gopalganj | Singhwaliya | Middle School, Amarpura Jagiraha 9801115115 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Not Available
719 | USS-185-1 | 2010-11 | Saran | Gopalganj | Bhore | Middle School, Kuaridih 9006390431 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5271801
720 | USS-185-2 | 2010-11 | Saran | Gopalganj | Gopalganj | Middle School, Karariya 9934499260 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Problem
721 | USS-185-3 | 2010-11 | Saran | Gopalganj | Thawe | Middle School, Lakshawar 9570377954 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated |  | 5271802
722 | USS-185-4 | 2010-11 | Saran | Gopalganj | Gopalganj | Middle School, Baraipatti 9955771721 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land Problem
723 | USS-186-1 | 2010-11 | Saran | Gopalganj | Hathua | U. M. S, Satai 8757888461 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.01.2015 | 5243983.9967
724 | USS-186-2 | 2010-11 | Saran | Gopalganj | Hathua | Upgraded Middle School, Singha Tola 9771268847 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 | Inaugurated | 10.01.2015 | 5243984.9967
725 | USS-186-3 | 2010-11 | Saran | Gopalganj | Hathua | Upgraded Middle School, Ekdenga Bhagwanpur 9430878571 | 138 dated 16.08.2011 |  | 1 | [9 empty] | 0 | Land not available
726 | USS-186-4 | 2010-11 | Saran | Gopalganj | Hathua | M. S., Baraipatti (Ananta) 9546066924 | 138 dated 16.08.2011 | [10 empty] | 1 | 0 |  |  | 5243984.9967
| Total No. of Schools-RMSA (USS) |  |  |  |  | 726 |  |  | 87 | 2 | 2 | 4 | 8 | 20 | 9 | 16 | 49 | 529
Note on U45: Group will closed due dely in land availability.
Note on B60: ACCORD. TO 475 USS-108-1
Note on G351: Gurudev Const.
Note on G354: Gurudev Const.
Note on B716: List from 161 & 250 ing list

## Sheet8
Column Labels
|  | 2009-10 |  |  |  | 2010-11 |  |  |  | Total Not Started | Total In Progress | Total Completed | Total Total Completion Cost (in Rs.)
S. No. | Name of Division | Not Started | In Progress | Completed | Total Completion Cost (in Rs.) | Not Started | In Progress | Completed | Total Completion Cost (in Rs.)
1 | Bhagalpur | 1 | 5 | 15 | 80825494 |  | 7 | 16 | 104297325 | 1 | 12 | 31 | 185122819
2 | Darbhanga | 2 | 0 | 34 | 164172989 | 7 | 6 | 12 | 71919336.99 | 9 | 6 | 46 | 236092325.99
3 | Kosi | 1 | 1 | 19 | 96732905 | 1 | 0 | 3 | 15976843 | 2 | 1 | 22 | 112709748
4 | Magadh | 3 | 2 | 30 | 134195076 | 10 | 15 | 37 | 230351817.9967 | 13 | 17 | 67 | 364546893.9967
5 | Munger | 3 | 2 | 19 | 92932099 | 7 | 5 | 31 | 166960483.9967 | 10 | 7 | 50 | 259892582.9967
6 | Patna East | 6 | 9 | 16 | 85240656 | 9 | 7 | 43 | 232682085 | 15 | 16 | 59 | 317922741
7 | Patna West | 2 | 0 | 20 | 85685831 | 7 | 6 | 35 | 193995903 | 9 | 6 | 55 | 279681734
8 | Purnea | 8 | 0 | 30 | 155904853 | 5 | 9 | 13 | 111920999.01 | 13 | 9 | 43 | 267825852.01
9 | Saran |  | 4 | 22 | 107511438 | 5 | 2 | 36 | 184148292.98 | 5 | 6 | 58 | 291659730.98
10 | Tirhut East | 2 | 4 | 28 | 138133016 | 4 | 7 | 43 | 250605603.01 | 6 | 11 | 71 | 388738619.01
11 | Tirhut West | 2 | 14 | 19 | 114568120 | 2 | 5 | 8 | 62531399.01 | 4 | 19 | 27 | 177099519.01
| Grand Total | 30 | 41 | 252 | 1255902477 | 57 | 69 | 277 | 1625390088.9933 | 87 | 110 | 529 | 2881292565.9933

## Summary
BSEIDC Ltd., Patna
Division wise Summary Report of USS 2009-10 & 2010-11 (RMSA) 31.05.2017
S. No. | Name of Division | USS (2009-10) |  |  |  | USS 2010-11 |  |  |  | USS 2009-10 & USS 2010-11
|  | Physical Status |  |  | Financial Status | Physical Status |  |  | Financial Status | Physical Status |  |  | Financial Status
|  | Not Started | In Progress | Completed | Total Completion Cost (in Rs.) | Not Started | In Progress | Completed | Total Completion Cost (in Rs.) | Total Not Started | Total In Progress | Total Completed | Total Total Completion Cost (in Rs.)
1 | Bhagalpur | 1 | 5 | 15 | 80825494 | 0 | 7 | 16 | 104297325 | 1 | 12 | 31 | 185122819
2 | Darbhanga | 2 | 0 | 34 | 164172989 | 7 | 6 | 12 | 71919336.99 | 9 | 6 | 46 | 236092325.99
3 | Kosi | 1 | 1 | 19 | 96732905 | 1 | 0 | 3 | 15976843 | 2 | 1 | 22 | 112709748
4 | Magadh | 3 | 2 | 30 | 134195076 | 10 | 15 | 37 | 230351817.9967 | 13 | 17 | 67 | 364546893.9967
5 | Munger | 3 | 2 | 19 | 92932099 | 7 | 5 | 31 | 166960483.9967 | 10 | 7 | 50 | 259892582.9967
6 | Patna East | 6 | 9 | 16 | 85240656 | 9 | 7 | 43 | 232682085 | 15 | 16 | 59 | 317922741
7 | Patna West | 2 | 0 | 20 | 85685831 | 7 | 6 | 35 | 193995903 | 9 | 6 | 55 | 279681734
8 | Purnea | 8 | 0 | 30 | 155904853 | 5 | 9 | 13 | 111920999.01 | 13 | 9 | 43 | 267825852.01
9 | Saran | 0 | 4 | 22 | 107511438 | 5 | 2 | 36 | 184148292.98 | 5 | 6 | 58 | 291659730.98
10 | Tirhut East | 2 | 4 | 28 | 138133016 | 4 | 7 | 43 | 250605603.01 | 6 | 11 | 71 | 388738619.01
11 | Tirhut West | 2 | 14 | 19 | 114568120 | 2 | 5 | 8 | 62531399.01 | 4 | 19 | 27 | 177099519.01
Grand Total |  | 30 | 41 | 252 | 1255902477 | 57 | 69 | 277 | 1625390088.9933 | 87 | 110 | 529 | 2881292565.9933