## GH-List
BSEIDC , Patna
Progress Report of Girls Hostel
S.N. | Division | Group No. | Session | Name of District | Name of Block | S.N. | Name of School | Physical Status | [9 empty] | Remarks | Division
[8 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[12 empty] | LL | RL | LL | RL
1 | Patna East | GH-07-1 | 2009-10 | Bhojpur | Agioan | 1 | D.N.H.S., Gorpa | [8 empty] | 1 |  |  | Patna East
2 | Patna East | GH-08-1 | 2009-10 | Bhojpur | Jagdishpur | 1 | Janta H.S., Baligaw | [8 empty] | 1 |  |  | Patna East
3 | Patna East | GH-101-1 | 2010-11 | Patna | Daniyawa | 1 | Rajkiyakrit H.S., Sigariyawa | [9 empty] | 1 | Inaugurated 16.07.2016 | Patna East
4 | Patna East | GH-101-2 | 2010-11 | Patna | Khusrupur | 2 | Rajkiyakrit Mahadeo H.S., Fatuwa, Khusrupur | [9 empty] | 1 | Inaugurated | Patna East
5 | Patna East | GH-102-1 | 2010-11 | Patna | Bakhtiyarpur | 1 | Rajkiyakrit H.S., Salimpur | 1 | [9 empty] | Land not available. Site to be changed | Patna East
6 | Patna East | GH-102-2 | 2010-11 | Patna | Belchhi | 2 | Rajkiyakrit H.S., Saksohar | [8 empty] | 1 |  | Flooring (DEBAR) | Patna East
7 | Patna East | GH-103-1 | 2010-11 | Patna | Paliganj | 1 | Rajkiyakrit H.S., Paliganj | [8 empty] | 1 |  |  | Patna East
8 | Patna East | GH-103-2 | 2010-11 | Patna | Dulhin Bazar | 2 | Banshidhari H.S., Bharatpura | [8 empty] | 1 |  | DEBAR | Patna East
9 | Patna East | GH-103-3 | 2010-11 | Patna | Bikram | 3 | Parwati H.S., Bikram | [9 empty] | 1 | Inaugurated | Patna East
10 | Patna East | GH-104-1 | 2010-11 | Patna | Masaurih | 1 | Smt. Girija Kuwar H.S., Masaurih | [8 empty] | 1 |  | DEBAR | Patna East
11 | Patna East | GH-104-2 | 2010-11 | Patna | Punpun | 2 | Sahid Ramanand R. Govind H.S., Punpun | [8 empty] | 1 |  |  | Patna East
12 | Patna East | GH-105-1 | 2010-11 | Patna | Patna Sadar (Gramin) | 1 | Rajkiyakrit Mahanth Hanuman Sharan H.S.School,Rajapur | 1 | [9 empty] | Dispute | Patna East
13 | Patna East | GH-105-2 | 2010-11 | Patna | Danapur | 2 | Baldeo Senior Secondary School, Danapur | [9 empty] | 1 | Inaugurated | Patna East
14 | Patna East | GH-105-3 | 2010-11 | Patna | Maner | 3 | Rajkiyakrit H/S, Maner | [9 empty] | 1 |  | Patna East
15 | Patna East | GH-106-1 | 2010-11 | Patna | Mokama | 1 | Railway Aided H.S., Mokama | [9 empty] | 1 | Inaugurated | Patna East
16 | Patna East | GH-106-2 | 2010-11 | Patna | Ghoswari | 2 | Rajkiyakrit H.S., Kumhra | [9 empty] | 1 | Inaugurated | Patna East
17 | Patna East | GH-107-1 | 2010-11 | Patna | Barh | 1 | Rajkiyakrit Anugrah Narayan Singh Senior Secondary School, Barh | [9 empty] | 1 | Inaugurated | Patna East
18 | Patna East | GH-107-2 | 2010-11 | Patna | Pandarak | 2 | Laxmi Narayan Rajbanshi H.S., Dhibar | 1 | [9 empty] | Sufficient land not available | Patna East
19 | Patna East | GH-108-1 | 2010-11 | Patna | Naubatpur | 1 | Rajkiyakrit H.S., Amarpura | [9 empty] | 1 | Inaugurated | Patna East
20 | Patna East | GH-108-2 | 2010-11 | Patna | Sampatchak | 2 | Gramin S.S.School Chakbairiya, Patna | [9 empty] | 1 | Inaugurated | Patna East
21 | Patna West | GH-109-1 | 2010-11 | Buxar | Rajpur | 1 | H.S.Rajpur Compound | [8 empty] | 1 |  |  | Patna West
22 | Patna West | GH-109-2 | 2010-11 | Buxar | Itarhi | 2 | H.S.Itarhi | [8 empty] | 1 |  |  | Patna West
23 | Patna West | GH-109-3 | 2010-11 | Buxar | Nawanagar | 3 | H.S. Nawanagar | [9 empty] | 1 | Inaugurated 16.07.2016 | Patna West
24 | Patna West | GH-110-1 | 2010-11 | Rohtas | Chenari | 1 | Middle School, Khurmabad, Chenari | [9 empty] | 1 | Inaugurated | Patna West
25 | Patna West | GH-111-1 | 2010-11 | Kaimur | Durgawati | 1 | K.G.B.V. Compound | [9 empty] | 1 | Inaugurated | Patna West
26 | Patna West | GH-111-2 | 2010-11 | Kaimur | Adhaura | 2 | H. S. Adhaura | [9 empty] | 1 | Inaugurated | Patna West
27 | Magadh | GH-09-1 | 2009-10 | Aurangabad | Madanpur | 1 | Anugrah H.S., Madanpur | [9 empty] | 1 | Inaugurated | Magadh
28 | Magadh | GH-09-2 | 2009-10 | Aurangabad | Rafiganj | 2 | R.B.R. High School, Rafiganj | [9 empty] | 1 | Inaugurated | Magadh
29 | Magadh | GH-10-1 | 2009-10 | Aurangabad | Haspura | 1 | Haspura H.S., Haspura | 1 | [9 empty] | Land Disput, due to court-stay order | Magadh
30 | Magadh | GH-11-1 | 2009-10 | Aurangabad | Kutumba | 1 | Govt. Middle School, Kutumba | 1 | [9 empty] | Insufficient land | Magadh
31 | Magadh | GH-112-1 | 2010-11 | Arwal | Karpi | 1 | High School, Karpi | [9 empty] | 1 | Inaugurated 16.07.2016 | Magadh
32 | Magadh | GH-112-2 | 2010-11 | Arwal | Arwal | 2 | Balika High School, Arwal | [9 empty] | 1 | Inaugurated 16.07.2016 | Magadh
33 | Magadh | GH-113-1 | 2010-11 | Jehanabad | Jehanabad | 1 | H.S., Jehanabad | 1 | [10 empty] | Magadh
34 | Magadh | GH-113-2 | 2010-11 | Jehanabad | Kako | 2 | H.S. Pali Bazar | 1 | [10 empty] | Magadh
35 | Magadh | GH-113-3 | 2010-11 | Jehanabad | Ghosi | 3 | H.S. Ghosi | 1 | [10 empty] | Magadh
36 | Magadh | GH-114-1 | 2010-11 | Jehanabad | Ratni Faridpur | 1 | H.S. Dayalbagh, Nehalpur | 1 | [9 empty] | Inspection | Magadh
37 | Magadh | GH-114-2 | 2010-11 | Jehanabad | Makhdumpur | 2 | S.S. Tehta | 1 | [9 empty] | Low land | Magadh
38 | Magadh | GH-115-1 | 2010-11 | Jehanabad | Hulashganj | 1 | H.S. Hulashganj | 1 | [9 empty] | local problem | Magadh
39 | Magadh | GH-115-2 | 2010-11 | Jehanabad | Modanganj | 2 | D.N.H.S. Bandhuganj | 1 | [9 empty] | Not Start | Magadh
40 | Bhagalpur | GH-30-1 | 2009-10 | Bhagalpur | Sanhoula | 1 | M.S., Arar, | [9 empty] | 1 | Inaugurated | Bhagalpur
41 | Bhagalpur | GH-31-1 | 2009-10 | Bhagalpur | Nathnagar | 1 | M.S., Kanjhiya, | 1 | [9 empty] | Land not available. (DROP OUT ) | Bhagalpur
42 | Bhagalpur | GH-31-2 | 2009-10 | Bhagalpur | Narayanpur | 2 | M.S., Manoharpur, | [9 empty] | 1 | Inaugurated 16.07.2016 | Bhagalpur
43 | Bhagalpur | GH-32-1 | 2009-10 | Bhagalpur | Rangra Chowk | 1 | M.S, Rangra Chowk | 1 | [9 empty] | Land problem. Drop out | Bhagalpur
44 | Bhagalpur | GH-32-2 | 2009-10 | Bhagalpur | Kharik Bazar | 2 | Basic Sch. Teldih* | 1 | [9 empty] | Land problem. Drop out | Bhagalpur
45 | Bhagalpur | GH-32-3 | 2009-10 | Bhagalpur | Ishmailpur | 3 | M.S.Parvatta* | 1 | [9 empty] | Land problem. Drop out | Bhagalpur
46 | Bhagalpur | GH-143-1 | 2010-11 | Bhagalpur | Pirpaiti | 1 | M.S, Simanpur | [9 empty] | 1 | Inaugurated | Bhagalpur
47 | Bhagalpur | GH-143-2 | 2010-11 | Bhagalpur | Kahalgaon | 2 | R. S. H.S, Rampur | [9 empty] | 1 | Inaugurated | Bhagalpur
48 | Bhagalpur | GH-143-3 | 2010-11 | Bhagalpur | Sabour | 3 | H.S, Mamalkha | [9 empty] | 1 | Inaugurated | Bhagalpur
49 | Bhagalpur | GH-144-1 | 2010-11 | Bhagalpur | Goradih | 1 | M.S, Goradih | [9 empty] | 1 | Inaugurated | Bhagalpur
50 | Bhagalpur | GH-144-2 | 2010-11 | Bhagalpur | Sultanganj | 2 | K.N.S.M.H.S, Sultanganj | [9 empty] | 1 | Inaugurated | Bhagalpur
51 | Bhagalpur | GH-145-1 | 2010-11 | Bhagalpur | Bihpur | 1 | H.S, Jairampur | [9 empty] | 1 | Inaugurated | Bhagalpur
52 | Bhagalpur | GH-145-2 | 2010-11 | Bhagalpur | Naugachhia | 2 | H.S, Sahu Parbatta | [9 empty] | 1 | Inaugurated | Bhagalpur
53 | Bhagalpur | GH-146-1 | 2010-11 | Bhagalpur | Gopalpur | 1 | Proj. Girls H.S, Saidpur | [9 empty] | 1 | Inaugurated | Bhagalpur
54 | Bhagalpur | GH-147-1 | 2010-11 | Bhagalpur | Shahkund | 1 | Proj. H.S, Shahkund | [9 empty] | 1 | Inaugurated | Bhagalpur
55 | Bhagalpur | GH-147-2 | 2010-11 | Bhagalpur | Jagdishpur | 2 | Proj. Girls H.S, Jagdishpur | [9 empty] | 1 | Inaugurated | Bhagalpur
56 | Bhagalpur | GH-148-1 | 2010-11 | Banka | Rajaoun | 1 | R.H.S, Douni | [9 empty] | 1 | Inaugurated | Bhagalpur
57 | Munger | GH-33-1 | 2009-10 | Munger | Haveli Kharagpur | 1 | Govt.+2 H.S., Haweli Kharagpur | [9 empty] | 1 | Inaugurated | Munger
58 | Munger | GH-33-2 | 2009-10 | Munger | Dharahara | 2 | K.R.S.K.H H.S., Dharahra | 1 | [9 empty] | Land not available | Munger
59 | Munger | GH-33-3 | 2009-10 | Munger | Tetiabamber | 3 | Jagannath H.S Tetia Bamber | [9 empty] | 1 | Inaugurated | Munger
60 | Munger | GH-34-1 | 2009-10 | Lakhisarai | Surajgarha | 1 | Project K. K.H., Surajgarha | 1 | [9 empty] | Land not available | Munger
61 | Munger | GH-34-2 | 2009-10 | Lakhisarai | Pipariya | 2 | M.M.P. H.S., Walipur | [9 empty] | 1 | Inaugurated 16.07.2016 | Munger
62 | Munger | GH-35-1 | 2009-10 | Lakhisarai | Halsi | 1 | High School, Halsi | [8 empty] | 1 |  |  | Munger
63 | Munger | GH-35-2 | 2009-10 | Lakhisarai | Ramgarh Chowk | 2 | D.M H.S., Sharma | [6 empty] | 1 |  |  |  | Partially upto FF Lintel | Munger
64 | Munger | GH-149-1 | 2010-11 | Munger | Tarapur | 1 | M.S, Tarapur | [5 empty] | 1 | [5 empty] | Munger
65 | Munger | GH-150-1 | 2010-11 | Jamui | Khaira | 1 | Project G.H.S, Khaira | [9 empty] | 1 | Inaugurated | Munger
66 | Munger | GH-150-2 | 2010-11 | Jamui | Sono | 2 | Project H.S, Sona | [9 empty] | 1 | Inaugurated | Munger
67 | Munger | GH-151-1 | 2010-11 | Lakhisarai | Lakhisarai | 1 | M.V.M H.S.Nayatola, Lakhisarai | 1 | [9 empty] | Dropped. PPO R.M.S.A | Munger
68 | Munger | GH-151-2 | 2010-11 | Lakhisarai | Barahiya | 2 | S.R.R.S Girls H.S, Barahiya | 1 | [9 empty] | Dropped. Land problem | Munger
69 | Koshi | GH-21-1 | 2009-10 | Supaul | Raghopur | 1 | M.S., Kajayan, Raghopur | [9 empty] | 1 | Inaugurated | Kosi
70 | Koshi | GH-21-2 | 2009-10 | Supaul | Pratapganj | 2 | Public H.S., Pratapganj | [9 empty] | 1 | Inaugurated | Kosi
71 | Koshi | GH-141-1 | 2010-11 | Saharsa | Kahra | 1 | Govt. Girls H. S, Saharsa | [9 empty] | 1 | Inaugurated | Kosi
72 | Koshi | GH-141-2 | 2010-11 | Saharsa | Saur Bazar | 2 | Gajadhar Sahu H.S, Saur Bazar | [9 empty] | 1 | Inaugurated | Kosi
73 | Koshi | GH-142-1 | 2010-11 | Saharsa | Salkhua | 1 | H.S, Salkhua | 1 | [9 empty] | Land not available. | Kosi
74 | Koshi | GH-142-2 | 2010-11 | Saharsa | Sonbarsa | 2 | Sir Hariballabh Inst. | [9 empty] | 1 |  | Kosi
75 | Purnea | GH-22-1 | 2009-10 | Purnea | Dhamdaha | 1 | H.S., Dhamdaha | [8 empty] | 1 |  |  | Purnea
76 | Purnea | GH-22-2 | 2009-10 | Purnea | Rupouli | 2 | Project Girl's H.S., Rupouli | [8 empty] | 1 |  |  | Purnea
77 | Purnea | GH-22-3 | 2009-10 | Purnea | Bhawanipur | 3 | H.S., Bhawanipur | [8 empty] | 1 |  |  | Purnea
78 | Purnea | GH-23-1 | 2009-10 | Purnea | Barharakothi | 1 | Shyama H.S., Bhatotar | [8 empty] | 1 |  |  | Purnea
79 | Purnea | GH-23-2 | 2009-10 | Purnea | K. Nagar | 2 | H.S., Champanagar | [8 empty] | 1 |  |  | Purnea
80 | Purnea | GH-24-1 | 2009-10 | Purnea | Purnia East | 1 | Proj. Girl's H.S., Ranipatra | 1 | [9 empty] | Land not available | Purnea
81 | Purnea | GH-24-2 | 2009-10 | Purnea | Jalalgarh | 2 | N.D Rungata H.S., Jalalgarh | [9 empty] | 1 | Inaugurated | Purnea
82 | Purnea | GH-24-3 | 2009-10 | Purnea | Kasba | 3 | Kalanand H.S., Garabnaili | [9 empty] | 1 | Inaugurated | Purnea
83 | Purnea | GH-25-1 | 2009-10 | Purnea | Dagarua | 1 | Abul Kalam H.S., Ichalo | 1 | [9 empty] | Not Start. Agreement not done | Purnea
84 | Purnea | GH-25-2 | 2009-10 | Purnea | Srinagar | 2 | Govt. S.S., Srinagar | 1 | [9 empty] | Not Start | Purnea
85 | Purnea | GH-25-3 | 2009-10 | Purnea | Baisi | 3 | Proj. Girl's School Baisi | 1 | [9 empty] | Not Start | Purnea
86 | Purnea | GH-26-1 | 2009-10 | Purnea | Baisa | 1 | H.S., Rauta | [8 empty] | 1 |  |  | Purnea
87 | Purnea | GH-26-2 | 2009-10 | Purnea | Amour | 2 | Project Girl's School, Amour | [8 empty] | 1 |  |  | Purnea
88 | Purnea | GH-27-1 | 2009-10 | Katihar | Kadwa | 1 | N.C.C. Smarak H.S Balia Belon | [9 empty] | 1 | Inaugurated | Purnea
89 | Purnea | GH-27-2 | 2009-10 | Katihar | Balrampur | 2 | S.S., High School, Telta | [9 empty] | 1 | Inaugurated | Purnea
90 | Purnea | GH-27-3 | 2009-10 | Katihar | Sameli | 3 | D.G.H.S., Krishna Nagar | [9 empty] | 1 | Inaugurated | Purnea
91 | Purnea | GH-28-1 | 2009-10 | Katihar | Manihari | 1 | B.P.S.P.H.S., Manihari | [9 empty] | 1 | Inaugurated | Purnea
92 | Purnea | GH-28-2 | 2009-10 | Katihar | Azamnagar | 2 | H.S., Salmari | [9 empty] | 1 | Inaugurated | Purnea
93 | Purnea | GH-28-3 | 2009-10 | Katihar | Pranpur | 3 | M.S., Bastol | 1 | [9 empty] | Land Dispute | Purnea
94 | Purnea | GH-29-1 | 2009-10 | Katihar | Falka | 1 | B.S.M.High School, Pothiya | [8 empty] | 1 |  |  | Purnea
95 | Purnea | GH-29-2 | 2009-10 | Katihar | Kursela | 2 | Sampat Raj Devi Girl's H.S., Kursela | [8 empty] | 1 |  |  | Purnea
96 | Tirhut East | GH-01-1 | 2009-10 | Sitamarhi | Parihar | 1 | S.G.H.S., Parihar | [9 empty] | 1 | Inaugurated | Tirhut East
97 | Tirhut East | GH-01-2 | 2009-10 | Sitamarhi | Sonbarsa | 2 | H.S., Bhutahi | [9 empty] | 1 | Inaugurated | Tirhut East
98 | Tirhut East | GH-01-3 | 2009-10 | Sitamarhi | Bathnaha | 3 | H.S., Yogibana Bazar | [9 empty] | 1 | Inaugurated | Tirhut East
99 | Tirhut East | GH-02-1 | 2009-10 | Sitamarhi | Parsauni | 1 | H.S., Parsauni Chowk | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut East
100 | Tirhut East | GH-02-2 | 2009-10 | Sitamarhi | Riga | 2 | H.S., Rewasi | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut East
101 | Tirhut East | GH-02-3 | 2009-10 | Sitamarhi | Belsand | 3 | H.S., Belsand | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut East
102 | Tirhut East | GH-3-1 | 2009-10 | Sitamarhi | Bairgania | 1 | Jaurimal H.S., Bairgania | [5 empty] | 1 | [5 empty] | Tirhut East
103 | Tirhut East | GH-3-2 | 2009-10 | Sitamarhi | Suppi | 2 | H.S., Suppi | [5 empty] | 1 | [5 empty] | Tirhut East
104 | Tirhut East | GH-3-3 | 2009-10 | Sitamarhi | Majarganj | 3 | H.S., Majarganj | [5 empty] | 1 | [5 empty] | Tirhut East
105 | Tirhut East | GH-4-1 | 2009-10 | Sitamarhi | Sursand | 1 | Saryu H.S., Sursand | [7 empty] | 1 |  |  |  | Tirhut East
106 | Tirhut East | GH-4-2 | 2009-10 | Sitamarhi | Pupri | 2 | Proj. H.S., Pupri | 1 | [9 empty] | small land | Tirhut East
107 | Tirhut East | GH-4-3 | 2009-10 | Sitamarhi | Choraut | 3 | H.S., Choraut | [8 empty] | 1 |  | Grill ,flooring Electric Running Plaster Done | Tirhut East
108 | Tirhut East | GH-5-1 | 2009-10 | Sitamarhi | Bajpatti | 1 | H.S., Bajpatti | [9 empty] | 1 | Inaugurated | Tirhut East
109 | Tirhut East | GH-5-2 | 2009-10 | Sitamarhi | Nanpur | 2 | H.S., Janipur | [9 empty] | 1 | Inaugurated | Tirhut East
110 | Tirhut East | GH-5-3 | 2009-10 | Sitamarhi | Bokhra | 3 | H.S., Kharka | [9 empty] | 1 | Inaugurated | Tirhut East
111 | Tirhut East | GH-6-1 | 2009-10 | Sitamarhi | Dumra | 1 | K.G.H.S., Dumra | [8 empty] | 1 |  | Work stopped | Tirhut East
112 | Tirhut East | GH-6-2 | 2009-10 | Sitamarhi | Runni saidpur | 2 | H.S., Morsand | [8 empty] | 1 |  | Work stopped | Tirhut East
113 | Tirhut East | GH-121-1 | 2010-11 | Vaishali | Rajapakar | 1 | H.S.,Rajapakar | 1 | [10 empty] | Tirhut East
114 | Tirhut East | GH-121-2 | 2010-11 | Vaishali | Mahua | 2 | M.S. Singhara | [9 empty] | 1 | Inaugurated | Tirhut East
115 | Tirhut East | GH-122-1 | 2010-11 | Vaishali | Raghopur | 1 | B.S.J.S.H.S.Fatehpur, Vaishali | 1 | [9 empty] | Land problem | Tirhut East
116 | Tirhut East | GH-122-2 | 2010-11 | Vaishali | Bidupur | 2 | S.S.V.M.H.S., Ramdauli | [9 empty] | 1 | Inaugurated | Tirhut East
117 | Tirhut East | GH-122-3 | 2010-11 | Vaishali | Deshri | 3 | H.S. Bhataulla | 1 | [9 empty] | Dismantling | Tirhut East
118 | Tirhut East | GH-123-1 | 2010-11 | Vaishali | Patepur | 1 | S.R.C.H.S.,Patepur, Vaishali | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut East
119 | Tirhut East | GH-123-2 | 2010-11 | Vaishali | Lalganj | 2 | G.A.H/S, Lalganj | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct | Tirhut East
120 | Tirhut East | GH-123-3 | 2010-11 | Vaishali | Goraul | 3 | H.S., Goraul | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct | Tirhut East
121 | Tirhut East | GH-124-1 | 2010-11 | Vaishali | Vaishali | 1 | S.M.T.H.S., Vaishali | 1 | [9 empty] | No apparoch road | Tirhut East
122 | Tirhut East | GH-124-2 | 2010-11 | Vaishali | Bhagwanpur | 2 | M.S.Ratnapura Bhagwanpur | [8 empty] | 1 |  | Inaugurated 16.07.2016 | Tirhut East
123 | Tirhut East | GH-124-3 | 2010-11 | Vaishali | Chehrakala | 3 | B.N. High School, Sehan * | [8 empty] | 1 |  |  | Tirhut East
124 | Tirhut West | GH-116-1 | 2010-11 | East Champaran | Chakiya | 1 | K.G.B.N., Chakiya | 1 | [9 empty] | Land not available | Tirhut West
125 | Tirhut West | GH-116-2 | 2010-11 | East Champaran | Kalyanpur | 2 | K.G.B.N., Kalyanpur | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut West
126 | Tirhut West | GH-117-1 | 2010-11 | East Champaran | Dhaka | 1 | K.G.B.N., Dhaka | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut West
127 | Tirhut West | GH-117-2 | 2010-11 | East Champaran | Ghorasahan | 2 | K.G.B.N.,Ghorasahan | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut West
128 | Tirhut West | GH-118-1 | 2010-11 | East Champaran | Kesariya | 1 | K.G.B.N., Kesariya | [9 empty] | 1 | Inaugurated 16.07.2016 | Tirhut West
129 | Tirhut West | GH-118-2 | 2010-11 | East Champaran | Kotwa | 2 | K.G.B.N., Kotwa | [8 empty] | 1 |  |  | Tirhut West
130 | Tirhut West | GH-118-3 | 2010-11 | East Champaran | Sangrampur | 3 | K.G.B.N., Sangrampur | [8 empty] | 1 |  |  | Tirhut West
131 | Tirhut West | GH-119-1 | 2010-11 | East Champaran | Madhuwan | 1 | K.G.B.N., Madhuwan | 1 | [9 empty] | Not start | Tirhut West
132 | Tirhut West | GH-119-2 | 2010-11 | East Champaran | Mehsi | 2 | K.G.B.N., Mehsi | 1 | [9 empty] | Not start | Tirhut West
133 | Tirhut West | GH-119-3 | 2010-11 | East Champaran | Tetariya | 3 | K.G.B.N., Tetariya | 1 | [9 empty] | Not Start | Tirhut West
134 | Tirhut West | GH-120-1 | 2010-11 | East Champaran | Ramgharwa | 1 | K.G.B.N., Ramgharwa | [8 empty] | 1 |  |  | Tirhut West
135 | Tirhut West | GH-125-1 | 2010-11 | West Champaran | Bagha-1 | 1 | R.S.H.S. Parsuniform | 1 | [9 empty] | Not start | Tirhut West
136 | Darbhanga | GH-14-1 | 2009-10 | Madhubani | Benipatti | 1 | B.J.J.H.S. Adher* | [8 empty] | 1 |  |  | Darbhanga
137 | Darbhanga | GH-14-2 | 2009-10 | Madhubani | Bisfi | 1 | H.S. Parsauni* | [8 empty] | 1 |  |  | Darbhanga
138 | Darbhanga | GH-15-1 | 2009-10 | Madhubani | Madhepur | 1 | H.S. Madhepur* | [9 empty] | 1 | Inaugurated 16.07.2016 | Darbhanga
139 | Darbhanga | GH-15-2 | 2009-10 | Madhubani | Lakhanaur | 1 | P Girl H.S. Lakhanaur* | [9 empty] | 1 | Inaugurated 16.07.2016 | Darbhanga
140 | Darbhanga | GH-15-3 | 2009-10 | Madhubani | Andarathari | 1 | M.S., Andarathari | [9 empty] | 1 | Inaugurated 16.07.2016 | Darbhanga
141 | Darbhanga | GH-16-1 | 2009-10 | Madhubani | Rajnagar | 1 | R. H.S.Raj Nagar* | 1 | [9 empty] | Required land 125'x100' available land50'x25' | Darbhanga
142 | Darbhanga | GH-16-2 | 2009-10 | Madhubani | Pandaul | 1 | Anup Lal Project Girls H.S. Barmotra Pandaul* | [9 empty] | 1 | Inaugurated 16.07.2016 | Darbhanga
143 | Darbhanga | GH-16-3 | 2009-10 | Madhubani | Babubarhi | 1 | M.S., Bhupatti | [9 empty] | 1 | Inaugurated 16.07.2016 | Darbhanga
144 | Darbhanga | GH-17-1 | 2009-10 | Madhubani | Ladania | 1 | M.S., Ladania Girl's | 1 | [9 empty] | Land not available | Darbhanga
145 | Darbhanga | GH-17-2 | 2009-10 | Madhubani | Jainagar | 1 | M.S., Dullipatti | [9 empty] | 1 | Inaugurated | Darbhanga
146 | Darbhanga | GH-18-1 | 2009-10 | Madhubani | Basopatti | 1 | H.S. Basopatti * | [9 empty] | 1 |  | Darbhanga
147 | Darbhanga | GH-18-2 | 2009-10 | Madhubani | Madhwapur | 1 | H.S. Madhwapur* | [6 empty] | 1 |  |  |  |  | Darbhanga
148 | Darbhanga | GH-18-3 | 2009-10 | Madhubani | Ghoghardiha | 1 | H.S., Dewadh | [8 empty] | 1 |  | avialable | Darbhanga
149 | Darbhanga | GH-19-1 | 2009-10 | Samastipur | Singhia | 1 | K.G., Academy, Singhia | 1 | [9 empty] | Land not available (required land 125'x100' avlaible land22'x11') | Darbhanga
150 | Darbhanga | GH-19-2 | 2009-10 | Samastipur | Bithan | 1 | H.S., Bithan | [9 empty] | 1 | Inaugurated | Darbhanga
151 | Darbhanga | GH-20-1 | 2009-10 | Samastipur | Warisnagar | 1 | M.S., Hajpurwa, Warisnagar | [9 empty] | 1 | Inaugurated | Darbhanga
152 | Darbhanga | GH-20-2 | 2009-10 | Samastipur | Marwa | 1 | H.S., Morwa | 1 | [9 empty] | Land not available | Darbhanga
153 | Darbhanga | GH-133-1 | 2010-11 | Darbhanga | Keoti | 1 | R. S. H.S, Keoti | [9 empty] | 1 | Inaugurated | Darbhanga
154 | Darbhanga | GH-133-2 | 2010-11 | Darbhanga | Ghanshyampur | 2 | H.S, Pohadidibela | [9 empty] | 1 | Inaugurated | Darbhanga
155 | Darbhanga | GH-134-1 | 2010-11 | Darbhanga | Kusheswara | 1 | M.S, Kushe .Sthan | [9 empty] | 1 | Inaugurated | Darbhanga
156 | Darbhanga | GH-134-2 | 2010-11 | Darbhanga | Hanuman Nagar | 2 | G..H. S.Kolhanta Patori | [9 empty] | 1 | Inaugurated | Darbhanga
157 | Darbhanga | GH-135-1 | 2010-11 | Darbhanga | Gora Bauram | 1 | H.S, Gourabauram | [6 empty] | 1 |  |  |  |  | Darbhanga
158 | Darbhanga | GH-135-2 | 2010-11 | Darbhanga | Manigachhi | 2 | H.S, Balour | [9 empty] | 1 | Inaugurated | Darbhanga
159 | Darbhanga | GH-135-3 | 2010-11 | Darbhanga | Tardih | 3 | H.S, Narainpur | [9 empty] | 1 | Inaugurated | Darbhanga
160 | Darbhanga | GH-136-1 | 2010-11 | Madhubani | Kaulahi | 1 | H.S, Kaulahi | 1 | [9 empty] | Land Dispute | Darbhanga
161 | Darbhanga | GH-136-2 | 2010-11 | Madhubani | Harlakhi | 2 | H.S, Umgaun | [9 empty] | 1 | Inaugurated | Darbhanga
162 | Darbhanga | GH-137-1 | 2010-11 | Samastipur | Kalyanpur | 1 | K.G.B.V, Kalyanpur | 1 | [9 empty] | Land not available | Darbhanga
163 | Darbhanga | GH-137-2 | 2010-11 | Samastipur | Pusa | 2 | Girls Int. Sch. Pusa | [9 empty] | 1 | Inaugurated | Darbhanga
164 | Darbhanga | GH-138-1 | 2010-11 | Samastipur | Ujiarpur | 1 | B.R.C, Ujiarpur Campus | [9 empty] | 1 | Inaugurated | Darbhanga
165 | Darbhanga | GH-138-2 | 2010-11 | Samastipur | Sarayranjan | 2 | H.S, Bathua Bujurg | [9 empty] | 1 | Inaugurated | Darbhanga
166 | Darbhanga | GH-138-3 | 2010-11 | Samastipur | Samastipur | 3 | M. I. S. Samastipur | [9 empty] | 1 | Inaugurated | Darbhanga
167 | Darbhanga | GH-139-1 | 2010-11 | Samastipur | Vidyapati Nagar | 1 | I.Sch.Vidyapati Nagar N | [9 empty] | 1 | Inaugurated | Darbhanga
168 | Darbhanga | GH-139-2 | 2010-11 | Samastipur | Bibhutipur | 2 | M.S, Sirsi | [9 empty] | 1 | Inaugurated | Darbhanga
169 | Darbhanga | GH-139-3 | 2010-11 | Samastipur | Dalsingh Sarai | 3 | C.H. I. S.Dalsingh Sarai | [9 empty] | 1 | Inaugurated | Darbhanga
170 | Darbhanga | GH-140-1 | 2010-11 | Samastipur | Hasanpur | 1 | N.H.S, Hasanpur Road | [9 empty] | 1 | Inaugurated | Darbhanga
171 | Darbhanga | GH-140-2 | 2010-11 | Samastipur | Sihivaji nagar | 2 | H.S, Shivaji Nagar | [9 empty] | 1 | Inaugurated | Darbhanga
172 | Darbhanga | GH-140-3 | 2010-11 | Samastipur | Khanpur | 3 | I.Sch. Siropatti Khatu | [9 empty] | 1 | Inaugurated | Darbhanga
173 | Saran | GH-12-1 | 2009-10 | Saran | Marhourah | 1 | U.M.S., Awari, Marhourah | [9 empty] | 1 | Inaugurated | Saran
174 | Saran | GH-12-2 | 2009-10 | Saran | Taraiyan | 1 | M.S., Gawandary, Taria | 1 | [9 empty] | Location changed & But Land Problem | Saran
175 | Saran | GH-13-1 | 2009-10 | Saran | Parsa | 1 | M.S., Bishnupur, Parsa | [9 empty] | 1 | Inaugurated. Handover | Saran
176 | Saran | GH-13-2 | 2009-10 | Saran | Ishuapur | 1 | U.M.S., Satasi, Ishuapur | 1 | [9 empty] | Land problem | Saran
177 | Saran | GH-126-1 | 2010-11 | Saran | Garkha | 1 | MS Chainpur Bhaiswara | [9 empty] | 1 |  | Saran
178 | Saran | GH-126-2 | 2010-11 | Saran | Maker | 1 | UMS Baghakol | [9 empty] | 1 | Inaugurated. Handover | Saran
179 | Saran | GH-127-1 | 2010-11 | Siwan | Maharajganj | 1 | H.S.Sikatiya | [9 empty] | 1 | Inaugurated. Handover | Saran
180 | Saran | GH-127-2 | 2010-11 | Siwan | Barhariya | 1 | Sri Krishan H.S. Kailgarh | [9 empty] | 1 | Inaugurated. Handover | Saran
181 | Saran | GH-127-3 | 2010-11 | Siwan | Bhagwanpur Hatt | 1 | S.S. High School, Bhagawanpur Hatt | [9 empty] | 1 | Inaugurated. Handover | Saran
182 | Saran | GH-128-1 | 2010-11 | Siwan | Goreya Kothi | 1 | Narayan Karmayogi H.S, Goreyakothi | [9 empty] | 1 | Inaugurated. Handover | Saran
183 | Saran | GH-128-2 | 2010-11 | Siwan | Basantpur | 1 | H.S, Basantpur | [9 empty] | 1 | Inaugurated. Handover | Saran
184 | Saran | GH-128-3 | 2010-11 | Siwan | Dharaunda | 1 | G.S. H.S, Ujaini | [9 empty] | 1 | Inaugurated. Handover | Saran
185 | Saran | GH-129-1 | 2010-11 | Gopalganj | Baikunthpur | 1 | H.S, Sirsa | [9 empty] | 1 | Inaugurated | Saran
186 | Saran | GH-129-2 | 2010-11 | Gopalganj | Sidhwaliya | 1 | H.S, Mahamadpur | [9 empty] | 1 | Inaugurated. Handover | Saran
187 | Saran | GH-129-3 | 2010-11 | Gopalganj | Manjha | 1 | H.S, Manjha(old) H/s Dharm Parsa(New) | [9 empty] | 1 | Handover | Saran
188 | Saran | GH-130-1 | 2010-11 | Gopalganj | Panchdewari | 1 | H.S, Jamunaha Bazar | [9 empty] | 1 | Inaugurated | Saran
189 | Saran | GH-130-2 | 2010-11 | Gopalganj | Bhorey | 1 | H.S, Bhore | [8 empty] | 1 |  |  | Saran
190 | Saran | GH-131-1 | 2010-11 | Gopalganj | Uchakagaon | 1 | H.S, Uchakagaon | [8 empty] | 1 |  |  | Saran
191 | Saran | GH-131-2 | 2010-11 | Gopalganj | Kateya | 1 | Kanya H.S, Kateya(old) G.A H/S Kateya | 1 | [9 empty] | Land Dispute | Saran
192 | Saran | GH-132-1 | 2010-11 | Gopalganj | Kuchaikote | 1 | H.S, Sonekola | [9 empty] | 1 | Inaugurated. Handover | Saran
193 | Saran | GH-132-2 | 2010-11 | Gopalganj | Gopalganj | 1 | S.S Girls Inter School, Gopalganj | [9 empty] | 1 | Inaugurated | Saran
|  | Total No. of Schools (Girls Hostel) : |  |  |  |  | 193 | 47 | 0 | 0 | 0 | 0 | 4 | 3 | 1 | 32 | 106