## DIET-31
BSEIDC Ltd., Patna
PROGRESS REPORT OF DIET
S.No. | SL NO. | Group No. | District | Name Of Institution | S. No. | Name Of Building | Name of Agency with Mo- | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks |  | Division
[11 empty] | Not Start | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL | LL | RL |  |  |  | Scheme
| 1 | D-1 | Banka | DIET Babu Tola | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 455 SBD OF 14-15 (15.11.14) | [12 empty] | 1 |  |  | DIET | Bhagalpur
[5 empty] | 2 | Boys Hostel | Satendra Kumar Construction 9431130085 | [12 empty] | 1 |  |  |  | DIET | Bhagalpur
[5 empty] | 3 | Girls Hostel | Satendra Kumar Construction 9431130085 | [12 empty] | 1 |  |  |  | DIET | Bhagalpur
| 2 | D-2 | Buxar | DIET Dumraon | 1 | Institutional Building | Recon Construction mo-9771496617 | 341 SBD OF 2014-2015(18.09.14) | [5 empty] | 1 | [9 empty] | DIET | Patna West
[5 empty] | 2 | Boys Hostel | Recon Construction mo-9771496617 | [6 empty] | 1 | [9 empty] | DIET | Patna West
[5 empty] | 3 | Girls Hostel | Recon Construction mo-9771496617 | [5 empty] | 1 | [10 empty] | DIET | Patna West
| 3 | D-3 | Kaimur | DIET Mohaniya | 1 | Institutional Building | Recon Construction mo-9771496617 | 340 SBD OF 2014-2015(18.09.14) |  |  |  |  | 1 | [10 empty] | DIET | Patna West
[5 empty] | 2 | Boys Hostel | Recon Construction mo-9771496617 | [8 empty] | 1 | [7 empty] | DIET | Patna West
[5 empty] | 3 | Girls Hostel | Recon Construction mo-9771496617 | [8 empty] | 1 | [7 empty] | DIET | Patna West
| 4 | D-4 | Kishanganj | DIET Chaklaghat Kishanganj | 1 | Institutional Building | Ashok Kumar mo-9431096238 | 236 SBD OF 2015-15(29.08.15) | [13 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
[5 empty] | 2 | Boys Hostel | Ashok Kumar mo-9431096238 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
[5 empty] | 3 | Girls Hostel | Ashok Kumar mo-9431096238 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
| 5 | D-5 | Lakhisarai | DIET Lakhisarai | 1 | Institutional Building | Sai highway & builder Pvt. Ltd. | 35 SBD OF 2016-17(19.05.16) | [9 empty] | 1 |  |  | 1 |  |  | DIET | Munger
[5 empty] | 2 | Boys Hostel | Sai highway & builder Pvt. Ltd. | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 3 | Girls Hostel | Sai highway & builder Pvt. Ltd. | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 4 | Principal Quarter | Sai highway & builder Pvt. Ltd. | [9 empty] | X | X | X | X | 1 |  |  | DIET | Munger
| 6 | D-6 | Araria | DIET Forbesganj | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 227 SBD of 2013-14(24-2-2014) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Purnea
[5 empty] | 2 | Boys Hostel | Topline Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
[5 empty] | 3 | Girls Hostel | Topline Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Purnea
| 7 | D-7 | Gopalganj | DIET Thawe | 1 | Institutional Building | C.K.infrastructure | 383SBD OF 2014-2014(10.10.14) | [12 empty] | 1 |  |  | DIET | Saran
[5 empty] | 2 | Boys Hostel | C.K.infrastructure | [10 empty] | 1 | [5 empty] | DIET | Saran
[5 empty] | 3 | Girls Hostel | C.K.infrastructure | [10 empty] | 1 | [5 empty] | DIET | Saran
| 8 | D-8 | Madhubani | DIET Narar | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 233 SBD of 2013-14(6-3-2014) | [13 empty] | 1 |  | DIET | Darbhanga
[5 empty] | 2 | Boys Hostel | Phular Construction Pvt.Ltd Mo-9431813608 | [14 empty] | 1 |  | DIET | Darbhanga
[5 empty] | 3 | Girls Hostel | Phular Construction Pvt.Ltd Mo-9431813608 | [14 empty] | 1 |  | DIET | Darbhanga
| 9 | D-9 | Saran | DIET Sonpur | 1 | Institutional Building | Phular Construction Pvt.Ltd Mo-9431813608 | 233 SBD of 2013-14(6-3-2014) | [13 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
[5 empty] | 2 | Boys Hostel | Phular Construction Pvt.Ltd Mo-9431813608 |  |  |  | 1 | [11 empty] | Land problem | DIET | Saran
[5 empty] | 3 | Girls Hostel | Phular Construction Pvt.Ltd Mo-9431813608 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
| 10 | D-10 | Samastipur | DIET Pusa | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 220 SBD of 2013-14(5-2-2014) |  |  | 1 | [11 empty] | old building dismalting | DIET | Darbhanga
[5 empty] | 2 | Boys Hostel | Delco Infrastructure ph-011-28042498 | [13 empty] | 1 |  |  | DIET | Darbhanga
[5 empty] | 3 | Girls Hostel | Delco Infrastructure ph-011-28042498 | [13 empty] | 1 |  |  | DIET | Darbhanga
| 11 | D-11 | Madhepura | DIET Madhepura | 1 | Institutional Building | Delco Infrastructure ph-011-28042498 | 221 SBD of 2013-14(5-2-2014) | [9 empty] | 1 | [5 empty] | DIET | Koshi
[5 empty] | 2 | Boys Hostel | Delco Infrastructure ph-011-28042498 | [12 empty] | 1 |  |  |  | DIET | Koshi
[5 empty] | 3 | Girls Hostel | Delco Infrastructure ph-011-28042498 | [5 empty] | 1 | [10 empty] | DIET | Koshi
| 12 | D-12 | Siwan | DIET Siwan | 1 | Institutional Building | Durga Pratap Singh Mo-7781003700 | 169 SBD of 2013-14(30-11-2013) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Saran
[5 empty] | 2 | Boys Hostel | Durga Pratap Singh Mo-7781003700 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
[5 empty] | 3 | Girls Hostel | Durga Pratap Singh Mo-7781003700 | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Saran
| 13 | D-13 | Aurangabad | DIET Tarar | 1 | Institutional Building | Satyendra Kumar construction | 19 SBD OF 2016-17 (05.05.16) | [12 empty] | 1 |  |  | DIET | Magadh
[5 empty] | 2 | Boys Hostel | Satyendra Kumar construction | [13 empty] | 1 |  |  | DIET | Magadh
[5 empty] | 3 | Girls Hostel | Satyendra Kumar construction | [13 empty] | 1 |  |  | DIET | Magadh
[5 empty] | 4 | Principal Quarter | Satyendra Kumar construction | [8 empty] | 1 | X | X | X | X |  |  |  | DIET | Magadh
| 14 | D-14 | Katihar | DIET Tikkapatti | 1 | Institutional Building | Topline Infrastructure Mo-943188439 | 48 SBD OF 2014-15 (29.05.14 | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2017 | DIET | Purnea
[5 empty] | 2 | Boys Hostel | Topline Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Purnea
[5 empty] | 3 | Girls Hostel | Topline Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Purnea
| 15 | D-15 | Nalanda | DIET Noorsarai | 1 | Institutional Building | Shristi Devloper Pvt.Ltd Mo-9334998030 | 214 SBD OF 2014-15 (31.07.14) | [12 empty] | 1 |  |  | DIET | Patna East
[5 empty] | 2 | Boys Hostel | Shristi Devloper Pvt.Ltd Mo-9334998030 | [13 empty] | 1 |  |  | DIET | Patna East
[5 empty] | 3 | Girls Hostel | Shristi Devloper Pvt.Ltd Mo-9334998030 | [13 empty] | 1 |  |  | DIET | Patna East
| 16 | D-16 | East Champaran | DIET Chhatauni, Motihari | 1 | Institutional Building | Ramesh Kumar mo-8294249534 | 144SBD OF 2013-14 (1-11-13) | [13 empty] | 1 | Inaugurated 16.07.2017 | DIET | Tirhut West
[5 empty] | 2 | Boys Hostel | Ramesh Kumar mo-8294249534 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Tirhut West
[5 empty] | 3 | Girls Hostel | Ramesh Kumar mo-8294249534 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Tirhut West
| 17 | D-17 | Patna | DIET Vikram | 1 | Institutional Building | Arvind Kumar | 458 SBD OF 14-15 (17.11.14) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2017 | DIET | Patna East
[5 empty] | 2 | Boys Hostel | Arvind Kumar | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Patna East
[5 empty] | 3 | Girls Hostel | Arvind Kumar | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Patna East
[5 empty] | 4 | Principal Quarter | Arvind Kumar | [9 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | DIET | Patna East
| 18 | D-18 | Shahpur | DIET Begusarai | 1 | Institutional Building | M/S VIKASH CONSTRUCTION | 716 SBD OF 2014-15 (25.02.15) | [10 empty] | X | X | 1 |  |  | DIET | Munger
[5 empty] | 2 | Boys Hostel | M/S VIKASH CONSTRUCTION | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 3 | Girls Hostel | M/S VIKASH CONSTRUCTION | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 4 | Principal Quarter | M/S VIKASH CONSTRUCTION | [9 empty] | X | X | X | X | 1 |  |  | DIET | Munger
| 19 | D-19 | Darbhanga | DIET Kilaghat | 1 | Institutional Building | Bablu Kumar Bhagat |  |  |  | 1 | [11 empty] | LOA Issue. Land Dispute | DIET | Darbhanga
[5 empty] | 2 | Boys Hostel | Bablu Kumar Bhagat | [8 empty] | 1 | [7 empty] | DIET | Darbhanga
[5 empty] | 3 | Girls Hostel | Bablu Kumar Bhagat |  |  |  | 1 | [11 empty] | LOA Issue. Land Dispute | DIET | Darbhanga
| 20 | D-20 | Nawada | DIET Jawahar Nagar | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 453SBD OF 14-15 (15.11.14) | [13 empty] | 1 | Handover | DIET | Magadh
[5 empty] | 2 | Boys Hostel | Satendra Kumar Construction 9431130085 | [14 empty] | 1 | Handover | DIET | Magadh
[5 empty] | 3 | Girls Hostel | Satendra Kumar Construction 9431130085 | [14 empty] | 1 | Handover | DIET | Magadh
[5 empty] | 4 | Principal Quarter | Satendra Kumar Construction 9431130085 | [9 empty] | X | X | X | X |  | 1 | Handover | DIET | Magadh
| 21 | D-21 | Munger | DIET Purabsarai | 1 | Institutional Building | Satendra Kumar Construction 9431130085 | 114 SBD OF 2015-16 (15.06.15) | [9 empty] | 1 |  |  |  |  | BW upto PL | DIET | Munger
[5 empty] | 2 | Boys Hostel | Satendra Kumar Construction 9431130085 | [9 empty] | 1 | [5 empty] | Not start | DIET | Munger
[5 empty] | 3 | Girls Hostel | Satendra Kumar Construction 9431130085 | [12 empty] | 1 |  |  | RCC in Found | DIET | Munger
[5 empty] | 4 | Principal Quarter | Satendra Kumar Construction 9431130085 | [5 empty] | 1 |  |  |  | X | X | X | X |  |  | Excavation | DIET | Munger
| 22 | D-22 | Khagaria | DIET Ramganj | 1 | Institutional Building | Surender Prasad Singh | 549 SBD OF 2014-15 (22.12.14) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Munger
[5 empty] | 2 | Boys Hostel | Surender Prasad Singh | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
[5 empty] | 3 | Girls Hostel | Surender Prasad Singh | [14 empty] | 1 | Inaugurated 16.07.2016 | DIET | Munger
[5 empty] | 4 | Principal Quarter | Surender Prasad Singh | [9 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | DIET | Munger
| 23 | D-23 | Sheikhpura | DIET Sheikhpura | 1 | Institutional Building | Satay Narayan Singh | 113 SBD OF 2015-16 (15.06.15) | [7 empty] | 1 | [7 empty] | DIET | Munger
[5 empty] | 2 | Boys Hostel | Satay Narayan Singh | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 3 | Girls Hostel | Satay Narayan Singh | [13 empty] | 1 |  |  | DIET | Munger
[5 empty] | 4 | Principal Quarter | Satay Narayan Singh | [9 empty] | X | X | X | X | 1 |  |  | DIET | Munger
| 24 | D-24 | Purnea | DIET Purnea | 1 | Institutional Building | Top Line Infrastructure Mo-943188439 | 502 SBD OF 14-15 (12.12.14 | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2017 | DIET | Purnea
[5 empty] | 2 | Boys Hostel | Top Line Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Purnea
[5 empty] | 3 | Girls Hostel | Top Line Infrastructure Mo-943188439 | [14 empty] | 1 | Inaugurated 16.07.2017 | DIET | Purnea
[5 empty] | 4 | Principal Quarter | Top Line Infrastructure Mo-943188439 | [9 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | DIET | Purnea
| 25 | D-25 | West Champaran | DIET Kumarbag, West Champaran | 1 | Institutional Building | Satyendra kumar construction | 20 SBD OF 2016-17 (05.05.2016) | [12 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 2 | Boys Hostel | Satyendra kumar construction | [13 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 3 | Girls Hostel | Satyendra kumar construction | [13 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 4 | Principal Quarter | Satyendra kumar construction | [9 empty] | X | X | X | X | 1 |  |  | DIET | Tirhut West
| 26 | D-26 | Sheohar | DIET Sheohar | 1 | Institutional Building | SHASHIKANT SINGH | 11 SBD OF 2016-17(20.04.2016) | [12 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 2 | Boys Hostel | SHASHIKANT SINGH | [13 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 3 | Girls Hostel | SHASHIKANT SINGH | [13 empty] | 1 |  |  | DIET | Tirhut West
[5 empty] | 4 | Principal Quarter | SHASHIKANT SINGH | [9 empty] | X | X | X | X | 1 |  |  | DIET | Tirhut West
| 27 | D-27 | Arwal | DIET Haibatpur | 1 | Institutional Building | MS RAJ CONSTRUCTION, VILL-DIHURI , PO-MALWAN PS-KHUDWAN DIST-AURANGABAD BIHAR 9431247120, |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 2 | Boys Hostel | MS RAJ CONSTRUCTION, VILL-DIHURI , PO-MALWAN PS-KHUDWAN DIST-AURANGABAD BIHAR 9431247120, |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 3 | Girls Hostel | MS RAJ CONSTRUCTION, VILL-DIHURI , PO-MALWAN PS-KHUDWAN DIST-AURANGABAD BIHAR 9431247120, |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 4 | Principal Quarter | MS RAJ CONSTRUCTION, VILL-DIHURI , PO-MALWAN PS-KHUDWAN DIST-AURANGABAD BIHAR 9431247120, |  |  |  | 1 | [12 empty] | DIET | Magadh
| 28 | D-28 | Jamui | DIET , Giddhour | 1 | Institutional Building | SUDESH KUMAR SINGH AND CO CONST PVT LTD, MOH-KALYANPUR, NEAR GIRISH TALKIES, JAMUI, 9934658786 | [5 empty] | 1 | [10 empty] | DIET | Munger
[5 empty] | 2 | Boys Hostel | SUDESH KUMAR SINGH AND CO CONST PVT LTD, MOH-KALYANPUR, NEAR GIRISH TALKIES, JAMUI, 9934658786 | [5 empty] | 1 | [10 empty] | DIET | Munger
[5 empty] | 3 | Girls Hostel | SUDESH KUMAR SINGH AND CO CONST PVT LTD, MOH-KALYANPUR, NEAR GIRISH TALKIES, JAMUI, 9934658786 | [7 empty] | 1 | [8 empty] | DIET | Munger
[5 empty] | 4 | Principal Quarter | SUDESH KUMAR SINGH AND CO CONST PVT LTD, MOH-KALYANPUR, NEAR GIRISH TALKIES, JAMUI, 9934658786 |  |  |  |  | 1 | [11 empty] | DIET | Munger
| 29 | D-29 | Jehanabad | DIET Dogra, Hulasganj | 1 | Institutional Building | SANJAY CONSTRUCTION,LOHAR LANE,MUSALLAHPUR |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 2 | Boys Hostel | SANJAY CONSTRUCTION,LOHAR LANE,MUSALLAHPUR |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 3 | Girls Hostel | SANJAY CONSTRUCTION,LOHAR LANE,MUSALLAHPUR |  |  |  | 1 | [12 empty] | DIET | Magadh
[5 empty] | 4 | Principal Quarter | SANJAY CONSTRUCTION,LOHAR LANE,MUSALLAHPUR |  |  |  | 1 | [12 empty] | DIET | Magadh
| 30 | D-30 | Saharsa | DIET , Suhath | 1 | Institutional Building | Umakant Singh,OFFICER'S COLONY, MIRCHAIBARI, KATIHAR ,9431096239 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 2 | Boys Hostel | Umakant Singh,OFFICER'S COLONY, MIRCHAIBARI, KATIHAR ,9431096239 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 3 | Girls Hostel | Umakant Singh,OFFICER'S COLONY, MIRCHAIBARI, KATIHAR ,9431096239 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 4 | Principal Quarter | Umakant Singh,OFFICER'S COLONY, MIRCHAIBARI, KATIHAR ,9431096239 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
| 31 | D-31 | Supual | DIET , Basaho | 1 | Institutional Building | PRASAD CONSTRUCTION AND CO, LILA MOHAN NIWAS, NAISARAI, BIHAR SHARIF, NALANDA , 803101, 9431174533 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 2 | Boys Hostel | PRASAD CONSTRUCTION AND CO, LILA MOHAN NIWAS, NAISARAI, BIHAR SHARIF, NALANDA , 803101, 9431174533 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 3 | Girls Hostel | PRASAD CONSTRUCTION AND CO, LILA MOHAN NIWAS, NAISARAI, BIHAR SHARIF, NALANDA , 803101, 9431174533 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
[5 empty] | 4 | Principal Quarter | PRASAD CONSTRUCTION AND CO, LILA MOHAN NIWAS, NAISARAI, BIHAR SHARIF, NALANDA , 803101, 9431174533 |  |  |  | 1 | [11 empty] | Land Dispute | DIET | Koshi
| Total No. of Institution |  |  |  | 31 |  |  |  | 0 | 0 | 20 | 1 | 6 | 2 | 1 | 5 | 1 | 5 | 0 | 4 | 29 | 36
| Total No. of Institution |  | Name of Institution |  | Total No. of Buildings | Name of Institutional Buildings | Total No. of Buildings |  | Retender | Tender Process | Physical Status
[11 empty] | Not Start | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL | LL | RL
| 31 |  | District Institute of Education and Training (DIET) |  | 31 | Institutional Building |  |  | 0 | 0 | 6 | 0 | 2 | 1 | 0 | 1 | 0 | 3 | 0 | 0 | 8 | 11
[5 empty] | 31 | Boys Hostel |  |  | 0 | 0 | 5 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 2 | 8 | 10
[5 empty] | 31 | Girls Hostel |  |  | 0 | 0 | 5 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 2 | 8 | 11
[5 empty] | 16 | Principal Quarter |  |  | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 4
| Total No. of Institutional Buildings |  |  |  | 109 |  |  |  | 0 | 0 | 20 | 1 | 6 | 2 | 1 | 5 | 1 | 5 | 0 | 4 | 29 | 36