## Summary
BSEIDC, PATNA
Progress report for the construction of Model School building (2010-11) | [22 empty] | Date:-31.05.2014
S.N. | Division | Name & Designation | Total |  |  | Contract Awarded |  |  | Fin. Exp. (in lac) | Physical Status | [9 empty] | Summary |  |  | Fin. Exp. (in Lac) | Remarks
|  |  | No. of Groups | No. of School | Total Estimated Amount | No. of Groups | No. of School | Total Estimated Amount |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Not Start | In-Progress | Complete
[13 empty] | LL | RL | LL | RL | LL | RL | [6 empty] | Chek
1 | PATNA | Satish Prasad (8987263065) E.E. BSEIDC, Div.-Patna | 25 | 59 | 14866.91 | 19 | 44 | 10333.57 |  | 0 | 4 | 3 | 1 | 8 | 1 | 13 | 0 | 0 | 4 | 10 | 34 | 0 | 2769.74
0
2 | MAGADH | Rajeev Ranjan (9234271071), E.E. BSEIDC, Div.-Magadh | 19 | 41 | 10058.31 | 6 | 13 | 2455.61 |  | 0 | 5 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 12 | 0 | 624.1 |  | 0
0
3 | BHAGALPUR | Ranvijay Kr. Sinha (9934961293) E.E. BSEIDC, Div.- Bhagalpur | 5 | 12 | 3096.82 | 3 | 7 | 1803.68 |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 1 | 6 | 0 | 555.61 |  | 0
0
4 | MUNGER | Surendra Kumar (9939599803) E.E. BSEIDC, Div.-Munger | 8 | 17 | 4315.9967 | 5 | 10 | 2518.3367 |  | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 0 | 1 | 0 | 1 | 9 | 0 | 824.16 |  | 0
0
5 | KOSI | Anil Kumar (9334128101) E.E. BSEIDC, Div.- Koshi | 3 | 7 | 1907.2 | 3 | 7 | 1907.2 |  | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 6 | 0 | 157.87 |  | 0
0
6 | PURNEA | Manoj Kumar Pandey (9661818750) E.E. BSEIDC, Div.- Purnia | 7 | 15 | 4054.44 | 4 | 9 | 1361.29 |  | 0 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 0 |  | 0
0
7 | TIRHUT | Anil Kr. Singh (9801494702) E.E. BSEIDC, Div.-Tirhut | 22 | 58 | 15888.15 | 14 | 38 | 9506.16 |  | 0 | 9 | 5 | 0 | 14 | 0 | 1 | 0 | 3 | 1 | 5 | 33 | 0 | 2101.66 |  | 0
0
8 | DARBHANGA | Sanjeev Kumar (9199601788) E.E. BSEIDC, Div.-Darbhanga | 15 | 37 | 10256.45 | 9 | 23 | 6333.79 |  | 0 | 7 | 2 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 4 | 19 | 0 | 1233.88 |  | 0
0
9 | SARAN | Pramod Kumar (9955128483) E.E. BSEIDC, Div.- Saran | 5 | 9 | 2368.97 | 4 | 6 | 1587.01 |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 5 | 0 | 642.42 |  | 0
0
Total (Model School) |  |  | 109 | 255 | 66813.2467 | 67 | 157 | 37806.6467 | 0 | 1 | 29 | 13 | 9 | 35 | 6 | 25 | 0 | 6 | 7 | 26 | 131 | 0 | 8909.44 |  | 0
.

## Patna
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- Patna | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Satish Prasad (8987263065) , AE :- S. Tiwari (9431495949), AE :- Atul Kr. Varanwal (9835658494)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-101 | Patna | Maner | 1 | M.Y. H/S, Gorakhatola | Shiv Vijay Engicon | 796.66 | 1 | 1.10.2013 | 15 Month | [11 empty] | 46.38 | Land not Available Site changed proposal goes to BMSP
|  | Patna | Bihta | 2 | R.T.P. H/S, Bihta |  |  | 1 | [14 empty] | Land not Available Site changed proposal goes to BMSP
|  | Patna | Bikram | 3 | D.D.S. H/S, Morlawa | [7 empty] | 1 | [9 empty] | High water level
2 | MS-102 | Patna | Danapur | 1 | R.G.S.S. School, khagaul | Shailendra Kumar | 802.81 |  | 7.10.2013 | 15 Month | \ | 1 | [9 empty] | 78.26 | 1st A/C Bill paid
|  | Patna | Dulhin Bazar | 2 | Basidhar H/S, Bharatpur | [11 empty] | 1
|  | Patna | Naubatpur | 3 | Govt. H/S, Amarpur |  |  | 1 | [14 empty] | Land problem, Local dispute regarding play ground
3 | MS-103 | Patna | Dhanarua | 1 | H/S, Biroiyara | Shristi Developers Pvt. Ltd. | 537.5 | [7 empty] | 1 | [6 empty] | 78.05 | E/W
|  | Patna | Khusrupur | 2 | Mahadeo H/S, Khusrupur |  |  | 1 | [14 empty] | Dismentally
4 | MS-104 | Patna | Daniyawa | 1 | Rajkiyakrit H/S, Daniyawa | Shristi Developers Pvt. Ltd. | 535.17 | 1 | [13 empty] | 43.68 | Land not available
|  | Patna | Fatuwa | 2 | A.N.S, H/S, Usfa | [9 empty] | 1 | [7 empty] | 1st A/C Bill paid
5 | MS-105 | Patna | Belchi | 1 | Govt. H/S, Saksohars | Trishul Engicon Pvt. Ltd. | 786.93 |  | 11.9.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 226.84
|  | Patna | Mokama | 2 | R.A. H/S, Mokama | [9 empty] | 1
|  | Patna | Pandark | 3 | P.B.M. H/S, Pandark | [11 empty] | 1
6 | MS-106 | Patna | Ghoswari | 1 | Govt. H/S, Kurmichak | Trishul Engicon Pvt. Ltd. | 791.15 |  | 11.9.2013 | 15 Month |  |  |  | 1 | [7 empty] | 169.63
|  | Patna | Bhakhtiyarpur | 2 | Govt. H/S, Sawani | [11 empty] | 1 | [5 empty] | 2nd A/C Bill paid
|  | Patna | Barh | 3 | Govt. H/S, Badhna | [6 empty] | 1
7 | MS-107 | Buxar | Buxar | 1 | Govt. Basic School, Karhansi | Tara Rajat Enclave Pvt. Ltd. | 782.48 |  |  |  |  | 1 | [9 empty] | 43.04 | Name to be changed (govt.basic school sarenza)
|  | Buxar | Chausa | 2 | Govt. Basic School, Saraiya |  |  | 1 | [14 empty] | PCC
|  | Buxar | Dumraon | 3 | (+2) Raj H/S, Dumraon | [9 empty] | 1
8 | MS-108 | Buxar | Brahampur | 1 | (+2) B.N. H/S, Brahampur | Retender | 780
|  | Buxar | Simri | 2 | (+2) H/S, Simri
|  | Buxar | Kesath | 3 | (+2) H/S, Kesath
9 | MS-135 | Bhojpur | Barahara | 1 | Govt. Basic School, Barhara | Retender | 513.97
|  | Bhojpur | Bihia | 2 | (+2) H/S, Bihia
10 | MS-136 | Bhojpur | Koilawar | 1 | M.B. H/S, Kulhariya | Narendra Kumar | 766.06 | [5 empty] | 1 | [8 empty] | 51.81
|  | Bhojpur | Udwant Nagar | 2 | H/S, Udwant Nagar |  |  | 1
|  | Bhojpur | Charpokhari | 3 | Macha H/S, Barami | [6 empty] | 1
11 | MS-137 | Bhojpur | Sahar | 1 | H/S, Sahar, Bhojpur | Surendra Kumar Rai | 512.55 |  | 25.7.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 213.82 | 4th A/C Bill Paid
|  | Bhojpur | Sandesh | 2 | H/S, Sandesh | [11 empty] | 1 | [5 empty] | Shuttering
12 | MS-138 | Bhojpur | Garahani | 1 | R.D. H/S, Garhani | Sudarshan Mahto | 512 |  | 19.8.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 153.52
|  | Bhojpur | Agiaon | 2 | Govt. Basic School, Agiaon/ Pawna | [9 empty] | 1
13 | MS-139 | Nalanda | Silaw | 1 | Gandhi h.s.Silaw | Ksishna Deo Pd | 498.1 | 1 | [14 empty] | EMD return by BSEIDC & Retender as same
|  | Nalanda | Rajgir | 2 | R.D.H.S. Rajgir |  |  | 1
14 | MS-140 | Nalanda | Katrisarai | 1 | H.S. Badi | Roy Engineers | 503.36 |  | 27.8.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 269.36
|  | Nalanda | Giriak | 2 | H/S, Giriak Adampur | [14 empty] | 1 |  |  | 4th A/C Bill paid
15 | MS-141 | Nalanda | Nagarnausa | 1 | H.S. Nagarnousa | Shristi Developers Pvt. Ltd. | 504.28 | 1 | 24.7.2013 | 15 Month | [11 empty] | 133.65 | Land problem water logged 8'-0" deep land
|  | Nalanda | Chandi | 2 | Govt. Basic School, Kaurnawa | [11 empty] | 1 | [5 empty] | 3rd A/C Bill paid
16 | MS-142 | Nalanda | Tharthari | 1 | H/S, Bhathar | Ksishna Deo Pd | 500.94 |  | 19.8.2013 | 15 Month | [9 empty] | 1 |  | 286.96
|  | Nalanda | Noorsarai | 2 | H/S, Noorsarai | [11 empty] | 1 | [5 empty] | 2nd A/C Bill paid
17 | MS-143 | Nalanda | Islampur | 1 | Govt. Basic School, Sanda | M/S Magadh Construction | 748.65 |  | 8.10.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 265.11
|  | Nalanda | Ben | 2 | H/S, Eksara | [7 empty] | 1 | [9 empty] | 2nd A/C Bill paid
|  | Nalanda | Ekangarsarai | 3 | S.S. Academy, Ekangarsarai | [11 empty] | 1
18 | MS-144 | Nalanda | Harnaut | 1 | Govt. Basic School, Gokulpur Math | Buddha Infrastructure Pvt. Ltd. | 758 | [7 empty] | 1 | [6 empty] | 260.91
|  | Nalanda | Sarmera | 2 | H/S, Sarmera | [11 empty] | 1 | [5 empty] | 2nd A/C Bill paid
|  | Nalanda | Bind | 3 | H/S, Bind | [11 empty] | 1
19 | MS-145 | Rohtas | Akodhigola | 1 | H.S. Prem Nagar, Akodhigola | Shailendra Kumar | 498.96 | [7 empty] | 1 | [6 empty] | 140.82
|  | Rohtas | Dihri | 2 | H.S. Dihri-on-sone, Dehri | [10 empty] | 1 | [6 empty] | 2nd A/C Bill paid
20 | MS-146 | Rohtas | Bikramganj | 1 | Govt. Basic School, Kabhai | Retender | 456.8
|  | Rohtas | Suryapura | 2 | R.R. H.S. Suryappura
|  | Rohtas | Dawath | 3 | R.P.S. H.S.Kabai, Dawath
21 | MS-147 | Rohtas | Kochas | 1 | H.S. Kochas | Retender | 507.81
|  | Rohtas | Dinara | 2 | M.H.S. Basdihan, Dinara
22 | MS-148 | Rohtas | Nokha | 1 | H.S. Garh Nokha, Nokha | Retender | 747.74
|  | Rohtas | Karakat | 2 | S.S.D.H.S. Amauna, Karakat
|  | Rohtas | Nasriganj | 3 | Basant H.S. Itimiha Karma
23 | MS-149 | Rohtas | Chenari | 1 | R.D.G.H.S. Chenari | Retender | 507.31
|  | Rohtas | Sheo Sagar | 2 | S.D.H.S. Sheo Sagar
24 | MS-150 | Rohtas | Nauhatta | 1 | H.S.Boulian | S.A.B. Construction | 261.71 | [12 empty] | 1 |  | 153.26
25 | MS-151 | Rohtas | Tilauthu | 1 | H.S.Tilauthu | Sideshwar Singh | 255.97 |  | 23.9.2013 | 15 Month | [9 empty] | 1 |  | 154.64
|  | Total nos. of school |  | 59 |  |  | 14866.91 | 10 |  |  | 0 | 4 | 3 | 1 | 8 | 1 | 13 | 0 | 0 | 4 | 0 | 2769.74

## Magadh
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- Magadh | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Ranvijay Kr. Sinha (9934961293), AE :- Vindo Kr. Pandey (9472722090), & Sanjeev Kumar (9431487994)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-152 | Arwal | Kurtha | 1 | H/S, Kurtha | Retender | 489.99
|  | Arwal | Bansi Suryapur | 2 | H/S, Khatangi
2 | MS-153 | Gaya | Manpur | 1 | H.S.Rasalpur | Arvind Kumar | 723.47 |  |  |  |  | 1 | [9 empty] | 34.6
|  | Gaya | Bodhgaya | 2 | H.S. Bodhgaya | [6 empty] | 1
|  | Gaya | Belaganj | 3 | A.H.S. Belaganj | [6 empty] | 1
3 | MS-154 | Gaya | Tikari | 1 | Govt. Basic School, Bhawanpur | Retender | 727.37
|  | Gaya | Konch | 2 | G.H.S. Konch
|  | Gaya | Paraiya | 3 | A.H.S. Paraiya
4 | MS-155 | Gaya | Tankupa | 1 | Govt. Basic School, Makhdumpur | Retender | 482.48
|  | Gaya | Guraru | 2 | B.S.H.S. Esmailpur
5 | MS-156 | Gaya | Dobhi | 1 | Govt. Basic School, Bajaura | Retender | 725.97
|  | Gaya | Mohanpur | 2 | H.S.Mohanpur
|  | Gaya | Barachati | 3 | Govt. Basic School, Pataluka
6 | MS-157 | Gaya | Imamganj | 1 | Govt. Basic School, Wara | Retender | 493.66
|  | Gaya | Dumariya | 2 | J.H.S. Dumariya
7 | MS-158 | Gaya | Amas | 1 | H.S. Amas | Retender | 729.47
|  | Gaya | Goruva | 2 | H.S. Bharsanthu
|  | Gaya | Mohra | 3 | Govt. Basic School, Jatian
8 | MS-159 | Gaya | Atri | 1 | H.S.Tetua | Retender | 738.48
|  | Gaya | Nimchak Bathani | 2 | Govt. Basic School, Rahui
|  | Gaya | Khijarsarai | 3 | H.S. Khijarsarai
9 | MS-160 | Gaya | Chandouti | 1 | H.S. Chandaouti | Retender | 245.61
10 | MS-161 | Jehanabad | Ghoshi | 1 | H.S. Ghoshi | Sanjay Kumar Singh | 489.32 |  | 21.9.2013 | 15 Month | [5 empty] | 1 | [5 empty] | 184.23
|  | Jehanabad | Jehanabad | 2 | H.S.Pandooe | [10 empty] | 1
11 | MS-162 | Jehanabad | Modanganj | 1 | H.S. Okari, Modanganj | Umashankar Singh | 489.32 | [9 empty] | 1 |  |  |  |  | 202.58
|  | Jehanabad | RatniFaridPur | 2 | H.S. Sarta | [11 empty] | 1
12 | MS-177 | Nawada | Kawakol | 1 | Govt. Basic School, Baraun Bajitpur | Sujay Bhan Singh | 737.13 |  |  |  |  | 1 | [9 empty] | 85.21
|  | Nawada | Roh | 2 | Inter School, Roh | [8 empty] | 1
|  | Nawada | Nardiganj | 3 | Govt. Basic School, Nadariganj |  |  | 1 | [14 empty] | Land not available
13 | MS-178 | Nawada | Warisaliganj | 1 | Govt. Basic School, Dariyapur | Retender | 492.49
|  | Nawada | Kashichak | 2 | Inter School, Chandinawa
14 | MS-179 | Nawada | Govindpur | 1 | Inter School, Govindpur | Retender | 493.07
|  | Nawada | Pakribarawan | 2 | Inter School, Pakribarawan
15 | MS-180 | Nawada | Narhat | 1 | Inter School, Narhat | Retender | 488.65
|  | Nawada | Akbarpur | 2 | Govt. Basic School, Gopalpur
16 | MS-181 | Nawada | Meskaur | 1 | Inter School, Meskaur | Pramod Construction | 242.57 |  |  |  |  | 1
17 | MS-182 | Aurangabad | Aurangabad | 1 | Govt. M/S, Babhandi | M/S Raj Construction | 505.69 | [7 empty] | 1 | [6 empty] | 117.48
|  | Aurangabad | Barun | 2 | R.D.B. H/S, Sunderganj | [9 empty] | 1
18 | MS-183 | Aurangabad | Deo | 1 | Govt. Basic School, Vishnupur | Retender | 509.48
|  | Aurangabad | Rafiganj | 2 | R.B.R. H/S, Rafiganj
19 | MS-184 | Aurangabad | Haspura | 1 | Govt. Basic School, Dindir | Retender | 254.09
|  | Total nos. of school |  | 41 |  |  | 10058.31 | 1 |  |  | 0 | 5 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 624.1

## Bhagalpur
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- Bhagalpur | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Anil Kumar Singh (9801494702), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-133 | Banka | Rajaoun | 1 | Govt. Basic School, Chilkawar | Tender Process | 517.13
|  | Banka | Dhoraiya | 2 | Tribhuwan Academy
2 | MS-204 | Bhagalpur | Sabour | 1 | H/S, Parsadih Simri | Lalan Kumar | 767.21 | [5 empty] | 1 | [8 empty] | 65.55
|  | Bhagalpur | Jagdishpur | 2 | Loknath H/S, Jagdishpur |  |  | 1
|  | Bhagalpur | Nath Nagar | 3 | H/S, Shapur | [5 empty] | 1
3 | MS-205 | Bhagalpur | Goradih | 1 | H/S, Jamin Murhan Hat | Retender | 776.01
|  | Bhagalpur | Shahkund | 2 | Govt. Basic School, Hajipur
|  | Bhagalpur | SultanGanj | 3 | H/S, Karharia
4 | MS-206 | Bhagalpur | Bihpur | 1 | M.S. H/S, Bihpur | Dharmendra Kumar Chaudhary | 518.15 |  | 18.9.2013 | 15 Month | [8 empty] | 1 |  |  | 249.27
|  | Bhagalpur | Kharik | 2 | Govt. Basic School, Telghi | [13 empty] | 1
5 | MS-207 | Bhagalpur | Naugachhia | 1 | H/S, Sahu Parbatta | Shristi Developers | 518.32 |  | 21.8.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 240.79
|  | Bhagalpur | Gopalpur | 2 | Govt. Basic School, Tintanga | [11 empty] | 1 | [5 empty] | 1st A/C bill paid
|  | Total nos. of school |  | 12 |  |  | 3096.82 | 1 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 555.61

## Munger
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- Munger | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :-Surendra Kumar (9939599803), AE :- M.K.Pandey (9835806534), & Rajiv Kr. (8986897214)
S.N. | Group No. | Name of District | Name of Block | S. N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-132 | Sheikhpura | Chewara | 1 | H/S, Chewara | Arbind Prasad | 250.15 |  | 2.8.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 118.02 | 1st A/C bill paid
2 | MS-134 | Begusarai | Balia | 1 | Govt. H/S, Sadanandpur | Delco Infrastructure Projects Ltd. | 519.5267 |  | 16.8.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 160.55
|  | Begusarai | Teghra | 2 | Govt. Basic School, Bajatpur | [11 empty] | 1
3 | MS-173 | Jamui | Jamui | 1 | Janta H/S, Sataya | Balkrishna Bhalotia Construction Pvt. Ltd. | 744.99 |  | 7.10.2013 | 15 Month | [5 empty] | 1 | [5 empty] | 299.48
|  | Jamui | Sikandra | 2 | J.S.P.S. H/S. Lachhuar | [13 empty] | 1
|  | Jamui | Islamnagar Aliganj | 3 | M.R.P. H/S, Tajpur | [9 empty] | 1
4 | MS-174 | Jamui | Barhat | 1 | Govt. Basic School, Barhat | Ashok & Co. Nivas Pvt. Ltd. | 501.57 |  | 9.9.2013 | 15 Month | [6 empty] | 1 |  |  |  |  | 185.88
|  | Jamui | Laxmipur | 2 | Govt. Basic School, Kajinhara | [11 empty] | 1
5 | MS-175 | Jamui | Gidhour | 1 | M.C.Vidya Mandir, Gidhour | Lal Rupak Kumar Singh | 502.1 |  | 30.10.2013 | 15 Month |  |  |  | 1 | [7 empty] | 60.23
|  | Jamui | Jhajha | 2 | M.G.S. H/S, Jhajha |  |  | 1 | [14 empty] | Land problem
6 | MS-176 | Khagaria | Beldaur | 1 | Gandhi H/S, Beldaur | Tender Process | 794.96
|  | Khagaria | Mansi | 2 | Gandhi H/S, Mansi
|  | Khagaria | Chautham | 3 | Brahma H/S, Pipra
7 | MS-208 | Lakhisarai | Ramgarh Chowk | 1 | Govt. Basic School, Nandnama | Retender | 501.93
|  | Lakhisarai | Chanan | 2 | R.S. +2 H.S., Mananpur
8 | MS-209 | Lakhisarai | Pipriya | 1 | M.R.M.P. +2 H.S., Ramchandrapur | Retender | 500.77
|  | Lakhisarai | Barahiya | 2 | Govt. Basic School, Bispur
|  | Total nos. of school |  | 17 |  |  | 4315.9967 | 1 |  |  | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 0 | 1 | 0 | 0 | 824.16
In above list one school name hasbeen deleted due to repeat of name in fin year 09-10 & 10-11
1 | MS-134 | Begusarai | Nawkothi | 1 | Govt. S.S.L. H.S, Samsa

## Kosi
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- KOSI | [20 empty] | Date:-31.05.2014
Name & contact no. of EE :- Anil Kumar (9334128101) , AE :- Haider Jamal (8294246338), AE :- Neeraj Kumar (7543014790)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) |  |  | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Date of Aggrement | Time of Completion | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-163 | Supaul | Kishanpur | 1 | H/S, Kishanpur | K.D. Company | 825.41 | 1.11.2013 | 15 Month |  |  |  |  | 1 | [7 empty] | 65.39
|  | Supaul | Supaul | 2 | H/S, Sukhpur | [11 empty] | 1
|  | Supaul | Pipra | 3 | Govt. Basic School, Basaha | [6 empty] | 1
2 | MS-164 | Supaul | Raghopur | 1 | L.S. H/S, Simrahi Bazar, Raghopur | Delco Infrastructure Projects Ltd. | 804.31 | 19.8.2013 | 15 Month | [5 empty] | 1 | [6 empty] | 23.51
|  | Supaul | Pratapganj | 2 | Public H/S, Pratapganj | [8 empty] | 1 | [8 empty] | Water logged
|  | Supaul | Chatapur | 3 | S.S. H/S, Sukhpur |  |  |  |  | 1
3 | MS-165 | Supaul | Saraigarh | 1 | B.G H/S, Bhaptiyahi | Ashok Kumar | 277.48 | [7 empty] | 1 | [6 empty] | 68.97
|  | Total nos. of school |  | 7 |  |  | 1907.2 |  |  | 1 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 157.87

## Purnea
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- PURNEA | [20 empty] | Date:-31.05.2014
Name & contact no. of EE :-Manoj Kumar Pandey (9661818750) , AE :- Madan Mohan (9431413291), JE :- Uttam Kr. (9973563185)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) |  |  | Physical Status | [11 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Date of Aggrement | Time of Completion | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-166 | Purnea | Purnia East | 1 | Govt. Basic School, Chadirjiganj | Retender | 806.12
|  | Purnea | K.Nagar | 2 | Govt. Basic School, Kalyanpur
|  | Purnea | Kasba | 3 | Govt. Basic School, Sabdalpur
2 | MS-167 | Purnea | Jalalgarh | 1 | N.D. Rungta H/S, Jalalgarh | Rajendra Prasad Podar | 816.34 | [7 empty] | 1
|  | Purnea | Sri Nagar | 2 | Govt. Basic School, Srinagar | [7 empty] | 1
|  | Purnea | Dagurwa | 3 | H/S, Soura | [9 empty] | 1
3 | MS-168 | Purnea | Baisi | 1 | H/S, Baisi | Md. Shafique Alam | 544.95 |  |  |  |  | 1
|  | Purnea | Baisa | 2 | T.N.H/S, Piyaji | [8 empty] | 1
4 | MS-169 | Purnea | Bhawanipur | 1 | Govt. Basic School, Barhari | Retender | 536.04
|  | Purnea | Rupali | 2 | Govt. Basic School, Sapaha
5 | MS-170 | Katihar | Sameli | 1 | D.G. H/S, Krishna Ngr | Ashok Kumar | 543.61 |  |  |  |  | 1
|  | Katihar | Azam Nagar | 2 | R.K. H/S, Azam Ngr |  |  |  |  | 1
6 | MS-171 | Katihar | Falka | 1 | Govt. Basic School, Mangha | Ashok Kumar | 534.7 |  |  |  |  | 1
|  | Katihar | Kursela | 2 | A.P. H/S Ayodhyaganj |  |  |  |  | 1
7 | MS-172 | Katihar | Dand Khora | 1 | SadaNand H/S, Dumaria | Tender Process | 272.68
|  | Total nos. of school |  | 15 |  |  | 4054.44 |  |  | 2 | 0 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tirhut
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- TIRHUT | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Anil Kr. Singh (9801494702) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-109 | Vaishali | Raghopur | 1 | T.R.S.S. H/S Jurawanpur | Man Mardan Shukla | 798.46 | 1
|  | Vaishali | Mahnar | 2 | Govt. Basic School, Karnauti | [6 empty] | 1
|  | Vaishali | Bidupur | 3 | Govt. Basic School, Chechar |  |  | 1 | [14 empty] | Land not available
2 | MS-110 | Vaishali | Vaishali | 1 | H.S H/S, Chintamanipur | Amit Kumar Shahi | 795.18 |  | 10.10.2013 | 15 Month | [9 empty] | 1 |  | 481.48
|  | Vaishali | Pathedhibelsar | 2 | Govt. Basic School, Surhattha | [13 empty] | 1
|  | Vaishali | Lalganj | 3 | Govt. Basic School, Michagadh | [13 empty] | 1
3 | MS-111 | Vaishali | Bhagwanpur | 1 | Govt. Basic School, Warispur | Satyendra Kumar Construction Pvt. Ltd. | 799.66 | [7 empty] | 1 | [6 empty] | 296.99
|  | Vaishali | Goraul | 2 | Govt. Basic School, Kanhauli | [9 empty] | 1
|  | Vaishali | Chehrakala | 3 | B.N. H/S, Sehan | [9 empty] | 1
4 | MS-112 | Vaishali | Rajapakar | 1 | Govt. Basic School, Narayanpur | Shristi Developers | 792.34 | [7 empty] | 1 | [6 empty] | 170.22
|  | Vaishali | Desari | 2 | S.G.B.B.A.S. H/S, Bhatauliya |  |  | 1 | [14 empty] | Required old building demolision
|  | Vaishali | Sahdai Buzurg | 3 | Gandhi H/S, Sahadai Buzurg | [9 empty] | 1
5 | MS-120 | Sitamarhi | Riga | 1 | T.R.N.H.S, Sahbajpur Kharsan | Tender Process | 827.78
|  | Sitamarhi | Parsauni | 2 | Govt. Basic School, Raghopur Bhakhari
|  | Sitamarhi | Belsand | 3 | Govt. Basic School, Machi Bhandari
6 | MS-121 | Sitamarhi | Nanpur | 1 | Govt. Basic School, Janipur | Retender | 830.56
|  | Sitamarhi | Chorout | 2 | S.L.N.S H/S, Chorout
|  | Sitamarhi | Sursand | 3 | Saryu H/S, Sursand
7 | MS-122 | Sitamarhi | Bajpatti | 1 | S.R.P.N. H/S, Bajpatti | Anuj Enterprises | 833.81 |  |  |  |  | 1
|  | Sitamarhi | Majorganj | 2 | J.B. H/S, Majorganj | [6 empty] | 1
|  | Sitamarhi | Parihar | 3 | S.G. H/S, Parihar |  |  | 1
8 | MS-123 | East Champaran | Pipra Kothi | 1 | Govt. Basic School, Piprakothi | Virendra Kumar Chaudhary | 536.19 | [7 empty] | 1 | [6 empty] | 146.21
|  | East Champaran | Kotwa | 2 | H/S, Machh-agargawa | [9 empty] | 1
9 | MS-124 | East Champaran | Mehsi | 1 | High School, Mehsi | M/S Durga Construction | 542.58 | [5 empty] | 1
|  | East Champaran | Kesaria | 2 | High School, Kesariya | [7 empty] | 1
10 | MS-125 | East Champaran | Turkaulia | 1 | S.R.R. H/S, Turkaulia | Mishra Const. Ranjan Mishra | 812.75 |  |  |  |  | 1
|  | East Champaran | Sugauli | 2 | Nand High School, Sugauli | [6 empty] | 1
|  | East Champaran | Banjaria | 3 | H/S, Mokhlishpur | [7 empty] | 1
11 | MS-126 | East Champaran | Raxaul | 1 | H/S, Purandara Bhelahi | Retender | 852.91
|  | East Champaran | Ramgarhwa | 2 | Govt. Basic School, Siswaniya
|  | East Champaran | Chaurandano | 3 | H/S, Chhoradano
12 | MS-127 | East Champaran | Adapur | 1 | Govt. Basic School, Bhawanati | Retender | 831.38
|  | East Champaran | Ghorasahan | 2 | Govt. Basic School, Bhelwa Circle
|  | East Champaran | Dhaka | 3 | H/S, Dhaka
13 | MS-128 | East Champaran | Phenhara | 1 | H/S, Phenhara | M/S Anoj Enterprises | 816.75 |  | 24.9.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 220.26
|  | East Champaran | Chiraiya | 2 | M.S. H/S, Chiraiya | [9 empty] | 1
|  | East Champaran | Patahi | 3 | H/S, Patahi | [9 empty] | 1
14 | MS-129 | East Champaran | Madhuban | 1 | H/S, Madhuban | Shiv Shankar Singh Contract Pvt. Ltd. | 815.2 |  | 26.8.2013 | 15 Month | [8 empty] | 1 |  |  | 306.09
|  | East Champaran | Tetaria | 2 | H/S, Tetaria | [7 empty] | 1
|  | East Champaran | Pakkari Dayal | 3 | H/S, Barkawan | [11 empty] | 1
15 | MS-130 | East Champaran | Areraj | 1 | H/S, Areraj | Hitendra Kr. Mishra | 540.44 |  | 1.11.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 158.74
|  | East Champaran | Sangrampur | 2 | H/S, Sangrampur | [9 empty] | 1
16 | MS-131 | East Champaran | Harsidhhi | 1 | Govt. Basic School, Kritpur Mathiya | M/S Thakur Construction | 541.02 | [7 empty] | 1 | [6 empty] | 127.56
|  | East Champaran | Paharpur | 2 | Govt. Basic School, Baluahar Siddhi | [7 empty] | 1
17 | MS-185 | West Champaran | Bairiya | 1 | H/S, Bathna | Retender | 848.15
|  | West Champaran | Thakaraha | 2 | G.M. H/S, Thakaraha
|  | West Champaran | Bhitaha | 3 | H/S. Ajaynagar Rerha
18 | MS-186 | West Champaran | Nautan | 1 | Janta H/S, Telua | Retender | 546.98
|  | West Champaran | Bettiah | 2 | B.H.S.S, Bettiah
19 | MS-187 | West Champaran | Yogapatty | 1 | Govt. Basic School, Balua | Retender | 831.48
|  | West Champaran | Chanpatia | 2 | Govt. Basic School, Chaubetola
|  | West Champaran | Sikta | 3 | Janta H/S, Sikta
20 | MS-188 | West Champaran | Ramnagar | 1 | H/S, Harinagar | M/S Nikumbh Bhardwaj | 559.74 | 1 | 18.9.2013 | 15 Month | [11 empty] | 83.78 | Land problem
|  | West Champaran | Lauria | 2 | A.H. H/S, Bagahi | [9 empty] | 1
21 | MS-189 | West Champaran | Piprasi | 1 | Govt. Basic School, Manjhariya | M/S Sarswati Company | 569.46 |  |  |  |  | 1 | [9 empty] | 110.33
|  | West Champaran | Madhubani | 2 | M/S, Tamkuhwa | [6 empty] | 1
22 | MS-190 | West Champaran | Gaunaha | 1 | Govt. Basic School, Bhithakha | Sisley Construction | 565.33 |  |  |  |  | 1
|  | West Champaran | Mainatand | 2 | R.S. H/S, Rampurwa | [6 empty] | 1
|  | Total nos. of school |  | 58 |  |  | 15888.15 | 5 |  |  | 0 | 9 | 5 | 0 | 14 | 0 | 1 | 0 | 3 | 1 | 0 | 2101.66

## Darbhanga
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- DARBHANGA | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Sanjeev Kumar (9199601788) , AE :- Ram Babu Mahto (9835619212) & Rajesh Kumar (9431620115)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-113 | Madhubani | Basopatti | 1 | Govt. Basic School, Sukhasi | Retender | 555.55
|  | Madhubani | Bisfi | 2 | Govt. Basic School, Simari
2 | MS-114 | Madhubani | Harlakhi | 1 | Govt. Basic School, Hisar | Retender | 555.68
|  | Madhubani | Madhawapur | 2 | Govt. Basic School, Rema
3 | MS-115 | Madhubani | Jhanjharpur | 1 | Kejriwal H/S, Jhanjharpur | Dharam Nath Construction Pvt. Ltd. | 838.72 | 1 | [13 empty] | 87.96
|  | Madhubani | Lakhnour | 2 | High School, Lakhnaur | [9 empty] | 1
|  | Madhubani | Madhepur | 3 | High School, Madhepur |  |  | 1
4 | MS-116 | Madhubani | Babubarhi | 1 | J.N. H/S, Babubarhi | Retender | 832.64
|  | Madhubani | Pandaul | 2 | Govt. Basic School, Maukarampur
|  | Madhubani | Rajnagar | 3 | Govt. Basic School, Nakati
5 | MS-117 | Madhubani | Ghowardiha | 1 | High School, Devadh | Shristi Developers | 851.54 | 1
|  | Madhubani | Laukhi | 2 | High School, Laukhi | [6 empty] | 1
|  | Madhubani | Phulparas | 3 | High School, Phulparas | [6 empty] | 1
6 | MS-118 | Madhubani | Jainagar | 1 | High School, Jainagar | Shristi Developers | 838.38 | 1 | [13 empty] | 57.1
|  | Madhubani | Kaluahi | 2 | High School, Narar | [6 empty] | 1
|  | Madhubani | Khajauli | 3 | High School, Khajauli | [6 empty] | 1
7 | MS-119 | Madhubani | Khutauna | 1 | High School, Khutauna | Retender | 579.64
|  | Madhubani | Ladania | 2 | High School, Matha Ladania
8 | MS-196 | Samastipur | Ujairpur | 1 | Govt. Basic School, Kariyara | Sudhakant Enterprises Pvt. Ltd. | 795.34 | [7 empty] | 1 | [6 empty] | 207.2
|  | Samastipur | Morwa | 2 | Govt. Basic School, Mariya | [10 empty] | 1
|  | Samastipur | Rosera | 3 | Govt. Basic School, Dharmpur | [6 empty] | 1 | [10 empty] | Land not available
9 | MS-197 | Samastipur | Dalsingh Sarai | 1 | Govt. Basic School, Salkhani | Vinod Kumar Singh | 528.37 | [8 empty] | 1 | [5 empty] | 164.72
|  | Samastipur | Bibhutipur | 2 | L.L. H/S, Sirsi | [9 empty] | 1
10 | MS-198 | Darbhanga | Benipur | 1 | Jayanand H/S. Bahera | Retender | 557.48
|  | Darbhanga | Kiratpur | 2 | H/S, Rasiyari
11 | MS-199 | Darbhanga | Ghanshyampur | 1 | Janta H/S, Shivnagar Gah | Mother India | 560.56 |  | 9.9.2013 | 15 Month |  |  |  |  | 1 | [6 empty] | 176.49
|  | Darbhanga | Gora Bauram | 2 | H/S, Azi | [8 empty] | 1
12 | MS-200 | Darbhanga | Keoti | 1 | R.J. H/S, Keoti Baubari | Mother India | 551.72 |  | 9.9.2013 | 15 Month |  | 1 | [9 empty] | 86.97
|  | Darbhanga | Jalley | 2 | Govt. Basic School, Daughara | [7 empty] | 1
13 | MS-201 | Darbhanga | Tardih | 1 | Govt. Basic School, Narayanpur | Mother India Contract | 553.22 | [6 empty] | 1 | [7 empty] | 107.74
|  | Darbhanga | Manigachhi | 2 | High School, Nehra | [6 empty] | 1
14 | MS-202 | Darbhanga | Hayaghat | 1 | Govt. Basic School, Sreerampur | Avaneesh Enterprises | 815.94 |  | 26.8.2013 | 15 Month |  |  | 1 | [8 empty] | 345.7
|  | Darbhanga | Singhwara | 2 | Govt. Basic School, Haripur Ladaur | [11 empty] | 1
|  | Darbhanga | Hanuman Nagar | 3 | Govt. Basic School, Goraipatti | [11 empty] | 1
15 | MS-203 | Darbhanga | Kusheshwar Asthan East | 1 | S.K. H/S, Kusheshwar Asthan | Retender | 841.67
|  | Darbhanga | Kusheshwar Asthan | 2 | G.P. H/S, Bhahar
|  | Darbhanga | Biraul | 3 | Onkar H/S, Supaul Bazar
|  | Total nos. of school |  | 37 |  |  | 10256.45 | 4 |  |  | 0 | 7 | 2 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 1233.88

## Saran
BSEIDC, PATNA
Progress Report for the construction of Model School (2010-11)
Name of Division :- Saran | [21 empty] | Date:-31.05.2014
Name & contact no. of EE :- Pramod Kumar (9955128483) , AE :- Hemant kr. (7488022930), AE :- Chandramadhav Singh (9431474663)
S.N. | Group No. | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Estimated Amount (in lac) | Physical Status | [13 empty] | Fin. Exp. (in lac) | Remarks
[8 empty] | Not Start | Date of Aggrement | Time of Completion | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL | LL | RL
1 | MS-191 | Saran | Amnaur | 1 | Govt. Basic School, Mandroli | Retender | 781.96
|  | Saran | Parsa | 2 | H/S, Parsa
|  | Saran | Marhaura | 3 | Govt. Basic School, Agahara
2 | MS-192 | Saran | Ekma | 1 | Govt. Basic School, Rasulpur | Mohan Prasad | 264.73 | 1
3 | MS-193 | Siwan | Hasanpura | 1 | C.B. H/S, Usari Dhanauti | Shiv Shankar Singh Contract Pvt. Ltd. | 527.57 | [5 empty] | 1 | [8 empty] | 134.48
|  | Siwan | Darauli | 2 | H/S, Don | [8 empty] | 1
4 | MS-194 | Siwan | Zeradei | 1 | Mahendra H/S, Zeradei | Shiv Shankar Singh Contract Pvt. Ltd. | 527.62 |  | 26.8.2013 | 15 Month | [9 empty] | 1 |  | 411.64
|  | Siwan | Zakari Nabiganj | 2 | Govt. Basic School, Jalalpur | [14 empty] | 1
5 | MS-195 | Siwan | Nawatan | 1 | H/S, Nawatan | Rajesh Kumar | 267.09 | [7 empty] | 1 | [6 empty] | 96.3
|  | Total nos. of school |  | 9 |  |  | 2368.97 | 1 |  |  | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 642.42