## CDPO
BSEIDC Ltd., PATNA
Progress Report for the construction of CDPO BUILDING
S.N. | Group No. | Name of District | Name of Block | Name of Work | Retender | Tender Process | Physical Status | [11 empty] | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%) | Financial Achievement (%) | Remarks | Division
[7 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete
[11 empty] | LL | RL | LL | RL | LL | RL
1 | CDPO-1 | Madhepura | Kumarkhand | Child Development Project Office co-housing (CDPO) at Kumarkhand | [11 empty] | 1 |  |  | 123.0744 | 39.32 | 32.21 |  |  | Koshi
2 | CDPO-2 | Madhepura | Bihariganj | Child Development Project Office co-housing (CDPO) at Bihariganj |  |  | 1 | [11 empty] | 122.0866 |  | #REF! |  | Land not Available | Koshi
3 | CDPO-3 | Madhepura | Gwalpara | Child Development Project Office co-housing (CDPO) at Gwalpara |  |  | 1 | [11 empty] | 121.9103 |  | 0 |  | Land not Available | Koshi
4 | CDPO-4 | Supaul | Basantpur | Child Development Project Office co-housing (CDPO) at Batihani( basantpur) | [7 empty] | 1 | [6 empty] | 129.676 |  | 0 |  |  | Koshi
5 | CDPO-5 | Supaul | Pipra | Child Development Project Office co-housing (CDPO) at Pipra | [8 empty] | 1 | [5 empty] | 126.8432 | 28.02 | 22.09 |  | Work in Progress | Koshi
6 | CDPO-6 | Supaul | Kishanpur | Child Development Project Office co-housing (CDPO) at Kishanpure | [11 empty] | 1 |  |  | 125.0252 | 40.35 | 32.27 |  |  | Koshi
7 | CDPO-7 | Supaul | Triveniganj | Child Development Project Office co-housing (CDPO) at Triveniganj | [11 empty] | 1 |  |  | 123.6204 | 39.5 | 31.95 |  |  | Koshi
8 | CDPO-8 | Purnea | Bhawanipur | Child Development Project Office co-housing (CDPO) at Bhawanipur | [11 empty] | 1 |  |  | 125.783 | 38.3 | 30.45 |  |  | Purnea
9 | CDPO-9 | Purnea | Srinagar | Child Development Project Office co-housing (CDPO) at Srinagar | [11 empty] | 1 |  |  | 124.2528 | 23.02 | 18.53 |  |  | Purnea
10 | CDPO-10 | Arariya | Raniganj | Child Development Project Office co-housing (CDPO) at Raniganj | [7 empty] | 1 | [6 empty] | 121.4178 |  | 0 |  |  | Purnea
11 | CDPO-11 | Arariya | Arariya | Child Development Project Office co-housing (CDPO) at Arariya | [11 empty] | 1 |  |  |  |  | #DIV/0! |  | FF sill level | Purnea
12 | CDPO-12 | Arariya | Palashi | Child Development Project Office co-housing (CDPO) at Palashi | [8 empty] | 1 | [5 empty] | 123.7937 |  | 0 |  |  | Purnea
13 | CDPO-13 | Arariya | Narpatganj | Child Development Project Office co-housing (CDPO) at Narpatganj | [5 empty] | 1 | [8 empty] | 130.114 |  | 0 |  |  | Purnea
14 | CDPO-14 | Arariya | Bhargama | Child Development Project Office co-housing (CDPO) at Bhargama | [7 empty] | 1 | [6 empty] | 126.3785 | 26.96 | 21.33 |  |  | Purnea
15 | CDPO-15 | Arariya | Kursakatta | Child Development Project Office co-housing (CDPO) at Kursakatta | [7 empty] | 1 | [6 empty] | 134.21 |  | 0 |  |  | Purnea
16 | CDPO-16 | Sheohar | Taryiani | Child Development Project Office co-housing (CDPO) at Taryiani |  |  | 1 | [11 empty] | 121.6844 |  | 0 |  | Not Start | Tirhut West
17 | CDPO-17 | Kishanganj | Kochadhaman | Child Development Project Office co-housing (CDPO) at Kochadhaman | [8 empty] | 1 | [5 empty] | 128.2715 |  | 0 |  |  | Purnea
18 | CDPO-18 | Kishanganj | Digal-Bank | Child Development Project Office co-housing (CDPO) at Digal-Bank |  |  |  |  | 1 | [9 empty] | 129.35 |  | 0 |  |  | Purnea
19 | CDPO-19 | Kishanganj | Pothiya | Child Development Project Office co-housing (CDPO) at Pothiya | [9 empty] | 1 |  |  |  |  | 129.9387 | 30.16 | 23.21 |  |  | Purnea
20 | CDPO-20 | Kishanganj | Teragachi | Child Development Project Office co-housing (CDPO) at Teragachi | [7 empty] | 1 | [6 empty] | 128.2377 |  | 0 |  |  | Purnea
21 | CDPO-21 | Jamui | Sikandra | Child Development Project Office co-housing (CDPO) at Sikandra |  |  | 1 | [11 empty] | 115.9959 |  | 0 |  | Land not Available | Munger
22 | CDPO-22 | Jamui | Chakai | Child Development Project Office co-housing (CDPO) at Chakai |  |  |  |  | 1 | [9 empty] | 119.335 |  | 0 |  | Land not Available | Munger
23 | CDPO-23 | Jamui | Sono | Child Development Project Office co-housing (CDPO) at Sono |  |  |  |  | 1 | [14 empty] | Munger
24 | CDPO-24 | Madhubani | Pandaul | Child Development Project Office co-housing (CDPO) at Pandaul |  |  |  |  | 1 | [14 empty] | Darbhanga
25 | CDPO-25 | Madhubani | Bisfi | Child Development Project Office co-housing (CDPO) at Bisfi |  |  |  | 1 | [15 empty] | Darbhanga
26 | CDPO-26 | Madhubani | Harlakhi | Child Development Project Office co-housing (CDPO) at Harlakhi |  |  |  | 1 | [15 empty] | Darbhanga
27 | CDPO-27 | Madhubani | Madhavpur | Child Development Project Office co-housing (CDPO) at Madhavpur |  |  |  | 1 | [15 empty] | Darbhanga
28 | CDPO-28 | Madhubani | Khutauna | Child Development Project Office co-housing (CDPO) at Khutauna |  |  |  | 1 | [15 empty] | Darbhanga
29 | CDPO-29 | Banka | Dhoraiya | Child Development Project Office co-housing (CDPO) at Dhoraiya |  |  |  |  | 1 | [14 empty] | Bhagalpur
30 | CDPO-30 | Banka | Barhat | Child Development Project Office co-housing (CDPO) at Barhat |  |  | 1 | [16 empty] | Bhagalpur
31 | CDPO-31 | Banka | Banka | Child Development Project Office co-housing (CDPO) at Banka |  |  | 1 | [16 empty] | Bhagalpur
32 | CDPO-32 | Banka | Belhar | Child Development Project Office co-housing (CDPO) at Belhar |  |  | 1 | [16 empty] | Bhagalpur
33 | CDPO-33 | Banka | Chandan | Child Development Project Office co-housing (CDPO) at Chandan |  |  | 1 | [16 empty] | Bhagalpur
Total Number of CDPO Buildings |  |  |  | 33 | 0 | 0 | 8 | 4 | 5 | 1 | 0 | 5 | 3 | 1 | 0 | 6 | 0 | 0 | 2630.9992 | 265.63 | #REF! | 0