## CT
Bihar State Educational Infrastruture Development Corporation, Patna
Name of Division :-
Name & contact no. of EE :-
Progress Report for the construction of College Toilets As on 30.04.2016
S.N. | Group No. | Name of District | S.N. | Name Of College | Name Of Agency | Land Dipute | Physical Status | [7 empty] | Handed Over | Remarks
[7 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | Finishing | Complete
[11 empty] | LL | RL
1 | CT-1 | Muzafferpur | 1 | L.S COLLEGE MUZAFFARPUR | M/S CHANDAN CONSTRUCTION | [8 empty] | 1
|  |  | 2 | mddm college muzaffarpur | [9 empty] | 1
|  |  | 3 | RDS college muzaffarpur |  | 1 | 1 | [8 empty] | Land not available
|  |  | 4 | Rameshwar college muzaffarpur | [9 empty] | 1
|  |  | 5 | MSKB college muzaffarpur | [9 empty] | 1
|  |  | 6 | MP Sinha Since college muzaffarpur | [9 empty] | 1
|  |  | 7 | Dr. RLMS college muzaffarpur |  | 1 | 1 | [8 empty] | Land not available
|  |  | 8 | LNT college muzaffarpur | [9 empty] | 1
|  |  | 9 | Nitishwar college muzaffarpur |  | 1 | 1 | [8 empty] | Land not available
|  |  | 10 | RBBM college muzaffarpur |  | 1 | 1 | [8 empty] | Land not available
2 | CT-2 | Muzaffarpur | 1 | SRPS College Jaintpur | Braj Bihari Singh | [8 empty] | 1
|  |  | 2 | Jiwachh college Motipur | [9 empty] | 1 | 1
|  |  | 3 | jbsd college Bakuchi | [9 empty] | 1 | 1
|  |  | 4 | cn college Sahebganj | [9 empty] | 1 | 1
3 | CT-3 | Vaishali | 1 | RN college Hajipur | Anup kumar Singh | [8 empty] | 1 | 1
|  |  | 2 | jamuni lal college hajipur | [9 empty] | 1 | 1
|  |  | 3 | DC College, Hajipur | [9 empty] | 1 | 1
|  |  | 4 | LN College, Bhagwanpur | [9 empty] | 1 | 1
|  |  | 5 | BMD College, Dayalpur | [9 empty] | 1 | 1
|  |  | 6 | RPS College, Chakiyaj | [9 empty] | 1 | 1
|  |  | 7 | Vaishali Mahila College | [9 empty] | 1 | 1
|  |  | 8 | YN College,Dighwara | [9 empty] | 1 | 1
|  |  | 9 | Samta College Jandaha, Vaishali | [9 empty] | 1 | 1
4 | CT-4 | chapra | 1 | Ganga Singh College ,Chapra | M/S Shiv Shakti construction | [8 empty] | 1 | 1
|  |  | 2 | J.P Mahila College, Chapra | [9 empty] | 1 | 1
|  |  | 3 | Jagdam College ,Chapra | [9 empty] | 1 | 1
|  |  | 4 | P.C vigyan college, Chapra |  | 1 | 1 | [8 empty] | Land not available (Dropped)
|  |  | 5 | Rajendra College, chapra | [9 empty] | 1 | 1
|  |  | 6 | Ram Jaipal College,chapra | [9 empty] | 1 | 1
|  |  | 7 | H.R. College, Amnaur | [9 empty] | 1 | 1
|  |  | 8 | R.B.G.R.College,Maharajganj |  | 1 | 1 | [8 empty] | Land not available
|  |  | 9 | Jaglal Chaudhary college,chapra | [9 empty] | 1 | 1
5 | CT-5 | siwan | 1 | BPS College, Bhore | [9 empty] | 1 | 1
|  |  | 2 | DAV Collage, siwan | [9 empty] | 1 | 1
|  |  | 3 | Gopalgang college,Gopalganj | [9 empty] | 1 | 1
|  |  | 4 | Gopeshwar College , Hathwa | [9 empty] | 1 | 1
|  |  | 5 | H.R. College, Mairwa | [9 empty] | 1 | 1
|  |  | 6 | Mahendra Mahila College,Gopalganj | [9 empty] | 1 | 1
|  |  | 7 | NlsCollege,Jaitpur,Daudpur | [9 empty] | 1 | 1
|  |  | 8 | P.N. College,Parsa | Ashiana Contract Pvt. Ltd | [8 empty] | 1 | 1
|  |  | 9 | Raja singh college siwan | [9 empty] | 1 | 1
|  |  | 10 | Vidya Bhawan Mahila college, Siwan | [9 empty] | 1
|  |  | 11 | Bharat Mishra Sans, college, chapra |  | 1 | 1 | [8 empty] | Land not available
|  |  | 12 | Baijnath Pandey Arya Sans college Siwan | [9 empty] | 1 | 1
|  |  | 13 | Sri Ram College Vijayapur, Gopalgang | [9 empty] | 1 | 1
|  |  | 14 | Narayan college, Goriyakothi | [9 empty] | 1 | 1
6 | CT-6 | Ara | 1 | H.D.Jain College Ara | [9 empty] | 1 | 1
|  |  | 2 | Maharaja college,Ara | [9 empty] | 1 | 1
|  |  | 3 | J.J College ,Ara | [9 empty] | 1 | 1
|  |  | 4 | M.M.Mahila college, Ara |  | 1 | 1 | [8 empty] | Land not available
|  |  | 5 | S.B.College,Ara | M/S Shiv Shakti construction | [8 empty] | 1 | 1
|  |  | 6 | D.K.College, Dumraon | [9 empty] | 1 | 1
|  |  | 7 | M.V.College, Buxar | [9 empty] | 1 | 1
|  |  | 8 | Sidheswari sans.College,Pachrukhiya,Bhojpur | [9 empty] | 1 | 1
|  |  | 9 | Shiv Prasad Sans.DegreeCollege,Rampur,Buxer | [9 empty] | 1 | 1
|  |  | 10 | Ramadhin Mishra Bhaskroday Sanskrit College, Deorahia, Buxer | [9 empty] | 1 | 1
7 | CT- 7 | Sasaram | 1 | S.P. Jain College,Sasaram | [9 empty] | 1 | 1
|  |  | 2 | A.S.College,Bikramganj | [9 empty] | 1 | 1
|  |  | 3 | J.L.N. College,Dehari-on-sone,Rohtas | [9 empty] | 1 | 1
|  |  | 4 | S.N.College,shahmal khaira_Deo,Rohtas | [9 empty] | 1 | 1
|  |  | 5 | Sri Shankar college, sasaram | Amrendar Kumar Singh | [8 empty] | 1 | 1
|  |  | 6 | Rohtas Mahila college, sasaram | [9 empty] | 1 | 1
|  |  | 7 | Mahila college,Dalmianagar | [9 empty] | 1 | 1
|  |  | 8 | sher shah college, sasaram |  | 1 | 1 | [8 empty] | Land not available
|  |  | 9 | s.v.p. College, Bhabhua | [9 empty] | 1 | 1
|  |  | 10 | G.B. College,RamGarh,Kaimur | [9 empty] | 1 | 1
8 | CT-8 | patna | 1 | Science college,patna | [9 empty] | 1 | 1
|  |  | 2 | Patna college,patna | [9 empty] | 1 | 1
|  |  | 3 | B.N.college, Patna | [9 empty] | 1 | 1
|  |  | 4 | MagadhMahila College,Patna | [9 empty] | 1 | 1
|  |  | 5 | Patna Women'sTraningCollege,Patna | [9 empty] | 1 | 1
|  |  | 6 | Patna Training college,patna | M/s Pramod Construction | [8 empty] | 1 | 1
|  |  | 7 | Patna Law College,Patna | [9 empty] | 1 | 1
|  |  | 8 | College Of Arts&Crafts,patna | [9 empty] | 1 | 1
|  |  | 9 | Vanijya Mahavidyalaya,patna | [9 empty] | 1 | 1
|  |  | 10 | College of Commerce,patna |  | 1 | 1 | [8 empty] | Landless
|  |  | 11 | Govt.Sanskrit College,Kajipur,patna | [9 empty] | 1 | 1
|  |  | 12 | Sir Arvind Mahila College, Patna | [9 empty] | 1 | 1
|  |  | 13 | T.P.S. College,Patna | [9 empty] | 1 | 1
9 | CT- 9 | Patna | 1 | B.S.College,Danapur,patna | [9 empty] | 1 | 1
|  |  | 2 | J.D.Women's college,patna |  | 1 | 1 | [8 empty] | No Need
|  |  | 3 | J.N.L.college,Khagual | Om Prakash | 1 | 1 | [8 empty] | Landless
|  |  | 4 | R.K.D.College,Patna |  |  | 1 | [8 empty] | Intenal Dispute
|  |  | 5 | Ganga Devi Mahila College,Patna |  |  | 1 | [8 empty] | not started by contractor
|  |  | 6 | AG.College,Rambagh,Bihta | [9 empty] | 1 | 1
10 | CT- 10 | East Champran | 1 | M.S college,Motihari | [9 empty] | 1 | 1
|  |  | 2 | L.N.D.College,Mothari | [9 empty] | 1 | 1
|  |  | 3 | S.N.S. College,Mothari | [9 empty] | 1 | 1
|  |  | 4 | SRAP College,Barachaika | [9 empty] | 1 | 1
|  |  | 5 | JlLNM College,Ghorasahan | Braj Bihari Singh | [8 empty] | 1 | 1
|  |  | 6 | MJK College,Bettiah | [9 empty] | 1 | 1
|  |  | 7 | KCTC College | [9 empty] | 1 | 1
|  |  | 8 | RLSY College,Bettiah | [9 empty] | 1 | 1
|  |  | 9 | TP Varma College |  | 1 | 1 | [8 empty] | Land not available
|  |  | 10 | Dr.S.K.Sinha College | [9 empty] | 1 | 1
|  |  | 11 | Mssg College,Areraj | [9 empty] | 1 | 1
11 | CT-11 | Gaya+ Aurangabad | 1 | A.M. College,Gaya | [9 empty] | 1 | 1
|  |  | 2 | G.B.M College,Gaya |  | 1 | 1 | [8 empty] | Project to be drop since college is running in private building according to principle
|  |  | 3 | Jagivan College,Gaya | [10 empty] | 1
|  |  | 4 | S.M.S.G,College,Sherghati (Gaya) |  |  |  | 1
|  |  | 5 | S.N.S College,Tekari,Gaya | [10 empty] | 1
|  |  | 6 | Gaya College,Gaya | Sanjeev Kumar | [9 empty] | 1
|  |  | 7 | R.L.S.Y,College,Aurangabad | [9 empty] | 1 | 1
|  |  | 8 | K.s.m. College,Aurangabad | [9 empty] | 1 | 1
|  |  | 9 | A.N.S.College,Nabinagar,Aurangabad | [5 empty] | 1 | [5 empty] | Works Stop due to local problem
|  |  | 10 | S. N. Sinha College,Aurangabad |  | 1 | 1 | [8 empty] | Not Start due to tree
12 | CT-12 | Patna | 1 | R.P.M.College,Patna city |  | 1 | 1 | [8 empty] | Land not available
|  |  | 2 | A.N.S.College,Barh | [10 empty] | 1
|  |  | 3 | R.R.S.College,Mokama,patna | [10 empty] | 1
|  |  | 4 | R.L.S.Ycollege,Bakhtayarpur | [10 empty] | 1
|  |  | 5 | S.G.G.S.College, Patna,City | Nawal Kishore Shingh | [9 empty] | 1
|  |  | 6 | Mahanth keshav sans. College fatuha , patna | [10 empty] | 1
|  |  | 7 | Nimbark krishna Madhwanand sans. College' Dhanamath, patna | [8 empty] | 1
|  |  | 8 | Raghwendra sans. College , Taretpali, patna | [8 empty] | 1
13 | CT-13 | Biharsarif+ Nalanda+ Nawada | 1 | K.L.S College, Nawada | [9 empty] | 1 | 1
|  |  | 2 | Kisan college sohsarai, Nalanda | [9 empty] | 1 | 1
|  |  | 3 | Nalanda Mahila College , Biharsarif | [9 empty] | 1 | 1
|  |  | 4 | R.M.W. College , Nawada | Raja Ram Prasad Sharma | [8 empty] | 1 | 1
|  |  | 5 | S.N Sinha college, Warisaliganj | [9 empty] | 1 | 1
|  |  | 6 | S.P.M. College, Udantpuri, Biharsharif | [9 empty] | 1 | 1
|  |  | 7 | S.U. College, Hilsa | [9 empty] | 1 | 1
|  |  | 8 | T.S. College Hisua | [9 empty] | 1 | 1
14 | CT-14 | Arwal+ Jehanabad | 1 | S.D.College, kelar (Arwal) | [9 empty] | 1 | 1
|  |  | 2 | S.N Sinha college Jehanabad | [9 empty] | 1 | 1
|  |  | 3 | S.S college Jehanabad | [9 empty] | 1 | 1
|  |  | 4 | S.B.A.N. College, Derheta Lari Arwal | Er. Ashok kumar singh | [8 empty] | 1
|  |  | 5 | S.M.D.College Punpun, Patna | [9 empty] | 1 | 1
|  |  | 6 | M.D. College Naubatpur | [9 empty] | 1 | 1
|  |  | 7 | M.M.College, Bikram | [9 empty] | 1
|  |  | 8 | Daudnagar College , Daudnagar | [9 empty] | 1 | 1
15 | CT-15 | Darbhanga | 1 | C.M.Science college, Darbhanga | M/S SRI JAN ENGICON PVT LTD | [8 empty] | 1
|  |  | 2 | Marwari college Darbhanga | [9 empty] | 1
|  |  | 3 | Millat college Laheriasarai | [9 empty] | 1
|  |  | 4 | M.R.M college Darbhanga | [9 empty] | 1
|  |  | 5 | k.s college Laheriasarai,Darbhanga | [9 empty] | 1
|  |  | 6 | m.k.College laheriasarai | [9 empty] | 1
|  |  | 7 | M.A.R. L.Sans. College, Darbhanga | [9 empty] | 1
16 | CT-16 | Darbhanga | 1 | J.K.College Biroul | M/S SRI JAN ENGICON PVT LTD | [8 empty] | 1
|  |  | 2 | J.N College, Nehra | [9 empty] | 1
|  |  | 3 | M.K.S College, Trimuhan, Chandauna | [9 empty] | 1
|  |  | 4 | jagdamba Sans. College, Batho, Darbhanga | [9 empty] | 1
|  |  | 5 | Umesh Sans. College, Tarauni Darbhanga | [9 empty] | 1
|  |  | 6 | M.L.S..M..College Darbhanga | [9 empty] | 1
|  |  | 7 | Baba saheb Ram Sans. College, Pacharhi, Darbhanga | [9 empty] | 1
|  |  | 8 | Purnima Ram Pratap Sans. College, Pacharhi, Darbhanga | [9 empty] | 1
|  |  | 9 | Ramawatar Gautamm Sans. College, Ahilyasthan, Darbhanga | [9 empty] | 1
|  |  | 10 | Laxmi Narayan Rameshwar Sans College, jaideo patti, Darbhanga | [9 empty] | 1
17 | CT-17 | Madhubani | 1 | H.P.S. College, Madhepur | [9 empty] | 1 | 1
|  |  | 2 | V.SJ.College Raj Nagar | [9 empty] | 1 | 1
|  |  | 3 | B.M College, Rahika | [9 empty] | 1 | 1
|  |  | 4 | C.M.J. College, Donwarihat | [9 empty] | 1 | 1
|  |  | 5 | C. M. B College, Deorh, Ghoghardiha | [9 empty] | 1 | 1
|  |  | 6 | K.V.Science College , Bennipatti | M/S R. Construction& Co. | [8 empty] | 1 | 1
|  |  | 7 | L. N. J. College, Jhanjharpur | [9 empty] | 1 | 1
|  |  | 8 | R. N. College, Panadaul, Madhubani | [9 empty] | 1 | 1
|  |  | 9 | M. L. S. College, Sarisabpahi | [9 empty] | 1 | 1
|  |  | 10 | D. B. College, Jainagar | [9 empty] | 1 | 1
|  |  | 11 | M. M. L.Sans.Vidyapeeth, Lohana, Madhubani |  | 1 | 1 | [8 empty] | No location
|  |  | 12 | Aditya Nath Paras Mani Sans College, Rahua Sangram, Madhubani | [9 empty] | 1 | 1
|  |  | 13 | Rishikul Br.Sans.College, Vedivan, Madhubani |  | 1 | 1 | [8 empty] | college not located
18 | CT-18 | Madhubani | 1 | J. N. College, Madhubani | [9 empty] | 1 | 1
|  |  | 2 | R. K. College, Madhubani | [9 empty] | 1 | 1
|  |  | 3 | J. M. D. P. L. M. College, Madhubani |  | 1 | 1 | [8 empty] | land problem
|  |  | 4 | Nandan Sans. College, Isahpur, Madhubani | Kumari Sindhu | [8 empty] | 1 | 1
|  |  | 5 | Kalyani Mithila College, Dip, Madhubani | [9 empty] | 1 | 1
|  |  | 6 | Madaneshwar Sans.College, Madaneshwar Sthan | [9 empty] | 1 | 1
|  |  | 7 | Nirmali College, Nirmali | [9 empty] | 1 | 1
19 | CT-19 | Samastipur | 1 | Samastipur College, Samastipur | [9 empty] | 1 | 1
|  |  | 2 | A. N. D. College, Shahpur Patori | [9 empty] | 1 | 1
|  |  | 3 | U. R. College, Rosrha | [9 empty] | 1 | 1
|  |  | 4 | R. B. College, Dalsinghsarai | [9 empty] | 1 | 1
|  |  | 5 | U. P. College, Pusa | [9 empty] | 1 | 1
|  |  | 6 | G. M. R. D. College, Mohanpur | Amrender Kumar | [8 empty] | 1 | 1
|  |  | 7 | Dr. L. K. D. V. College, Tajpur | [9 empty] | 1 | 1
|  |  | 8 | D. B. K. N. College, Narhan | [9 empty] | 1 | 1
|  |  | 9 | B. R. B. College, Samastipur | [9 empty] | 1 | 1
|  |  | 10 | Women's"College, Samastipur | [9 empty] | 1 | 1
|  |  | 11 | R. N. A. R. College, Samastipur | [9 empty] | 1 | 1
|  |  | 12 | R. B. S. College, Andour | [9 empty] | 1 | 1
|  |  | 13 | R. C. College, Sakra | [9 empty] | 1 | 1
20 | CT-20 | Begusarai+ Khagaria+ Lakhisarai | 1 | Akhil Bhartiya Sans. Vidyapeeth, Khamhar , Begusarai | [9 empty] | 1
|  |  | 2 | awadh Buihari Sans. College, Rahimpur, Khagaria | [9 empty] | 1
|  |  | 3 | G. D. College, Begusarai | [9 empty] | 1
|  |  | 4 | A. P. S. M. College, Barauni | [9 empty] | 1
|  |  | 5 | S. K. Mahila College, Begusarai | Agni kumar Singh | [8 empty] | 1
|  |  | 6 | Co-Operative College, Begusarai | [9 empty] | 1
|  |  | 7 | R. C. S. College, Manjhaul | [9 empty] | 1
|  |  | 8 | B. N. M. College, Barhiya | [9 empty] | 1
|  |  | 9 | K. S. S. College, Lakhisarai | [9 empty] | 1
|  |  | 10 | Koshi College, Khagarhiya | [9 empty] | 1
21 | CT-21 | Bhagalpur+ Banka+ Khagaria | 1 | Bhagalpur national college, Bhagalpur | [8 empty] | 1
|  |  | 2 | G. B. College, Naugachhia | [9 empty] | 1 | 1
|  |  | 3 | J. P. College, Narayanpur | [8 empty] | 1
|  |  | 4 | Marwani College, Bhagalpur | [8 empty] | 1
|  |  | 5 | Muraka College, Sultanganj | [8 empty] | 1
|  |  | 6 | P. B. S. College, Banka | [8 empty] | 1
|  |  | 7 | S. M. College, Bhagalpur | D.P. Maheswari pvt Ltd | [7 empty] | 1
|  |  | 8 | S. S. V. College, Kahalgaon |  | 1 | 1 | [8 empty] | land not avilable
|  |  | 9 | T. N. B. College, Bhagalpur | [8 empty] | 1
|  |  | 10 | Sabour College, Sabour |  | 1 | 1 | [8 empty] | Sufficient land not avilable
|  |  | 11 | T. N. B. Law College, Bhagalpur | [5 empty] | 1
|  |  | 12 | Mahila college, Khagaria |  |  | 1
|  |  | 13 | M. A. M. College, Naugachhia | [9 empty] | 1 | 1
|  |  | 14 | L. P. N. S. College, Banka |  | 1 | 1 | [8 empty] | college not located
22 | CT-22 | Purnia+ Araria+ Katihar+ Kishanganj | 1 | Purnia College, Purnia, | [9 empty] | 1 | 1
|  |  | 2 | D. S. College, Katihar | [9 empty] | 1
|  |  | 3 | Forbisganj College, Forbisganj | [9 empty] | 1 | 1
|  |  | 4 | Purnia Mahila College, |  | 1 | 1 | [8 empty] | Land problem
|  |  | 5 | M. L. Arya College, Kasba | [9 empty] | 1 | 1
|  |  | 6 | Araria College, Araria | Bansidhar Tirupati Agency | [8 empty] | 1 | 1
|  |  | 7 | R. L. College, Madhopur, Purnia | [9 empty] | 1 | 1
|  |  | 8 | K. B. Jha College, Katihar | [9 empty] | 1 | 1
|  |  | 9 | Marwari College, Kishanganj |  | 1 | 1 | [8 empty] | land problem
|  |  | 10 | M. J. M. Mahila College |  | 1 | 1 | [8 empty] | land problem
|  |  | 11 | R. D. S. College, Salmari | [9 empty] | 1
|  |  | 12 | Radha Umakant Sans.College,Sukhsena, Purnia |  | 1 | 1 | [8 empty] | land problem
23 | CT-23 | Madhepura | 1 | G. L. M. College, Banmankhi | [9 empty] | 1 | 1
|  |  | 2 | T. P. College, Madhepura | [9 empty] | 1 | 1
|  |  | 3 | H. S. College, Udakishanganj | [9 empty] | 1 | 1
|  |  | 4 | K. P. College, Murliganj | SanjeevRanjan Sinha | [8 empty] | 1 | 1
|  |  | 5 | Nehru College, Bahadurganj |  | 1 | 1 | [8 empty] | land problem
|  |  | 6 | L. K. M. College, Birpur |  | 1 | 1 | [8 empty] | land problem
|  |  | 7 | B. N. M. V. College, Madhepura | [9 empty] | 1 | 1
|  |  | 8 | P. Sc. College, Madhepura | [9 empty] | 1 | 1
24 | CT-24 | Munger+ jamui+ seikhpura+ khagaria | 1 | B. R. M. College, Monger | [8 empty] | 1
|  |  | 2 | D. S. M. College, Jhajha | [8 empty] | 1
|  |  | 3 | H. S. College, Havelikharhagpur | [7 empty] | 1
|  |  | 4 | J. M. S. College, Monger | [8 empty] | 1
|  |  | 5 | J. R. S. College, Jamalpur | [8 empty] | 1
|  |  | 6 | K. D. S. College, Gogari | [5 empty] | 1
|  |  | 7 | K. K. M. College, Jamui | D.P. M aheswari Const. | [7 empty] | 1
|  |  | 8 | K. M. D. College, Parbatta | [7 empty] | 1
|  |  | 9 | R. D. College, Sheishpur | [7 empty] | 1
|  |  | 10 | R. S. College, tarapur | [8 empty] | 1
|  |  | 11 | R. D. & D. J. College, Monger | [7 empty] | 1
|  |  | 12 | S. K. R. College, Barbigha | [7 empty] | 1
|  |  | 13 | Jamalpur College, Jamalpur | [7 empty] | 1
25 | CT-25 | Saharsa+ Supaul | 1 | M. L. T. College, Saharsa | [9 empty] | 1 | 1
|  |  | 2 | M. H. M. College, Saharsa | [9 empty] | 1 | 1
|  |  | 3 | R. M. M. Law College, Saharsa |  | 1 | 1 | [8 empty] | Land Problem
|  |  | 4 | R. Jha. Mahila College, Saharsa |  | 1 | 1 | [8 empty] | Land Problem
|  |  | 5 | R. M. College, Saharsa | Sanjeev Rsanjan Sinha. | [8 empty] | 1 | 1
|  |  | 6 | B. S. S. College, Supaul | [9 empty] | 1 | 1
|  |  | 7 | S. N. S. R. K. S. College, Saharsa | [9 empty] | 1 | 1
|  |  | 8 | Ugratara Bharati Mandan Sans. College, Maheshi, Saharsa | [9 empty] | 1 | 1
26 | CT-26 | Sitamarhi | 1 | S. R. K. G. College, Sitamarhi | [9 empty] | 1 | 1
|  |  | 2 | J. S. College, Chandauli | [9 empty] | 1 | 1
|  |  | 3 | R. S. S. M. College, Sitamarhi | Amit Kumar | [8 empty] | 1 | 1
|  |  | 4 | S. L. K. College, Sitamarhi | [9 empty] | 1 | 1
|  |  | 5 | R. S. S. Sc. College, Sitamarhi | [9 empty] | 1 | 1
|  |  | 250 |  |  | 26 | 33 | 1 | 0 | 3 | 0 | 6 | 15 | 184 | 153