## EXAM-HALL
BSEIDC Ltd., Patna
Progress Report for the construction of Examination Hall
S.N. | Group No. | Name of Division | Name of District | Name of College | Name of Agency | Physical Status | [27 empty] | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%) | Remarks
[6 empty] | A/A | T/S | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Date of Tender Comitt. Meeting | Date of Exec. Comitt. Meeting | L.O.A &Issued Date | Contract price | Performance Security | Date of verification for Earnest Money Issue to | Verification for Earnest Money Received Date | Date of Verification for (P.S) issue to | Verification of (P.S) Received Date | Date of Aggrement | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete
[26 empty] | LL | RL | LL | RL | LL | RL
1 | 1 | Saran | Chapra | Rajendra College, Chapra (Zone-iv) | Shiv Sankar Singh Pvt. Ltd | 366.186 | 403.635 | 368.1508 | 18.03.2013 | 16.04.2013 | 26.04.2013 | 2013-05-27 |  | ISSUED | 37532975 | 751000 |  |  | 2013-06-13 | 2013-06-24 | 88 SBD OF 2013-14 & 26.08.2013 | [11 empty] | 1 | 375.32 | 28.3 | 7.54
2 | 2 | Darbhanga | Madhubani | R.K.College, Madhubani (Zone-v) | Phullar construction Pvt. Ltd | 366.186 | 478.15 | 436.2125 | Do | Do | Do |  |  | ISSUED | 44493671 | 890000 |  |  | 2013-07-03 | 2013-07-19 | 117SBD 2013-14 & 24.09.2013 | [11 empty] | 1 | 444.93 | 107.95 | 24.26 | MB in Division
3 | 3 | Tirhut West | East Champaran | M. S. College, Motihari (Zone-iv) | M/s C.S. Construction | 366.186 | 418.62 | 381.8484 | Do | Do | Do | 2013-05-13 |  | ISSUED | 36981191 | [5 empty] | 388 SBD OF 2014-15 & 13.10.14 | [10 empty] | 1 |  | 369.8119 |  | 0
4 | 4 | Tirhut West | West Champaran | M. J. K. College, Bettiah (Zone-iv) | Pawan Construction | 366.186 | 428.59 | 390.9516 | Do | Do | Do | [9 empty] | 751 SBD of 2014-15 (13.03.2015) | [8 empty] | 1 | [5 empty] | #DIV/0!
5 | 5 | Munger | Munger | R.D & D.J. College, Munger (Zone-iv) | Rajendra Prasad Yadav | 366.186 | 405.29 | 369.6688 | Do | Do | Do |  | 2014-02-10 | ISSUED | 35808869 | [5 empty] | 342 SBD OF 2014-15 & 18.09.14 | [11 empty] | 1 | 358.0887 | 100.02 | 27.93
6 | 6 | Tirhut East | Muzaffarpur | L. S. College, Muzaffarpur (Zone-iv) | M/S Maa Ambey Enterprises | 366.186 | 414.71 | 378.2736 | Do | Do | Do |  |  | ISSUED |  | 900000 |  |  | 2013-07-25 | 2013-08-19 | 105 SBD OF 2013-14 & 11/09/2013 | [10 empty] | 1 |  | 371.94 | 86.51 | 23.26 | SF Bricwork Running, GF,FF Brickwork and Internal Plaster Done
7 | 7 | Bhagalpur | Bhagalpur | Sunderwati Mahila College Bhagalpur (Zone-iv) | Lalan Kumar | 366.186 | 402.41 | 367.029 | Do | Do | Do |  |  | ISSUED | 35106319 | 702000 |  |  | 2013-11-18 | 2013-11-25 | 167SBD OF 2013-14 & 28/11/2013 | [11 empty] | 1 | 351.06 | 298.48 | 85.02
8 | 8 | Darbhanga | Darbhanga | C. M. Science College Darbhanga (Zone-v) | Avaneesh Enterprises | 366.186 | 468.24 | 427.1628 | Do | Do | Do | 2013-05-27 |  | ISSUED | 43570608 | 872000 |  |  | 2013-07-26 | 2013-12-05 | 194SBD OF 2013-14 & 20/12/2013 | [10 empty] | 1 |  | 435.7 | 98.31 | 22.56
9 | 9 | Kosi | Saharsa | Rajendra Mishara College Saharsa (Zone-v) | M/s R.K Construction | 366.186 | 466.91 | 425.9472 | Do | Do | Do |  |  | ISSUED | 43446609 | 869200 |  |  | 2013-06-20 | 2013-07-05 | 140SBD OF 2013-14 & 23/10/2013 | [11 empty] | 1 | 434.46 | 101.13 | 23.28
10 | 10 | Patna West | Sasaram | S.P. Jain College, Sasaram (Zone-iii) | Ajay Kumar Singh | 366.186 | 390.61 | 356.2574 | Do | Do | Do | 2013-08-23 |  | ISSUED | 36249190 | 725000 |  |  | 2013-10-30 | 2013-11-11 | 157SBD OF2013-14 & 26/11/2013 | [11 empty] | 1 | 362.49 | 103.59 | 28.58
11 | 11 | Purnea | Purnea | Purnea College, Purnea (Zone-iv) | JAY RAM CONSTRUCTION | 366.186 | 414.81 | 378.3643 | 18.02.2014 | 17.04.2014 | [10 empty] | 419 SBD OF 2014-15 & 03.11.2014 | [11 empty] | 1 | 384.3105 |  | 0
12 | 12 | Tirhut East | Sitamarhi | S.R.K.G. College Sitamarhi (Zone-v) | Malti Singh | 366.186 | 472.41 | 430.9725 | 2013-11-18 | 28.12.2013 | 04.01.2014 | 2014-01-21 |  | ISSUED&412/31.01.2014 | 44192308 | 1125000 |  |  | 2014-02-28 |  | 155 SBD OF 2014-15 (03.07.14) | [10 empty] | 1 |  | 441.9231 | 129.42 | 29.29 | FF Kota , Terrazo , Internal & External plaster Plumbing Grill Running
13 | 13 | Saran | Siwan | Raja Singh College, Siwan (Zone-iv) | Shiv Sankar Singh Pvt. Ltd. | 366.186 | 419.09 | 382.2751 | Do | Do | Do |  | 2014-01-21 | ISSUED | 39702017 | 820000 |  |  | 2014-03-20 |  | 64SBD OF 2014-15 (06.06.14) | [11 empty] | 1 | 397.0202 | 186.99 | 47.1 | Handover
14 | 14 | Patna West | Kaimur | S.B.B.P.College, Bhabhua (Zone-iii) | Ajay Kumar Mishra | 366.186 | 328.32 | 299.383 | Do | Do | Do | 2014-01-21 |  | ISSUED&411/31.01.2014 | 29436409 | 965000 |  |  |  |  | 174 SBD OF 2014-15 (11.07.14) | [10 empty] | 1 |  | 294.3641 | 53.48 | 18.17
15 | 15 | Kosi | Madhepura | B.N.Mandal College, Madhepura (Zone-v) | Avaneesh Enterprises | 366.186 | 468.67 | 427.5559 | Do | Do | Do |  | 2014-02-10 | ISSUED | 44824854 | [5 empty] | 87SBD OF 2014-15 (12.06.14) | [9 empty] | 1 |  |  | 44.8249 | 82.35 | 183.72
16 | 16 | Patna East | Nalanda | Nalanda College Biharsharif, (Zone-iv) | New Nalanda Tube well Boring & Engineering Works | 366.186 | 405.86 | 370.1942 | Do | Do | Do |  | 2014-02-10 | ISSUED | 38284207 | [5 empty] | 173 SBD OF 2014-15 (10.07.04) | [9 empty] | 1 |  |  | 382.8421 |  | 0
17 | 17 | Darbhanga | Samastipur | Samastipur College , Samastipur (Zone-iv) | R.K. Construction | 366.186 | 415.83 | 379.301 | 18.02.2014 | 17.04.2014 | [16 empty] | 1 | [8 empty] | #DIV/0!
18 | 18 | Kosi | Supaul | B.S.S.College, Supaul (Zone-v) | Sudesh Kumar Singh & Co. Construction Pvt. Ltd. | 366.186 | 476.34 | 434.5525 | 2013-11-18 | 28.12.2013 | 04.01.2014 | 2014-01-21 |  | ISSUED & 410 /31.01.2014 | 43597398 | 1341000 |  |  | 2014-02-19 | 2014-03-01 | 51 SBD OF 2014-15 (29.05.14) | [7 empty] | 1 |  |  |  |  | 435.974 | 52.3 | 12
19 | 19 | Magadh | Nawada | S.N.S College, Warsaliganj, Nawada (Zone-iv) | Arvind Prasad | 366.186 | 393.92 | 359.2854 | Do | Do | Do | 2014-01-21 |  | ISSUED&409/31.01.2014 | 36123989 | 1049000 |  |  |  |  | 128 SBD OF 2014-15 (24.06.14) | [10 empty] | 1 |  | 361.2399 | 102.9 | 28.49
20 | 20 | Tirhut East | Vaishali | R. N. College, Hajipur (Zone-iv) | Sanjay Kumar Singh | 366.186 | 415.31 | 378.8195 | Do | Do | Do | 2014-01-21 |  | ISSUED & 408 /31.01.2014 | 37854907 | 1143000 |  |  |  |  | 118 SBD OF 2014-15 (20.06.14) | [10 empty] | 1 |  | 378.5491 | 118.94 | 31.42 | Plaster, Flooring, Wiring, Plumbing done Painting In Progress
21 | 21 | Munger | Begusarai | J. D.College, Beguisarai (Zone-iv) | R.K. Construction | 366.186 | 406.47 | 370.7517 | Do | Do | Do |  | 2014-02-10 | ISSUED | 37346829 | [5 empty] | 262 SBD OF 2014-15 (16.08.14) | [10 empty] | 1 |  | 373.4683 | 122.23 | 32.73
22 | 22 | Purnea | Katihar | D. S.College, Katihar (Zone-iv) | Ashok Kumar Singh | 366.186 | 422.45 | 385.3406 | Do | Do | Do | 2014-01-21 |  | ISSUED &407/31.01.2014 | 37059811 | 1714000 |  |  | 2014-03-03 |  | 121 SBD OF 2014-15 (20.06.14 | [9 empty] | 1 |  |  | 370.5981 | 103.84 | 28.02
23 | 23 | Magadh | Aurangabad | S.N.S College, Aurangabad (Zone-iii) | Arvind Kumar Singh | 366.186 | 321.83 | 293.4501 | Do | Do | Do | 2014-01-21 |  | ISSUED 406/31.01.2014 | 28776811 | 972000 | [10 empty] | 1 | [8 empty] | #DIV/0!
24 |  | Darbhanga | Darbhanga | L.N.M.U. (Lalit Narayan Mithila University) | Malti Construction | [22 empty] | 1
25 |  | Darbhanga | Darbhanga | K.S.S.U (Kameshware Sanskrit Viswavidhyalaya) | Dayaram Singh | [26 empty] | 1
26 |  | Magadh | Gaya | Gaya College, Gaya | Kamaluddin khan | [26 empty] | 1
[22 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 3 | 10 | 8 | 7368.9147 | 1876.74 | 25.47