## SSS
BSEIDC Ltd., Patna
Physical Status of Senior Secondary Schools (SSS)
S.N. | Group No. | Name of District | Name of Block | Name of School | Retender | Tender Process | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | Remarks | Division
[11 empty] | LL | RL | LL | RL
1 | SSS-98-1 | Patna | fcgVk | e/; fo¦ky;] jk?kksiqj] fcgVk] iVuk | [10 empty] | 1 |  |  | Patna East
2 | SSS-99-1 | Patna | nkukiqj | mRØfer e/; fo¦ky;] cfj;kjiqj |  |  | 1 | [9 empty] | School not locate | Patna East
3 | SSS-100-1 | Nalanda | bLykeiqj | e/; fo¦ky;] dksfcy | [11 empty] | 1 | Handover | Patna East
4 | SSS-100-2 | Nalanda | bLykeiqj | e/; fo¦ky;] pkSjek | [11 empty] | 1 | Handover | Patna East
5 | SSS-101-1 | Nalanda | fcgkj | mRØfer e/; fo¦ky;] gosyh | [9 empty] | 1 |  |  |  | Patna East
6 | SSS-102-1 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] gjxk¡o | [10 empty] | 1 |  |  | Patna East
7 | SSS-102-2 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] ldjkSy |  |  | 1 | [9 empty] | Land not available | Patna East
8 | SSS-102-3 | Nalanda | fcgkj'kjhQ | mRØfer e/; fo¦ky;] ijkSgk | [7 empty] | 1 | [5 empty] | Patna East
9 | SSS-103-1 | Nalanda | fgylk | e/; fo¦ky;] diflvkou | [10 empty] | 1 |  |  | Patna East
10 | SSS-104-1 | Nalanda | flyko | mnwZ e/; fo¦ky;] lkscbZr | [10 empty] | 1 |  |  | Patna East
11 | SSS-104-2 | Nalanda | flyko | e/; fo¦ky;] pk¡nh ekWm | [10 empty] | 1 |  |  | Patna East
12 | SSS-104-3 | Nalanda | flyko | e/; fo¦ky;] dqy | [10 empty] | 1 |  |  | Patna East
13 | SSS-104-4 | Nalanda | flyko | mRØfer e/; fo¦ky;] ikadh | [7 empty] | 1 | [5 empty] | Patna East
14 | SSS-104-5 | Nalanda | flyko | mRØfer e/; fo¦ky;] t;fd'kqu fcxgk | [9 empty] | 1 |  |  |  | Patna East
15 | SSS-105-1 | Nalanda | fxfj;d | e/; fo¦ky;] vkneiqj |  |  | 1 | [9 empty] | Land not available | Patna East
16 | SSS-105-2 | Nalanda | fxfj;d | e/; fo¦ky;] pkSjlqvk | [11 empty] | 1 |  | Patna East
17 | SSS-106-1 | Nalanda | gjukSr | e/; fo¦ky;] usgqlk | [11 empty] | 1 | Handover | Patna East
18 | SSS-107-1 | Nalanda | ijoyiqj | m0vk0e/; fo¦ky;] ebZ |  |  | 1 | [9 empty] | Land not available | Patna East
19 | SSS-108-1 | Nalanda | jgqbZ | e/; fo¦ky;] eksM+kryko |  |  | 1 | [9 empty] | Land not available | Patna East
20 | SSS-108-2 | Nalanda | jgqbZ | e/; fo¦ky;] dFkkSyh | [10 empty] | 1 |  |  | Patna East
21 | SSS-109-1 | Nalanda | ljesjk | e/; fo¦ky;] dkthpd | [11 empty] | 1 |  | Patna East
22 | SSS-109-2 | Nalanda | ljesjk | e/; fo¦ky;] eykou | [11 empty] | 1 | Handover | Patna East
23 | SSS-120-1 | Nalanda | uwjljk; | e/; fo¦ky;] eeqjknkckn | [11 empty] | 1 | Handover | Patna East
24 | SSS-120-2 | Nalanda | uwjljk; | e/; fo¦ky;] ljnkjfoxgk | [11 empty] | 1 | Handover | Patna East
25 | SSS-121-1 | Nalanda | vLFkkok¡ | mnZw e/; fo¦ky;] mxkou |  |  | 1 | [9 empty] | Not Start | Patna East
26 | SSS-121-2 | Nalanda | vLFkkok¡ | mRØfer e/; fo¦ky;] vksb;kc | [11 empty] | 1 |  | Patna East
27 | SSS-121-3 | Nalanda | vLFkkok¡ | e/; fo¦ky;] [ksryiqjk | [11 empty] | 1 |  | Patna East
28 | SSS-121-4 | Nalanda | vLFkkok¡ | e/; fo¦ky;] tkuk |  |  | 1 | [9 empty] | Land problem | Patna East
29 | SSS-121-5 | Nalanda | vLFkkok¡ | e/; fo¦ky;] vkSUMk | [11 empty] | 1 |  | Patna East
30 | SSS-122-1 | Bhojpur | cM+gjk | e/; fo¦ky;] uFkeyiqj | [10 empty] | 1 |  |  | Patna East
31 | SSS-123-1 | Bhojpur | fcfg;kW | mRØfer e/; fo¦ky;] ohjiqj | [10 empty] | 1 |  |  | Patna East
32 | SSS-123-2 | Bhojpur | fcfg;kW | çk;ksfxd e/; fo¦ky;] fcfg;kW | [10 empty] | 1 |  |  | Patna East
33 | SSS-124-1 | Bhojpur | ihjks | mRØfer e/; fo¦ky;] ,;kj | [7 empty] | 1 | [5 empty] | Patna East
34 | SSS-124-2 | Bhojpur | ihjks | e/; fo¦ky;] ygjkckn | [5 empty] | 1 | [7 empty] | Patna East
35 | SSS-125-1 | Bhojpur | lans'k | e/; fo¦ky;] ppkj | [11 empty] | 1 | Handover | Patna East
36 | SSS-126-1 | Bhojpur | lkgiqj | e/; fo¦ky;] ygax Mqefj;k | [10 empty] | 1 |  |  | Patna East
37 | SSS-127-1 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky;] [kyhlk |  |  | 1 | [9 empty] | Work stop by DEO | Patna East
38 | SSS-127-2 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky;] ckeikWyh | [10 empty] | 1 |  |  | Patna East
39 | SSS-127-3 | Bhojpur | mnoUruxj | mRØfer e/; fo¦ky; ohjeiqj | [10 empty] | 1 |  | Shuttering | Patna East
40 | SSS-128-1 | Bhojpur | rjkjh | e/; fo¦ky;] pank | [10 empty] | 1 |  |  | Patna East
41 | SSS-128-2 | Bhojpur | rjkjh | e/; fo¦ky;] csjbZ | [10 empty] | 1 |  |  | Patna East
42 | SSS-129-1 | Bhojpur | txnh'kiqj | mRØfer e/; fo¦ky;] nkWok | [10 empty] | 1 |  |  | Patna East
43 | SSS-129-2 | Bhojpur | txnh'kiqj | mRØfer e/; fo¦ky;] cSjgh | [9 empty] | 1 |  |  |  | Patna East
44 | SSS-130-1 | Bhojpur | vkjk | e/; fo¦ky;] [ktqfj;kW | [9 empty] | 1 |  |  |  | Patna East
45 | SSS-130-2 | Bhojpur | vkjk | mRØfer e/; fo¦ky;] y{e.kiqj | [9 empty] | 1 |  |  |  | Patna East
46 | SSS-415-1 | Patna | ikyhxat | e/; fo¦ky;] /kks[kjk |  |  |  |  | 1 | [8 empty] | Patna East
47 | SSS-451-1 | Nalanda | bLykeiqj | e/; fo¦ky;] ekSyukpd | [7 empty] | 1 | [5 empty] | Patna East
48 | SSS-374-1 | Patna | ikyhxat | e/; fo¦ky;] esjk[kkuiqjk | [10 empty] | 1 |  |  | Patna East
49 | SSS-374-2 | Patna | ikyhxat | e/; fo¦ky;] lsgjk | [10 empty] | 1 |  |  | Patna East
50 | SSS-374-3 | Patna | ikyhxat | e/; fo¦ky;] dY;k.kiqj | [10 empty] | 1 |  |  | Patna East
51 | SSS-375 (A) | Patna | /ku:vk | e/; fo¦ky;] vatuh xksfoUniqj | [5 empty] | 1 | [7 empty] | Patna East
52 | SSS-376-1 | Patna | fcgVk | e/; fo¦ky;] fgjkeuiqj idM+hundred | [10 empty] | 1 |  |  | Patna East
53 | SSS-376-2 | Patna | Qqyokjh 'kjhQ | mPp ek/;fed fo¦ky;] xksuiqjk ¼funs'kd] ek/;fed f'k{kk ds Kkikad&11@;ksŒ&02&03@2012&123] fnukad&29-01-2014 esa fn, x, vkns'kkuqlkj xzke iapk;Rs.&xksuiqjk ds csfld Ldwy ds tehu ij Hkou fuekZ.k gksxkA½ | [10 empty] | 1 |  |  | Patna East
54 | SSS-377-1 | Patna | iquiqu | mRØfer e/; fo¦ky;] jkt?kkV uoknk |  |  | 1 | [9 empty] | Not Start | Patna East
55 | SSS-131-1 | Rohtas | djxgj | e/; fo¦ky;] efu;kjh | [10 empty] | 1 |  |  | Patna West
56 | SSS-131-2 | Rohtas | djxgj | mRØfer e/; fo¦ky;] :iSBk | [10 empty] | 1 |  |  | Patna West
57 | SSS-132-1 | Rohtas | dkspl | mRdzfer e/; fo¦ky;] ygsjh | [6 empty] | 1 | [6 empty] | Patna West
58 | SSS-132-2 | Rohtas | dkspl | e/; fo¦ky;] dq:lk | [7 empty] | 1 | [5 empty] | Patna West
59 | SSS-133-1 | Rohtas | f'kolkxj | e/; fo¦ky;] eqgEeniqj | [11 empty] | 1 | Inaugurated | Patna West
60 | SSS-133-2 | Rohtas | f'kolkxj | mRdzfer e/; fo¦ky;] xksrgj | [11 empty] | 1 | Inaugurated | Patna West
61 | SSS-133-3 | Rohtas | f'kolkxj | mRdzfer e/; fo¦ky;] lsejh |  |  | 1 | [9 empty] | Land Dispute | Patna West
62 | SSS-133-4 | Rohtas | f'kolkxj | e/; fo¦ky;] FkuqvkW | [11 empty] | 1 | Inaugurated | Patna West
63 | SSS-134-1 | Rohtas | fMgjh | mRdzfer e/; fo¦ky;] HkMdqfM;k | [8 empty] | 1 |  |  |  |  | Patna West
64 | SSS-134-2 | Rohtas | fMgjh | e/; fo¦ky;] nqxkZiqj | [7 empty] | 1 | [5 empty] | Patna West
65 | SSS-135 (A) | Rohtas | fnukjk | e/; fo¦ky;] osyoS;k | [11 empty] | 1 | 20.05.2016 | Patna West
66 | SSS-135 (B) | Rohtas | fnukjk | e/; fo¦ky;] cjk<hdyk |  |  | 1 | [9 empty] | Land Problem | Patna West
67 | SSS-135 (C) | Rohtas | fnukjk | e/; fo¦ky;] esnuhiqj | [11 empty] | 1 | 20.05.2016 | Patna West
68 | SSS-135 (D) | Rohtas | fnukjk | mRdzfer e/; fo¦ky;] [kylkiqj | [9 empty] | 1 |  |  |  | Patna West
69 | SSS-136-1 | Rohtas | frykSFkq | e/; fo¦ky;] lsogh | [11 empty] | 1 | Inaugurated. (CD-20.05.2016) | Patna West
70 | SSS-137-1 | Rohtas | frykSFkw | e/; fo¦ky;] Hknks[kjk |  |  | 1 | [9 empty] | Low Land about 12'-0" | Patna West
71 | SSS-138-1 | Rohtas | Lkklkjke | mRdzfer e/; fo¦ky;] nouiqj | [11 empty] | 1 | Inaugurated | Patna West
72 | SSS-138-2 | Rohtas | Lkklkjke | e/; fo¦ky;] nfjxkao | [11 empty] | 1 | Inaugurated | Patna West
73 | SSS-138-3 | Rohtas | Lkklkjke | e/; fo¦ky;] xksVik | [11 empty] | 1 | Inaugurated | Patna West
74 | SSS-139-1 | Rohtas | lklkjke | e/; fo¦ky;] HkSlgha | [11 empty] | 1 | Inaugurated | Patna West
75 | SSS-139-2 | Rohtas | lklkjke | e/; fo¦ky;] ukSxkbZ | [11 empty] | 1 | Inaugurated | Patna West | DOC (Date of Complete
76 | SSS-139-3 | Rohtas | lklkjke | e/; fo¦ky;] ifr;k< | [11 empty] | 1 | Inaugurated | Patna West
77 | SSS-140-1 | Rohtas | psukjh | e/; fo¦ky;] HkqMdqfM;k |  |  |  |  | 1 | [8 empty] | Patna West
78 | SSS-140-2 | Rohtas | psukjh | mRdzfer e/; fo¦ky;] x.ks'kiqj | [11 empty] | 1 |  | Patna West
79 | SSS-141-1 | Rohtas | uks[kk | e/; fo¦ky;] ef<;kW | [11 empty] | 1 | Inaugurated | Patna West
80 | SSS-142-1 | Rohtas | ukSgêk | mRØfer e/; fo¦ky;] HkoukFkiqj | [11 empty] | 1 | Inaugurated (DOC-30.04.2016) | Patna West
81 | SSS-143-1 | Rohtas | vdks<+hxksyk | mRdzfer e/; fo¦ky;] lyS;k | [11 empty] | 1 | Inaugurated (DOC- 20.12.2015) | Patna West
82 | SSS-143-2 | Rohtas | vdks<+hxksyk | e/; fo¦ky;] dkSik | [11 empty] | 1 | Inaugurated (DOC- 20.12.2015) | Patna West
83 | SSS-144-1 | Buxar | bVk<+h | e/; fo¦ky;] fc>kSjk | [10 empty] | 1 |  |  | Patna West
84 | SSS-144-2 | Buxar | bVk<+h | e/; fo¦ky;] cSjh | [10 empty] | 1 |  |  | Patna West
85 | SSS-145-1 | Buxar | cDlj | e/; fo¦ky;] cksDlk | [10 empty] | 1 |  |  | Patna West
86 | SSS-145-2 | Buxar | cDlj | e/; fo¦ky;] tklks | [10 empty] | 1 |  |  | Patna West
87 | SSS-146-1 | Buxar | czãiqj | g0m0 e/; fo¦ky;] j?kqukFkiqj | [10 empty] | 1 |  |  | Patna West
88 | SSS-146-2 | Buxar | czãiqj | e/; fo¦ky;] cjk<+h |  |  |  |  | 1 | [8 empty] | Patna West
89 | SSS-147-1 | Buxar | flejh | d0 e/; fo¦ky;] nqYygiqj | [10 empty] | 1 |  |  | Patna West
90 | SSS-147-2 | Buxar | flejh | e/; fo¦ky;] NksVdk flaguiqjk | [10 empty] | 1 |  |  | Patna West
91 | SSS-147-3 | Buxar | flejh | e/; fo¦ky;] ,dkSuk | [10 empty] | 1 |  |  | Patna West
92 | SSS-148-1 | Buxar | jktiqj | e/; fo¦ky;] eaxjko | [10 empty] | 1 |  |  | Patna West
93 | SSS-149-1 | Buxar | pkSlk | e/; fo¦ky;] iouh | [11 empty] | 1 | DOC - 12.05.2015 | Patna West
94 | SSS-149-2 | Buxar | pkSlk | e/; fo¦ky;] lxjk | [11 empty] | 1 | DOC - 12.05.2016 | Patna West
95 | SSS-149-3 | Buxar | pkSlk | e/; fo¦ky;] pqUuh | [11 empty] | 1 | Inaugurated. (DOC - 12.05.2016) | Patna West
96 | SSS-150-1 | Buxar | ukokuxj | e/; fo¦ky;] Hknkj | [7 empty] | 1 |  |  |  |  | Work of Tiebeam | Patna West
97 | SSS-150-2 | Buxar | ukokuxj | e/; fo¦ky;] xksfoUniqj |  |  |  |  | 1 | [8 empty] | Patna West
98 | SSS-151-1 | Kaimur | eksgfu;ka | mRØfer e/; fo¦ky;] nknj | [10 empty] | 1 |  |  | Patna West
99 | SSS-151-2 | Kaimur | eksgfu;ka | e/; fo¦ky;] Hkj[kj | [9 empty] | 1 |  |  |  | Patna West
100 | SSS-151-3 | Kaimur | eksgfu;ka | mRØfer e/; fo¦ky;] vesB | [10 empty] | 1 |  |  | Patna West
101 | SSS-152-1 | Kaimur | HkHkqvk | e/; fo¦ky;] Hksdkl | [10 empty] | 1 |  |  | Patna West
102 | SSS-153-1 | Kaimur | Hkxokuiqj | mRØfer e/; fo¦ky;] dlsj | [10 empty] | 1 |  |  | Patna West
103 | SSS-153-2 | Kaimur | Hkxokuiqj | mRØfer e/; fo¦ky;] fla/kh | [11 empty] | 1 | Inaugurated | Patna West
104 | SSS-154-1 | Kaimur | nwxkZorh | mRØfer e/; fo¦ky;] xksjkj | [10 empty] | 1 |  |  | Patna West
105 | SSS-155-1 | Kaimur | pkWan | e/; fo¦ky;] Hkjkjh | [11 empty] | 1 | 31.05.2016 | Patna West
106 | SSS-156-1 | Kaimur | pSuiqj | e/; fo¦ky;] c<kSuk | [11 empty] | 1 | Inaugurated. 05.05.2016 | Patna West
107 | SSS-157-1 | Kaimur | v/kkSjk | mRØfer e/; fo¦ky;] pQuk | [10 empty] | 1 |  |  | Patna West
108 | SSS-157-2 | Kaimur | v/kkSjk | mRØfer e/; fo¦ky;] U;w | [10 empty] | 1 |  |  | Patna West
109 | SSS-391 (A) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] cnokadyk |  |  | 1 | [9 empty] | Not Start | Patna West
110 | SSS-391 (B) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] cgsM+k |  |  |  |  | 1 | [8 empty] | Patna West
111 | SSS-391 (C) | Kaimur | v/kkSjk | mRØfer jktdh; e/; fo¦ky;] dUgukj | 1 | [11 empty] | Retender | Patna West
112 | SSS-391 (D) | Kaimur | v/kkSjk | e/; fo¦yk;] ngkj |  |  | 1 | [9 empty] | Not Start | Patna West
113 | SSS-392-1 | Kaimur | jkeiqj | e/; fo¦ky;] veho | [9 empty] | 1 |  |  | Tie beam | Patna West
114 | SSS-393-1 | Kaimur | Hkxokuiqj | e/; fo¦ky;] tSrqiqjdyk | [9 empty] | 1 |  |  |  | Patna West
115 | SSS-394-1 | Kaimur | eksguh;k¡ | e/; fo¦ky;] dFkst | [10 empty] | 1 |  |  | Patna West
116 | SSS-395-1 | Kaimur | uqvk¡o | e/; fo¦ky;] dksVk | [5 empty] | 1 | [7 empty] | Patna West
117 | SSS-396-1 | Kaimur | jkex<+ | e/; fo¦ky;] uksukj | [10 empty] | 1 |  |  | Patna West
118 | SSS-397-1 | Kaimur | pSuiqj | mRØfer e/; fo¦ky;] Mqekjdksu | [10 empty] | 1 |  |  | Patna West
119 | SSS-429-1 | Rohtas | foØexat | e/; fo¦ky;] uksugj | [10 empty] | 1 |  |  | Patna West
120 | SSS-429-2 | Rohtas |  | e/; fo¦ky;] mn; fMgjh | [10 empty] | 1 |  |  | Patna West
121 | SSS-430-1 | Rohtas | jksgrkl | mRØfer e/; fo¦ky;] VqEck | [10 empty] | 1 |  |  | Patna West
122 | SSS-431-1 | Rohtas | psukjh | mRØfer e/; fo¦ky;] fi;kdyk | [10 empty] | 1 |  |  | Patna West
123 | SSS-254 (A) | Gaya | bekexat | e/; fo¦ky;] oa'kh | [8 empty] | 1 |  |  |  |  | Magadh
124 | SSS-254 (B) | Gaya | bekexat | e/; fo¦ky;] fojkt |  |  | 1 | [9 empty] | Not Start | Magadh
125 | SSS-254 (C) | Gaya | bekexat | e/; fo¦ky;] f>dfV;kdyk | [8 empty] | 1 |  |  |  |  | Magadh
126 | SSS-254 (D) | Gaya | bekexat | e/; fo¦ky;] olsrk | [11 empty] | 1 | Handover | Magadh
127 | SSS-255-1 | Gaya | cFkkuh | mnwZ e/; fo¦ky;] oaMh | [10 empty] | 1 |  |  | Magadh
128 | SSS-256-1 | Gaya | ckads ctkj | e/; fo¦ky;] jkS'kuxat | [11 empty] | 1 | Inaugurated. Handover | Magadh
129 | SSS-257-1 | Gaya | ckds ctkj | e/; fo¦ky;] yqVqvk |  |  | 1 | [9 empty] | Not Start | Magadh
130 | SSS-257-2 | Gaya | ckds ctkj | e/; fo¦ky;] eksus;k | [10 empty] | 1 |  |  | Magadh
131 | SSS-258-1 | Gaya | ckjkpV~Vh | e/; fo¦ky;] fnofu;ka | [10 empty] | 1 |  |  | Magadh
132 | SSS-258-2 | Gaya | ckjkpV~Vh | e/; fo¦ky;] uokMhg | [10 empty] | 1 |  |  | Magadh
133 | SSS-259-1 | Gaya | cks/kx;k | e/; fo¦ky;] teM+h | [11 empty] | 1 | Handover | Magadh
134 | SSS-259-2 | Gaya | cks/kx;k | e/; fo¦ky;] ijfj;k | [11 empty] | 1 | Handover | Magadh
135 | SSS-259-3 | Gaya | cks/kx;k | e/; fo¦ky;] ekspkfje | [11 empty] | 1 | Handover | Magadh
136 | SSS-259-4 | Gaya | cks/kx;k | e/; fo¦ky;] 'ksjokjk | [10 empty] | 1 |  |  | Magadh
137 | SSS-260-1 | Gaya | cthjxat | e/; fo¦ky;] fo'kquiqj | [7 empty] | 1 | [5 empty] | Magadh
138 | SSS-261-1 | Gaya | eksguiqj | e/; fo¦ky;] tsBqvkMkgk | [5 empty] | 1 | [7 empty] | Magadh
139 | SSS-261-2 | Gaya | eksguiqj | e/; fo¦ky;] [kqMqvk | [9 empty] | 1 |  |  |  | Magadh
140 | SSS-262-1 | Gaya | ekuiqj | e/; fo¦ky;] xsjs | [11 empty] | 1 |  | Magadh
141 | SSS-262-2 | Gaya | ekuiqj | e/; fo¦ky;] Hkksjs | [11 empty] | 1 |  | Magadh
142 | SSS-263-1 | Gaya | f[ktjljk; | e/; fo¦ky;] lfj;k | [9 empty] | 1 |  |  |  | Magadh
143 | SSS-264-1 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] mfpjek | [11 empty] | 1 | Inaugurated | Magadh
144 | SSS-264-2 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] eksguiqj |  |  | 1 | [9 empty] | Land Dispute | Magadh
145 | SSS-264-3 | Gaya | 'ks[k?kkVh | e/; fo¦ky;] dpkSM+h | [11 empty] | 1 | Inaugurated | Magadh
146 | SSS-265 (A) | Gaya | Mqefj;k | e/; fo¦ky;] cjgk | [6 empty] | 1 | [6 empty] | Magadh
147 | SSS-265 (B) | Gaya | Mqefj;k | e/; fo¦ky;] gsljk jkeiqj |  |  | 1 | [9 empty] | Not Start | Magadh
148 | SSS-266-1 | Gaya | Qrsgiqj | e/; fo¦ky;] lyS;kdyk | [10 empty] | 1 |  |  | Magadh
149 | SSS-267-1 | Gaya | uxj | xzke&dsokyh] Fkkuk laŒ&197 | [10 empty] | 1 |  |  | Magadh
150 | SSS-267-2 | Gaya | uxj | e/; fo¦ky;] dksjeka | [7 empty] | 1 | [5 empty] | Magadh
151 | SSS-267-3 | Gaya | uxj | xzke&/kqosZ Fkkuk laŒ&177 | [7 empty] | 1 | [5 empty] | Magadh
152 | SSS-268-1 | Gaya | vkel | e/; fo¦ky;] ';kedyk | [10 empty] | 1 |  |  | Magadh
153 | SSS-268-2 | Gaya | vkel | e/; fo¦ky;] fuek cq)kSy | [10 empty] | 1 |  |  | Magadh
154 | SSS-269-1 | Gaya | Vsdkjh | e/; fo¦ky;] cych?kk | [11 empty] | 1 |  | Magadh
155 | SSS-270-1 | Gaya | VudqIik | e/; fo¦ky;] ukSokx<+ | [10 empty] | 1 |  |  | Magadh
156 | SSS-270-2 | Gaya | VudqIik | e/; fo¦ky;] HksVkSjk | [9 empty] | 1 |  |  |  | Magadh
157 | SSS-271 (A) | Gaya | xq:vk | e/; fo¦ky;] 'ksjiqj | [7 empty] | 1 | [5 empty] | Magadh
158 | SSS-271 (B) | Gaya | xq:vk | e/; fo¦ky;] ukSfMgk |  |  | 1 | [9 empty] | Not Start. File pending at DCLR sherghati since seven month for registry process | Magadh
159 | SSS-271 (C) | Gaya | xq:vk | e/; fo¦ky;] fojfgek | [9 empty] | 1 |  |  |  | Magadh
160 | SSS-271 (D) | Gaya | xq:vk | e/; fo¦ky;] dkt | [10 empty] | 1 |  |  | Magadh
161 | SSS-272-1 | Nawada | esLdkSj | mRØfer e/; fo¦ky;] iokbZ | [10 empty] | 1 |  |  | Magadh
162 | SSS-272-2 | Nawada | esLdkSj | mRØfer e/; fo¦ky;] vdfj | [10 empty] | 1 |  |  | Magadh
163 | SSS-273-1 | Nawada | fglqvk | mRØfer e/; fo¦ky;] ,dukj | [9 empty] | 1 |  |  |  | Magadh
164 | SSS-274-1 | Nawada | fljnyk | mRØfer e/; fo¦ky;] dksyfMgk | [10 empty] | 1 |  |  | Magadh
165 | SSS-274-2 | Nawada | fljnyk | e/; fo¦ky;] [kuiqjk | [10 empty] | 1 |  |  | Magadh
166 | SSS-274-3 | Nawada | fljnyk | e/; fo¦ky;] vdEck |  |  | 1 | [9 empty] | Not Start | Magadh
167 | SSS-275-1 | Nawada | idjhcjkok¡ | e/; fo¦ky;] ds'kkSjh | [10 empty] | 1 |  |  | Magadh
168 | SSS-276-1 | Nawada | jksg | e/; fo¦ky;] dqat | [10 empty] | 1 |  |  | Magadh
169 | SSS-277 (A) | Nawada | jtkSyh | mRØfer e/; fo¦ky;] /kkeqpd | [10 empty] | 1 |  |  | Magadh
170 | SSS-277 (B) | Nawada | jtkSyh | e/; fo¦ky;] pijk | [9 empty] | 1 |  |  |  | Magadh
171 | SSS-279-1 | Nawada | ujgV | mRØfer e/; fo¦ky;] cjcŸkk |  |  | 1 | [9 empty] | CROSSING HIGH TENSION WIRE | Magadh
172 | SSS-279-2 | Nawada | ujgV | mRØfer e/; fo¦ky;] nkbZfcxgk | [11 empty] | 1 |  | Magadh
173 | SSS-280-1 | Nawada | uoknk | mRØfer e/; fo¦ky;] ifN;k Mhg | [10 empty] | 1 |  |  | Magadh
174 | SSS-281-1 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] Qjgk | [10 empty] | 1 |  |  | Magadh
175 | SSS-281-2 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] rsyHknzks | [10 empty] | 1 |  |  | Magadh
176 | SSS-281-3 | Nawada | vdcjiqj | e/; fo¦ky;] Hkusy | [10 empty] | 1 |  |  | Magadh
177 | SSS-281-4 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] Qqyek | [10 empty] | 1 |  |  | Magadh
178 | SSS-281-5 | Nawada | vdcjiqj | mRØfer e/; fo¦ky;] ifl;k | [10 empty] | 1 |  |  | Magadh
179 | SSS-282-1 | Nawada | xksfoUniqj | mRØfer e/; fo¦ky;] rsrfj;k | [6 empty] | 1 | [6 empty] | Magadh
180 | SSS-282-2 | Nawada | xksfoUniqj | e/; fo¦ky;] cq/kokM+k | [7 empty] | 1 | [5 empty] | Magadh
181 | SSS-283-1 | Arwal | djih | e/; fo¦ky;] [ktqjh | [10 empty] | 1 |  |  | Magadh
182 | SSS-283-2 | Arwal | djih | e/; fo¦ky;] v/kkjpd | [10 empty] | 1 |  |  | Magadh
183 | SSS-284-1 | Arwal | dysj | e/; fo¦ky; mljh |  |  |  | 1 | [9 empty] | Magadh
184 | SSS-284-2 | Arwal | dysj | e/; fo¦ky; ofynkn | [9 empty] | 1 |  |  |  | Magadh
185 | SSS-285-1 | Arwal | dqFkkZ | mRØfer e/; fo¦ky;] dSFkksyksnhiqj | [7 empty] | 1 | [5 empty] | Magadh
186 | SSS-286-1 | Arwal | lksuHknz oa'kh lw;Ziqj | e/; fo¦ky;] iksfUny | [9 empty] | 1 |  |  |  | Magadh
187 | SSS-287-1 | Arwal | vjoy | e/; fo¦ky; jkeiqj pkSje | [11 empty] | 1 |  | Magadh
188 | SSS-288-1 | Aurangabad | ck:.k | e/; fo¦ky;] dnks[kjh | [5 empty] | 1 | [7 empty] | Magadh
189 | SSS-288-2 | Aurangabad | ck:.k | e/; fo¦ky;] fiBuqvk | [9 empty] | 1 |  |  |  | Magadh
190 | SSS-289-1 | Aurangabad | dqVqEck | e/; fo¦ky;] pkS[kMk | [10 empty] | 1 |  |  | Magadh
191 | SSS-289-2 | Aurangabad | dqVqEck | e/; fo¦ky;] fd'kquiqj | [10 empty] | 1 |  |  | Magadh
192 | SSS-289-3 | Aurangabad | dqVqEck | e/; fo¦ky;] cStkfcxgk | [10 empty] | 1 |  |  | Magadh
193 | SSS-289-4 | Aurangabad | dqVqEck | e/; fo¦ky;] cSjko | [10 empty] | 1 |  |  | Magadh
194 | SSS-289-5 | Aurangabad | dqVqEck | e/; fo¦ky;] ?ksmjk | [10 empty] | 1 |  |  | Magadh
195 | SSS-289-6 | Aurangabad | dqVqEck | e/; fo¦ky;] iksyk xksjMhgk | [10 empty] | 1 |  |  | Magadh
196 | SSS-289-7 | Aurangabad | dqVqEck | e/; fo¦ky;] ihijk cxkgh | [10 empty] | 1 |  |  | Magadh
197 | SSS-290 (A) | Aurangabad | jQhxat | e/; fo¦ky;] ljkod |  |  | 1 | [9 empty] | Not Start | Magadh
198 | SSS-290 (B) | Aurangabad | jQhxat | e/; fo¦ky;] i[kukSj |  |  | 1 | [9 empty] | Not Start | Magadh
199 | SSS-291-1 | Aurangabad | nso | e/; fo¦ky;] ukjk;.kiqj | [10 empty] | 1 |  |  | Magadh
200 | SSS-292-1 | Aurangabad | nso | e/; fo¦ky;] cjaMk jkeiqj | [10 empty] | 1 |  |  | Magadh
201 | SSS-292-2 | Aurangabad | nso | e/; fo¦ky;] dVS;k | [10 empty] | 1 |  |  | Magadh
202 | SSS-292-3 | Aurangabad | nso | e/; fo¦ky;] csyk | [10 empty] | 1 |  |  | Magadh
203 | SSS-293-1 | Aurangabad | uchuxj | e/; fo¦ky;] jkeuxj | [9 empty] | 1 |  |  |  | Magadh
204 | SSS-293-2 | Aurangabad | uchuxj | e/; fo¦ky;] e>hvko | [10 empty] | 1 |  |  | Magadh
205 | SSS-293-3 | Aurangabad | uchuxj | e/; fo¦ky;] dadsj | [10 empty] | 1 |  |  | Magadh
206 | SSS-293-4 | Aurangabad | uchuxj | e/; fo¦ky;] csykbZ | [10 empty] | 1 |  |  | Magadh
207 | SSS-294-1 | Aurangabad | vkSjaxkckn | e/; fo¦ky;] cHkUMh | [11 empty] | 1 |  | Magadh
208 | SSS-295-1 | Aurangabad | xksg | e/; fo¦ky;] ?kkVks | [6 empty] | 1 | [6 empty] | Magadh
209 | SSS-295-2 | Aurangabad | xksg | e/; fo¦ky;] 'ks[kiqjk | [7 empty] | 1 | [5 empty] | Magadh
210 | SSS-296-1 | Aurangabad |  | e/; fo¦ky;] rqjrk | [10 empty] | 1 |  |  | Magadh
211 | SSS-297-1 | Jahanabad | dkdks | mRØfer e/; fo¦ky;] nso/kjk | [10 empty] | 1 |  |  | Magadh
212 | SSS-297-2 | Jahanabad | dkdks | mRØfer e/; fo¦ky;] mÙkjlsjFkq |  |  | 1 | [9 empty] | Land not available | Magadh
213 | SSS-298-1 | Jahanabad | e[knqeiqj | mRØfer e/; fo¦ky;] mnwZ eykBh | [10 empty] | 1 |  |  | Magadh
214 | SSS-299-1 | Jahanabad | eksnuxat | e/; fo¦ky;] oSuk | [9 empty] | 1 |  |  |  | Magadh
215 | SSS-300-1 | Jahanabad | gqyklxat | e/; fo¦ky;] dsmj | [9 empty] | 1 |  |  |  | Magadh
216 | SSS-301-1 | Jahanabad | jruh | e/; fo¦ky;] ?kstu | [11 empty] | 1 |  | Magadh
217 | SSS-301-2 | Jahanabad | jruh | mRØfer e/; fo¦ky;] iaMkSy | [11 empty] | 1 |  | Magadh
218 | SSS-301-3 | Jahanabad | jruh | mRØfer e/; fo¦ky;] tgk¡xhjiqj | [11 empty] | 1 |  | Magadh
219 | SSS-301-4 | Jahanabad | jruh | mRØfer e/; fo¦ky;] c<srk |  |  |  |  | 1 | [8 empty] | Magadh
220 | SSS-302-1 | Jahanabad | tgkukckn | mRØfer e/; fo¦ky;] /kqfj;k | [10 empty] | 1 |  |  | Magadh
221 | SSS-452-1 | Nawada | jtkSyh | e/; fo¦ky;] fljSyk | [11 empty] | 1 |  | Magadh
222 | SSS-453-1 | Nawada | fljnyk | e/; fo¦ky;] pkScs | [9 empty] | 1 |  |  |  | Magadh
223 | SSS-454-1 | Nawada | dksvkdksy | e/; fo¦ky;] /keku | [7 empty] | 1 | [5 empty] | Magadh
224 | SSS-454-2 | Nawada | dksvkdksy | mRØfer e/; fo¦ky;] dkyqvkckj | [11 empty] | 1 |  | Magadh
225 | SSS-457-1 | Aurangabad | gliqjk | e/; fo¦ky;] vfg;kiqj |  |  | 1 | [9 empty] | Land Problem | Magadh
226 | SSS-458-1 | Aurangabad | jQhxat | e/; fo¦ky;] flMqyh njxkg |  |  | 1 | [9 empty] | Land Problem | Magadh
227 | SSS-458-2 | Aurangabad | jQhxat | e/; fo¦ky;] yksgjk | [10 empty] | 1 |  |  | Magadh
228 | SSS-459-1 | Aurangabad | uohxat | e/; fo¦ky;] Fksxks | [7 empty] | 1 | [5 empty] | Magadh
229 | SSS-459-2 | Aurangabad | uohxat | e/; fo¦ky;] daMh | [5 empty] | 1 | [7 empty] | Magadh
230 | SSS-460-1 | Aurangabad | nso | e/; fo¦ky; nykjs |  |  | 1 | [9 empty] | Not Start | Magadh
231 | SSS-461-1 | Aurangabad | enuiqj | e/; fo¦ky;] Nkyhnksgj |  |  |  |  | 1 | [8 empty] | Magadh
232 | SSS-462-1 | Aurangabad | xksg | e/; fo¦ky;] egnhuiqj |  |  |  |  | 1 | [8 empty] | Magadh
233 | SSS-463-1 | Gaya | gfFk;kok¡ | e/; fo¦ky;] egdkj | [11 empty] | 1 | Inaugurated | Magadh
234 | SSS-464-1 | Gaya | xq:vk | e/; fo¦ky;] ljS;kVkM+ | [10 empty] | 1 |  |  | Magadh
235 | SSS-465-1 | Gaya | bekexat | e/; fo¦ky; cgsM+k pkSHkkj | [10 empty] | 1 |  |  | Magadh
236 | SSS-465-2 | Gaya | bekexat | e/; fo¦ky;] njHkaxk | [10 empty] | 1 |  |  | Magadh
237 | SSS-356-1 | Aurangabad | xksg | e/; fo¦ky;] cUns;k | [10 empty] | 1 |  |  | Magadh
238 | SSS-356-2 | Aurangabad | xksg | e/; fo¦ky;] csuh dSFkh | [8 empty] | 1 |  |  |  |  | Magadh
239 | SSS-230 (A) | Bhagalpur | [kjhd | e/; fo¦ky;] vykyiqj | [10 empty] | 1 |  |  | Bhagalpur
240 | SSS-230 (B) | Bhagalpur | [kjhd | e/; fo¦ky;] cxMh | [5 empty] | 1 | [7 empty] | Bhagalpur
241 | SSS-231 (A) | Bhagalpur | bLekbZyiqj | e/; fo¦ky;] jkeuxj |  |  |  |  | 1 | [8 empty] | Bhagalpur
242 | SSS-231 (B) | Bhagalpur | bLekbZyiqj | e/; fo¦ky;] eksrh Vksyk |  |  | 1 | [9 empty] | Land Dispute | Bhagalpur
243 | SSS-232-1 | Bhagalpur | dgyxkao | e/; fo¦ky;] dVksfj;k | [11 empty] | 1 | Inaugurated | Bhagalpur
244 | SSS-233-1 | Bhagalpur | fcgiqj | e/; fo¦ky;] vkSfy;kokn | [11 empty] | 1 |  | Bhagalpur
245 | SSS-234-1 | Bhagalpur | ihjiSarh | e/; fo¦ky;] clariqj | [11 empty] | 1 |  | Bhagalpur
246 | SSS-234-2 | Bhagalpur | ihjiSarh | e/; fo¦ky;] nmok | [11 empty] | 1 |  | Bhagalpur
247 | SSS-234-3 | Bhagalpur | ihjiSarh | e/; fo¦ky;] Kkuorh Viqvk | [11 empty] | 1 |  | Bhagalpur
248 | SSS-234-4 | Bhagalpur | ihjiSarh | e/; fo¦ky;] ij'kqjkeiqj | [11 empty] | 1 |  | Bhagalpur
249 | SSS-235 (A) | Bhagalpur | jaxjk pkSd | e/; fo¦ky;] Hkokuhiqj Vksyk |  |  |  |  | 1 | [7 empty] | EXCAVATION | Bhagalpur
250 | SSS-235 (B) | Bhagalpur | jaxjk pkSd | e/; fo¦ky;] cfu;k | [10 empty] | 1 |  |  | Bhagalpur
251 | SSS-236-1 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] oklqnsoiqj | [11 empty] | 1 | Handover | Bhagalpur
252 | SSS-236-2 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] iap:[kh | [11 empty] | 1 |  | Bhagalpur
253 | SSS-236-3 | Bhagalpur | 'kkgdqaM | e/; fo¦ky;] HkaMkjou | [11 empty] | 1 | Inaugurated. Handover | Bhagalpur
254 | SSS-237-1 | Bhagalpur | lckSj | e/; fo¦ky;] cStukFkiqj | [11 empty] | 1 | Handover | Bhagalpur
255 | SSS-238-1 | Bhagalpur | lUgkSyk | e/; fo¦ky;] rsykaS/kk | [10 empty] | 1 |  |  | Bhagalpur
256 | SSS-239-1 | Bhagalpur | ukFkuxj | e/; fo¦ky;] fo'kuiqj | [10 empty] | 1 |  |  | Bhagalpur
257 | SSS-240-1 | Bhagalpur | ukjk;.kiqj | e/; fo¦ky;] jk;iqj | [8 empty] | 1 |  |  |  |  | Bhagalpur
258 | SSS-240-2 | Bhagalpur | ukjk;.kiqj | e/; fo¦ky;] Hkokuhiqj | [7 empty] | 1 | [5 empty] | Bhagalpur
259 | SSS-240-3 | Bhagalpur | ukjk;.kiqj | dU;k e/; fo¦ky;] eFkqjkiqj | [9 empty] | 1 |  |  |  | Bhagalpur
260 | SSS-241-1 | Bhagalpur | uoxfN;k | e/; fo¦ky;] txriqj | [11 empty] | 1 | Handover | Bhagalpur
261 | SSS-241-2 | Bhagalpur | uoxfN;k | e/; fo¦ky;] [kSjiqj | [11 empty] | 1 | Inaugurated. Handover | Bhagalpur
262 | SSS-242-1 | Bhagalpur | xksikyiqj | e/; fo¦ky;] edUniqj | [11 empty] | 1 | Inaugurated | Bhagalpur
263 | SSS-243-1 | Bhagalpur | xksikyiqj | e/; fo¦ky;] ipxfN;k |  |  | 1 | [9 empty] | Land not available | Bhagalpur
264 | SSS-243-2 | Bhagalpur | xksikyiqj | e/; fo¦ky;] fMegk |  |  | 1 | [9 empty] | Agreement not done | Bhagalpur
265 | SSS-244-1 | Bhagalpur | xksjkMhg | e/; fo¦ky;] fo'kuiqj ftPNksa | [11 empty] | 1 | Handover | Bhagalpur
266 | SSS-244-2 | Bhagalpur | xksjkMhg | e/; fo¦ky;] lksuwMhg | [11 empty] | 1 | Handover | Bhagalpur
267 | SSS-244-3 | Bhagalpur | xksjkMhg | e/; fo¦ky;] eksguiqj | [11 empty] | 1 |  | Bhagalpur
268 | SSS-244-4 | Bhagalpur | xksjkMhg | e/; fo¦ky;] xaxkdjgfj;k | [11 empty] | 1 |  | Bhagalpur
269 | SSS-244-5 | Bhagalpur | xksjkMhg | e/; fo¦ky;] eqDrkiqj | [11 empty] | 1 |  | Bhagalpur
270 | SSS-244-6 | Bhagalpur | xksjkMhg | e/; fo¦ky;] dk'khy | [11 empty] | 1 |  | Bhagalpur
271 | SSS-245-1 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] vLlh edSrk | [7 empty] | 1 |  |  |  |  | G.F. ROOF CASTING | Bhagalpur
272 | SSS-245-2 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] pUnkMhg | [7 empty] | 1 |  |  |  |  | G.F. SHUTTERING | Bhagalpur
273 | SSS-245-3 | Bhagalpur | /kkSjS;k | e/; fo¦ky;] eFkqjkiqj | [10 empty] | 1 |  |  | Bhagalpur
274 | SSS-246-1 | Banka | ckadk | izksŒ e/; fo¦ky;] vejiqj | [11 empty] | 1 | Inaugurated. Handover | Bhagalpur
275 | SSS-247-1 | Banka | ckjkgkV | izksŒ e/; fo¦ky;] egqvk | [11 empty] | 1 | Inaugurated | Bhagalpur
276 | SSS-248-1 | Banka | ckSalh | izksŒ e/; fo¦ky;] cHkuxkek | [6 empty] | 1 | [5 empty] | SLOW WORK | Bhagalpur
277 | SSS-248-2 | Banka | ckSalh | izksŒ e/; fo¦ky;] >ifu;ka | [7 empty] | 1 |  |  |  |  | F.F.Sill Level (SLOW WORK) | Bhagalpur
278 | SSS-249-1 | Banka | csygj | e/; fo¦ky;] Jhuxj |  |  | 1 | [9 empty] | LAND NOT AVILABLE | Bhagalpur
279 | SSS-250-1 | Banka | dVksfj;k | e/; fo¦ky;] bukjkoj.k |  |  | 1 | [9 empty] | LAND NOT AVILABLE | Bhagalpur
280 | SSS-250-2 | Banka | dVksfj;k | izksŒ e/; fo¦ky;] Nkrkdq:e | [6 empty] | 1 | [5 empty] | WORK STOPPED SINCE MANY MONTHS | Bhagalpur
281 | SSS-251 (A) | Banka | jtkSu | izksŒ e/; fo¦ky;] vyhiqj /kfu;ka | [5 empty] | 1 | [7 empty] | Bhagalpur
282 | SSS-251 (B) | Banka | jtkSu | e/; fo¦ky;] y'kdjh | [10 empty] | 1 |  |  | Bhagalpur
283 | SSS-252-1 | Banka | QqYyhMwej | e/; fo¦ky;] dksfM+;k bukjkoj.k | [11 empty] | 1 |  | Bhagalpur
284 | SSS-252-2 | Banka | QqYyhMwej | izksŒ e/; fo¦ky;] /kkok dU;k | [7 empty] | 1 | [5 empty] | Bhagalpur
285 | SSS-252-3 | Banka | QqYyhMwej | izksŒ e/; fo¦ky;] lkniqj | [11 empty] | 1 |  | Bhagalpur
286 | SSS-252-4 | Banka | QqYyhMwej | e/; fo¦ky;] /kudqfM+;k | [6 empty] | 1 | [6 empty] | Bhagalpur
287 | SSS-253-1 | Banka | vejiqj | izksŒ e/; fo¦ky;] eSuek | [10 empty] | 1 |  |  | Bhagalpur
288 | SSS-253-2 | Banka | vejiqj | xjhciqj mjnq | [10 empty] | 1 |  |  | Bhagalpur
289 | SSS-384 (A) | Banka | pkUnu | mRØfer e/; fo¦ky; Qqygjk | [6 empty] | 1 | [6 empty] | Bhagalpur
290 | SSS-384 (B) | Banka | pkUnu | e/; fo¦ky;] Hkksjk cktkj | [10 empty] | 1 |  |  | Bhagalpur
291 | SSS-385 (A) | Banka | csygj | mRØfer e/; fo¦ky;] Vsaxjk | [7 empty] | 1 | [5 empty] | Bhagalpur
292 | SSS-385 (B) | Banka | csygj | mRØfer e/; fo¦ky;] csyk fctgjk | [7 empty] | 1 | [5 empty] | Bhagalpur
293 | SSS-410-1 | Bhagalpur | ihjiSrh | mRØfer e/; fo¦ky;] ckcqiqj | [5 empty] | 1 | [7 empty] | Bhagalpur
294 | SSS-158 (A) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] lenk gfFk;k | [5 empty] | 1 | [6 empty] | Not start | Munger
295 | SSS-158 (B) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] yMqbZ | [10 empty] | 1 |  |  | Munger
296 | SSS-158 (C) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] dUnuh | 1 | [11 empty] | Retender | Munger
297 | SSS-158 (D) | Munger | gŒ [kM+xiqj | e/; fo¦ky;] vxzg.k | [9 empty] | 1 |  |  |  | Munger
298 | SSS-159-1 | Munger | laxzkeiqj | e/; fo¦ky;] pUnfu;ka | [10 empty] | 1 |  |  | Munger
299 | SSS-160-1 | Munger | rkjkiqj | e/; fo¦ky;] fcgek |  |  | 1 | [9 empty] | Land Problem | Munger
300 | SSS-160-2 | Munger | rkjkiqj | e/; fo¦ky;] jkeiqj | [10 empty] | 1 |  |  | Munger
301 | SSS-160-3 | Munger | rkjkiqj | e/; fo¦ky;] [kqfV;k | [9 empty] | 1 |  |  |  | Munger
302 | SSS-161-1 | Munger | tekyiqj | e/; fo¦ky;] ckspkgh | [10 empty] | 1 |  |  | Munger
303 | SSS-162-1 | Munger | vljxat | e/; fo¦ky;] eklqexat | [10 empty] | 1 |  |  | Munger
304 | SSS-163-1 | Munger | VsfV;kcEcj | e/; fo¦ky;] Hkquk | [9 empty] | 1 |  |  |  | Munger
305 | SSS-163-2 | Munger | VsfV;kcEcj | e/; fo¦ky;] /kkSjh | [10 empty] | 1 |  |  | Munger
306 | SSS-164-1 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] djdh | [11 empty] | 1 |  | Munger
307 | SSS-164-2 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] csyNh | [11 empty] | 1 |  | Munger
308 | SSS-164-3 | Shekhpura | vfj;kjh | mRØfer e/; fo¦ky;] o:.kk | [11 empty] | 1 |  | Munger
309 | SSS-165-1 | Shekhpura | psojk | e/; fo¦ky;] Nfr;kjk | [9 empty] | 1 |  |  |  | Munger
310 | SSS-166-1 | Shekhpura | 'ks[kiqjk | e/; fo¦ky;] cSfj;k ch?kk | [10 empty] | 1 |  |  | Munger
311 | SSS-167-1 | Begusarai | [kksnkoUriqqj | mRØfer e/; fo¦ky;] elqjkt | [11 empty] | 1 |  | Munger
312 | SSS-167-2 | Begusarai | [kksnkoUriqqj | mRØfer e/; fo¦ky;] eq'kgjh | [11 empty] | 1 |  | Munger
313 | SSS-168-1 | Begusarai | c[kjh | e/; fo¦ky;] c[kjh | [11 empty] | 1 |  | Munger
314 | SSS-168-2 | Begusarai | c[kjh | e/; fo¦ky;] pDdjehM] unSy | [11 empty] | 1 |  | Munger
315 | SSS-169-1 | Begusarai | cjkSuh | e/; fo¦ky;] fetkZiqj pkWn | [10 empty] | 1 |  |  | Munger
316 | SSS-169-2 | Begusarai | cjkSuh | e/; fo¦ky;] Hkouxkek | [10 empty] | 1 |  |  | Munger
317 | SSS-169-3 | Begusarai | cjkSuh | mRØfer e/; fo¦ky;] pdh;k iquokZl | [10 empty] | 1 |  |  | Munger
318 | SSS-169-4 | Begusarai | cjkSuh | mRØfer e/; fo¦ky;] vlqjkjh | [10 empty] | 1 |  |  | Munger
319 | SSS-169-5 | Begusarai | cjkSuh | e/; fo¦ky;] ds'kos |  |  | 1 | [9 empty] | No Land | Munger
320 | SSS-170-1 | Begusarai | cjkSuh | e/; fo¦ky;] iijkSj | [11 empty] | 1 |  | Munger
321 | SSS-171-1 | Begusarai | csxwljk; | mRØfer e/; fo¦ky;] dqlekSr |  |  | 1 | [9 empty] | Land Problem | Munger
322 | SSS-172-1 | Begusarai | efVgkuh | e/; fo¦ky;] nfj;kiqj | [11 empty] | 1 |  | Munger
323 | SSS-172-2 | Begusarai | efVgkuh | e/; fo¦ky;] xksnjxkek | [11 empty] | 1 |  | Munger
324 | SSS-173-1 | Begusarai | Hkxokuiqj | e/; fo¦ky;] rktiqj | [11 empty] | 1 |  | Munger
325 | SSS-174-1 | Begusarai | lkgsciqj deky | e/; fo¦ky;] lkniqj | [10 empty] | 1 |  |  | Munger
326 | SSS-174-2 | Begusarai | lkgsciqj deky | e/; fo¦ky;] jgqvk | [11 empty] | 1 |  | Munger
327 | SSS-174-3 | Begusarai | lkgsciqj deky | e/; fo¦ky;] jlyiqj |  |  | 1 | [9 empty] | Land Problem | Munger
328 | SSS-174-4 | Begusarai | lkgsciqj deky | e/; fo¦ky;] nhgk | [11 empty] | 1 |  | Munger
329 | SSS-174-5 | Begusarai | lkgsciqj deky | e/; fo¦ky;] j?kqukFkiqj | [11 empty] | 1 |  | Munger
330 | SSS-175-1 | Begusarai | MaMkjh | mRØfer e/; fo¦ky;] u;k Vksyk] dY;k.kiqj | [10 empty] | 1 |  |  | Munger
331 | SSS-175-2 | Begusarai | MaMkjh | e/; fo¦ky;] jktksiqj | [7 empty] | 1 | [5 empty] | Munger
332 | SSS-175-3 | Begusarai | MaMkjh | e/; fo¦ky;] fllkSuh | [10 empty] | 1 |  |  | Munger
333 | SSS-176-1 | Begusarai | rs?kM+k | e/; fo¦ky;] vdkgk jkeiqj | [11 empty] | 1 |  | Munger
334 | SSS-176-2 | Begusarai | rs?kM+k | mRØfer e/; fo¦ky;] vks>k Vksy | [11 empty] | 1 |  | Munger
335 | SSS-176-3 | Begusarai | rs?kM+k | e/; fo¦ky;] fi<+kSyh |  |  | 1 | [9 empty] | Land Problem | Munger
336 | SSS-177 (A) | Begusarai | ukodksBh | mRØfer e/; fo¦ky;] pdeqt¶Qj | [10 empty] | 1 |  |  | Munger
337 | SSS-177 (B) | Begusarai | ukodksBh | dU;k e/; fo¦ky;] igljk |  |  | 1 | [9 empty] | Not start | Munger
338 | SSS-178-1 | Begusarai | x<+iqjk | e/; fo¦ky;] eNjkgk] jtkSj | [10 empty] | 1 |  |  | Munger
339 | SSS-178-2 | Begusarai | x<+iqjk | mRØfer e/; fo¦ky;] dksfj;ek | [11 empty] | 1 |  | Munger
340 | SSS-178-3 | Begusarai | x<+iqjk | mRØfer e/; fo¦ky;] çk.kiqj fgUnh | [11 empty] | 1 |  | Munger
341 | SSS-179-1 | Lakhisarai | cM+fg;k | e/; fo¦ky;] izrkiiqj |  |  | 1 | [9 empty] | Not start | Munger
342 | SSS-179-2 | Lakhisarai | cM+fg;k | mRØfer e/; fo¦ky;] y{ehiqj] lgtkniqj |  |  | 1 | [9 empty] | Not start | Munger
343 | SSS-180-1 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] ?kks?kh cfj;kjiqj | [9 empty] | 1 |  |  |  | Munger
344 | SSS-180-2 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] uodkMhg mjSu | [10 empty] | 1 |  |  | Munger
345 | SSS-180-3 | Lakhisarai | lw;Zx<+k dtjk f'k{kkapy | e/; fo¦ky;] dtjk | [10 empty] | 1 |  |  | Munger
346 | SSS-181 (A) | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] fr;kpd | [10 empty] | 1 |  |  | Munger
347 | SSS-181 (B) | Lakhisarai | pkuu | e/; fo¦ky;] Hkkanj | [5 empty] | 1 | [7 empty] | Munger
348 | SSS-182-1 | Lakhisarai | pkuu | e/; fo¦ky;] cUuw cxhpk |  |  | 1 | [9 empty] | Land Problem | Munger
349 | SSS-182-2 | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] clqvkpd | [7 empty] | 1 | [5 empty] | Munger
350 | SSS-183-1 | Lakhisarai | y[khljk; | mRØfer e/; fo¦ky;] [kxkSj | [11 empty] | 1 |  | Munger
351 | SSS-184-1 | Jamaui | [kSjk | e/; fo¦ky;] :ikosy |  |  | 1 | [9 empty] | Land Problem | Munger
352 | SSS-184-2 | Jamaui | [kSjk | e/; fo¦ky;] /kjeiqj | [7 empty] | 1 |  |  |  |  | Land Problem | Munger
353 | SSS-184-3 | Jamaui | [kSjk | mRØfer e/; fo¦ky;] fVfg;kfnukjh | [11 empty] | 1 |  | Munger
354 | SSS-184-4 | Jamaui | [kSjk | e/; fo¦ky;] dSM+kdknks | [10 empty] | 1 |  |  | Munger
355 | SSS-185-1 | Jamaui | >k>k | e/; fo¦ky;] iSjxkgk | [8 empty] | 1 |  |  |  |  | Munger
356 | SSS-185-2 | Jamaui | >k>k | mRØfer e/; fo¦ky;] lqUnjh VkaM | [10 empty] | 1 |  |  | Munger
357 | SSS-185-3 | Jamaui | >k>k | e/; fo¦ky;] ps;u | [10 empty] | 1 |  |  | Munger
358 | SSS-186-1 | Jamaui | cjgV | e/; fo¦ky;] yk[ks; |  |  | 1 | [9 empty] | Not Start | Munger
359 | SSS-186-2 | Jamaui | cjgV | e/; fo¦ky;] iaps'ojh | [10 empty] | 1 |  |  | Munger
360 | SSS-187-1 | Jamaui | fldUnjk | e/; fo¦ky;] lcych?kk | [9 empty] | 1 |  |  |  | Munger
361 | SSS-187-2 | Jamaui | fldUnjk | e/; fo¦ky;]uodkMhg | [9 empty] | 1 |  |  |  | Munger
362 | SSS-188-1 | Jamaui | pdkbZ | e/; fo¦ky;] /keukMhg | [9 empty] | 1 |  |  |  | Munger
363 | SSS-188-2 | Jamaui | pdkbZ | e/; fo¦ky;] flejk |  |  | 1 | [9 empty] | Land Problem | Munger
364 | SSS-188-3 | Jamaui | pdkbZ | e/; fo¦ky;] njok | [11 empty] | 1 |  | Munger
365 | SSS-188-4 | Jamaui | pdkbZ | e/; fo¦ky;] ejgh clcqfV;k | [11 empty] | 1 |  | Munger
366 | SSS-188-5 | Jamaui | pdkbZ | e/; fo¦ky;] ikaMsMhg | [11 empty] | 1 |  | Munger
367 | SSS-188-6 | Jamaui | pdkbZ | e/; fo¦ky;] Bk<+h |  |  | 1 | [9 empty] | Land Problem | Munger
368 | SSS-188-7 | Jamaui | pdkbZ | e/; fo¦ky;] ek/kksiqj | [11 empty] | 1 |  | Munger
369 | SSS-188-8 | Jamaui | pdkbZ | e/; fo¦ky;] flefj;k | [11 empty] | 1 |  | Munger
370 | SSS-189-1 | Jamaui | teqbZ | e/; fo¦ky;] izrkiiqj | [11 empty] | 1 |  | Munger
371 | SSS-190-1 | Jamaui | y{ehiqj | mRØfer e/; fo¦ky;] flaf?k;k | [10 empty] | 1 |  |  | Munger
372 | SSS-191 (A) | Khagaria | csynkSj | e/; fo¦ky;] cksfcy Qqyofj;k | 1 | [11 empty] | Retender | Munger
373 | SSS-191 (B) | Khagaria | csynkSj | e/; fo¦ky;] ekyh | 1 | [11 empty] | Retender | Munger
374 | SSS-191 (C) | Khagaria | csynkSj | e/; fo¦ky;] ldjksgj |  |  |  |  | 1 | [7 empty] | Not start | Munger
375 | SSS-191 (D) | Khagaria | csynkSj | e/; fo¦ky;] ipkSr |  |  |  |  | 1 | [7 empty] | Not Start | Munger
376 | SSS-192-1 | Khagaria | ekulh | e/; fo¦ky;] veuh | [11 empty] | 1 |  | Munger
377 | SSS-193-1 | Khagaria | pkSFke | e/; fo¦ky;] jksfg;kj | [8 empty] | 1 |  |  |  |  | Munger
378 | SSS-379-1 | Khagaria | ekulh | e/; fo¦ky; vjs;k |  |  | 1 | [9 empty] | Not start | Munger
379 | SSS-380 (A) | Khagaria | ijoÙkk | e/; fo¦ky; cUnsgjk |  |  |  |  | 1 | [8 empty] | Munger
380 | SSS-380 (B) | Khagaria | ijoÙkk | e/; fo¦ky; dcSyk | [10 empty] | 1 |  |  | Munger
381 | SSS-380 (C) | Khagaria | ijoÙkk | e/; fo¦ky;] [khjk Mhg | [10 empty] | 1 |  |  | Munger
382 | SSS-381 (A) | Khagaria | xksxjh | e/; fo¦ky; jkeiqj | [8 empty] | 1 |  |  |  |  | Munger
383 | SSS-381 (B) | Khagaria | xksxjh | e/; fo¦ky; cM+h iSdkr | [10 empty] | 1 |  |  | Munger
384 | SSS-381 (C) | Khagaria | xksxjh | e/; fo¦ky; enkjiqj |  |  | 1 | [9 empty] | Not start | Munger
385 | SSS-381 (D) | Khagaria | xksxjh | e/; fo¦ky; u'dhiqj |  |  | 1 | [9 empty] | Not start | Munger
386 | SSS-381 (E) | Khagaria | xksxjh | e/; fo¦ky; nsoBk |  |  | 1 | [9 empty] | Not start | Munger
387 | SSS-382-1 | Khagaria | pkSFke | e/; fo¦ky; /kuNkj cqPpk | [5 empty] | 1 | [7 empty] | Munger
388 | SSS-383-1 | Khagaria | [kxfM+;k | e/; fo¦ky; dkf'keiqj | [10 empty] | 1 |  | Not Start | Munger
389 | SSS-386-1 | Begusarai | ukodkVh | e/; fo¦ky;] vdgk jfjvkSuk | [10 empty] | 1 |  |  | Munger
390 | SSS-387-1 | Begusarai | [kksnkoUriqj | mnwZ e/; foZ¦ky;] rq:Yykgiqj |  |  | 1 | [9 empty] | Not Start | Munger
391 | SSS-388-1 | Begusarai | NkSMkgh | e/; fo¦ky;] xhjhMhg |  |  |  |  | 1 | [8 empty] | Munger
392 | SSS-400-1 | Munger | tekyiqj | e/; fo¦ky;] bUnz:[k | [8 empty] | 1 |  |  |  |  | Munger
393 | SSS-401-1 | Munger | eqaxsj lnj | e/; fo¦ky;] pjkSu |  |  |  |  | 1 | [8 empty] | Munger
394 | SSS-402-1 | Munger | BsVh;k cEcj | e/; fo¦ky;] eksguiqj | [5 empty] | 1 | [7 empty] | Munger
395 | SSS-403-1 | Munger | /kjgjk | dU;k e/; fo¦ky;] f'kodqaM |  |  | 1 | [9 empty] | Land Problem | Munger
396 | SSS-445-1 | Jamaui | teqÃ | e/; fo¦ky;] cqdkj | [9 empty] | 1 |  |  |  | Munger
397 | SSS-445-2 | Jamaui | teqÃ | e/; fo¦ky;] lksuis | [10 empty] | 1 |  |  | Munger
398 | SSS-445-3 | Jamaui | teqÃ | e/; fo¦ky;] uohuxj | [10 empty] | 1 |  |  | Munger
399 | SSS-446-1 | Jamaui | cjgV | e/; fo¦ky;] xqxqyMhg |  |  |  |  | 1 | [8 empty] | Munger
400 | SSS-446-2 | Jamaui | cjgV | mRØfer e/; fo¦ky;] nsopd |  |  | 1 | [9 empty] | Land Problem | Munger
401 | SSS-447 (A) | Jamaui | [kSjk | e/; fo¦ky;] pkuuokj |  |  | 1 | [9 empty] | Not Start | Munger
402 | SSS-447 (B) | Jamaui | [kSjk | e/; fo¦ky;] Á/kkupd |  |  | 1 | [9 empty] | Not Start | Munger
403 | SSS-448-1 | Jamaui | lksuks | e/; fo¦ky;] cfV;k |  |  | 1 | [9 empty] | Land Problem | Munger
404 | SSS-448-2 | Jamaui | lksuks | mRØfer e/; fo¦ky;] jtkSy |  |  |  |  | 1 | [8 empty] | Munger
405 | SSS-449 (A) | Jamaui | >k>k | e/; fo¦ky;] fleqyryk |  |  | 1 | [9 empty] | Not Start | Munger
406 | SSS-449 (B) | Jamaui | >k>k | e/; fo¦ky;] ckftyk | [7 empty] | 1 | [5 empty] | Munger
407 | SSS-449 (C) | Jamaui | >k>k | e/; fo¦ky;] cq/kh[kj | [6 empty] | 1 | [6 empty] | Munger
408 | SSS-450 (A) | Jamaui | pdkÃ | e/; fo¦ky;] cksub |  |  |  |  | 1 | [8 empty] | Munger
409 | SSS-450 (B) | Jamaui | pdkÃ | e/; fo¦ky;] csUnzk |  |  | 1 | [9 empty] | Not Start | Munger
410 | SSS-467-1 | Lakhisarai | pkuu | mRØfer e/; fo¦ky;] dqanj |  |  | 1 | [9 empty] | Not Start | Munger
411 | SSS-468 (A) | Lakhisarai | lw;Zx<+k | e/; fo¦ky;] jlqyiqj |  |  | 1 | [9 empty] | Land Problem | Munger
412 | SSS-468 (B) | Lakhisarai | lw;Zx<+k | mRØfer e/; fo¦ky;] dfueksg |  | 1 | [10 empty] | TENDER PROCESS (NIT-38) 2015-16 | Munger
413 | SSS-469-1 | Shekhpura | 'ks[kksiqj | e/; fo¦ky;] i{kh | [10 empty] | 1 |  |  | Munger
414 | SSS-358-1 | Shekhpura | 'ks[kiqjk | e/; fo¦ky;] iSu | [11 empty] | 1 |  | Munger
415 | SSS-378-1 | Lakhisarai | fiifj;k | mRØfer e/; fo¦ky;] fiifj;k fn;kjk ¼fo¦ky; ds LokfeRo esa 50 fMlfey ijrh Hkwfe gksus ds 'krZ ds lkFk½ |  |  | 1 | [9 empty] | Not Start | Munger
416 | SSS-303-1 | Saharsa | cuek bVgjh | e/; fo¦ky;] ikjlcUuh | [5 empty] | 1 | [7 empty] | Kosi
417 | SSS-304-1 | Saharsa | dgjk | e/; fo¦ky;] lqfyaUnkckn | [11 empty] | 1 |  | Kosi
418 | SSS-305-1 | Saharsa | efg"kh | e/; fo¦ky;] dUnkgk | [7 empty] | 1 | [5 empty] | Kosi
419 | SSS-305-2 | Saharsa | efg"kh | e/; fo¦ky;] Fkuokj | [9 empty] | 1 |  |  |  | Kosi
420 | SSS-305-3 | Saharsa | efg"kh | e/; fo¦ky;] rsygj | [8 empty] | 1 |  |  |  |  | Kosi
421 | SSS-305-4 | Saharsa | efg"kh | e/; fo¦ky;] eaxjkSuh | [6 empty] | 1 | [6 empty] | Kosi
422 | SSS-306-1 | Saharsa | flejh | e/; fo¦ky;] osyokjk | [11 empty] | 1 |  | Kosi
423 | SSS-307-1 | Saharsa | flejh c[fr;kjiqj | e/; fo¦ky;] dFkMqej |  |  | 1 | [9 empty] | Land Not Available | Kosi
424 | SSS-308-1 | Saharsa | irj?kV | e/; fo¦ky;] fd'kuiqj | [9 empty] | 1 |  |  |  | Kosi
425 | SSS-308-2 | Saharsa | irj?kV | e/; fo¦ky;] iLrij | [10 empty] | 1 |  |  | Kosi
426 | SSS-309-1 | Saharsa | lksuo"kkZ | e/; fo¦ky;] xksnjke | [8 empty] | 1 |  |  |  |  | Kosi
427 | SSS-309-2 | Saharsa | lksuo"kkZ | e/; fo¦ky;] dksik | [8 empty] | 1 |  |  |  |  | Kosi
428 | SSS-309-3 | Saharsa | lksuo"kkZ | e/; fo¦ky;] [ktqjkgk | [8 empty] | 1 |  |  |  |  | Kosi
429 | SSS-309-4 | Saharsa | lksuo"kkZ | e/; fo¦ky;] vkjlh | [9 empty] | 1 |  |  |  | Kosi
430 | SSS-310-1 | Saharsa | lrj dVS;k | e/; fo¦ky;] fcgjk | [10 empty] | 1 |  |  | Kosi
431 | SSS-311-1 | Saharsa | ly[kqvk | e/; fo¦ky;] vyuh | [9 empty] | 1 |  |  |  | Kosi
432 | SSS-311-2 | Saharsa | ly[kqvk | e/; fo¦ky;] [kkspjnsok | [10 empty] | 1 |  |  | Kosi
433 | SSS-312-1 | Saharsa | uogêk | dU;k e/; fo¦ky;] dkfleiqj | [10 empty] | 1 |  |  | Kosi
434 | SSS-313-1 | Supaul | clariqj | e/; fo¦ky; cuSyhiÍh | [9 empty] | 1 |  |  |  | Kosi
435 | SSS-313-2 | Supaul | clariqj | e/; fo¦ky;] lenk | [9 empty] | 1 |  |  |  | Kosi
436 | SSS-313-3 | Supaul | clariqj | e/; fo¦ky;] fueZyh | [9 empty] | 1 |  |  |  | Kosi
437 | SSS-313-4 | Supaul | clariqj | e/; fo¦ky; <k<k | [9 empty] | 1 |  |  |  | Kosi
438 | SSS-313-5 | Supaul | clariqj | e/; fo¦ky; gn;uxj |  |  | 1 | [9 empty] | Work cancelled as per order no. 28 dt. 14.05.2015 | Kosi
439 | SSS-313-6 | Supaul | clariqj | e/; fo¦ky; iVsjok | [9 empty] | 1 |  |  |  | Kosi
440 | SSS-313-7 | Supaul | clariqj | e/; fo¦ky;] ijlk mnwZ | [9 empty] | 1 |  |  |  | Kosi
441 | SSS-313-8 | Supaul | clariqj | e/; fo¦ky;] fo'kuiqj pkS/kjh | [10 empty] | 1 |  |  | Kosi
442 | SSS-314-1 | Supaul | çrkixat | e/; fo¦ky;] Vsdquk | [10 empty] | 1 |  |  | Kosi
443 | SSS-315 (A) | Supaul | f=os.khxat | e/; fo¦ky;] xksugk | [9 empty] | 1 |  |  |  | Kosi
444 | SSS-315 (B) | Supaul | f=os.khxat | e/; fo¦ky; ijlkgh gkV | [9 empty] | 1 |  |  |  | Kosi
445 | SSS-315 (C) | Supaul | f=os.khxat | e/; fo¦ky;] ik.Ms;iÍh | [8 empty] | 1 |  |  |  |  | Kosi
446 | SSS-315 (D) | Supaul | f=os.khxat | e/; fo¦ky;] fejtkok | [9 empty] | 1 |  |  |  | Kosi
447 | SSS-315 (E) | Supaul | f=os.khxat | e/; fo¦ky;] ekSu | [6 empty] | 1 | [5 empty] | Not Start | Kosi
448 | SSS-316-1 | Supaul | fd'kuiqj | e/; fo¦ky;] deyngk | [8 empty] | 1 |  |  |  |  | Kosi
449 | SSS-317-1 | Supaul | fiijk | e/; fo¦ky;] clqyh | [10 empty] | 1 |  |  | Kosi
450 | SSS-318-1 | Supaul | jk?kksiqj | e/; fo¦ky;] jkeiqjdyk |  |  | 1 | [9 empty] | Land not available | Kosi
451 | SSS-318-2 | Supaul | jk?kksiqj | e/; fo¦ky; dkfj;kiÍh nsohiqj | [9 empty] | 1 |  |  |  | Kosi
452 | SSS-318-3 | Supaul | jk?kksiqj | e/; fo¦ky; gqykl | [10 empty] | 1 |  |  | Kosi
453 | SSS-318-4 | Supaul | jk?kksiqj | e/; fo¦ky; ckSjkgk] fgUnh |  |  | 1 | [9 empty] | Land not available | Kosi
454 | SSS-318-5 | Supaul | jk?kksiqj | e/; fo¦ky;] eksfriqj | [10 empty] | 1 |  | Work Stopped | Kosi
455 | SSS-318-6 | Supaul | jk?kksiqj | jkeukFk e/; fo¦ky;] xkSliqj | [10 empty] | 1 |  | work in progress | Kosi
456 | SSS-319-1 | Supaul | ljk;x<+ | e/; fo¦ky;] fiijk[kqnZ | [9 empty] | 1 |  |  | work in progress | Kosi
457 | SSS-319-2 | Supaul | ljk;x<+ | e/; fo¦ky;] >Yyk Mqejh | [9 empty] | 1 |  |  | work in progress | Kosi
458 | SSS-320-1 | Supaul | ljk;x<+& HkifV;kgh | e/; fo¦ky;] ykyxat | [11 empty] | 1 |  | Kosi
459 | SSS-321-1 | Supaul | lqikSy | e/; fo¦ky;] cSjks | [9 empty] | 1 |  |  |  | Kosi
460 | SSS-321-2 | Supaul | lqikSy | dU;k e/; fo¦ky;] ckM+k | [10 empty] | 1 |  |  | Kosi
461 | SSS-321-3 | Supaul | lqikSy | eqjyh euksgj e/; fo¦ky; cjSy | [10 empty] | 1 |  |  | Kosi
462 | SSS-322-1 | Supaul | Nkrkiqj | e/; fo¦ky;] jrulkj | [9 empty] | 1 |  |  |  | Kosi
463 | SSS-322-2 | Supaul | Nkrkiqj | e/; fo¦ky;] dVgh | [9 empty] | 1 |  |  |  | Kosi
464 | SSS-322-3 | Supaul | Nkrkiqj | e/; fo¦ky;] fxfj/kjiÍh | [10 empty] | 1 |  |  | Kosi
465 | SSS-322-4 | Supaul | Nkrkiqj | e/; fo¦ky;] egnhiqj | [9 empty] | 1 |  |  |  | Kosi
466 | SSS-322-5 | Supaul | Nkrkiqj | e/; fo¦ky;] 'ks[kVksyk y{ehfu;ka |  |  | 1 | [9 empty] | Deleted School For N.I.T-45 | Kosi
467 | SSS-323-1 | Madhepura | dqekj[kaM | e/; fo¦ky;] csykjh | [9 empty] | 1 |  |  |  | Kosi
468 | SSS-323-2 | Madhepura | dqekj[kaM | e/; fo¦ky;] j?kqfu;k | [9 empty] | 1 |  |  |  | Kosi
469 | SSS-323-3 | Madhepura | dqekj[kaM | e/; fo¦ky; jhrk | [9 empty] | 1 |  |  |  | Kosi
470 | SSS-323-4 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] [kWwVgk jtsS | [9 empty] | 1 |  |  |  | Kosi
471 | SSS-323-5 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] bljk;u xksB | [9 empty] | 1 |  |  |  | Kosi
472 | SSS-323-6 | Madhepura | dqekj[kaM | mRØfer e/; fo¦ky;] lqUnjuxj ¼v0tk0½ | [7 empty] | 1 | [5 empty] | Kosi
473 | SSS-324-1 | Madhepura | eqjyhxat | e/; fo¦ky; frudksuek |  |  |  | 1 | [8 empty] | Layout Done/Very poor in Progress | Kosi
474 | SSS-324-2 | Madhepura | eqjyhxat | mRØfe.r e/; fo¦ky;] jtuh fefYyd | [7 empty] | 1 |  |  |  |  | Very Poor work progress | Kosi
475 | SSS-325-1 | Madhepura | eqjyhxat | e/; fo¦ky;] jruiÍh] Hksykgh | [10 empty] | 1 |  |  | Kosi
476 | SSS-325-2 | Madhepura | eqjyhxat | e/; fo¦ky;] thrkiqj | [10 empty] | 1 |  |  | Kosi
477 | SSS-325-3 | Madhepura | eqjyhxat | e/; fo¦ky;] fnX?kh | [10 empty] | 1 |  |  | Kosi
478 | SSS-326 (A) | Madhepura | fcgkjhxat | e/; fo¦ky;] dBkSfr;k |  |  | 1 | [9 empty] | Not Start | Kosi
479 | SSS-326 (B) | Madhepura | fcgkjhxat | e/; fo¦ky;] y{ehiqj | [7 empty] | 1 |  |  |  |  | Not Start | Kosi
480 | SSS-326 (C) | Madhepura | fcgkjhxat | mRØfer e/; fo¦ky;] jkexat | [10 empty] | 1 |  | GF Roof level work in progress | Kosi
481 | SSS-327-1 | Madhepura | flags'oj | e/; fo¦ky;] rjgk MaMkjh | [10 empty] | 1 |  | Grill work in progress | Kosi
482 | SSS-327-2 | Madhepura | flags'oj | e/; fo¦ky;] lcSyk | [10 empty] | 1 |  | Grill work in progress | Kosi
483 | SSS-327-3 | Madhepura | flags'oj | mRØfer e/; fo¦ky;] ekuiqj | [10 empty] | 1 |  | Kota & Grill work in progress | Kosi
484 | SSS-327-4 | Madhepura | flags'oj | e/; fo¦ky;] iVksjh | [10 empty] | 1 |  | Kota, Grill & Plastering work in progress | Kosi
485 | SSS-328-1 | Madhepura | mnkfd'kquxat | dchj xaxk e/; fo¦ky;] chM+hj.kiky | [10 empty] | 1 |  |  | Kosi
486 | SSS-328-2 | Madhepura | mnkfd'kquxat | e/; fo¦ky;] eatkSjk | [10 empty] | 1 |  |  | Kosi
487 | SSS-329-1 | Madhepura | vkyeuxj | e/; fo¦ky;] fo"kiÍh | [10 empty] | 1 |  |  | Kosi
488 | SSS-329-2 | Madhepura | vkyeuxj | e/; fo¦ky;] gfjgjiqj ctjkgk | [9 empty] | 1 |  |  |  | Kosi
489 | SSS-329-3 | Madhepura | vkyeuxj | e/; fo¦ky;] difl;k | [7 empty] | 1 | [5 empty] | Kosi
490 | SSS-330-1 | Madhepura | XokyikM+k | e/; fo¦ky;] 'kkgiqj | [6 empty] | 1 | [5 empty] | Very Poor work in progress | Kosi
491 | SSS-330-2 | Madhepura | XokyikM+k | e/; fo¦ky;] VsekHksyk |  |  |  | 1 | [8 empty] | Layout Done/Very poor work in Progress | Kosi
492 | SSS-330-3 | Madhepura | XokyikM+k | e/; fo¦ky;] [kks[klh ckM+k] jkexat | [9 empty] | 1 |  |  |  | Kosi
493 | SSS-399-1 | Madhepura | eqjyhxat | e/; fo¦ky;] o``nkou | [9 empty] | 1 |  |  |  | Kosi
494 | SSS-399-2 | Madhepura | eqjyhxat | e/; fo¦ky;] ijekuUniqj | [9 empty] | 1 |  |  |  | Kosi
495 | SSS-439-1 | Supaul | lqikSy | e/; fo¦ky;] yksdgk | [6 empty] | 1 | [5 empty] | Work Stop/Slow Progress | Kosi
496 | SSS-439-2 | Supaul | lqikSy | ckfydk e/; fo¦ky;] lqikSy |  |  | 1 | [9 empty] | Land not available | Kosi
497 | SSS-440-1 | Supaul | fd'kuiqj | e/; fo¦ky;] czgecqyksd nqfc;kgh | [7 empty] | 1 |  |  |  |  | Layout Done | Kosi
498 | SSS-359-1 | Supaul | fueZyh | e/; fo¦ky;] csyk Vksyk] nkseqgku | [9 empty] | 1 |  |  | Roof comp. work in progress | Kosi
499 | SSS-360-1 | Supaul | lqikSy | e/; fo¦ky;] eYguh | [10 empty] | 1 |  | Plaster Work in progress | Kosi
500 | SSS-360-2 | Supaul | lqikSy | e/; fo¦ky;] clfoV~Vh | [6 empty] | 1 | [5 empty] | WORK IN PROGRESS | Kosi
501 | SSS-361(A) | Supaul | ljk;x<+ | e/; fo¦ky;] cSlk | [5 empty] | 1 | [7 empty] | Kosi
502 | SSS-361(B) | Supaul | ljk;x<+ | e/; fo¦ky;] eqjyh |  |  |  | 1 | [9 empty] | Kosi
503 | SSS-362(A) | Supaul | ejkSuk | e/; fo¦ky;] ejkSuk | [7 empty] | 1 | [5 empty] | Kosi
504 | SSS-362(B) | Supaul | ejkSuk | e/; fo¦ky;] ljkstk csyk | [9 empty] | 1 |  |  |  | Kosi
505 | SSS-363-1 | Supaul | fd'kuiqj | e/; fo¦ky;] rqykiV~Vh | [9 empty] | 1 |  |  |  | Kosi
506 | SSS-73-1 | Purnea | /kenkgk | ukScr yky eŒfoŒ dqdjkSu&2 | [10 empty] | 1 |  |  | Purnea
507 | SSS-73-2 | Purnea | /kenkgk | e/; fo¦ky;] jaxiqjk |  |  |  |  | 1 | [8 empty] | Purnea
508 | SSS-73-3 | Purnea | /kenkgk | vkŒ e/; fo¦ky;] uhjiqj | [5 empty] | 1 | [7 empty] | Purnea
509 | SSS-74-1 | Purnea | chŒ dksBh | e/; fo¦ky;] xfgyLFkku | [7 empty] | 1 | [5 empty] | Purnea
510 | SSS-74-2 | Purnea | chŒ dksBh | e/; fo¦ky;] fpduh iVjkgk | [6 empty] | 1 | [6 empty] | Purnea
511 | SSS-74-3 | Purnea | chŒ dksBh | e/; fo¦ky;] xqykcVksy eYyMhgk |  |  | 1 | [9 empty] | Not Start | Purnea
512 | SSS-74-4 | Purnea | chŒ dksBh | e/; fo¦ky;] Hkrlkjk | [9 empty] | 1 |  |  |  | Purnea
513 | SSS-74-5 | Purnea | chŒ dksBh | e/; fo¦ky;] lq[klsuk | [5 empty] | 1 | [7 empty] | Purnea
514 | SSS-74-6 | Purnea | chŒ dksBh | e/; fo¦ky;] fuifu;k¡ |  |  | 1 | [9 empty] | Not Start | Purnea
515 | SSS-74-7 | Purnea | chŒ dksBh | e/; fo¦ky;] lglkSy |  |  | 1 | [9 empty] | Not Start | Purnea
516 | SSS-75-1 | Purnea | cueu[kh | e/; fo¦ky;] xaxSyh |  |  |  |  | 1 | [8 empty] | Purnea
517 | SSS-75-2 | Purnea | cueu[kh | e/; fo¦ky;] ft;uxaat e/; |  |  |  | 1 | [9 empty] | Purnea
518 | SSS-75-3 | Purnea | cueu[kh | e/; fo¦ky;] dk>h |  |  |  |  | 1 | [8 empty] | Purnea
519 | SSS-75-4 | Purnea | cueu[kh | e/; fo¦ky;] gfjiqjeknh |  |  |  | 1 | [9 empty] | Purnea
520 | SSS-75-5 | Purnea | cueu[kh | e/; fo¦ky;] nsoksÙkj |  |  |  |  | 1 | [8 empty] | Purnea
521 | SSS-75-6 | Purnea | cueu[kh | e/; fo¦ky;] cksjkgh |  |  | 1 | [9 empty] | Not Start | Purnea
522 | SSS-75-7 | Purnea | cueu[kh | e/; fo¦ky;] jkeiqj fryd iwoZ |  |  |  | 1 | [9 empty] | Purnea
523 | SSS-76-1 | Purnea | iwf.kZ;k¡ iwoZ | e/; fo¦ky;] ykyxat |  |  | 1 | [9 empty] | Land not available | Purnea
524 | SSS-77-1 | Purnea | Jhuxj | vkŒ e/; fo¦ky;] glSyh [kqWÎh | [10 empty] | 1 |  |  | Purnea
525 | SSS-78-1 | Araria | dqlkZdkaVk | mRØfer e/; fo¦ky;] fcduh | [10 empty] | 1 |  |  | Purnea
526 | SSS-78-2 | Araria | dqlkZdkaVk | mRØfer e/; fo¦ky;] gksfj;k | [10 empty] | 1 |  |  | Purnea
527 | SSS-79-1 | Araria | fldVh | e/; fo¦ky;] Msfu;k | [10 empty] | 1 |  |  | Purnea
528 | SSS-80-1 | Araria | Hkjxkek | mRØfer e/; fo¦ky;] fljfl;k dyk | [9 empty] | 1 |  |  |  | Purnea
529 | SSS-81 (A) | Araria | iyklh | e/; fo¦ky;] neZxat | [7 empty] | 1 | [5 empty] | Purnea
530 | SSS-81 (B) | Araria | iyklh | e/; fo¦ky; Qqyljk | [7 empty] | 1 | [5 empty] | Purnea
531 | SSS-81 (C) | Araria | iyklh | e/; fo¦ky;] Mkyk | [10 empty] | 1 |  |  | Purnea
532 | SSS-82-1 | Araria | jkuhxat | e/; fo¦ky;] ykyiqj egqvk | [10 empty] | 1 |  |  | Purnea
533 | SSS-82-2 | Araria | jkuhxat | e/; fo¦ky;] cM+gkjk | [10 empty] | 1 |  |  | Purnea
534 | SSS-82-3 | Araria | jkuhxat | dU;k e/; fo¦ky;] iksfB;k | [7 empty] | 1 | [5 empty] | Purnea
535 | SSS-84-1 | Araria | jkuhxat | e/; fo¦ky;] ekStgk | [9 empty] | 1 |  |  |  | Purnea
536 | SSS-84-2 | Araria | jkuhxat | e/; fo¦ky;] e/kqyrk | [9 empty] | 1 |  |  |  | Purnea
537 | SSS-85-1 | Araria | Qkjfclxat | e/; fo¦ky;] ijokgk gfjtu | [8 empty] | 1 |  |  |  |  | Purnea
538 | SSS-85-2 | Araria | Qkjfclxat | e/; fo¦ky;] clxM+k jkeiqj | [9 empty] | 1 |  |  |  | Purnea
539 | SSS-85-3 | Araria | Qkjfclxat | e/; fo¦ky;] ckjk | [10 empty] | 1 |  |  | Purnea
540 | SSS-85-4 | Araria | Qkjfclxat | e/; fo¦ky;] HkkxijHkkgk | [9 empty] | 1 |  |  |  | Purnea
541 | SSS-85-5 | Araria | Qkjfclxat | e/; fo¦ky;] lekSy | [9 empty] | 1 |  |  |  | Purnea
542 | SSS-86-1 | Araria | tksdhgkV | e/; fo¦ky;] nkseksguk 2 | [10 empty] | 1 |  |  | Purnea
543 | SSS-87 (A) | Araria | ujirxat | e/; fo¦ky;] lkgscxat | [9 empty] | 1 |  |  |  | Purnea
544 | SSS-87 (B) | Araria | ujirxat | e/; fo¦ky;] MqejcUuk | [9 empty] | 1 |  |  |  | Purnea
545 | SSS-87 (C) | Araria | ujirxat | e/; fo¦ky;] x<+xkek |  |  |  | 1 | [9 empty] | Purnea
546 | SSS-87 (D) | Araria | ujirxat | e/; fo¦ky;] Hkokuhiqj | [7 empty] | 1 | [5 empty] | Purnea
547 | SSS-88 (A) | Araria | vjfj;k | e/; fo¦ky;] csyokr |  | 1 | [10 empty] | TENDER PROCESS (NIT-38/15-16) | Purnea
548 | SSS-88 (B) | Araria | vjfj;k | e/; fo¦ky;] dqfl;kjxkao | [10 empty] | 1 |  |  | Purnea
549 | SSS-88 (C) | Araria | vjfj;k | mRØfer e/; fo¦ky;] frjgqrfcêk |  | 1 | [10 empty] | TENDER PROCESS (NIT-38/15-16) | Purnea
550 | SSS-89-1 | Katihar | leSyh | e/; fo¦ky;] Nksgkj |  |  | 1 | [9 empty] | Land not avialable | Purnea
551 | SSS-89-2 | Katihar | leSyh | e/; fo¦ky;] eygfj;k | [10 empty] | 1 |  |  | Purnea
552 | SSS-90-1 | Katihar | dqlSyk | e/; fo¦ky;] dVfj;k | [9 empty] | 1 |  |  |  | Purnea
553 | SSS-90-2 | Katihar | dqlSyk | e/; fo¦ky;] tjykgh | [10 empty] | 1 |  |  | Purnea
554 | SSS-91-1 | Katihar | MaM[kksjk | e/; fo¦ky;] usigk | [10 empty] | 1 |  |  | Purnea
555 | SSS-91-2 | Katihar | MaM[kksjk | e/; fo¦ky;] fVdSyh | [10 empty] | 1 |  |  | Purnea
556 | SSS-92-1 | Kishanganj | Bkdqjxat | mRØfer e/; fo¦ky;] yks/kk | [5 empty] | 1 | [7 empty] | Purnea
557 | SSS-92-2 | Kishanganj | Bkdqjxat | e/; fo¦ky;] csgqynaxh |  |  |  |  | 1 | [8 empty] | Purnea
558 | SSS-92-3 | Kishanganj | Bkdqjxat | mRØfer e/; fo¦ky;] iapxkNh |  |  |  |  | 1 | [8 empty] | Purnea
559 | SSS-93 (A) | Kishanganj | cgknwjxat | mRØfer e/; fo¦ky;] ykSpk |  |  |  |  | 1 | [8 empty] | Purnea
560 | SSS-93 (B) | Kishanganj | cgknwjxat | mRØfer e/; fo¦ky;] eaMyVksyk Mksgj |  |  | 1 | [9 empty] | Double Scheme. | Purnea
561 | SSS-94-1 | Kishanganj | dkspk/kkeu | mRØfer e/; fo¦ky;] ckykuxj | [10 empty] | 1 |  |  | Purnea
562 | SSS-95-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] iuhlky | [11 empty] | 1 |  | Purnea
563 | SSS-96-1 | Kishanganj | iksfB;k | e/; fo¦ky;] tkyqpkSd |  |  | 1 | [9 empty] | Land not registered in the name of school | Purnea
564 | SSS-96-2 | Kishanganj | iksfB;k | mRØfer e/; fo¦ky;] lksukiqj |  |  | 1 | [9 empty] | Double Scheme | Purnea
565 | SSS-96-3 | Kishanganj | iksfB;k | e/; fo¦ky;] csyxkNh ohjiqj | [7 empty] | 1 | [5 empty] | Purnea
566 | SSS-97 (A) | Kishanganj | Vs<+kxkN | mRØfer e/; fo¦ky;] vkfnoklh Vksyk Hkksjgk | 1 | [11 empty] | Retender | Purnea
567 | SSS-97 (B) | Kishanganj | Vs<+kxkN | e/; fo¦ky;] Hkkstiqj] cyok |  | 1 | [10 empty] | TENDER PROCESS (NIT-38/15-16) | Purnea
568 | SSS-389-1 | Katihar | dks<+k | e/; fo¦ky; f'ko yky Vksyk pkWih | [9 empty] | 1 |  |  |  | Purnea
569 | SSS-390-1 | Katihar | Qydk | ckfydk e/; fo¦ky;] iksfB;k |  |  | 1 | [9 empty] | land not avaibale | Purnea
570 | SSS-404-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] gyeyk |  |  | 1 | [9 empty] | Not Start | Purnea
571 | SSS-405-1 | Kishanganj | dkspk/kkeu | mRØfer e/; fo¦ky;] lkgiqj | [5 empty] | 1 | [7 empty] | Purnea
572 | SSS-406-1 | Kishanganj | Vs<+kxkN | e/; fo¦ky;] >udh eqlgjh iqohZ |  | 1 | [10 empty] | TENDER PROCESS (NIT-38/15-16) | Purnea
573 | SSS-407-1 | Kishanganj | iksfFkok | e/; fo¦ky;] Mkeyckjh |  |  | 1 | [9 empty] | land not registered in the name of school | Purnea
574 | SSS-408-1 | Kishanganj | cgknqjxat | e/; fo¦ky;] HkkVkckjh | [9 empty] | 1 |  |  |  | Purnea
575 | SSS-416 (A) | Purnea | dlck | e/; fo¦ky;] lq/kqosyh | [9 empty] | 1 |  |  |  | Purnea
576 | SSS-416 (B) | Purnea | dlck | e/; fo¦ky;] ft;uxat] xqjgh |  |  | 1 | [9 empty] | Not Start | Purnea
577 | SSS-416 (C) | Purnea | dlck | e/; fo¦ky;] deyiqj] vejk] ykxu | [9 empty] | 1 |  |  |  | Purnea
578 | SSS-417-1 | Purnea | tykyx<+ | e/; fo¦ky;] lksjlksuh fctqfy;k | [9 empty] | 1 |  |  |  | Purnea
579 | SSS-418-1 | Purnea | ok;lh | e/; fo¦ky;] e<+ok | [9 empty] | 1 |  |  |  | Purnea
580 | SSS-419-1 | Purnea | Mx:vk | e/; fo¦ky;] egyckjh | [7 empty] | 1 | [5 empty] | Purnea
581 | SSS-420-1 | Purnea | iwf.kZ;k¡ ¼iwohZ½ | e/; fo¦ky;] csyok |  |  | 1 | [9 empty] | Not Start. land not registered in the name of school | Purnea
582 | SSS-421-1 | Purnea | Hkokuhiqj | e/; fo¦ky;] lksunhi | [9 empty] | 1 |  |  |  | Purnea
583 | SSS-455-1 | Araria | jkuhxat | mRØfer e/; fo¦ky;] Hkokuhuxj | [7 empty] | 1 |  |  |  |  | Not Start | Purnea
584 | SSS-456-1 | Araria | tksdhgkV | mRØfer e/; fo¦ky;] ckjk bLrkecjkj | [10 empty] | 1 |  |  | Purnea
585 | S.S.S-357(A) | Purnea | /kenkgk | e/; fo¦ky;] la>k?kkV |  |  | 1 | [9 empty] | double scheme, cancelled | Purnea
586 | S.S.S-357(B) | Purnea | /kenkgk | e/; fo¦ky;] ehjxat |  |  |  |  | 1 | [8 empty] | Purnea
587 | S.S.S-357(C) | Purnea | /kenkgk | e/; fo¦ky;] xaxkjke] nexkM+k |  |  |  |  | 1 | [8 empty] | Purnea
588 | SSS-35-1 | Sitamarhi | :uh lSniqj | e/; fo¦ky;] egs'kk 1 | [11 empty] | 1 | Inaugurated. Handover | Tirhut East
589 | SSS-35-2 | Sitamarhi | :uh lSniqj | e/; fo¦ky;] oxkgh | [11 empty] | 1 | Inaugurated. Handover | Tirhut East
590 | SSS-36 (A) | Sitamarhi | cFkukgk | e/; fo¦ky;] gjcsy |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
591 | SSS-36 (B) | Sitamarhi | cFkukgk | e/; fo¦ky;] jukSyh |  |  |  |  | 1 | [8 empty] | Tirhut East
592 | SSS-36 (C) | Sitamarhi | cFkukgk | e/; fo¦ky;] ;equk cjgh | [10 empty] | 1 |  |  | Tirhut East
593 | SSS-36 (D) | Sitamarhi | cFkukgk | e/; fo¦ky;] gjiqj cygk |  |  | 1 | [9 empty] | Not Start | Tirhut East
594 | SSS-37-1 | Sitamarhi | cktiÍh | e/; fo¦ky;] clsiqj | [10 empty] | 1 |  |  | Tirhut East
595 | SSS-38 (A) | Sitamarhi | csylaM | e/; fo¦ky;] Mqejk |  |  | 1 | [9 empty] | Land Problem To be solved within week | Tirhut East
596 | SSS-38 (B) | Sitamarhi | csylaM | e/; fo¦ky;] nekeh eB | [5 empty] | 1 | [6 empty] | Layout Just Start | Tirhut East
597 | SSS-38 (C) | Sitamarhi | csylaM | e/; fo¦ky;] e/kdkSy | [6 empty] | 1 | [5 empty] | excavation | Tirhut East
598 | SSS-39-1 | Sitamarhi | ijlkSuh | e/; fo¦ky;] /kuxsj | [11 empty] | 1 | Inaugurated. Handover | Tirhut East
599 | SSS-40 (A) | Sitamarhi | jhxk | e/; fo¦ky;] cqykdhiqj | [9 empty] | 1 |  |  |  | Tirhut East
600 | SSS-40 (B) | Sitamarhi | jhxk | e/; fo¦ky;] mljfg;k | [10 empty] | 1 |  |  | Tirhut East
601 | SSS-40 (C) | Sitamarhi | jhxk | e/; fo¦ky;] nks?kjk | [10 empty] | 1 |  |  | Tirhut East
602 | SSS-40 (D) | Sitamarhi | jhxk | e/; fo¦ky;] ikSlk |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
603 | SSS-41-1 | Sitamarhi | lksuo"kkZ | e/; fo¦ky;] clgh;k fgUnh | [10 empty] | 1 |  |  | Tirhut East
604 | SSS-41-2 | Sitamarhi | lksuo"kkZ | e/; fo¦ky;] ejik dpkSj | [10 empty] | 1 |  |  | Tirhut East
605 | SSS-42 (A) | Sitamarhi | lqjlaM | e/; fo¦ky;] dksfj;kgh |  |  | 1 | [9 empty] | Not Start | Tirhut East
606 | SSS-42 (B) | Sitamarhi | lqjlaM | e/; fo¦ky;] c[kjh | [10 empty] | 1 |  |  | Tirhut East
607 | SSS-43-1 | Muzaffarpur | canjk | mRØfer e/; fo¦ky;] ?kksljkek dksBh | [10 empty] | 1 |  |  | Tirhut East
608 | SSS-43-2 | Muzaffarpur | canjk | e/; fo¦ky;] cuxgh |  |  | 1 | [9 empty] | Not Start | Tirhut East
609 | SSS-43-3 | Muzaffarpur | canjk | e/; fo¦ky;] jruefu;k | [10 empty] | 1 |  |  | Tirhut East
610 | SSS-43-4 | Muzaffarpur | canjk | mRØfer e/; fo¦ky;] caxjk | [10 empty] | 1 |  |  | Tirhut East
611 | SSS-44-1 | Muzaffarpur | ckspgkW | e/; fo¦ky;] /kjHkjk | [9 empty] | 1 |  |  |  | Tirhut East
612 | SSS-45-1 | Muzaffarpur | ckspkgkW | e/; fo¦ky;] okftriqj | [10 empty] | 1 |  |  | Tirhut East
613 | SSS-45-2 | Muzaffarpur | ckspkgkW | e/; fo¦ky;] vrgj |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
614 | SSS-46 (A) | Muzaffarpur | dkWVh | e/; fo¦ky;] cjfj;k |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
615 | SSS-46 (B) | Muzaffarpur | dkWVh | e/; fo¦ky;] eqLrQkiqj |  |  | 1 | [9 empty] | Not Start | Tirhut East
616 | SSS-46 (C) | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] e/kqcu | [7 empty] | 1 | [5 empty] | Tirhut East
617 | SSS-46 (D) | Muzaffarpur | dkWVh | e/; fo¦ky;] diyiqjk |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
618 | SSS-46 (E) | Muzaffarpur | dkWVh | e/; fo¦ky;] ';keiqj Hkkstk | [10 empty] | 1 |  |  | Tirhut East
619 | SSS-47-1 | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] dksfB;kiqj | [5 empty] | 1 | [7 empty] | Tirhut East
620 | SSS-47-2 | Muzaffarpur | dkWVh | mRØfer e/; fo¦ky;] jruiqjk | [9 empty] | 1 |  |  | F .F ROOF SLAB CASTED | Tirhut East
621 | SSS-48-1 | Muzaffarpur | dq<+uh | e/; fo¦ky;] caxjk | [10 empty] | 1 |  | Plaster Done Flooring & Painting In Progress | Tirhut East
622 | SSS-48-2 | Muzaffarpur | dq<+uh | e/; fo¦ky;] rsfy;k | [10 empty] | 1 |  | Plaster Done Grill In Progress | Tirhut East
623 | SSS-48-3 | Muzaffarpur | dq<+uh | e/; fo¦ky;] djepUn jkeiqj cyjk | [10 empty] | 1 |  | Plaster Done Grill In Progress | Tirhut East
624 | SSS-48-4 | Muzaffarpur | dq<+uh | e/; fo¦ky;] Qrsgiqj | [10 empty] | 1 |  | Electric, Sanitary Painting In process | Tirhut East
625 | SSS-48-5 | Muzaffarpur | dq<+uh | e/; fo¦ky;] p<+qvk | [10 empty] | 1 |  | Flooring , Sanitary in Progress Plaster Done | Tirhut East
626 | SSS-48-6 | Muzaffarpur | dq<+uh | e/; fo¦ky;] fd'kquiqj] e/kqcu | [10 empty] | 1 |  | Internal & external Plaster Just Started | Tirhut East
627 | SSS-48-7 | Muzaffarpur | dq<+uh | e/; fo¦ky;] vej[k | [10 empty] | 1 |  | Plaster Done Grill , Sanitary In Progress | Tirhut East
628 | SSS-48-8 | Muzaffarpur | dq<+uh | e/; fo¦ky;] efjpk | [10 empty] | 1 |  | Plaster , Flooring Done Grill , Sanitary In Progress | Tirhut East
629 | SSS-48-9 | Muzaffarpur | dq<+uh | e/; fo¦ky;] flykSV | [10 empty] | 1 |  | Plaster , Flooring Done Painting , Sanitary In Progress | Tirhut East
630 | SSS-48-10 | Muzaffarpur | dq<+uh | e/; fo¦ky;] eksfjfuLd mnwZ | [10 empty] | 1 |  | Flooring , Putty in Progress Plaster Done | Tirhut East
631 | SSS-49-1 | Muzaffarpur | ehukiqj | e/; fo¦ky;] ed'kqniqj | [11 empty] | 1 | Fire fighting in progress | Tirhut East
632 | SSS-49-2 | Muzaffarpur | ehukiqj | e/; fo¦ky;] [kfjdk | [11 empty] | 1 | Fire fighting in progress | Tirhut East
633 | SSS-49-3 | Muzaffarpur | ehukiqj | e/; fo¦ky;] dksngfj;k | [11 empty] | 1 | Fire fighting in progress | Tirhut East
634 | SSS-49-4 | Muzaffarpur | ehukiqj | e/; fo¦ky;] flok;iÍh | [11 empty] | 1 | Fire fighting in progress | Tirhut East
635 | SSS-50-1 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] eksjlaMh | [10 empty] | 1 |  | Pianting electric plumbing Running Flooring Done | Tirhut East
636 | SSS-50-2 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] vatukdksV | [10 empty] | 1 |  | Brickwork above FFLL | Tirhut East
637 | SSS-50-3 | Muzaffarpur | eksrhiqj | e/; fo¦ky;] /kqeuxj | [10 empty] | 1 |  | Pianting electric plumbing GF Flooring Running | Tirhut East
638 | SSS-51-1 | Muzaffarpur | eMou | mRØfer e/; fo¦ky;] xolkjk | [11 empty] | 1 | Handover | Tirhut East
639 | SSS-51-2 | Muzaffarpur | eMou | mRØfer e/; fo¦ky;] cFkuk jke | [11 empty] | 1 | Inaugurated. Handover | Tirhut East
640 | SSS-52-1 | Muzaffarpur | eqjkSy | e/; fo¦ky;] cyqvk | [10 empty] | 1 |  |  | Tirhut East
641 | SSS-52-2 | Muzaffarpur | eqjkSy | e/; fo¦ky;] fVVjk fo'kquiqj | [10 empty] | 1 |  |  | Tirhut East
642 | SSS-52-3 | Muzaffarpur | eqjkSy | mRØfer e/; fo¦ky;] eq'kgjk ykSru |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
643 | SSS-52-4 | Muzaffarpur | eqjkSy | e/; fo¦ky;] fo¦k>kai | [9 empty] | 1 |  |  |  | Tirhut East
644 | SSS-53-1 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] idM+h LekbZy | [10 empty] | 1 |  |  | Tirhut East
645 | SSS-53-2 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] [kcjk |  |  | 1 | [9 empty] | Not Start | Tirhut East
646 | SSS-53-3 | Muzaffarpur | eq'kgjh | e/; fo¦ky;] izgykniqj | [10 empty] | 1 |  |  | Tirhut East
647 | SSS-53-4 | Muzaffarpur | eq'kgjh | mRØŒ e/; fo¦ky;] eqlgjh QkeZ |  |  | 1 | [9 empty] | L P Very small land available | Tirhut East
648 | SSS-54 (A) | Muzaffarpur | ik: | e/; fo¦ky;] jkepUnziqj | [10 empty] | 1 |  | Reinforcement In Proceess | Tirhut East
649 | SSS-54 (B) | Muzaffarpur | ik: | e/; fo¦ky;] lygiqj | 1 | [11 empty] | Retender | Tirhut East
650 | SSS-54 (C) | Muzaffarpur | ik: | e/; fo¦ky;] l[kgjk | [10 empty] | 1 |  |  | Tirhut East
651 | SSS-55-1 | Muzaffarpur | ldjk | e/; fo¦ky;] y{ehiqj | [10 empty] | 1 |  |  | Tirhut East
652 | SSS-56 (A) | Muzaffarpur | ldjk | mRØfer e/; fo¦ky;] egenkiqj cuokjh |  |  |  |  | 1 | [8 empty] | Tirhut East
653 | SSS-56 (B) | Muzaffarpur | ldjk | e/; fo¦ky;] eFkqjkiqj] xksoZ/kuiqj | 1 | [11 empty] | Retender | Tirhut East
654 | SSS-56 (C) | Muzaffarpur | ldjk | e/; fo¦ky;] xfu;kjh |  |  |  |  | 1 | [8 empty] | Tirhut East
655 | SSS-56 (D) | Muzaffarpur | ldjk | e/; fo¦ky;] eglh |  |  |  | 1 | [9 empty] | Tirhut East
656 | SSS-56 (E) | Muzaffarpur | ldjk | e/; fo¦ky;] flejh | [10 empty] | 1 |  |  | Tirhut East
657 | SSS-56 (F) | Muzaffarpur | ldjk | e/; fo¦ky;] gfjiqj d`".k |  |  | 1 | [9 empty] | Not Start | Tirhut East
658 | SSS-56 (G) | Muzaffarpur | ldjk | mRØfer e/; fo¦ky;] jfgeiqj jldk mnwZ |  |  | 1 | [9 empty] | Not Start | Tirhut East
659 | SSS-56 (H) | Muzaffarpur | ldjk | e/; fo¦ky;] ljeLriqj |  |  | 1 | [9 empty] | Not Start | Tirhut East
660 | SSS-56 (I) | Muzaffarpur | ldjk | e/; fo¦ky;] ipMgh | [9 empty] | 1 |  |  |  | Tirhut East
661 | SSS-57-1 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] oklqnso | [10 empty] | 1 |  |  | Tirhut East
662 | SSS-57-2 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] fo".kqiqj clSFkk | [11 empty] | 1 | Handover | Tirhut East
663 | SSS-57-3 | Muzaffarpur | ljS;k | mRØfer e/; fo¦ky;] xkSjhxkok | [11 empty] | 1 | Handover | Tirhut East
664 | SSS-57-4 | Muzaffarpur | ljS;k | e/; fo¦ky;] /kqch;kgh jked`".k | [10 empty] | 1 |  |  | Tirhut East
665 | SSS-58 (A) | Muzaffarpur | vkSjkb | e/; fo¦ky;] vkSjkb fgUnh | [5 empty] | 1 | [7 empty] | Tirhut East
666 | SSS-58 (B) | Muzaffarpur | vkSjkb | e/; fo¦ky;] 'kaHkqrk |  |  |  | 1 | [9 empty] | Tirhut East
667 | SSS-58 (C) | Muzaffarpur | vkSjkb | e/; fo¦ky;] HkjFkqvk | [7 empty] | 1 |  |  |  |  | GFRC | Tirhut East
668 | SSS-58 (D) | Muzaffarpur | vkSjkb | e/; fo¦ky;] HknbZ |  |  | 1 | [9 empty] | Not Start | Tirhut East
669 | SSS-58 (E) | Muzaffarpur | vkSjkb | e/; fo¦ky;] veukSj | [9 empty] | 1 |  |  |  | Tirhut East
670 | SSS-59-1 | Muzaffarpur | xk;?kkV | e/; fo¦ky; cq'kgjk eu | [8 empty] | 1 |  |  |  | Centering in progress | Tirhut East
671 | SSS-62-1 | Vaishali | egqvk | mRØfer e/; fo¦ky;] ijekuaniqj | [8 empty] | 1 |  |  |  |  | Tirhut East
672 | SSS-62-2 | Vaishali | egqvk | mRØfer e/; fo¦ky;] 'kkgiqj pdqEej | [10 empty] | 1 |  | Internal Plaster FF Done GF Running, Electric Plumbing Not Started | Tirhut East
673 | SSS-62-3 | Vaishali | egqvk | mRØfer e/; fo¦ky;] gjiqj xaxkjke |  |  | 1 | [9 empty] | No Land DEO Letter To drop | Tirhut East
674 | SSS-62-4 | Vaishali | egqvk | jktdh; e/; fo¦ky;] pdmej | [10 empty] | 1 |  | Internal Plaster Done External Plaster , Flooring, Plumbing Running | Tirhut East
675 | SSS-62-5 | Vaishali | egqvk | mRØfer e/; fo¦ky;] idM+h | [10 empty] | 1 |  | Plaster Done , Flooring & Plumbing Running | Tirhut East
676 | SSS-63-1 | Vaishali | egukj | e/; fo¦ky; etfyliqj | [10 empty] | 1 |  | Plaster Internal Done External In Progress | Tirhut East
677 | SSS-64-1 | Vaishali | ikrsiqj | e/; fo¦ky;] ckftriqj] drkZj | [10 empty] | 1 |  |  | Tirhut East
678 | SSS-64-2 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] eksgEeniqj tqEeu | [10 empty] | 1 |  | Roof Casted on 21.12.15 plaster Going On GF | Tirhut East
679 | SSS-64-3 | Vaishali | ikrsiqj | e/; fo¦ky;] igkM+iqj | [9 empty] | 1 |  |  |  | Tirhut East
680 | SSS-64-4 | Vaishali | ikrsiqj | e/; fo¦ky;] cfyxkWo | [9 empty] | 1 |  |  |  | Tirhut East
681 | SSS-65-1 | Vaishali | ikrsiqj | e/; fo¦ky;] cyk<+ | [9 empty] | 1 |  |  | Shuttering, electric, plaster running | Tirhut East
682 | SSS-65-2 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] ekSng pkrqj | [9 empty] | 1 |  |  | Shuttering, electric, running | Tirhut East
683 | SSS-65-3 | Vaishali | ikrsiqj | e/; fo¦ky;] ikrsiqj | [9 empty] | 1 |  |  | Brickwork above GF | Tirhut East
684 | SSS-65-4 | Vaishali | ikrsiqj | mRØfer e/; fo¦ky;] iLrkjk | [9 empty] | 1 |  |  |  | Tirhut East
685 | SSS-66-1 | Vaishali | iVs<+h csylj | mRØfer e/; fo¦ky;] csylj gkV | [10 empty] | 1 |  | Plaster Done Electric Plumbing Flooring Running | Tirhut East
686 | SSS-67-1 | Vaishali | jk?kksiqj | pdflaxkj e/; fo¦ky; |  |  | 1 | [9 empty] | Cancled | Tirhut East
687 | SSS-67-2 | Vaishali | jk?kksiqj | pkWniqjk e/; fo¦ky; |  |  | 1 | [9 empty] | Cancled | Tirhut East
688 | SSS-68-1 | Vaishali | jktkikdj | mRØfer e/; fo¦ky;] xkSliqj |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
689 | SSS-68-2 | Vaishali | jktkikdj | e/; fo¦ky; cu?kkM+k |  |  | 1 | [9 empty] | Land Dispute | Tirhut East
690 | SSS-69-1 | Vaishali | nsljh | mRØŒ e/; fo¦kŒ] eejstiqj dU;k | [10 empty] | 1 |  |  | Tirhut East
691 | SSS-69-2 | Vaishali | nsljh | e/; fo¦ky;] mQjkSy | [11 empty] | 1 | Handover | Tirhut East
692 | SSS-70-1 | Vaishali | oS'kkyh | e/; fo¦ky;] trdkSyh | [10 empty] | 1 |  | Painting External, Electrical Running Plumbing Flooring Done | Tirhut East
693 | SSS-70-2 | Vaishali | oS'kkyh | e/; fo¦ky;] cjfV;k e>kSyh | [10 empty] | 1 |  | Plaster Done , Plumbing Running | Tirhut East
694 | SSS-70-3 | Vaishali | oS'kkyh | e/; fo¦ky; pdvYgnkn ifjlj | [10 empty] | 1 |  |  | Tirhut East
695 | SSS-70-4 | Vaishali | oS'kkyh | mRØfer e/; fo¦ky;] gqlSuiqj | [10 empty] | 1 |  | Flooring, Running Plaster Done Electric Plumbing To Be Start | Tirhut East
696 | SSS-70-5 | Vaishali | oS'kkyh | mRØfer e/; fo¦ky;] [ktqvrk | [10 empty] | 1 |  | Plumbing, Painting Running Electrical Remaining | Tirhut East
697 | SSS-70-6 | Vaishali | oS'kkyh | e/; fo¦ky;] nkmnuxj ifjlj | [7 empty] | 1 |  |  |  |  | Brickwork & Plinth Band | Tirhut East
698 | SSS-71-1 | Vaishali | tUnkgk | mRØfer e/; fo¦ky;] lksgjFkh |  |  | 1 | [9 empty] | Land in Pokhar | Tirhut East
699 | SSS-72-1 | Vaishali | ykyxat | mRØfer e/; fo¦ky;] txksMhg gfjtu | [10 empty] | 1 |  | Brickwork running | Tirhut East
700 | SSS-437-1 | Sitamarhi | बाजपट्टी | jktdh; e/; fo¦ky;] fuekgh |  |  | 1 | [9 empty] | Not Start | Tirhut East
701 | SSS-438-1 | Sitamarhi | Mqejk | e/; fo¦ky;] rkjknsoh] jathriqj | [10 empty] | 1 |  | Flooring pcc & Grill running Plaster Done | Tirhut East
702 | SSS-01-1 | East Champaran | pfd;k | mRØfer e/; fo¦ky;] [kSjh teqfu;k |  |  | 1 | [9 empty] | Not Start | Tirhut West
703 | SSS-01-2 | East Champaran | pfd;k | mRØfer e/; fo¦ky;] cSfj;k |  |  | 1 | [9 empty] | Not Start | Tirhut West
704 | SSS-01-3 | East Champaran | pfd;k | e/; fo¦ky;] jkedj.k idM+h |  |  | 1 | [9 empty] | Not Start | Tirhut West
705 | SSS-02-1 | East Champaran | rqjdkSfy;k | e/; fo¦ky;] liêh | [10 empty] | 1 |  |  | Tirhut West
706 | SSS-02-2 | East Champaran | rqjdkSfy;k | mŒe/; fo¦kŒ Hkxr Vksyk] eksgCcr Nijk | [10 empty] | 1 |  |  | Tirhut West
707 | SSS-03-1 | East Champaran | dksVok | e/; fo¦ky;] jketh Vksyk | [11 empty] | 1 | Inaugurated. Handover | Tirhut West
708 | SSS-03-2 | East Champaran | dksVok | e/; fo¦ky;] iêh] ¼egkRek½ | [11 empty] | 1 | Inaugurated. Handover | Tirhut West
709 | SSS-03-3 | East Champaran | dksVok | mRØfer e/; fo¦ky;] djfj;k tkxhj | [11 empty] | 1 | Inaugurated. Handover | Tirhut West
710 | SSS-04-1 | East Champaran | idMh+n;ky | e/; fo¦ky;] jktsiqj] uoknk |  |  |  |  | 1 | [8 empty] | Tirhut West
711 | SSS-04-2 | East Champaran | idMh+n;ky | e/; fo¦ky;] /kukSth |  |  | 1 | [9 empty] | Not Start | Tirhut West
712 | SSS-05-1 | East Champaran | jkex<+ok | e/; fo¦ky;] eqjyk | [9 empty] | 1 |  |  |  | Tirhut West
713 | SSS-06-1 | East Champaran | gjlhnh | e/; fo¦ky;] mTtSu yksfg;kj | [8 empty] | 1 |  |  |  |  | Tirhut West
714 | SSS-07-1 | East Champaran | fiijkdksBh | mRØfer e/; fo¦ky;] gfFk;kgh | [10 empty] | 1 |  |  | Tirhut West
715 | SSS-08-1 | East Champaran | lqxkSyh | mRØfer e/; fo¦ky;] ';keiqj | [10 empty] | 1 |  |  | Tirhut West
716 | SSS-09-1 | East Champaran | esglh | e/; fo¦ky;] e>kSfy;k | [10 empty] | 1 |  |  | Tirhut West
717 | SSS-10-1 | East Champaran | fpjS;k | e/; fo¦ky;] gjkt?kkV | [11 empty] | 1 |  | Tirhut West
718 | SSS-11-1 | East Champaran | eksfrgkjh | mRØfer e/; fo¦ky;] ePNgkW | [10 empty] | 1 |  |  | Tirhut West
719 | SSS-12-1 | East Champaran | vjsjkt | e/; fo¦ky;] jeflfj;k¡ | [9 empty] | 1 |  |  |  | Tirhut West
720 | SSS-12-2 | East Champaran | vjsjkt | e/; fo¦ky;] >[kjk | [10 empty] | 1 |  |  | Tirhut West
721 | SSS-13-1 | East Champaran | <+kdk | e/; fo¦ky;] rsygkjk dyk | [10 empty] | 1 |  |  | Tirhut West
722 | SSS-14-1 | East Champaran | vnkiqj | mRØfer e/; fo¦ky;] cjok |  |  | 1 | [9 empty] | Not Start | Tirhut West
723 | SSS-14-2 | East Champaran | vnkiqj | mRØfer e/; fo¦ky;] y{ehiqj | [6 empty] | 1 | [6 empty] | Tirhut West
724 | SSS-14-3 | East Champaran | vnkiqj | e/; fo¦ky;] Hkokuhiqj cktkj | [11 empty] | 1 | Handover | Tirhut West
725 | SSS-15-1 | East Champaran | igkjiqj | e/; fo¦ky;] jk;djfj;k | [10 empty] | 1 |  |  | Tirhut West
726 | SSS-16-1 | East Champaran | Qsugjk | e/; fo¦ky;] fo'kquiqj clar | [11 empty] | 1 | Handover | Tirhut West
727 | SSS-16-2 | East Champaran | Qsugjk | e/; fo¦ky; Vsolk | [10 empty] | 1 |  |  | Tirhut West
728 | SSS-16-3 | East Champaran | Qsugjk | e/; fo¦ky;] ijlkSuh dksBh | [11 empty] | 1 | Handover | Tirhut West
729 | SSS-17-1 | East Champaran | jDlkSy | e/; fo¦ky;] tksfd;kjh | [11 empty] | 1 | Handover | Tirhut West
730 | SSS-18-1 | East Champaran | catfj;k | mRØfer e/; fo¦ky; xkSfj;k | [8 empty] | 1 |  |  |  |  | Tirhut West
731 | SSS-18-2 | East Champaran | catfj;k | mRØfer e/; fo¦ky;] vtxjok fgUnh |  |  | 1 | [9 empty] | Not Start. Converted to Group No USSS176 | Tirhut West
732 | SSS-19-1 | East Champaran | dY;k.kiqj | e/; fo¦ky;] j?kqukFkiqj | [11 empty] | 1 | Handover | Tirhut West
733 | SSS-20-1 | West Champaran | cxgk II | e/; fo¦ky;] egqvk | [10 empty] | 1 |  |  | Tirhut West
734 | SSS-20-2 | West Champaran | cxgk II | e/; fo¦ky;] cksjoy | [10 empty] | 1 |  |  | Tirhut West
735 | SSS-20-3 | West Champaran | cxgk II | mRØfer e/; fo¦ky; csyok p[kuh | [10 empty] | 1 |  |  | Tirhut West
736 | SSS-20-4 | West Champaran | cxgk II | mRØfer e/; fo¦ky;] ukSruok | [10 empty] | 1 |  |  | Tirhut West
737 | SSS-20-5 | West Champaran | cxgk II | e/; fo¦ky;] fl/kko | [10 empty] | 1 |  |  | Tirhut West
738 | SSS-20-6 | West Champaran | cxgk II | mRØfer e/; fo¦ky;] feJkSSyh | [10 empty] | 1 |  |  | Tirhut West
739 | SSS-20-7 | West Champaran | cxgk II | mRØfer e/; fo¦ky; jeofy;k | [10 empty] | 1 |  |  | Tirhut West
740 | SSS-20-8 | West Champaran | cxgk II | e/; fo¦ky;] egqvkj | [10 empty] | 1 |  |  | Tirhut West
741 | SSS-20-9 | West Champaran | cxgk II | mRØfer e/; fo¦ky; ePNjxkoka] | [10 empty] | 1 |  |  | Tirhut West
742 | SSS-21-1 | West Champaran | jkeuxj | mRØfer e/; fo¦ky; tqM+k idM+h | [11 empty] | 1 | Handover | Tirhut West
743 | SSS-21-2 | West Champaran | jkeuxj | mRØfer e/; fo¦ky; Mqejh | [11 empty] | 1 | Handover | Tirhut West
744 | SSS-21-3 | West Champaran | jkeuxj | e/; fo¦ky;] f'koiqj dkWyuh | [11 empty] | 1 | Handover | Tirhut West
745 | SSS-21-4 | West Champaran | jkeuxj | e/; fo¦ky;] chŒ,eŒlhŒ Qqydksy | [11 empty] | 1 | Handover | Tirhut West
746 | SSS-21-5 | West Champaran | jkeuxj | e/; fo¦ky;] Hkkoy | [11 empty] | 1 | Handover | Tirhut West
747 | SSS-21-6 | West Champaran | jkeuxj | e/; fo¦ky;] eqM+sjk | [11 empty] | 1 | Handover | Tirhut West
748 | SSS-21-7 | West Champaran | jkeuxj | e/; fo¦ky; cM+xks | [11 empty] | 1 | Handover | Tirhut West
749 | SSS-22-1 | West Champaran | ea>kSfy;k | mRØfer e/; fo¦ky; cSBfu;k | [10 empty] | 1 |  |  | Tirhut West
750 | SSS-22-2 | West Champaran | ea>kSfy;k | e/; fo¦ky;] efB;k o`r cSBfu;k | [10 empty] | 1 |  |  | Tirhut West
751 | SSS-22-3 | West Champaran | ea>kSfy;k | mRØfer e/; fo¦ky;] ijlk ckcw Vksyk | [10 empty] | 1 |  |  | Tirhut West
752 | SSS-22-4 | West Champaran | ea>kSfy;k | e/; fo¦ky;] lsuqvfj;k | [10 empty] | 1 |  |  | Tirhut West
753 | SSS-23 (A) | West Champaran | ujdfV;kxat | e/; fo¦ky;] euok ijlh | [9 empty] | 1 |  |  |  | Tirhut West
754 | SSS-23 (B) | West Champaran | ujdfV;kxat | mRØfer e/; fo¦ky;] cuofj;k | [7 empty] | 1 | [5 empty] | Tirhut West
755 | SSS-23 (C) | West Champaran | ujdfV;kxat | e/; fo¦ky;] jktiqj enku |  |  | 1 | [9 empty] | Not Start | Tirhut West
756 | SSS-23 (D) | West Champaran | ujdfV;kxat | mRØfer e/; fo¦ky; pxkSuk | [5 empty] | 1 | [7 empty] | Tirhut West
757 | SSS-24-1 | West Champaran | fHkrgk | e/; fo¦ky;] fcugh | [10 empty] | 1 |  |  | Tirhut West
758 | SSS-24-2 | West Champaran | fHkrgk | e/; fo¦ky;] [kSjok | [10 empty] | 1 |  |  | Tirhut West
759 | SSS-25 (A) | West Champaran | xkSukgk | e/; fo¦ky;] gkSnk Mqejk | [6 empty] | 1 | [6 empty] | Tirhut West
760 | SSS-25 (B) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] fHkfrgjok |  |  | 1 | [9 empty] | Not Start. Less Land | Tirhut West
761 | SSS-25 (C) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] MjkSy |  |  |  | 1 | [9 empty] | Tirhut West
762 | SSS-25 (D) | West Champaran | xkSukgk | mRØfer e/; fo¦ky;] c[kjh | [7 empty] | 1 | [5 empty] | Tirhut West
763 | SSS-25 (E) | West Champaran | xkSukgk | e/; fo¦ky;] /kekSjk | [10 empty] | 1 |  |  | Tirhut West
764 | SSS-26-1 | West Champaran | ;ksxkiÍh | mRØfer e/; fo¦ky;] cklksiÍh | [10 empty] | 1 |  |  | Tirhut West
765 | SSS-26-2 | West Champaran | ;ksxkiÍh | mRØfer e/; fo¦ky;] nqf/kvok | [6 empty] | 1 | [6 empty] | Tirhut West
766 | SSS-27-1 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] dksokgk | [10 empty] | 1 |  |  | Tirhut West
767 | SSS-27-2 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] ghjk ikdM+ | [10 empty] | 1 |  |  | Tirhut West
768 | SSS-27-3 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] HkjifV;k |  |  | 1 | [9 empty] | Land Problem | Tirhut West
769 | SSS-27-4 | West Champaran | puifV;k | mRØfer e/; fo¦ky; lcs;k dkyk | [10 empty] | 1 |  |  | Tirhut West
770 | SSS-27-5 | West Champaran | puifV;k | mRØfer e/; fo¦ky;] eksgNh lqXxk | [10 empty] | 1 |  |  | Tirhut West
771 | SSS-28-1 | West Champaran | cSfj;k | mŒe/; fo¦ky;] r/kokuUniqj y[kuh cktkj |  |  | 1 | [9 empty] | Not Start | Tirhut West
772 | SSS-28-2 | West Champaran | cSfj;k | mRØfer e/; fo¦ky; Kkuhth dk VksYkk |  |  | 1 | [9 empty] | Not Start | Tirhut West
773 | SSS-28-3 | West Champaran | cSfj;k | mRØfer e/; fo¦ky; cyqvk jeiqjok |  |  | 1 | [9 empty] | Not Start | Tirhut West
774 | SSS-29-1 | West Champaran | cxgk I | e/; fo¦ky;] pUnzgkW |  |  | 1 | [9 empty] | Not Start | Tirhut West
775 | SSS-30-1 | West Champaran | ukSru | mRØfer e/; fo¦ky; fl;kjgh | [9 empty] | 1 |  |  |  | Tirhut West
776 | SSS-30-2 | West Champaran | ukSru | vkn'kZ e/; fo¦ky;] eMqvkgkW | [11 empty] | 1 |  | Tirhut West
777 | SSS-30-3 | West Champaran | ukSru | e/; fo¦ky;] Mcfj;k | [9 empty] | 1 |  |  |  | Tirhut West
778 | SSS-30-4 | West Champaran | ukSru | mRØfer e/; fo¦ky;] f'kojktiqj |  |  | 1 | [9 empty] | Land Problem | Tirhut West
779 | SSS-30-5 | West Champaran | ukSru | mRØfer e/; fo¦ky;] y{ehiqj nqcksfy;k | [11 empty] | 1 |  | Tirhut West
780 | SSS-31-1 | West Champaran | csfr;k | e/; fo¦ky;] flaXkkNkij | [10 empty] | 1 |  |  | Tirhut West
781 | SSS-31-2 | West Champaran | csfr;k | e/; fo¦ky;] 'ks[kkSuk | [10 empty] | 1 |  |  | Tirhut West
782 | SSS-32-1 | West Champaran | fldVk | e/; fo¦ky;] flfjfl;k |  |  | 1 | [9 empty] | Not Start. Convert to SSSM21A | Tirhut West
783 | SSS-33-1 | West Champaran | e/kqcuh | e/; fo¦ky;] /kugk |  |  |  |  | 1 | [8 empty] | Tirhut West
784 | SSS-33-2 | West Champaran | e/kqcuh | mRØfer e/; fo¦ky;] rudwgk | [8 empty] | 1 |  |  |  |  | Tirhut West
785 | SSS-34-1 | West Champaran | ykSfj;k | e/; fo¦ky;] cudVok | [10 empty] | 1 |  |  | Tirhut West
786 | SSS-60 (A) | Sheohar | rfj;kuh | e/; fo¦ky;] vkSjk | [10 empty] | 1 |  |  | Tirhut West
787 | SSS-60 (B) | Sheohar | rfj;kuh | e/; fo¦ky;] eqlgjh |  |  |  | 1 | [9 empty] | Tirhut West
788 | SSS-60 (C) | Sheohar | rfj;kuh | e/; fo¦ky;] NrkSuh | [10 empty] | 1 |  |  | Tirhut West
789 | SSS-60 (D) | Sheohar | rfj;kuh | e/; fo¦ky;] exqjkgk |  |  | 1 | [9 empty] | Not Start | Tirhut West
790 | SSS-61-1 | Sheohar | f'kogj | e/; fo¦ky;] lqanjiqj [kjkSuk | [5 empty] | 1 | [7 empty] | Tirhut West
791 | SSS-409-1 | Sheohar | f'kogj | e/; fo¦ky; dVljh | [6 empty] | 1 | [5 empty] | Not Start | Tirhut West
792 | SSS-411-1 | West Champaran | cxgk &1 | e/; fo¦ky;] cjxk¡o | [9 empty] | 1 |  |  | Not Start | Tirhut West
793 | SSS-412-1 | West Champaran | cxgk &2 | mRØfer e/; fo¦ky;] Hksjhgjh dkWyksuh | [10 empty] | 1 |  |  | Tirhut West
794 | SSS-412-2 | West Champaran | cxgk &2 | mRØfer e/; fo¦ky;] ip:[kk |  |  |  | 1 | [9 empty] | Tirhut West
795 | SSS-413-1 | West Champaran | ujdfV;kxat | e/; fo¦ky;] vtqvk lqxkSyh | [10 empty] | 1 |  |  | Tirhut West
796 | SSS-414-1 | West Champaran | ykSfj;k | mRØfer e/; fo¦ky;] ejfg;k | [10 empty] | 1 |  |  | Tirhut West
797 | SSS-422-1 | East Champaran | jkex<+ok | mRØfer e/; fo¦ky;] f=os.kh | [11 empty] | 1 | Handover | Tirhut West
798 | SSS-423-1 | East Champaran | eksfrgkjh | jktdh; e/; fo¦ky;] dVgk |  |  | 1 | [9 empty] | Land not available | Tirhut West
799 | SSS-424-1 | East Champaran | laxzkeiqj | mRØfer e/; fo¦ky;] bUnzxkNh uohu | [11 empty] | 1 | Handover | Tirhut West
800 | SSS-425-1 | East Champaran | dksVok | mRØfer e/; fo¦ky;] VdVdkiqj | [10 empty] | 1 |  |  | Tirhut West
801 | SSS-426-1 | East Champaran | e/kqcu | jktdh; e/; fo¦ky;] catfj;k |  |  | 1 | [9 empty] | Not Start | Tirhut West
802 | SSS-427-1 | East Champaran | <+kdk | mRØfer e/; fo¦ky;] Qqyofj;k | [5 empty] | 1 | [7 empty] | Tirhut West
803 | SSS-427-2 | East Champaran |  | e/; fo¦ky;] ipidM+h |  |  | 1 | [9 empty] | Not Start | Tirhut West
804 | SSS-428-1 | East Champaran | ?kksM+klkgu | e/; fo¦ky;] iqjufg;k | [10 empty] | 1 |  |  | Tirhut West
805 | SSS-194-1 | Darbhanga | /ku';keiqj | e/; fo¦ky;] ?ku';keiqj | [7 empty] | 1 | [5 empty] | Darbhanga
806 | SSS-195 (A) | Darbhanga | dq0LFkku | mRØfer e/; fo¦ky;] mljh |  |  | 1 | [9 empty] | Not Start. LOA not issue | Darbhanga
807 | SSS-195 (B) | Darbhanga | dq0LFkku | e/; fo¦ky;] gjkSyh |  |  | 1 | [9 empty] | No Land | Darbhanga
808 | SSS-195 (C) | Darbhanga | dq0LFkku | e/; fo¦ky;] vkSjkgh | [10 empty] | 1 |  |  | Darbhanga
809 | SSS-195 (D) | Darbhanga | dq0LFkku | e/; fo¦ky;] gfjuxj | [10 empty] | 1 |  |  | Darbhanga
810 | SSS-195 (E) | Darbhanga | dq0LFkku | e/; fo¦ky;] ?kksjnkSj | [8 empty] | 1 |  |  |  |  | Darbhanga
811 | SSS-195 (F) | Darbhanga | dq0LFkku | e/; fo¦ky;] cjxkWo | [5 empty] | 1 | [7 empty] | Darbhanga
812 | SSS-196 (A) | Darbhanga | fcjkSy | e/; fo¦ky;] f'kouxj |  |  | 1 | [9 empty] | Land Problem | Darbhanga
813 | SSS-196 (B) | Darbhanga | fcjkSy | e/; fo¦ky;] vEckfctqfy;k | [9 empty] | 1 |  |  |  | Darbhanga
814 | SSS-196 (C) | Darbhanga | fcjkSy | e/; fo¦ky;] yngks | [7 empty] | 1 | [5 empty] | Darbhanga
815 | SSS-196 (D) | Darbhanga | fcjkSy | e/; fo¦ky;] lkgks | [7 empty] | 1 | [5 empty] | Darbhanga
816 | SSS-197-1 | Darbhanga | guqekuuxj | mRØfer e/; fo¦ky;] jkeiqj | [10 empty] | 1 |  |  | Darbhanga
817 | SSS-198 (A) | Madhubani | ?kks?kjMhgk | e/; fo¦ky;] fpduk | [10 empty] | 1 |  |  | Darbhanga
818 | SSS-198 (B) | Madhubani | ?kks?kjMhgk | mRØfer e/; fo¦ky;] dsoVuk | [9 empty] | 1 |  |  |  | Darbhanga
819 | SSS-198 (C) | Madhubani | ?kks?kjMhgk | mRØefr e/; fo¦ky;] clqvkjk |  |  | 1 | [9 empty] | stop by director education | Darbhanga
820 | SSS-199-1 | Madhubani | [kqVkSuk | e/; fo¦ky;] ugjh |  |  | 1 | [9 empty] | LAND PROBLEM | Darbhanga
821 | SSS-199-2 | Madhubani | [kqVkSuk | e/; fo¦ky;] va/kkjou |  |  |  |  | 1 | [8 empty] | Darbhanga
822 | SSS-199-3 | Madhubani | [kqVkSuk | e/; fo¦ky;] fldfV;kgh | [10 empty] | 1 |  |  | Darbhanga
823 | SSS-200 (A) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] dqlekj | [7 empty] | 1 | [5 empty] | Darbhanga
824 | SSS-200 (B) | Madhubani | [ktkSyh | e/; fo¦ky;] dlek ejkj | [10 empty] | 1 |  |  | Darbhanga
825 | SSS-200 (C) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] Nijk<+h |  |  |  |  | 1 | [8 empty] | Darbhanga
826 | SSS-200 (D) | Madhubani | [ktkSyh | e/; fo¦ky;] jlhniqj | [10 empty] | 1 |  |  | Darbhanga
827 | SSS-200 (E) | Madhubani | [ktkSyh | mRØfer e/; fo¦ky;] bujok iwjc | [10 empty] | 1 |  |  | Darbhanga
828 | SSS-201-1 | Madhubani | >a>kjiqj | e/; fo¦ky;] flejk | [10 empty] | 1 |  |  | Darbhanga
829 | SSS-201-2 | Madhubani | >a>kjiqj | e/; fo¦ky;] flM+[kfj;k | [5 empty] | 1 | [7 empty] | Darbhanga
830 | SSS-201-3 | Madhubani | >a>kjiqj | e/; fo¦ky;] vM+fj;k laxzke | [10 empty] | 1 |  |  | Darbhanga
831 | SSS-202-1 | Madhubani | ckcwcjgh | e/; fo¦ky;] dqYgfM+;k | [10 empty] | 1 |  |  | Darbhanga
832 | SSS-202-2 | Madhubani | ckcwcjgh | e/; fo¦ky;] fodze'ksj | [10 empty] | 1 |  |  | Darbhanga
833 | SSS-202-3 | Madhubani | ckcwcjgh | mRØfer e/; fo¦ky;] cyku'ksjiqjc | [6 empty] | 1 | [6 empty] | Darbhanga
834 | SSS-203 (A) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] dkSvkgk | [11 empty] | 1 |  | Darbhanga
835 | SSS-203 (B) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] pUnu dlsjk | [7 empty] | 1 | [5 empty] | Darbhanga
836 | SSS-203 (C) | Madhubani | cklksiÍh | e/; fo¦ky;] xkSluxj | [10 empty] | 1 |  |  | Darbhanga
837 | SSS-203 (D) | Madhubani | cklksiÍh | mRØfer e/; fo¦ky;] egFkkSaj |  |  | 1 | [9 empty] | Not Start. LOA not issue | Darbhanga
838 | SSS-203 (E) | Madhubani | cklksiÍh | e/; fo¦ky;] ?kksM+cadh | [7 empty] | 1 | [5 empty] | Darbhanga
839 | SSS-204-1 | Madhubani | csuhiêh | e/; fo¦ky;] tjSy | [11 empty] | 1 | Inaugurated | Darbhanga
840 | SSS-205 (A) | Madhubani | e/kokiqj | e/; fo¦ky;] iks[kjkSuh |  |  |  |  | 1 | [8 empty] | Darbhanga
841 | SSS-205 (B) | Madhubani | e/kokiqj | e/; fo¦ky;] fcgkjh | [9 empty] | 1 |  |  |  | Darbhanga
842 | SSS-205 (C) | Madhubani | e/kokiqj | mRØfer e/; fo¦ky;] vkSjk | [10 empty] | 1 |  |  | Darbhanga
843 | SSS-205 (D) | Madhubani | e/kokiqj | mRØfer e/; fo¦ky;] dsjck | [10 empty] | 1 |  |  | Darbhanga
844 | SSS-206 (A) | Madhubani | e/ksiqj | mRØfer e/; fo¦ky;] cdqvk | [5 empty] | 1 | [7 empty] | Darbhanga
845 | SSS-206 (B) | Madhubani | e/ksiqj | e/; fo¦ky;] }ky[k | [7 empty] | 1 | [5 empty] | Darbhanga
846 | SSS-206 (C) | Madhubani | e/ksiqj | e/; fo¦ky;] Vsaxjkgk | [7 empty] | 1 | [5 empty] | Darbhanga
847 | SSS-206 (D) | Madhubani | e/ksiqj | mRØfer e/; fo¦ky;] ijcyiqj | [6 empty] | 1 | [6 empty] | Darbhanga
848 | SSS-207-1 | Madhubani | gjyk[kh | mRØfer e/; fo¦ky;] jkeiqj | [11 empty] | 1 | Inaugurated | Darbhanga
849 | SSS-208-1 | Madhubani | iaMkSy | e/; fo¦ky;] HkkSj | [10 empty] | 1 |  |  | Darbhanga
850 | SSS-208-2 | Madhubani | iaMkSy | e/; fo¦ky;] uogFk | [10 empty] | 1 |  |  | Darbhanga
851 | SSS-208-3 | Madhubani | iaMkSy | e/; fo¦ky;] Hkokuhiqj | [10 empty] | 1 |  |  | Darbhanga
852 | SSS-209 (A) | Madhubani | jfgdk | mRØfer e/; fo¦ky;] ekM+j | [9 empty] | 1 |  |  |  | Darbhanga
853 | SSS-209 (B) | Madhubani | jfgdk | e/; fo¦ky;] cfy;k | [8 empty] | 1 |  |  |  |  | Darbhanga
854 | SSS-209 (C) | Madhubani | jfgdk | e/; fo¦ky;] btjk |  |  | 1 | [9 empty] | Not Start | Darbhanga
855 | SSS-209 (D) | Madhubani | jfgdk | mRØfer e/; fo¦ky;] uhek |  |  | 1 | [9 empty] | Land Problem | Darbhanga
856 | SSS-210 (A) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] jgh iwjc | [10 empty] | 1 |  |  | Darbhanga
857 | SSS-210 (B) | Madhubani | jktuxj | e/; fo¦ky;] lqxkSuk iks[kj v0tk0 |  |  |  |  | 1 | [8 empty] | Darbhanga
858 | SSS-210 (C) | Madhubani | jktuxj | e/; fo¦ky;] flejh |  |  | 1 | [9 empty] | LAND PROBLEM | Darbhanga
859 | SSS-210 (D) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] cM+gkjk | [10 empty] | 1 |  |  | Darbhanga
860 | SSS-210 (E) | Madhubani | jktuxj | e/; fo¦ky;] tgjeksgjk | [6 empty] | 1 | [6 empty] | Darbhanga
861 | SSS-210 (F) | Madhubani | jktuxj | mRØfer e/; fo¦ky;] jk/kksiqj | [7 empty] | 1 | [5 empty] | Darbhanga
862 | SSS-211 (A) | Madhubani | Qqyijkl | e/; fo¦ky;] vekStk | [8 empty] | 1 |  |  |  |  | Darbhanga
863 | SSS-211 (B) | Madhubani | Qqyijkl | e/; fo¦ky;] egFkkSj [kqnZ |  |  |  | 1 | [9 empty] | Darbhanga
864 | SSS-211 (C) | Madhubani | Qqyijkl | e/; fo¦ky;] fltkSfy;k] xksB | [10 empty] | 1 |  |  | Darbhanga
865 | SSS-212-1 | Madhubani | t;uxj | e/; fo¦ky;] dqok<+ | [10 empty] | 1 |  |  | Darbhanga
866 | SSS-213-1 | Madhubani | va/kjkBk<+h | e/; fo¦ky;] enuiêh | [10 empty] | 1 |  |  | Darbhanga
867 | SSS-214 (A) | Madhubani | ykSdgh | e/; fo¦ky;] HkjQksM+h | 1 | [11 empty] | Retender | Darbhanga
868 | SSS-214 (B) | Madhubani | ykSdgh | e/; fo¦ky;] ujsUnziqj | [5 empty] | 1 | [7 empty] | Darbhanga
869 | SSS-214 (C) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] dfj;kSr | [6 empty] | 1 | [6 empty] | Darbhanga
870 | SSS-214 (D) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] ujgh | [12 empty] | Not Start | Darbhanga
871 | SSS-214 (E) | Madhubani | ykSdgh | e/; fo¦ky;] csygh dpujok |  |  |  |  | 1 | [8 empty] | Darbhanga
872 | SSS-214 (F) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] dqjhou |  |  |  |  | 1 | [8 empty] | Darbhanga
873 | SSS-214 (G) | Madhubani | ykSdgh | mRØfer e/; fo¦ky;] Fk:vkjh | [5 empty] | 1 | [7 empty] | Darbhanga
874 | SSS-215 (A) | Madhubani | ynfu;k¡ | e/; fo¦ky;] ,dgjh |  | 1 | [10 empty] | Not Start | Darbhanga
875 | SSS-215 (B) | Madhubani | ynfu;k¡ | mRØfer e/; fo¦ky;] Hkxorhiqj |  | 1 | [10 empty] | Not Start | Darbhanga
876 | SSS-215 (C) | Madhubani | ynfu;k¡ | e/; fo¦ky;] dqej[kr |  |  | 1 | [9 empty] | Not Start | Darbhanga
877 | SSS-215 (D) | Madhubani | ynfu;k¡ | e/; fo¦ky;] fla/ki ijlkgh |  | 1 | [10 empty] | Not Start | Darbhanga
878 | SSS-216-1 | Samastipur | [kkuiqj | mRØfer e/; fo¦ky;] elhuk | [10 empty] | 1 |  |  | Darbhanga
879 | SSS-216-2 | Samastipur | [kkuiqj | mRØfer e/; fo¦ky;] cFkukgk |  |  | 1 | [9 empty] | LOW LAND MORE THAN 10 FEET | Darbhanga
880 | SSS-216-3 | Samastipur | [kkuiqj | e/; fo¦ky;] Hkkuiqj | [11 empty] | 1 |  | Darbhanga
881 | SSS-217-1 | Samastipur | dY;k.kiqj | mRØfer e/; fo¦ky;] /kksyh;kgh | [11 empty] | 1 |  | Darbhanga
882 | SSS-218-1 | Samastipur | eksjok | e/; fo¦ky; /keZiqj cans | [11 empty] | 1 |  | Darbhanga
883 | SSS-219-1 | Samastipur | f'kokthuxj | mRØfer e/; fo¦ky;] tUnkgk | [10 empty] | 1 |  |  | Darbhanga
884 | SSS-220-1 | Samastipur | flaf?k;k | mRØfer e/; fo¦ky;] ijgV | [10 empty] | 1 |  |  | Darbhanga
885 | SSS-220-2 | Samastipur | flaf?k;k | mRØfer e/; fo¦ky;] uhjiqj Hkjfj;k | [9 empty] | 1 |  |  |  | Darbhanga
886 | SSS-221-1 | Samastipur | fo¦kifruxj | vkn'kZ jktdh; e/; fo¦ky;] dkaWpk | [11 empty] | 1 |  | Darbhanga
887 | SSS-221-2 | Samastipur | fo¦kifruxj | mRØfer e/; fo¦ky;] lksBxkek | [11 empty] | 1 |  | Darbhanga
888 | SSS-222-1 | Samastipur | foHkqrhiqj | e/; fo¦ky;] dY;k.kiqj |  |  | 1 | [9 empty] | LOW LAND MORE THAN 10 FEET DEEP IN HALF PORTION AND ENCROCHMENT IN HALF PORTION | Darbhanga
889 | SSS-223-1 | Samastipur | gluiqj | mRØfer e/; fo¦ky;] nso?kk | [8 empty] | 1 |  |  |  |  | Darbhanga
890 | SSS-223-2 | Samastipur | gluiqj | mRØfer e/; fo¦ky;] gluiqj | [5 empty] | 1 | [7 empty] | Darbhanga
891 | SSS-224-1 | Samastipur | jksljk | mRØfer e/; fo¦ky;] xksfoUniqj | [6 empty] | 1 | [6 empty] | Darbhanga
892 | SSS-225 (A) | Samastipur | jksljk | mRØfer e/; fo¦ky;] egqyh | [10 empty] | 1 |  |  | Darbhanga
893 | SSS-225 (B) | Samastipur | jksljk | e/; fo¦ky;] iapxkek | [10 empty] | 1 |  |  | Darbhanga
894 | SSS-225 (C) | Samastipur | jksljk | mRØfer e/; fo¦ky;] HkVksVj |  |  |  |  | 1 | [8 empty] | Darbhanga
895 | SSS-225 (D) | Samastipur | jksljk | mRØfer e/; fo¦ky;] ihV/kknksHkh | [5 empty] | 1 | [7 empty] | Darbhanga
896 | SSS-226-1 | Samastipur | leLrhiqj | e/; fo¦ky;] 'kaHkqiêh | [11 empty] | 1 | Inaugurated | Darbhanga
897 | SSS-226-2 | Samastipur | leLrhiqj | mRØfer e/; fo¦ky;] ckftriqj | [11 empty] | 1 | Inaugurated | Darbhanga
898 | SSS-226-3 | Samastipur | leLrhiqj | e/; fo¦ky; /kwjy[k |  |  |  | 1 | [8 empty] | ENCROCHEMENT | Darbhanga
899 | SSS-226-4 | Samastipur | leLrhiqj | mRØfer e/; fo¦ky;] flykSV |  |  |  | 1 | [8 empty] | Land not available | Darbhanga
900 | SSS-227-1 | Samastipur | ljk;jatu | mRØfer e/; fo¦ky;] jlyiqj | [11 empty] | 1 | Inaugurated | Darbhanga
901 | SSS-227-2 | Samastipur | ljk;jatu | jktdh; e/; fo¦ky;] vf[r;kjiqj | [11 empty] | 1 | Inaugurated | Darbhanga
902 | SSS-227-3 | Samastipur | ljk;jatu | mRØfer e/; fo¦ky;] ukSvkpd | [11 empty] | 1 | Inaugurated | Darbhanga
903 | SSS-228-1 | Samastipur | mft;kjiqj | mRØfer e/; fo¦ky;] ijksfj;k | [7 empty] | 1 | [5 empty] | Darbhanga
904 | SSS-229-1 | Samastipur | okfj"kuxj | mRØfer e/; fo¦ky;] gtiqjok | [11 empty] | 1 | MODEL/ BUILDING TO BE DISMANTED | Darbhanga
905 | SSS-355-1 | Madhubani | y[kukSj | e/; fo¦ky;] nhi | [10 empty] | 1 |  |  | Darbhanga
906 | SSS-398-1 | Madhubani | Qqyijkl | e/; fo¦ky;] lqfj;kgh | [10 empty] | 1 |  |  | Darbhanga
907 | SSS-432-1 | Samastipur | ljk;jatu | e/; fo¦ky;] fe;kjh | [11 empty] | 1 |  | Darbhanga
908 | SSS-432-2 | Samastipur | ljk;jatu | e/; fo¦ky;] eqlkiqj | [10 empty] | 1 |  |  | Darbhanga
909 | SSS-433-1 | Samastipur | fo¦kifruxj | e/; fo¦ky;] 'ksjiqj | [11 empty] | 1 |  | Darbhanga
910 | SSS-434-1 | Samastipur | uks[kk | e/; fo¦ky;] xqukÃ] clgh | [11 empty] | 1 |  | Darbhanga
911 | SSS-435 (A) | Samastipur | foHkqfriqj | jktdh; e/; fo¦ky;] csylaMh] rkjk | [9 empty] | 1 |  |  |  | Darbhanga
912 | SSS-435 (B) | Samastipur | foHkqfriqj | e/; fo¦ky;] [kEgkj | [7 empty] | 1 | [5 empty] | Darbhanga
913 | SSS-435 (C) | Samastipur | foHkqfriqj | jktdh; e/; fo¦ky;] ekukjk; Vksyk | [10 empty] | 1 |  |  | Darbhanga
914 | SSS-436-1 | Samastipur | nyflag ljk; | jktdh; e/; fo¦ky;] dejkm | [7 empty] | 1 | [5 empty] | Darbhanga
915 | SSS-441-1 | Darbhanga | e.khxkNh | mRØfer e/; fo¦ky;] VVqvkj | [10 empty] | 1 |  |  | Darbhanga
916 | SSS-442-1 | Darbhanga | fcjkSy | mRØfer e/; fo¦ky;] fcjkSy vdcjiqj | [10 empty] | 1 |  |  | Darbhanga
917 | SSS-442-2 | Darbhanga | fcjkSy | mRØfer e/; fo¦ky;] lksuiqj i?kkjh | [10 empty] | 1 |  |  | Darbhanga
918 | SSS-443-1 | Darbhanga | ?ku';keiqj | mRØfer e/; fo¦ky;] t;nsoiV~~Vh | [9 empty] | 1 |  |  |  | Darbhanga
919 | SSS-444-1 | Darbhanga | tkys | e/; fo¦ky;] eqjSBk | [10 empty] | 1 |  |  | Darbhanga
920 | SSS-331-1 | Saran | tykyiqj | e/; fo¦ky;] dksBs;kW | [10 empty] | 1 |  |  | Saran
921 | SSS-331-2 | Saran | tykyiqj | e/; fo¦ky;] vuoy | [10 empty] | 1 |  |  | Saran
922 | SSS-332-1 | Saran | Nijk lnj | e/; fo¦ky;] clk<+h | [10 empty] | 1 |  |  | Saran
923 | SSS-332-2 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] me/kk | [10 empty] | 1 |  |  | Saran
924 | SSS-332-3 | Saran | Nijk lnj | dU;k e/; fo¦ky;] 'ksjiqj |  |  | 1 | [9 empty] | Land problem | Saran
925 | SSS-332-4 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] mn;iqjk | [10 empty] | 1 |  |  | Saran
926 | SSS-332-5 | Saran | Nijk lnj | mRØfer e/; fo¦ky;] cyou Vksyk | [10 empty] | 1 |  |  | Saran
927 | SSS-333-1 | Saran | rjS;k | e/; fo¦ky;] gjiqj Qfjnu | [10 empty] | 1 |  |  | Saran
928 | SSS-333-2 | Saran | rjS;k | e/; fo¦ky;] ljS;k clar | [10 empty] | 1 |  |  | Saran
929 | SSS-334-1 | Saran | ,dek | mRØfer e/; fo¦ky;] xkSliqj | [7 empty] | 1 | [5 empty] | Saran
930 | SSS-334-2 | Saran | ,dek | mRØfer e/; fo¦ky;] ukSru |  |  | 1 | [9 empty] | Land Problem | Saran
931 | SSS-335-1 | Saran | cfu;kiqj | mRØfer e/; fo¦ky;] djgh | [10 empty] | 1 |  |  | Saran
932 | SSS-335-2 | Saran | cfu;kiqj | mRØfer e/; fo¦ky;] fiiM+k | [7 empty] | 1 | [5 empty] | Saran
933 | SSS-336-1 | Saran | blqvkiqj | e/; fo¦ky;] fllokW | [10 empty] | 1 |  |  | Saran
934 | SSS-337-1 | Saran | ijlk | e/; fo¦ky;] HksYnh | [10 empty] | 1 |  |  | Saran
935 | SSS-338-1 | Saran | e<+kSjk | e/; fo¦ky;] eqckjdiqj |  |  |  |  | 1 | [8 empty] | Saran
936 | SSS-339-1 | Saran | Eklj[k | e/; fo¦ky;] xaMkeu | [11 empty] | 1 | Handover | Saran
937 | SSS-340-1 | Siwan | ip:[kh | mRØfer e/; fo¦ky;] MVokW | [11 empty] | 1 | Handover | Saran
938 | SSS-341-1 | Gopalganj | dVs;k | e/; fo¦ky;] /kjgjk esyk | [10 empty] | 1 |  |  | Saran
939 | SSS-341-2 | Gopalganj | dVs;k | mRØfer e/; fo¦ky;] idM+h Mhg | [10 empty] | 1 |  |  | Saran
940 | SSS-341-3 | Gopalganj | dVs;k | e/; fo¦ky;] jlkSrh | [10 empty] | 1 |  |  | Saran
941 | SSS-342-1 | Gopalganj | ek>kW | e/; fo¦ky;] rsfy;k ckW/k | [10 empty] | 1 |  |  | Saran
942 | SSS-342-2 | Gopalganj | ek>kW | mRØfer e/; fo¦ky;] e/kq ljs;k | [10 empty] | 1 |  |  | Saran
943 | SSS-343-1 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] lksucjlk | [9 empty] | 1 |  |  |  | Saran
944 | SSS-343-2 | Gopalganj | cjkSyh | e/; fo¦ky;] dY;k.kiqj | [11 empty] | 1 |  | Saran
945 | SSS-344-1 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] osylM | [10 empty] | 1 |  |  | Saran
946 | SSS-344-2 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] [ktqfj;k ckyd | [11 empty] | 1 |  | Saran
947 | SSS-344-3 | Gopalganj | cjkSyh | e/; fo¦ky;] ekMuiqj | [11 empty] | 1 |  | Saran
948 | SSS-344-4 | Gopalganj | cjkSyh | mRØfer e/; fo¦ky;] usmjh | [11 empty] | 1 |  | Saran
949 | SSS-345-1 | Gopalganj | Hkksjs | e/; fo¦ky;] dqlgkW | [10 empty] | 1 |  |  | Saran
950 | SSS-345-2 | Gopalganj | Hkksjs | mRØfer e/; fo¦ky;] egjknsmj | [7 empty] | 1 | [5 empty] | Saran
951 | SSS-345-3 | Gopalganj | Hkksjs | e/; fo¦ky;] ftxuk nwcs | [10 empty] | 1 |  |  | Saran
952 | SSS-345-4 | Gopalganj | Hkksjs | e/; fo¦ky;] fllbZ | [10 empty] | 1 |  |  | Saran
953 | SSS-345-5 | Gopalganj | Hkksjs | e/; fo¦ky;] ykehpkSj | [10 empty] | 1 |  |  | Saran
954 | SSS-345-6 | Gopalganj | Hkksjs | e/; fo¦ky;] oudVk tkxhjnkjh | [10 empty] | 1 |  |  | Saran
955 | SSS-346-1 | Gopalganj | fl/kofy;k | mRØfer e/; fo¦ky;] oq/klh | [10 empty] | 1 |  |  | Saran
956 | SSS-346-2 | Gopalganj | fl/kofy;k | mRØfer e/; fo¦ky;] cqfp;k | [10 empty] | 1 |  |  | Saran
957 | SSS-346-3 | Gopalganj | fl/kofy;k | e/; fo¦ky;] >>okW | [10 empty] | 1 |  |  | Saran
958 | SSS-347-1 | Gopalganj | oSdq.Biqj | mRØfer e/; fo¦ky;] calrNkijk | [10 empty] | 1 |  |  | Saran
959 | SSS-347-2 | Gopalganj | oSdq.Biqj | mRØfer e/; fo¦ky;] eMok | [7 empty] | 1 | [5 empty] | Saran
960 | SSS-348-1 | Gopalganj | dqpk;dksV | mRØfer e/; fo¦ky;] HkkstNkij | [10 empty] | 1 |  |  | Saran
961 | SSS-348-2 | Gopalganj | dqpk;dksV | e/; fo¦ky;] fo'kEHkjiqj | [10 empty] | 1 |  |  | Saran
962 | SSS-348-3 | Gopalganj | dqpk;dksV | mRØfer e/; fo¦ky;] o`rHkkeh Vksyk | [10 empty] | 1 |  |  | Saran
963 | SSS-349-1 | Gopalganj | xksikyxat | mRØfer e/; fo¦ky;] ekfudiqj dU;k | [11 empty] | 1 |  | Saran
964 | SSS-349-2 | Gopalganj | xksikyxat | mRØfer e/; fo¦ky;] [kSjfV;k jke uxj | [10 empty] | 1 |  |  | Saran
965 | SSS-350-1 | Gopalganj | gFkqvk | e/; fo¦ky;] lsejko | [11 empty] | 1 |  | Saran
966 | SSS-350-2 | Gopalganj | gFkqvk | e/; fo¦ky;] pSuiqj |  |  | 1 | [9 empty] | Land Problem | Saran
967 | SSS-351-1 | Gopalganj | Qqyofj;k | mRØfer e/; fo¦ky;] exgkW | [10 empty] | 1 |  |  | Saran
968 | SSS-351-2 | Gopalganj | Qqyofj;k | e/; fo¦ky;] ekMhiqj | [10 empty] | 1 |  |  | Saran
969 | SSS-351-3 | Gopalganj | Qqyofj;k | mRØfer e/; fo¦ky;] laxzkeiqj xksiky | [9 empty] | 1 |  |  |  | Saran
970 | SSS-352-1 | Gopalganj | mpdkxkWo | mRØfer e/; fo¦ky;] eqMk edlwniqj | [11 empty] | 1 | Handover | Saran
971 | SSS-353-1 | Gopalganj | iapnsojh | mRØfer e/; fo¦ky;] fiijgh | [10 empty] | 1 |  |  | Saran
972 | SSS-354-1 | Gopalganj | fot;hiqj | e/; fo¦ky;] lqvjgkW gadkjiqj | [10 empty] | 1 |  |  | Saran
973 | SSS-466-1 | Gopalganj | cSdq.Biqj ¼cjkSyh½ | mRØfer e/; fo¦ky;] cyjk |  |  | 1 | [9 empty] | Land Problem | Saran
974 | SSS-466-2 | Gopalganj | cSdq.Biqj | e/; fo¦ky;] eqatk c[kjh | [9 empty] | 1 |  |  |  | Saran
975 | SSS-364-1 | Siwan | njkSyh | mRØfer e/; fo¦ky;] d`".kkikyh |  |  | 1 | [9 empty] | land problem | Saran
976 | SSS-364-2 | Siwan | njkSyh | e/; fo¦ky;] pdjh | [10 empty] | 1 |  |  | Saran
977 | SSS-364-3 | Siwan | njkSyh | e/; fo¦ky;] gjukVkaM | [10 empty] | 1 |  |  | Saran
978 | SSS-364-4 | Siwan | njkSyh | mRØfer e/; fo¦ky;] Vmoka ijfl;ka | [10 empty] | 1 |  |  | Saran
979 | SSS-365(A) | Siwan | njkSank | mRØfer e/; fo¦ky;]cSnkiqj | [11 empty] | 1 | Handover | Saran
980 | SSS-365(B) | Siwan | njkSank | e/; fo¦ky;] idofy;k | [9 empty] | 1 |  |  |  | Saran
981 | SSS-366-1 | Siwan | egkjktxat | e/; fo¦ky;] ek/kksijq |  |  |  |  | 1 | [8 empty] | Saran
982 | SSS-367-1 | Siwan | Hkkxokuiqj gkV | mRØfer e/; fo¦ky;] ljk; iMkSyh | [10 empty] | 1 |  |  | Saran
983 | SSS-367-2 | Siwan | Hkkxokuiqj gkV | e/; fo¦ky;] tqvkQj | [9 empty] | 1 |  |  |  | Saran
984 | SSS-367-3 | Siwan | Hkkxokuiqj gkV | mRØfer e/; fo¦ky;][kfM+;k Vksyk | [11 empty] | 1 | Handover | Saran
985 | SSS-368-1 | Siwan | xqBuh | e/; fo¦ky;] cdqykjh | [10 empty] | 1 |  |  | Saran
986 | SSS-368-2 | Siwan | xqBuh | e/; fo¦ky;] rkyh | [9 empty] | 1 |  |  |  | Saran
987 | SSS-369(A) | Siwan | j?kqukFkiqj | e/; fo¦ky;] fn?koyh;k |  |  | 1 | [9 empty] | Land Problem | Saran
988 | SSS-369(B) | Siwan | j?kqukFkiqj | e/; fo¦ky;] uoknk | [7 empty] | 1 | [5 empty] | Saran
989 | SSS-370(A) | Siwan | fllou | e/; fo¦ky;] iM+jh | [9 empty] | 1 |  |  |  | Saran
990 | SSS-370(B) | Siwan | fllou | e/; fo¦ky;] Hkkxj | [10 empty] | 1 |  |  | Saran
991 | SSS-371-1 | Siwan | thjknsbZ | e/; fo¦ky;] latyiqj | [10 empty] | 1 |  |  | Saran
992 | SSS-372-1 | Siwan | xksjs;kdksBh | mRØfer e/; fo¦ky;] e>ofy;k | [11 empty] | 1 |  | Saran
993 | SSS-373-1 | Siwan | ip:[kh | e/; fo¦ky;] orZofy;k | [10 empty] | 1 |  |  | Saran
Total No. of Schools |  |  |  | 993 | 8 | 8 | 143 | 16 | 41 | 32 | 25 | 64 | 25 | 113 | 347 | 170
Note on E334: e/; fo¦ky; eksgCck*
Note on R646: LATE DUE TO CONTRACTOR