## GH-List
BSEIDC , Patna
Girls Hostel 2009-10 & 2010-11
S.N. | Division | Group No. |  | Session | Name of District | Name of Block | S.N. | Name of School | Sanction Order No. | Date of Commencement | Physical Status | [9 empty] | Remarks | Date of Completion | Total Completion Cost
[11 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
|  |  | UDISE No. | [11 empty] | LL | RL | LL | RL | [5 empty] | 6a | 6b | 6c | 7a | 7b (i) | 7b (ii) | 7b (iii) | 8 (i) | 8 (ii) | 8 (iii) | 9 | 10 | 11 | 12 | Division
1 | Patna East | GH-07-1 |  | 2009-10 | Bhojpur | Agioan | 1 | D.N.H.S., Gorpa | BMSP/INF-253/2012-867 | 25 SBD of 2013-14/ 10.05.2013 | [8 empty] | 1 |  |  |  | 8764831 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
2 | Patna East | GH-08-1 |  | 2009-10 | Bhojpur | Jagdishpur | 1 | Janta H.S., Baligaw | BMSP/INF-253/2012-867 | 22 SBD of 2013-14/ 24.04.2013 | [8 empty] | 1 |  |  |  | 10754003 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
3 | Patna East | GH-101-1 |  | 2010-11 | Patna | Daniyawa | 1 | Rajkiyakrit H.S., Sigariyawa | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 13865367 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
4 | Patna East | GH-101-2 |  | 2010-11 | Patna | Khusrupur | 2 | Rajkiyakrit Mahadeo H.S., Fatuwa, Khusrupur | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 13865367 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
5 | Patna East | GH-102-1 |  | 2010-11 | Patna | Bakhtiyarpur | 1 | Rajkiyakrit H.S., Salimpur | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | 1 | [9 empty] | Land not available. Site to be changed |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
6 | Patna East | GH-102-2 |  | 2010-11 | Patna | Belchhi | 2 | Rajkiyakrit H.S., Saksohar | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | [8 empty] | 1 |  | Flooring (DEBAR) |  | 11920568 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
7 | Patna East | GH-103-1 |  | 2010-11 | Patna | Paliganj | 1 | Rajkiyakrit H.S., Paliganj | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  |  |  | 15692151 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
8 | Patna East | GH-103-2 |  | 2010-11 | Patna | Dulhin Bazar | 2 | Banshidhari H.S., Bharatpura | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  | DEBAR |  | 12553720 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
9 | Patna East | GH-103-3 |  | 2010-11 | Patna | Bikram | 3 | Parwati H.S., Bikram | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 12553721 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
10 | Patna East | GH-104-1 |  | 2010-11 | Patna | Masaurih | 1 | Smt. Girija Kuwar H.S., Masaurih | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 | DEBAR | 08.03.17 | 11571154 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
11 | Patna East | GH-104-2 |  | 2010-11 | Patna | Punpun | 2 | Sahid Ramanand R. Govind H.S., Punpun | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 |  | 05.03.17 | 11571153 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
12 | Patna East | GH-105-1 |  | 2010-11 | Patna | Patna Sadar (Gramin) | 1 | Rajkiyakrit Mahanth Hanuman Sharan H.S.School,Rajapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | 1 | [9 empty] | Land Dispute |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
13 | Patna East | GH-105-2 |  | 2010-11 | Patna | Danapur | 2 | Baldeo Senior Secondary School, Danapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 | Inaugurated | 06.04.2016 | 13012761 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
14 | Patna East | GH-105-3 |  | 2010-11 | Patna | Maner | 3 | Rajkiyakrit H/S, Maner | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 |  | 24.12.16 | 13012761 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
15 | Patna East | GH-106-1 |  | 2010-11 | Patna | Mokama | 1 | Railway Aided H.S., Mokama | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
16 | Patna East | GH-106-2 |  | 2010-11 | Patna | Ghoswari | 2 | Rajkiyakrit H.S., Kumhra | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
17 | Patna East | GH-107-1 |  | 2010-11 | Patna | Barh | 1 | Rajkiyakrit Anugrah Narayan Singh Senior Secondary School, Barh | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14329584 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
18 | Patna East | GH-107-2 |  | 2010-11 | Patna | Pandarak | 2 | Laxmi Narayan Rajbanshi H.S., Dhibar | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | 1 | [9 empty] | Sufficient land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
19 | Patna East | GH-108-1 |  | 2010-11 | Patna | Naubatpur | 1 | Rajkiyakrit H.S., Amarpura | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
20 | Patna East | GH-108-2 |  | 2010-11 | Patna | Sampatchak | 2 | Gramin S.S.School Chakbairiya, Patna | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna East
21 | Patna West | GH-109-1 |  | 2010-11 | Buxar | Rajpur | 1 | H.S.Rajpur Compound | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 15.03.2017 | 11860829 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
22 | Patna West | GH-109-2 |  | 2010-11 | Buxar | Itarhi | 2 | H.S.Itarhi | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 28.02.2017 | 14826037 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
23 | Patna West | GH-109-3 |  | 2010-11 | Buxar | Nawanagar | 3 | H.S. Nawanagar | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 14826037 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
24 | Patna West | GH-110-1 |  | 2010-11 | Rohtas | Chenari | 1 | Middle School, Khurmabad, Chenari | 475 dated 03.11.2011 | 190 SBD of 2013-14/ 16.12.13 | [9 empty] | 1 | Inaugurated | 30.08.2015 | 13987787 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
25 | Patna West | GH-111-1 |  | 2010-11 | Kaimur | Durgawati | 1 | K.G.B.V. Compound | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14150475 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
26 | Patna West | GH-111-2 |  | 2010-11 | Kaimur | Adhaura | 2 | H. S. Adhaura | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 31.01.2017 | 14150474 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Patna West
27 | Magadh | GH-09-1 |  | 2009-10 | Aurangabad | Madanpur | 1 | Anugrah H.S., Madanpur | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662880 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
28 | Magadh | GH-09-2 |  | 2009-10 | Aurangabad | Rafiganj | 2 | R.B.R. High School, Rafiganj | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662879 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
29 | Magadh | GH-10-1 |  | 2009-10 | Aurangabad | Haspura | 1 | Haspura H.S., Haspura | BMSP/INF-253/2012-867 | 154 SBD of 2013-14 (21.11.13 ) | 1 | [9 empty] | Land Disput, due to court-stay order |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
30 | Magadh | GH-11-1 |  | 2009-10 | Aurangabad | Kutumba | 1 | Govt. Middle School, Kutumba | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Insufficient land |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
31 | Magadh | GH-112-1 |  | 2010-11 | Arwal | Karpi | 1 | High School, Karpi | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179021 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
32 | Magadh | GH-112-2 |  | 2010-11 | Arwal | Arwal | 2 | Balika High School, Arwal | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179020 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
33 | Magadh | GH-113-1 |  | 2010-11 | Jehanabad | Jehanabad | 1 | H.S., Jehanabad | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
34 | Magadh | GH-113-2 |  | 2010-11 | Jehanabad | Kako | 2 | H.S. Pali Bazar | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
35 | Magadh | GH-113-3 |  | 2010-11 | Jehanabad | Ghosi | 3 | H.S. Ghosi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
36 | Magadh | GH-114-1 |  | 2010-11 | Jehanabad | Ratni Faridpur | 1 | H.S. Dayalbagh, Nehalpur | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
37 | Magadh | GH-114-2 |  | 2010-11 | Jehanabad | Makhdumpur | 2 | S.S. Tehta | 475 dated 03.11.2011 |  | 1 | [9 empty] | Low land. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
38 | Magadh | GH-115-1 |  | 2010-11 | Jehanabad | Hulashganj | 1 | H.S. Hulashganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Local problem. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
39 | Magadh | GH-115-2 |  | 2010-11 | Jehanabad | Modanganj | 2 | D.N.H.S. Bandhuganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Started. EMD to be returned |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Magadh
40 | Bhagalpur | GH-30-1 |  | 2009-10 | Bhagalpur | Sanhoula | 1 | M.S., Arar, | BMSP/INF-253/2012-867 | 107 SBD OF 2012-13 ( 26.2.2013) | [9 empty] | 1 | Inaugurated | 2015-07-01 | 11639798 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
41 | Bhagalpur | GH-31-1 |  | 2009-10 | Bhagalpur | Nathnagar | 1 | M.S., Kanjhiya, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available. (DROP OUT ) |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
42 | Bhagalpur | GH-31-2 |  | 2009-10 | Bhagalpur | Narayanpur | 2 | M.S., Manoharpur, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 | 2016-02-28 | 13126242 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
43 | Bhagalpur | GH-32-1 |  | 2009-10 | Bhagalpur | Rangra Chowk | 1 | M.S, Rangra Chowk | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
44 | Bhagalpur | GH-32-2 |  | 2009-10 | Bhagalpur | Kharik Bazar | 2 | Basic Sch. Teldih* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
45 | Bhagalpur | GH-32-3 |  | 2009-10 | Bhagalpur | Ishmailpur | 3 | M.S.Parvatta* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
46 | Bhagalpur | GH-143-1 |  | 2010-11 | Bhagalpur | Pirpaiti | 1 | M.S, Simanpur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
47 | Bhagalpur | GH-143-2 |  | 2010-11 | Bhagalpur | Kahalgaon | 2 | R. S. H.S, Rampur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
48 | Bhagalpur | GH-143-3 |  | 2010-11 | Bhagalpur | Sabour | 3 | H.S, Mamalkha | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
49 | Bhagalpur | GH-144-1 |  | 2010-11 | Bhagalpur | Goradih | 1 | M.S, Goradih | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
50 | Bhagalpur | GH-144-2 |  | 2010-11 | Bhagalpur | Sultanganj | 2 | K.N.S.M.H.S, Sultanganj | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
51 | Bhagalpur | GH-145-1 |  | 2010-11 | Bhagalpur | Bihpur | 1 | H.S, Jairampur | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
52 | Bhagalpur | GH-145-2 |  | 2010-11 | Bhagalpur | Naugachhia | 2 | H.S, Sahu Parbatta | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
53 | Bhagalpur | GH-146-1 |  | 2010-11 | Bhagalpur | Gopalpur | 1 | Proj. Girls H.S, Saidpur | 475 dated 03.11.2011 | 37 SBD OF 2013-14 (10.6.2013) | [9 empty] | 1 | Inaugurated | 2014-02-08 | 14473004 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
54 | Bhagalpur | GH-147-1 |  | 2010-11 | Bhagalpur | Shahkund | 1 | Proj. H.S, Shahkund | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395969 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
55 | Bhagalpur | GH-147-2 |  | 2010-11 | Bhagalpur | Jagdishpur | 2 | Proj. Girls H.S, Jagdishpur | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395970 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
56 | Bhagalpur | GH-148-1 |  | 2010-11 | Banka | Rajaoun | 1 | R.H.S, Douni | 475 dated 03.11.2011 | 66 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2015-06-07 | 13168871 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Bhagalpur
57 | Munger | GH-33-1 |  | 2009-10 | Munger | Haveli Kharagpur | 1 | Govt.+2 H.S., Haweli Kharagpur | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459708 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
58 | Munger | GH-33-2 |  | 2009-10 | Munger | Dharahara | 2 | K.R.S.K.H H.S., Dharahra | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
59 | Munger | GH-33-3 |  | 2009-10 | Munger | Tetiabamber | 3 | Jagannath H.S Tetia Bamber | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459707 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
60 | Munger | GH-34-1 |  | 2009-10 | Lakhisarai | Surajgarha | 1 | Project K. K.H., Surajgarha | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
61 | Munger | GH-34-2 |  | 2009-10 | Lakhisarai | Pipariya | 2 | M.M.P. H.S., Walipur | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11286461 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
62 | Munger | GH-35-1 |  | 2009-10 | Lakhisarai | Halsi | 1 | High School, Halsi | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [8 empty] | 1 |  |  |  | 10390217 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
63 | Munger | GH-35-2 |  | 2009-10 | Lakhisarai | Ramgarh Chowk | 2 | D.M H.S., Sharma | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [6 empty] | 1 | [5 empty] | 3896331 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
64 | Munger | GH-149-1 |  | 2010-11 | Munger | Tarapur | 1 | M.S, Tarapur | 475 dated 03.11.2011 | 104 SBD 2013-14 (11.9.2013) | [6 empty] | 1 | [5 empty] | 6098553 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
65 | Munger | GH-150-1 |  | 2010-11 | Jamui | Khaira | 1 | Project G.H.S, Khaira | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-09-20 | 11102710 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
66 | Munger | GH-150-2 |  | 2010-11 | Jamui | Sono | 2 | Project H.S, Sona | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-02-25 | 11102709 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
67 | Munger | GH-151-1 |  | 2010-11 | Lakhisarai | Lakhisarai | 1 | M.V.M H.S.Nayatola, Lakhisarai | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. PPO R.M.S.A |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
68 | Munger | GH-151-2 |  | 2010-11 | Lakhisarai | Barahiya | 2 | S.R.R.S Girls H.S, Barahiya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. Land problem |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Munger
69 | Koshi | GH-21-1 |  | 2009-10 | Supaul | Raghopur | 1 | M.S., Kajayan, Raghopur | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265108 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
70 | Koshi | GH-21-2 |  | 2009-10 | Supaul | Pratapganj | 2 | Public H.S., Pratapganj | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265107 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
71 | Koshi | GH-141-1 |  | 2010-11 | Saharsa | Kahra | 1 | Govt. Girls H. S, Saharsa | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
72 | Koshi | GH-141-2 |  | 2010-11 | Saharsa | Saur Bazar | 2 | Gajadhar Sahu H.S, Saur Bazar | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
73 | Koshi | GH-142-1 |  | 2010-11 | Saharsa | Salkhua | 1 | H.S, Salkhua | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | 1 | [9 empty] | Land not available. |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
74 | Koshi | GH-142-2 |  | 2010-11 | Saharsa | Sonbarsa | 2 | Sir Hariballabh Inst. | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | [9 empty] | 1 |  |  | 12885961 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Kosi
75 | Purnea | GH-22-1 |  | 2009-10 | Purnea | Dhamdaha | 1 | H.S., Dhamdaha | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
76 | Purnea | GH-22-2 |  | 2009-10 | Purnea | Rupouli | 2 | Project Girl's H.S., Rupouli | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
77 | Purnea | GH-22-3 |  | 2009-10 | Purnea | Bhawanipur | 3 | H.S., Bhawanipur | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742809 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
78 | Purnea | GH-23-1 |  | 2009-10 | Purnea | Barharakothi | 1 | Shyama H.S., Bhatotar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679264 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
79 | Purnea | GH-23-2 |  | 2009-10 | Purnea | K. Nagar | 2 | H.S., Champanagar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679263 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
80 | Purnea | GH-24-1 |  | 2009-10 | Purnea | Purnia East | 1 | Proj. Girl's H.S., Ranipatra | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
81 | Purnea | GH-24-2 |  | 2009-10 | Purnea | Jalalgarh | 2 | N.D Rungata H.S., Jalalgarh | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509025 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
82 | Purnea | GH-24-3 |  | 2009-10 | Purnea | Kasba | 3 | Kalanand H.S., Garabnaili | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509024 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
83 | Purnea | GH-25-1 |  | 2009-10 | Purnea | Dagarua | 1 | Abul Kalam H.S., Ichalo | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start. Agreement not done |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
84 | Purnea | GH-25-2 |  | 2009-10 | Purnea | Srinagar | 2 | Govt. S.S., Srinagar | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
85 | Purnea | GH-25-3 |  | 2009-10 | Purnea | Baisi | 3 | Proj. Girl's School Baisi | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
86 | Purnea | GH-26-1 |  | 2009-10 | Purnea | Baisa | 1 | H.S., Rauta | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541239 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
87 | Purnea | GH-26-2 |  | 2009-10 | Purnea | Amour | 2 | Project Girl's School, Amour | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541238 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
88 | Purnea | GH-27-1 |  | 2009-10 | Katihar | Kadwa | 1 | N.C.C. Smarak H.S Balia Belon | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 13455545 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
89 | Purnea | GH-27-2 |  | 2009-10 | Katihar | Balrampur | 2 | S.S., High School, Telta | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2016-01-15 | 13455546 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
90 | Purnea | GH-27-3 |  | 2009-10 | Katihar | Sameli | 3 | D.G.H.S., Krishna Nagar | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2015-02-04 | 13455545 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
91 | Purnea | GH-28-1 |  | 2009-10 | Katihar | Manihari | 1 | B.P.S.P.H.S., Manihari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 14782767 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
92 | Purnea | GH-28-2 |  | 2009-10 | Katihar | Azamnagar | 2 | H.S., Salmari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-11-28 | 14782767 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
93 | Purnea | GH-28-3 |  | 2009-10 | Katihar | Pranpur | 3 | M.S., Bastol | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | 1 | [9 empty] | Land Dispute |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
94 | Purnea | GH-29-1 |  | 2009-10 | Katihar | Falka | 1 | B.S.M.High School, Pothiya | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
95 | Purnea | GH-29-2 |  | 2009-10 | Katihar | Kursela | 2 | Sampat Raj Devi Girl's H.S., Kursela | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Purnea
96 | Tirhut East | GH-01-1 |  | 2009-10 | Sitamarhi | Parihar | 1 | S.G.H.S., Parihar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
97 | Tirhut East | GH-01-2 |  | 2009-10 | Sitamarhi | Sonbarsa | 2 | H.S., Bhutahi | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
98 | Tirhut East | GH-01-3 |  | 2009-10 | Sitamarhi | Bathnaha | 3 | H.S., Yogibana Bazar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
99 | Tirhut East | GH-02-1 |  | 2009-10 | Sitamarhi | Parsauni | 1 | H.S., Parsauni Chowk | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
100 | Tirhut East | GH-02-2 |  | 2009-10 | Sitamarhi | Riga | 2 | H.S., Rewasi | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022030 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
101 | Tirhut East | GH-02-3 |  | 2009-10 | Sitamarhi | Belsand | 3 | H.S., Belsand | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
102 | Tirhut East | GH-3-1 |  | 2009-10 | Sitamarhi | Bairgania | 1 | Jaurimal H.S., Bairgania | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP (Letter given)/13/12/2014 |  | 4751468 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
103 | Tirhut East | GH-3-2 |  | 2009-10 | Sitamarhi | Suppi | 2 | H.S., Suppi | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/12-04-2015 |  | 4751467 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
104 | Tirhut East | GH-3-3 |  | 2009-10 | Sitamarhi | Majarganj | 3 | H.S., Majarganj | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/5-12-2014 |  | 4751468 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
105 | Tirhut East | GH-4-1 |  | 2009-10 | Sitamarhi | Sursand | 1 | Saryu H.S., Sursand | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [8 empty] | 1 |  |  |  | 13056903 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
106 | Tirhut East | GH-4-2 |  | 2009-10 | Sitamarhi | Pupri | 2 | Proj. H.S., Pupri | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | 1 | [9 empty] | small land |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
107 | Tirhut East | GH-4-3 |  | 2009-10 | Sitamarhi | Choraut | 3 | H.S., Choraut | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [9 empty] | 1 |  |  | 16321128 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
108 | Tirhut East | GH-5-1 |  | 2009-10 | Sitamarhi | Bajpatti | 1 | H.S., Bajpatti | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
109 | Tirhut East | GH-5-2 |  | 2009-10 | Sitamarhi | Nanpur | 2 | H.S., Janipur | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
110 | Tirhut East | GH-5-3 |  | 2009-10 | Sitamarhi | Bokhra | 3 | H.S., Kharka | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
111 | Tirhut East | GH-6-1 |  | 2009-10 | Sitamarhi | Dumra | 1 | K.G.H.S., Dumra | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673297 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
112 | Tirhut East | GH-6-2 |  | 2009-10 | Sitamarhi | Runni saidpur | 2 | H.S., Morsand | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673296 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
113 | Tirhut East | GH-121-1 |  | 2010-11 | Vaishali | Rajapakar | 1 | H.S.,Rajapakar | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | 1 | [11 empty] | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
114 | Tirhut East | GH-121-2 |  | 2010-11 | Vaishali | Mahua | 2 | M.S. Singhara | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | [9 empty] | 1 | Inaugurated | 18.5.15 | 14587944 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
115 | Tirhut East | GH-122-1 |  | 2010-11 | Vaishali | Raghopur | 1 | B.S.J.S.H.S.Fatehpur, Vaishali | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Land problem |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
116 | Tirhut East | GH-122-2 |  | 2010-11 | Vaishali | Bidupur | 2 | S.S.V.M.H.S., Ramdauli | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | [9 empty] | 1 | Inaugurated | 28.4.16 | 13567869 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
117 | Tirhut East | GH-122-3 |  | 2010-11 | Vaishali | Deshri | 3 | H.S. Bhataulla | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Dismantling |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
118 | Tirhut East | GH-123-1 |  | 2010-11 | Vaishali | Patepur | 1 | S.R.C.H.S.,Patepur, Vaishali | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 13868106 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
119 | Tirhut East | GH-123-2 |  | 2010-11 | Vaishali | Lalganj | 2 | G.A.H/S, Lalganj | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
120 | Tirhut East | GH-123-3 |  | 2010-11 | Vaishali | Goraul | 3 | H.S., Goraul | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
121 | Tirhut East | GH-124-1 |  | 2010-11 | Vaishali | Vaishali | 1 | S.M.T.H.S., Vaishali | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | 1 | [9 empty] | No apparoch road |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
122 | Tirhut East | GH-124-2 |  | 2010-11 | Vaishali | Bhagwanpur | 2 | M.S.Ratnapura Bhagwanpur | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 26954587 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
123 | Tirhut East | GH-124-3 |  | 2010-11 | Vaishali | Chehrakala | 3 | B.N. High School, Sehan * | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [8 empty] | 1 |  |  |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut East
124 | Tirhut West | GH-116-1 |  | 2010-11 | East Champaran | Chakiya | 1 | K.G.B.N., Chakiya | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
125 | Tirhut West | GH-116-2 |  | 2010-11 | East Champaran | Kalyanpur | 2 | K.G.B.N., Kalyanpur | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14156805 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
126 | Tirhut West | GH-117-1 |  | 2010-11 | East Champaran | Dhaka | 1 | K.G.B.N., Dhaka | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669947 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
127 | Tirhut West | GH-117-2 |  | 2010-11 | East Champaran | Ghorasahan | 2 | K.G.B.N.,Ghorasahan | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669946 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
128 | Tirhut West | GH-118-1 |  | 2010-11 | East Champaran | Kesariya | 1 | K.G.B.N., Kesariya | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 | Inaugurated 16.07.2016 | 31.3.2016 | 12987881 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
129 | Tirhut West | GH-118-2 |  | 2010-11 | East Champaran | Kotwa | 2 | K.G.B.N., Kotwa | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 |  | 31.3.2016 | 12987881 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
130 | Tirhut West | GH-118-3 |  | 2010-11 | East Champaran | Sangrampur | 3 | K.G.B.N., Sangrampur | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [8 empty] | 1 |  |  | 31.3.2016 | 10390304 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
131 | Tirhut West | GH-119-1 |  | 2010-11 | East Champaran | Madhuwan | 1 | K.G.B.N., Madhuwan | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
132 | Tirhut West | GH-119-2 |  | 2010-11 | East Champaran | Mehsi | 2 | K.G.B.N., Mehsi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
133 | Tirhut West | GH-119-3 |  | 2010-11 | East Champaran | Tetariya | 3 | K.G.B.N., Tetariya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
134 | Tirhut West | GH-120-1 |  | 2010-11 | East Champaran | Ramgharwa | 1 | K.G.B.N., Ramgharwa | 475 dated 03.11.2011 | 226 SBD of 2014-15 (04.08.2014 | [8 empty] | 1 |  |  | 31.3.2016 | 10128657 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
135 | Tirhut West | GH-125-1 |  | 2010-11 | West Champaran | Bagha-1 | 1 | R.S.H.S. Parsuniform | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Tirhut West
136 | Darbhanga | GH-14-1 |  | 2009-10 | Madhubani | Benipatti | 1 | B.J.J.H.S. Adher* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
137 | Darbhanga | GH-14-2 |  | 2009-10 | Madhubani | Bisfi | 1 | H.S. Parsauni* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
138 | Darbhanga | GH-15-1 |  | 2009-10 | Madhubani | Madhepur | 1 | H.S. Madhepur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
139 | Darbhanga | GH-15-2 |  | 2009-10 | Madhubani | Lakhanaur | 1 | P Girl H.S. Lakhanaur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
140 | Darbhanga | GH-15-3 |  | 2009-10 | Madhubani | Andarathari | 1 | M.S., Andarathari | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168062 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
141 | Darbhanga | GH-16-1 |  | 2009-10 | Madhubani | Rajnagar | 1 | R. H.S.Raj Nagar* | BMSP/INF-253/2012-867 | 02.12.13 | 1 | [9 empty] | Required land 125'x100' available land50'x25' |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
142 | Darbhanga | GH-16-2 |  | 2009-10 | Madhubani | Pandaul | 1 | Anup Lal Project Girls H.S. Barmotra Pandaul* | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
143 | Darbhanga | GH-16-3 |  | 2009-10 | Madhubani | Babubarhi | 1 | M.S., Bhupatti | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
144 | Darbhanga | GH-17-1 |  | 2009-10 | Madhubani | Ladania | 1 | M.S., Ladania Girl's | BMSP/INF-253/2012-867 | 20.8.2013 | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
145 | Darbhanga | GH-17-2 |  | 2009-10 | Madhubani | Jainagar | 1 | M.S., Dullipatti | BMSP/INF-253/2012-867 | 20.8.2013 | [9 empty] | 1 | Inaugurated | 24.11.15 | 15076496 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
146 | Darbhanga | GH-18-1 |  | 2009-10 | Madhubani | Basopatti | 1 | H.S. Basopatti * | BMSP/INF-253/2012-867 | 15.07.13 | [9 empty] | 1 |  |  | 10783387 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
147 | Darbhanga | GH-18-2 |  | 2009-10 | Madhubani | Madhwapur | 1 | H.S. Madhwapur* | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
148 | Darbhanga | GH-18-3 |  | 2009-10 | Madhubani | Ghoghardiha | 1 | H.S., Dewadh | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
149 | Darbhanga | GH-19-1 |  | 2009-10 | Samastipur | Singhia | 1 | K.G., Academy, Singhia | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available (required land 125'x100' avlaible land22'x11') |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
150 | Darbhanga | GH-19-2 |  | 2009-10 | Samastipur | Bithan | 1 | H.S., Bithan | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 30.9.15 | 14010421 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
151 | Darbhanga | GH-20-1 |  | 2009-10 | Samastipur | Warisnagar | 1 | M.S., Hajpurwa, Warisnagar | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 23.10.15 | 15193375 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
152 | Darbhanga | GH-20-2 |  | 2009-10 | Samastipur | Marwa | 1 | H.S., Morwa | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available. (required land 125'x100' avlaible landx18'x13') |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
153 | Darbhanga | GH-133-1 |  | 2010-11 | Darbhanga | Keoti | 1 | R. S. H.S, Keoti | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
154 | Darbhanga | GH-133-2 |  | 2010-11 | Darbhanga | Ghanshyampur | 2 | H.S, Pohadidibela | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
155 | Darbhanga | GH-134-1 |  | 2010-11 | Darbhanga | Kusheswara | 1 | M.S, Kushe .Sthan | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773087 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
156 | Darbhanga | GH-134-2 |  | 2010-11 | Darbhanga | Hanuman Nagar | 2 | G..H. S.Kolhanta Patori | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773086 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
157 | Darbhanga | GH-135-1 |  | 2010-11 | Darbhanga | Gora Bauram | 1 | H.S, Gourabauram | 475 dated 03.11.2011 | 26.7.2013 | [6 empty] | 1 | [5 empty] | 4834375 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
158 | Darbhanga | GH-135-2 |  | 2010-11 | Darbhanga | Manigachhi | 2 | H.S, Balour | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
159 | Darbhanga | GH-135-3 |  | 2010-11 | Darbhanga | Tardih | 3 | H.S, Narainpur | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
160 | Darbhanga | GH-136-1 |  | 2010-11 | Madhubani | Kaulahi | 1 | H.S, Kaulahi | 475 dated 03.11.2011 | 02.12.13 | 1 | [9 empty] | Land Dispute |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
161 | Darbhanga | GH-136-2 |  | 2010-11 | Madhubani | Harlakhi | 2 | H.S, Umgaun | 475 dated 03.11.2011 | 02.12.13 | [9 empty] | 1 | Inaugurated | 22.1.15 | 15632869 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
162 | Darbhanga | GH-137-1 |  | 2010-11 | Samastipur | Kalyanpur | 1 | K.G.B.V, Kalyanpur | 475 dated 03.11.2011 | 27.01.14 | 1 | [9 empty] | Land not available |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
163 | Darbhanga | GH-137-2 |  | 2010-11 | Samastipur | Pusa | 2 | Girls Int. Sch. Pusa | 475 dated 03.11.2011 | 27.01.14 | [9 empty] | 1 | Inaugurated | 15.12.15 | 14509763 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
164 | Darbhanga | GH-138-1 |  | 2010-11 | Samastipur | Ujiarpur | 1 | B.R.C, Ujiarpur Campus | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
165 | Darbhanga | GH-138-2 |  | 2010-11 | Samastipur | Sarayranjan | 2 | H.S, Bathua Bujurg | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
166 | Darbhanga | GH-138-3 |  | 2010-11 | Samastipur | Samastipur | 3 | M. I. S. Samastipur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405740 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
167 | Darbhanga | GH-139-1 |  | 2010-11 | Samastipur | Vidyapati Nagar | 1 | I.Sch.Vidyapati Nagar N | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
168 | Darbhanga | GH-139-2 |  | 2010-11 | Samastipur | Bibhutipur | 2 | M.S, Sirsi | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
169 | Darbhanga | GH-139-3 |  | 2010-11 | Samastipur | Dalsingh Sarai | 3 | C.H. I. S.Dalsingh Sarai | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
170 | Darbhanga | GH-140-1 |  | 2010-11 | Samastipur | Hasanpur | 1 | N.H.S, Hasanpur Road | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
171 | Darbhanga | GH-140-2 |  | 2010-11 | Samastipur | Sihivaji nagar | 2 | H.S, Shivaji Nagar | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
172 | Darbhanga | GH-140-3 |  | 2010-11 | Samastipur | Khanpur | 3 | I.Sch. Siropatti Khatu | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648267 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Darbhanga
173 | Saran | GH-12-1 |  | 2009-10 | Saran | Marhourah | 1 | U.M.S., Awari, Marhourah | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | [9 empty] | 1 | Inaugurated |  | 11673134 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
174 | Saran | GH-12-2 |  | 2009-10 | Saran | Taraiyan | 1 | M.S., Gawandary, Taria | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | 1 | [9 empty] | Location changed & But Land Problem |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
175 | Saran | GH-13-1 |  | 2009-10 | Saran | Parsa | 1 | M.S., Bishnupur, Parsa | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | [9 empty] | 1 | Inaugurated. Handover | 2015-07-17 | 13994126 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
176 | Saran | GH-13-2 |  | 2009-10 | Saran | Ishuapur | 1 | U.M.S., Satasi, Ishuapur | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | 1 | [9 empty] | Land problem |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
177 | Saran | GH-126-1 |  | 2010-11 | Saran | Garkha | 1 | MS Chainpur Bhaiswara | 475 dated 03.11.2011 | [10 empty] | 1 |  | 2015-12-31 | 14183475 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
178 | Saran | GH-126-2 |  | 2010-11 | Saran | Maker | 1 | UMS Baghakol | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-31 | 14183475 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
179 | Saran | GH-127-1 |  | 2010-11 | Siwan | Maharajganj | 1 | H.S.Sikatiya | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
180 | Saran | GH-127-2 |  | 2010-11 | Siwan | Barhariya | 1 | Sri Krishan H.S. Kailgarh | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778882 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
181 | Saran | GH-127-3 |  | 2010-11 | Siwan | Bhagwanpur Hatt | 1 | S.S. High School, Bhagawanpur Hatt | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
182 | Saran | GH-128-1 |  | 2010-11 | Siwan | Goreya Kothi | 1 | Narayan Karmayogi H.S, Goreyakothi | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
183 | Saran | GH-128-2 |  | 2010-11 | Siwan | Basantpur | 1 | H.S, Basantpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
184 | Saran | GH-128-3 |  | 2010-11 | Siwan | Dharaunda | 1 | G.S. H.S, Ujaini | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
185 | Saran | GH-129-1 |  | 2010-11 | Gopalganj | Baikunthpur | 1 | H.S, Sirsa | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-09-30 | 13648071 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
186 | Saran | GH-129-2 |  | 2010-11 | Gopalganj | Sidhwaliya | 1 | H.S, Mahamadpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-09-30 | 13648072 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
187 | Saran | GH-129-3 |  | 2010-11 | Gopalganj | Manjha | 1 | H.S, Manjha(old) H/s Dharm Parsa(New) | 475 dated 03.11.2011 | [10 empty] | 1 | Handover | 2015-09-30 | 13648071 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
188 | Saran | GH-130-1 |  | 2010-11 | Gopalganj | Panchdewari | 1 | H.S, Jamunaha Bazar | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated |  | 14408719 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
189 | Saran | GH-130-2 |  | 2010-11 | Gopalganj | Bhorey | 1 | H.S, Bhore | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 11526975 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
190 | Saran | GH-131-1 |  | 2010-11 | Gopalganj | Uchakagaon | 1 | H.S, Uchakagaon | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 13375616 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
191 | Saran | GH-131-2 |  | 2010-11 | Gopalganj | Kateya | 1 | Kanya H.S, Kateya(old) G.A H/S Kateya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Land Dispute |  | 0 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
192 | Saran | GH-132-1 |  | 2010-11 | Gopalganj | Kuchaikote | 1 | H.S, Sonekola | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-03-20 | 14619495 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
193 | Saran | GH-132-2 |  | 2010-11 | Gopalganj | Gopalganj | 1 | S.S Girls Inter School, Gopalganj | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-03-20 | 14619495 | Load bearing wall | 12500 Sqft | Open foundation/ Pile Foundation | Summersable 1 HP 6000 litres / 10000 liters | Covered Drain | As Required | No | 3 Phase Wiring | LT | Sealing (only point) | Defect liablity up to three years offer the completion date by contractor. | 20 Nos ABC type fire Extenion | No defects | Yes | Saran
Total No. of Schools (Girls Hostel) 2009-10 & 2010-10 | [10 empty] | 47 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 27 | 113

## GH-List (2)
S.N. | Group No. | Session | Name of District | Name of Block | Name of School | Sanction Order No. | Date of Commencement | Not Start | Lay-out | Foundation | PL | LL | RL | LL | RL | Finishing | Complete | Remarks | Date of Completion | Total Completion Cost
1 | GH-112-1 | 2010-11 | Arwal | Karpi | High School, Karpi | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179021
2 | GH-112-2 | 2010-11 | Arwal | Arwal | Balika High School, Arwal | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179020
3 | GH-09-1 | 2009-10 | Aurangabad | Madanpur | Anugrah H.S., Madanpur | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662880
4 | GH-09-2 | 2009-10 | Aurangabad | Rafiganj | R.B.R. High School, Rafiganj | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662879
5 | GH-10-1 | 2009-10 | Aurangabad | Haspura | Haspura H.S., Haspura | BMSP/INF-253/2012-867 | 154 SBD of 2013-14 (21.11.13 ) | 1 | [9 empty] | Land Disput, due to court-stay order |  | 0
6 | GH-11-1 | 2009-10 | Aurangabad | Kutumba | Govt. Middle School, Kutumba | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Insufficient land |  | 0
7 | GH-148-1 | 2010-11 | Banka | Rajaoun | R.H.S, Douni | 475 dated 03.11.2011 | 66 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2015-06-07 | 13168871
8 | GH-30-1 | 2009-10 | Bhagalpur | Sanhoula | M.S., Arar, | BMSP/INF-253/2012-867 | 107 SBD OF 2012-13 ( 26.2.2013) | [9 empty] | 1 | Inaugurated | 2015-07-01 | 11639798
9 | GH-31-1 | 2009-10 | Bhagalpur | Nathnagar | M.S., Kanjhiya, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available. (DROP OUT ) |  | 0
10 | GH-31-2 | 2009-10 | Bhagalpur | Narayanpur | M.S., Manoharpur, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 | 2016-02-28 | 13126242
11 | GH-32-1 | 2009-10 | Bhagalpur | Rangra Chowk | M.S, Rangra Chowk | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
12 | GH-32-2 | 2009-10 | Bhagalpur | Kharik Bazar | Basic Sch. Teldih* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
13 | GH-32-3 | 2009-10 | Bhagalpur | Ishmailpur | M.S.Parvatta* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
14 | GH-143-1 | 2010-11 | Bhagalpur | Pirpaiti | M.S, Simanpur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
15 | GH-143-2 | 2010-11 | Bhagalpur | Kahalgaon | R. S. H.S, Rampur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
16 | GH-143-3 | 2010-11 | Bhagalpur | Sabour | H.S, Mamalkha | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
17 | GH-144-1 | 2010-11 | Bhagalpur | Goradih | M.S, Goradih | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852
18 | GH-144-2 | 2010-11 | Bhagalpur | Sultanganj | K.N.S.M.H.S, Sultanganj | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852
19 | GH-145-1 | 2010-11 | Bhagalpur | Bihpur | H.S, Jairampur | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852
20 | GH-145-2 | 2010-11 | Bhagalpur | Naugachhia | H.S, Sahu Parbatta | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852
21 | GH-146-1 | 2010-11 | Bhagalpur | Gopalpur | Proj. Girls H.S, Saidpur | 475 dated 03.11.2011 | 37 SBD OF 2013-14 (10.6.2013) | [9 empty] | 1 | Inaugurated | 2014-02-08 | 14473004
22 | GH-147-1 | 2010-11 | Bhagalpur | Shahkund | Proj. H.S, Shahkund | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395969
23 | GH-147-2 | 2010-11 | Bhagalpur | Jagdishpur | Proj. Girls H.S, Jagdishpur | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395970
24 | GH-07-1 | 2009-10 | Bhojpur | Agioan | D.N.H.S., Gorpa | BMSP/INF-253/2012-867 | 25 SBD of 2013-14/ 10.05.2013 | [8 empty] | 1 |  |  |  | 8764831
25 | GH-08-1 | 2009-10 | Bhojpur | Jagdishpur | Janta H.S., Baligaw | BMSP/INF-253/2012-867 | 22 SBD of 2013-14/ 24.04.2013 | [8 empty] | 1 |  |  |  | 10754003
26 | GH-109-1 | 2010-11 | Buxar | Rajpur | H.S.Rajpur Compound | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 15.03.2017 | 11860829
27 | GH-109-2 | 2010-11 | Buxar | Itarhi | H.S.Itarhi | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 28.02.2017 | 14826037
28 | GH-109-3 | 2010-11 | Buxar | Nawanagar | H.S. Nawanagar | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 14826037
29 | GH-133-1 | 2010-11 | Darbhanga | Keoti | R. S. H.S, Keoti | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009
30 | GH-133-2 | 2010-11 | Darbhanga | Ghanshyampur | H.S, Pohadidibela | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009
31 | GH-134-1 | 2010-11 | Darbhanga | Kusheswara | M.S, Kushe .Sthan | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773087
32 | GH-134-2 | 2010-11 | Darbhanga | Hanuman Nagar | G..H. S.Kolhanta Patori | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773086
33 | GH-135-1 | 2010-11 | Darbhanga | Gora Bauram | H.S, Gourabauram | 475 dated 03.11.2011 | 26.7.2013 | [6 empty] | 1 | [5 empty] | 4834375
34 | GH-135-2 | 2010-11 | Darbhanga | Manigachhi | H.S, Balour | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582
35 | GH-135-3 | 2010-11 | Darbhanga | Tardih | H.S, Narainpur | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582
36 | GH-116-1 | 2010-11 | East Champaran | Chakiya | K.G.B.N., Chakiya | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | 1 | [9 empty] | Land not available |  | 0
37 | GH-116-2 | 2010-11 | East Champaran | Kalyanpur | K.G.B.N., Kalyanpur | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14156805
38 | GH-117-1 | 2010-11 | East Champaran | Dhaka | K.G.B.N., Dhaka | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669947
39 | GH-117-2 | 2010-11 | East Champaran | Ghorasahan | K.G.B.N.,Ghorasahan | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669946
40 | GH-118-1 | 2010-11 | East Champaran | Kesariya | K.G.B.N., Kesariya | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 | Inaugurated 16.07.2016 | 31.3.2016 | 12987881
41 | GH-118-2 | 2010-11 | East Champaran | Kotwa | K.G.B.N., Kotwa | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 |  | 31.3.2016 | 12987881
42 | GH-118-3 | 2010-11 | East Champaran | Sangrampur | K.G.B.N., Sangrampur | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [8 empty] | 1 |  |  | 31.3.2016 | 10390304
43 | GH-119-1 | 2010-11 | East Champaran | Madhuwan | K.G.B.N., Madhuwan | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
44 | GH-119-2 | 2010-11 | East Champaran | Mehsi | K.G.B.N., Mehsi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
45 | GH-119-3 | 2010-11 | East Champaran | Tetariya | K.G.B.N., Tetariya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Start |  | 0
46 | GH-120-1 | 2010-11 | East Champaran | Ramgharwa | K.G.B.N., Ramgharwa | 475 dated 03.11.2011 | 226 SBD of 2014-15 (04.08.2014 | [8 empty] | 1 |  |  | 31.3.2016 | 10128657
47 | GH-129-1 | 2010-11 | Gopalganj | Baikunthpur | H.S, Sirsa | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-09-30 | 13648071
48 | GH-129-2 | 2010-11 | Gopalganj | Sidhwaliya | H.S, Mahamadpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-09-30 | 13648072
49 | GH-129-3 | 2010-11 | Gopalganj | Manjha | H.S, Manjha(old) H/s Dharm Parsa(New) | 475 dated 03.11.2011 | [10 empty] | 1 | Handover | 2015-09-30 | 13648071
50 | GH-130-1 | 2010-11 | Gopalganj | Panchdewari | H.S, Jamunaha Bazar | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated |  | 14408719
51 | GH-130-2 | 2010-11 | Gopalganj | Bhorey | H.S, Bhore | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 11526975
52 | GH-131-1 | 2010-11 | Gopalganj | Uchakagaon | H.S, Uchakagaon | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 13375616
53 | GH-131-2 | 2010-11 | Gopalganj | Kateya | Kanya H.S, Kateya(old) G.A H/S Kateya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Land Dispute |  | 0
54 | GH-132-1 | 2010-11 | Gopalganj | Kuchaikote | H.S, Sonekola | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-03-20 | 14619495
55 | GH-132-2 | 2010-11 | Gopalganj | Gopalganj | S.S Girls Inter School, Gopalganj | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-03-20 | 14619495
56 | GH-150-1 | 2010-11 | Jamui | Khaira | Project G.H.S, Khaira | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-09-20 | 11102710
57 | GH-150-2 | 2010-11 | Jamui | Sono | Project H.S, Sona | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-02-25 | 11102709
58 | GH-113-1 | 2010-11 | Jehanabad | Jehanabad | H.S., Jehanabad | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
59 | GH-113-2 | 2010-11 | Jehanabad | Kako | H.S. Pali Bazar | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
60 | GH-113-3 | 2010-11 | Jehanabad | Ghosi | H.S. Ghosi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
61 | GH-114-1 | 2010-11 | Jehanabad | Ratni Faridpur | H.S. Dayalbagh, Nehalpur | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started EMD to be returned |  | 0
62 | GH-114-2 | 2010-11 | Jehanabad | Makhdumpur | S.S. Tehta | 475 dated 03.11.2011 |  | 1 | [9 empty] | Low land. EMD to be returned |  | 0
63 | GH-115-1 | 2010-11 | Jehanabad | Hulashganj | H.S. Hulashganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Local problem. EMD to be returned |  | 0
64 | GH-115-2 | 2010-11 | Jehanabad | Modanganj | D.N.H.S. Bandhuganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Started. EMD to be returned |  | 0
65 | GH-111-1 | 2010-11 | Kaimur | Durgawati | K.G.B.V. Compound | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14150475
66 | GH-111-2 | 2010-11 | Kaimur | Adhaura | H. S. Adhaura | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 31.01.2017 | 14150474
67 | GH-27-1 | 2009-10 | Katihar | Kadwa | N.C.C. Smarak H.S Balia Belon | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 13455545
68 | GH-27-2 | 2009-10 | Katihar | Balrampur | S.S., High School, Telta | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2016-01-15 | 13455546
69 | GH-27-3 | 2009-10 | Katihar | Sameli | D.G.H.S., Krishna Nagar | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2015-02-04 | 13455545
70 | GH-28-1 | 2009-10 | Katihar | Manihari | B.P.S.P.H.S., Manihari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 14782767
71 | GH-28-2 | 2009-10 | Katihar | Azamnagar | H.S., Salmari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-11-28 | 14782767
72 | GH-28-3 | 2009-10 | Katihar | Pranpur | M.S., Bastol | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | 1 | [9 empty] | Land Dispute |  | 0
73 | GH-29-1 | 2009-10 | Katihar | Falka | B.S.M.High School, Pothiya | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780
74 | GH-29-2 | 2009-10 | Katihar | Kursela | Sampat Raj Devi Girl's H.S., Kursela | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780
75 | GH-34-1 | 2009-10 | Lakhisarai | Surajgarha | Project K. K.H., Surajgarha | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | 1 | [9 empty] | Land not available |  | 0
76 | GH-34-2 | 2009-10 | Lakhisarai | Pipariya | M.M.P. H.S., Walipur | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11286461
77 | GH-35-1 | 2009-10 | Lakhisarai | Halsi | High School, Halsi | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [8 empty] | 1 |  |  |  | 10390217
78 | GH-35-2 | 2009-10 | Lakhisarai | Ramgarh Chowk | D.M H.S., Sharma | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [6 empty] | 1 | [5 empty] | 3896331
79 | GH-151-1 | 2010-11 | Lakhisarai | Lakhisarai | M.V.M H.S.Nayatola, Lakhisarai | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. PPO R.M.S.A |  | 0
80 | GH-151-2 | 2010-11 | Lakhisarai | Barahiya | S.R.R.S Girls H.S, Barahiya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. Land problem |  | 0
81 | GH-14-1 | 2009-10 | Madhubani | Benipatti | B.J.J.H.S. Adher* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754
82 | GH-14-2 | 2009-10 | Madhubani | Bisfi | H.S. Parsauni* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754
83 | GH-15-1 | 2009-10 | Madhubani | Madhepur | H.S. Madhepur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063
84 | GH-15-2 | 2009-10 | Madhubani | Lakhanaur | P Girl H.S. Lakhanaur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063
85 | GH-15-3 | 2009-10 | Madhubani | Andarathari | M.S., Andarathari | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168062
86 | GH-16-1 | 2009-10 | Madhubani | Rajnagar | R. H.S.Raj Nagar* | BMSP/INF-253/2012-867 | 02.12.13 | 1 | [9 empty] | Required land 125'x100' available land50'x25' |  | 0
87 | GH-16-2 | 2009-10 | Madhubani | Pandaul | Anup Lal Project Girls H.S. Barmotra Pandaul* | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084
88 | GH-16-3 | 2009-10 | Madhubani | Babubarhi | M.S., Bhupatti | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084
89 | GH-17-1 | 2009-10 | Madhubani | Ladania | M.S., Ladania Girl's | BMSP/INF-253/2012-867 | 20.8.2013 | 1 | [9 empty] | Land not available |  | 0
90 | GH-17-2 | 2009-10 | Madhubani | Jainagar | M.S., Dullipatti | BMSP/INF-253/2012-867 | 20.8.2013 | [9 empty] | 1 | Inaugurated | 24.11.15 | 15076496
91 | GH-18-1 | 2009-10 | Madhubani | Basopatti | H.S. Basopatti * | BMSP/INF-253/2012-867 | 15.07.13 | [9 empty] | 1 |  |  | 10783387
92 | GH-18-2 | 2009-10 | Madhubani | Madhwapur | H.S. Madhwapur* | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709
93 | GH-18-3 | 2009-10 | Madhubani | Ghoghardiha | H.S., Dewadh | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709
94 | GH-136-1 | 2010-11 | Madhubani | Kaulahi | H.S, Kaulahi | 475 dated 03.11.2011 | 02.12.13 | 1 | [9 empty] | Land Dispute |  | 0
95 | GH-136-2 | 2010-11 | Madhubani | Harlakhi | H.S, Umgaun | 475 dated 03.11.2011 | 02.12.13 | [9 empty] | 1 | Inaugurated | 22.1.15 | 15632869
96 | GH-33-1 | 2009-10 | Munger | Haveli Kharagpur | Govt.+2 H.S., Haweli Kharagpur | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459708
97 | GH-33-2 | 2009-10 | Munger | Dharahara | K.R.S.K.H H.S., Dharahra | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available |  | 0
98 | GH-33-3 | 2009-10 | Munger | Tetiabamber | Jagannath H.S Tetia Bamber | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459707
99 | GH-149-1 | 2010-11 | Munger | Tarapur | M.S, Tarapur | 475 dated 03.11.2011 | 104 SBD 2013-14 (11.9.2013) | [6 empty] | 1 | [5 empty] | 6098553
100 | GH-101-1 | 2010-11 | Patna | Daniyawa | Rajkiyakrit H.S., Sigariyawa | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 13865367
101 | GH-101-2 | 2010-11 | Patna | Khusrupur | Rajkiyakrit Mahadeo H.S., Fatuwa, Khusrupur | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 13865367
102 | GH-102-1 | 2010-11 | Patna | Bakhtiyarpur | Rajkiyakrit H.S., Salimpur | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | 1 | [9 empty] | Land not available. Site to be changed |  | 0
103 | GH-102-2 | 2010-11 | Patna | Belchhi | Rajkiyakrit H.S., Saksohar | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | [8 empty] | 1 |  | Flooring (DEBAR) |  | 11920568
104 | GH-103-1 | 2010-11 | Patna | Paliganj | Rajkiyakrit H.S., Paliganj | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  |  |  | 15692151
105 | GH-103-2 | 2010-11 | Patna | Dulhin Bazar | Banshidhari H.S., Bharatpura | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  | DEBAR |  | 12553720
106 | GH-103-3 | 2010-11 | Patna | Bikram | Parwati H.S., Bikram | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 12553721
107 | GH-104-1 | 2010-11 | Patna | Masaurih | Smt. Girija Kuwar H.S., Masaurih | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 | DEBAR | 08.03.17 | 11571154
108 | GH-104-2 | 2010-11 | Patna | Punpun | Sahid Ramanand R. Govind H.S., Punpun | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 |  | 05.03.17 | 11571153
109 | GH-105-1 | 2010-11 | Patna | Patna Sadar (Gramin) | Rajkiyakrit Mahanth Hanuman Sharan H.S.School,Rajapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | 1 | [9 empty] | Land Dispute |  | 0
110 | GH-105-2 | 2010-11 | Patna | Danapur | Baldeo Senior Secondary School, Danapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 | Inaugurated | 06.04.2016 | 13012761
111 | GH-105-3 | 2010-11 | Patna | Maner | Rajkiyakrit H/S, Maner | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 |  | 24.12.16 | 13012761
112 | GH-106-1 | 2010-11 | Patna | Mokama | Railway Aided H.S., Mokama | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488
113 | GH-106-2 | 2010-11 | Patna | Ghoswari | Rajkiyakrit H.S., Kumhra | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488
114 | GH-107-1 | 2010-11 | Patna | Barh | Rajkiyakrit Anugrah Narayan Singh Senior Secondary School, Barh | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14329584
115 | GH-107-2 | 2010-11 | Patna | Pandarak | Laxmi Narayan Rajbanshi H.S., Dhibar | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | 1 | [9 empty] | Sufficient land not available |  | 0
116 | GH-108-1 | 2010-11 | Patna | Naubatpur | Rajkiyakrit H.S., Amarpura | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961
117 | GH-108-2 | 2010-11 | Patna | Sampatchak | Gramin S.S.School Chakbairiya, Patna | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961
118 | GH-22-1 | 2009-10 | Purnea | Dhamdaha | H.S., Dhamdaha | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808
119 | GH-22-2 | 2009-10 | Purnea | Rupouli | Project Girl's H.S., Rupouli | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808
120 | GH-22-3 | 2009-10 | Purnea | Bhawanipur | H.S., Bhawanipur | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742809
121 | GH-23-1 | 2009-10 | Purnea | Barharakothi | Shyama H.S., Bhatotar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679264
122 | GH-23-2 | 2009-10 | Purnea | K. Nagar | H.S., Champanagar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679263
123 | GH-24-1 | 2009-10 | Purnea | Purnia East | Proj. Girl's H.S., Ranipatra | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | 1 | [9 empty] | Land not available |  | 0
124 | GH-24-2 | 2009-10 | Purnea | Jalalgarh | N.D Rungata H.S., Jalalgarh | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509025
125 | GH-24-3 | 2009-10 | Purnea | Kasba | Kalanand H.S., Garabnaili | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509024
126 | GH-25-1 | 2009-10 | Purnea | Dagarua | Abul Kalam H.S., Ichalo | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start. Agreement not done |  | 0
127 | GH-25-2 | 2009-10 | Purnea | Srinagar | Govt. S.S., Srinagar | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0
128 | GH-25-3 | 2009-10 | Purnea | Baisi | Proj. Girl's School Baisi | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0
129 | GH-26-1 | 2009-10 | Purnea | Baisa | H.S., Rauta | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541239
130 | GH-26-2 | 2009-10 | Purnea | Amour | Project Girl's School, Amour | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541238
131 | GH-110-1 | 2010-11 | Rohtas | Chenari | Middle School, Khurmabad, Chenari | 475 dated 03.11.2011 | 190 SBD of 2013-14/ 16.12.13 | [9 empty] | 1 | Inaugurated | 30.08.2015 | 13987787
132 | GH-141-1 | 2010-11 | Saharsa | Kahra | Govt. Girls H. S, Saharsa | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981
133 | GH-141-2 | 2010-11 | Saharsa | Saur Bazar | Gajadhar Sahu H.S, Saur Bazar | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981
134 | GH-142-1 | 2010-11 | Saharsa | Salkhua | H.S, Salkhua | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | 1 | [9 empty] | Land not available. |  | 0
135 | GH-142-2 | 2010-11 | Saharsa | Sonbarsa | Sir Hariballabh Inst. | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | [9 empty] | 1 |  |  | 12885961
136 | GH-19-1 | 2009-10 | Samastipur | Singhia | K.G., Academy, Singhia | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available (required land 125'x100' avlaible land22'x11') |  | 0
137 | GH-19-2 | 2009-10 | Samastipur | Bithan | H.S., Bithan | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 30.9.15 | 14010421
138 | GH-20-1 | 2009-10 | Samastipur | Warisnagar | M.S., Hajpurwa, Warisnagar | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 23.10.15 | 15193375
139 | GH-20-2 | 2009-10 | Samastipur | Marwa | H.S., Morwa | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available. (required land 125'x100' avlaible landx18'x13') |  | 0
140 | GH-137-1 | 2010-11 | Samastipur | Kalyanpur | K.G.B.V, Kalyanpur | 475 dated 03.11.2011 | 27.01.14 | 1 | [9 empty] | Land not available |  | 0
141 | GH-137-2 | 2010-11 | Samastipur | Pusa | Girls Int. Sch. Pusa | 475 dated 03.11.2011 | 27.01.14 | [9 empty] | 1 | Inaugurated | 15.12.15 | 14509763
142 | GH-138-1 | 2010-11 | Samastipur | Ujiarpur | B.R.C, Ujiarpur Campus | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739
143 | GH-138-2 | 2010-11 | Samastipur | Sarayranjan | H.S, Bathua Bujurg | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739
144 | GH-138-3 | 2010-11 | Samastipur | Samastipur | M. I. S. Samastipur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405740
145 | GH-139-1 | 2010-11 | Samastipur | Vidyapati Nagar | I.Sch.Vidyapati Nagar N | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
146 | GH-139-2 | 2010-11 | Samastipur | Bibhutipur | M.S, Sirsi | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
147 | GH-139-3 | 2010-11 | Samastipur | Dalsingh Sarai | C.H. I. S.Dalsingh Sarai | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
148 | GH-140-1 | 2010-11 | Samastipur | Hasanpur | N.H.S, Hasanpur Road | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268
149 | GH-140-2 | 2010-11 | Samastipur | Sihivaji nagar | H.S, Shivaji Nagar | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268
150 | GH-140-3 | 2010-11 | Samastipur | Khanpur | I.Sch. Siropatti Khatu | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648267
151 | GH-12-1 | 2009-10 | Saran | Marhourah | U.M.S., Awari, Marhourah | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | [9 empty] | 1 | Inaugurated |  | 11673134
152 | GH-12-2 | 2009-10 | Saran | Taraiyan | M.S., Gawandary, Taria | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | 1 | [9 empty] | Location changed & But Land Problem |  | 0
153 | GH-13-1 | 2009-10 | Saran | Parsa | M.S., Bishnupur, Parsa | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | [9 empty] | 1 | Inaugurated. Handover | 2015-07-17 | 13994126
154 | GH-13-2 | 2009-10 | Saran | Ishuapur | U.M.S., Satasi, Ishuapur | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | 1 | [9 empty] | Land problem |  | 0
155 | GH-126-1 | 2010-11 | Saran | Garkha | MS Chainpur Bhaiswara | 475 dated 03.11.2011 | [10 empty] | 1 |  | 2015-12-31 | 14183475
156 | GH-126-2 | 2010-11 | Saran | Maker | UMS Baghakol | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-31 | 14183475
157 | GH-01-1 | 2009-10 | Sitamarhi | Parihar | S.G.H.S., Parihar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
158 | GH-01-2 | 2009-10 | Sitamarhi | Sonbarsa | H.S., Bhutahi | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
159 | GH-01-3 | 2009-10 | Sitamarhi | Bathnaha | H.S., Yogibana Bazar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
160 | GH-02-1 | 2009-10 | Sitamarhi | Parsauni | H.S., Parsauni Chowk | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029
161 | GH-02-2 | 2009-10 | Sitamarhi | Riga | H.S., Rewasi | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022030
162 | GH-02-3 | 2009-10 | Sitamarhi | Belsand | H.S., Belsand | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029
163 | GH-3-1 | 2009-10 | Sitamarhi | Bairgania | Jaurimal H.S., Bairgania | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP (Letter given)/13/12/2014 |  | 4751468
164 | GH-3-2 | 2009-10 | Sitamarhi | Suppi | H.S., Suppi | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/12-04-2015 |  | 4751467
165 | GH-3-3 | 2009-10 | Sitamarhi | Majarganj | H.S., Majarganj | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/5-12-2014 |  | 4751468
166 | GH-4-1 | 2009-10 | Sitamarhi | Sursand | Saryu H.S., Sursand | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [8 empty] | 1 |  |  |  | 13056903
167 | GH-4-2 | 2009-10 | Sitamarhi | Pupri | Proj. H.S., Pupri | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | 1 | [9 empty] | small land |  | 0
168 | GH-4-3 | 2009-10 | Sitamarhi | Choraut | H.S., Choraut | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [9 empty] | 1 |  |  | 16321128
169 | GH-5-1 | 2009-10 | Sitamarhi | Bajpatti | H.S., Bajpatti | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
170 | GH-5-2 | 2009-10 | Sitamarhi | Nanpur | H.S., Janipur | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
171 | GH-5-3 | 2009-10 | Sitamarhi | Bokhra | H.S., Kharka | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
172 | GH-6-1 | 2009-10 | Sitamarhi | Dumra | K.G.H.S., Dumra | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673297
173 | GH-6-2 | 2009-10 | Sitamarhi | Runni saidpur | H.S., Morsand | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673296
174 | GH-127-1 | 2010-11 | Siwan | Maharajganj | H.S.Sikatiya | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881
175 | GH-127-2 | 2010-11 | Siwan | Barhariya | Sri Krishan H.S. Kailgarh | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778882
176 | GH-127-3 | 2010-11 | Siwan | Bhagwanpur Hatt | S.S. High School, Bhagawanpur Hatt | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881
177 | GH-128-1 | 2010-11 | Siwan | Goreya Kothi | Narayan Karmayogi H.S, Goreyakothi | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
178 | GH-128-2 | 2010-11 | Siwan | Basantpur | H.S, Basantpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
179 | GH-128-3 | 2010-11 | Siwan | Dharaunda | G.S. H.S, Ujaini | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
180 | GH-21-1 | 2009-10 | Supaul | Raghopur | M.S., Kajayan, Raghopur | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265108
181 | GH-21-2 | 2009-10 | Supaul | Pratapganj | Public H.S., Pratapganj | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265107
182 | GH-121-1 | 2010-11 | Vaishali | Rajapakar | H.S.,Rajapakar | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | 1 | [11 empty] | 0
183 | GH-121-2 | 2010-11 | Vaishali | Mahua | M.S. Singhara | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | [9 empty] | 1 | Inaugurated | 18.5.15 | 14587944
184 | GH-122-1 | 2010-11 | Vaishali | Raghopur | B.S.J.S.H.S.Fatehpur, Vaishali | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Land problem |  | 0
185 | GH-122-2 | 2010-11 | Vaishali | Bidupur | S.S.V.M.H.S., Ramdauli | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | [9 empty] | 1 | Inaugurated | 28.4.16 | 13567869
186 | GH-122-3 | 2010-11 | Vaishali | Deshri | H.S. Bhataulla | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Dismantling |  | 0
187 | GH-123-1 | 2010-11 | Vaishali | Patepur | S.R.C.H.S.,Patepur, Vaishali | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 13868106
188 | GH-123-2 | 2010-11 | Vaishali | Lalganj | G.A.H/S, Lalganj | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0
189 | GH-123-3 | 2010-11 | Vaishali | Goraul | H.S., Goraul | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0
190 | GH-124-1 | 2010-11 | Vaishali | Vaishali | S.M.T.H.S., Vaishali | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | 1 | [9 empty] | No apparoch road |  | 0
191 | GH-124-2 | 2010-11 | Vaishali | Bhagwanpur | M.S.Ratnapura Bhagwanpur | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 26954587
192 | GH-124-3 | 2010-11 | Vaishali | Chehrakala | B.N. High School, Sehan * | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [8 empty] | 1 |  |  |  | 0
193 | GH-125-1 | 2010-11 | West Champaran | Bagha-1 | R.S.H.S. Parsuniform | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
Total No. of Schools (Girls Hostel) 2009-10 & 2010-11 |  |  |  |  | 193 |  |  | 47 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 27 | 113

## Sheet3
Column Labels
| 2009-10 | [10 empty] | 2010-11 | [10 empty] | Total Not Started | Total Completed | Total Lay-outed | Total Foundationd | Total Plinth | Total GF-LL | Total GF-RL | Total FF-LL2 | Total FF-RL | Total Finishing | Total Sum of Total Completion Cost
Row Labels | Not Started | Completed | Lay-outed | Foundationd | Plinth | GF-LL | GF-RL | FF-LL2 | FF-RL | Finishing | Sum of Total Completion Cost | Not Started | Completed | Lay-outed | Foundationd | Plinth | GF-LL | GF-RL | FF-LL2 | FF-RL | Finishing | Sum of Total Completion Cost
Arwal | [12 empty] | 2 | [8 empty] | 24358041 |  | 2 | [8 empty] | 24358041
Aurangabad | 2 | 2 | [8 empty] | 27325759 | [11 empty] | 2 | 2 | [8 empty] | 27325759
Banka | [12 empty] | 1 | [8 empty] | 13168871 |  | 1 | [8 empty] | 13168871
Bhagalpur | 4 | 2 | [8 empty] | 24766040 |  | 10 | [8 empty] | 135146746 | 4 | 12 | [8 empty] | 159912786
Bhojpur | [9 empty] | 2 | 19518834 | [20 empty] | 2 | 19518834
Buxar | [12 empty] | 3 | [8 empty] | 41512903 |  | 3 | [8 empty] | 41512903
Darbhanga | [12 empty] | 6 | [5 empty] | 1 |  |  | 99997730 |  | 6 | [5 empty] | 1 |  |  | 99997730
East Champaran | [11 empty] | 4 | 5 | [7 empty] | 2 | 89991421 | 4 | 5 | [7 empty] | 2 | 89991421
Gopalganj | [11 empty] | 1 | 6 | [7 empty] | 2 | 109494514 | 1 | 6 | [7 empty] | 2 | 109494514
Jamui | [12 empty] | 2 | [8 empty] | 22205419 |  | 2 | [8 empty] | 22205419
Jehanabad | [11 empty] | 7 | [9 empty] | 0 | 7 | [9 empty] | 0
Kaimur | [12 empty] | 2 | [8 empty] | 28300949 |  | 2 | [8 empty] | 28300949
Katihar | 1 | 5 | [7 empty] | 2 | 94417730 | [11 empty] | 1 | 5 | [7 empty] | 2 | 94417730
Lakhisarai | 1 | 1 | [5 empty] | 1 |  | 1 | 25573009 | 2 | [9 empty] | 0 | 3 | 1 | [5 empty] | 1 |  | 1 | 25573009
Madhubani | 2 | 7 | [7 empty] | 4 | 131711165 | 1 | 1 | [8 empty] | 15632869 | 3 | 8 | [7 empty] | 4 | 147344034
Munger | 1 | 2 | [8 empty] | 22919415 | [7 empty] | 1 |  |  | 6098553 | 1 | 2 | [5 empty] | 1 |  |  | 29017968
Patna | [11 empty] | 3 | 12 | [7 empty] | 3 | 202087205 | 3 | 12 | [7 empty] | 3 | 202087205
Purnea | 4 | 2 | [7 empty] | 7 | 102687478 | [11 empty] | 4 | 2 | [7 empty] | 7 | 102687478
Rohtas | [12 empty] | 1 | [8 empty] | 13987787 |  | 1 | [8 empty] | 13987787
Saharsa | [11 empty] | 1 | 3 | [8 empty] | 40701923 | 1 | 3 | [8 empty] | 40701923
Samastipur | 2 | 2 | [8 empty] | 29203796 | 1 | 10 | [8 empty] | 138396557 | 3 | 12 | [8 empty] | 167600353
Saran | 2 | 2 | [8 empty] | 25667260 |  | 2 | [8 empty] | 28366950 | 2 | 4 | [8 empty] | 54034210
Sitamarhi | 1 | 10 |  |  |  |  | 3 |  |  | 3 | 205830073 | [11 empty] | 1 | 10 |  |  |  |  | 3 |  |  | 3 | 205830073
Siwan | [12 empty] | 6 | [8 empty] | 79957504 |  | 6 | [8 empty] | 79957504
Supaul |  | 2 | [8 empty] | 24530215 | [12 empty] | 2 | [8 empty] | 24530215
Vaishali | [11 empty] | 6 | 4 | [7 empty] | 1 | 68978506 | 6 | 4 | [7 empty] | 1 | 68978506
West Champaran | [11 empty] | 1 | [9 empty] | 0 | 1 | [9 empty] | 0
Grand Total | 20 | 37 |  |  |  |  | 3 | 1 |  | 19 | 734150774 | 27 | 76 | [5 empty] | 2 |  | 8 | 1158384448 | 47 | 113 |  |  |  |  | 3 | 3 |  | 27 | 1892535222

## GH-List (3)
S.N. | Group No. | Session | Name of District | Name of Block | Name of School | Sanction Order No. | Date of Commencement | Not Start | Lay-out | Foundation | PL | LL | RL | LL | RL | Finishing | Complete | Remarks | Date of Completion | Total Completion Cost
1 | GH-112-1 | 2010-11 | Arwal | Karpi | High School, Karpi | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179021
2 | GH-112-2 | 2010-11 | Arwal | Arwal | Balika High School, Arwal | 475 dated 03.11.2011 | 122 SBD OF2013-14 (4.10.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 12179020
3 | GH-09-1 | 2009-10 | Aurangabad | Madanpur | Anugrah H.S., Madanpur | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662880
4 | GH-09-2 | 2009-10 | Aurangabad | Rafiganj | R.B.R. High School, Rafiganj | BMSP/INF-253/2012-867 | 5 SBD OF 2013-14 (9.4.2013) | [9 empty] | 1 | Inaugurated | 20.03.15 | 13662879
5 | GH-10-1 | 2009-10 | Aurangabad | Haspura | Haspura H.S., Haspura | BMSP/INF-253/2012-867 | 154 SBD of 2013-14 (21.11.13 ) | 1 | [9 empty] | Land Disput, due to court-stay order |  | 0
6 | GH-11-1 | 2009-10 | Aurangabad | Kutumba | Govt. Middle School, Kutumba | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Insufficient land |  | 0
7 | GH-148-1 | 2010-11 | Banka | Rajaoun | R.H.S, Douni | 475 dated 03.11.2011 | 66 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2015-06-07 | 13168871
8 | GH-30-1 | 2009-10 | Bhagalpur | Sanhoula | M.S., Arar, | BMSP/INF-253/2012-867 | 107 SBD OF 2012-13 ( 26.2.2013) | [9 empty] | 1 | Inaugurated | 2015-07-01 | 11639798
9 | GH-31-1 | 2009-10 | Bhagalpur | Nathnagar | M.S., Kanjhiya, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available. (DROP OUT ) |  | 0
10 | GH-31-2 | 2009-10 | Bhagalpur | Narayanpur | M.S., Manoharpur, | BMSP/INF-253/2012-867 | 56 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 | 2016-02-28 | 13126242
11 | GH-32-1 | 2009-10 | Bhagalpur | Rangra Chowk | M.S, Rangra Chowk | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
12 | GH-32-2 | 2009-10 | Bhagalpur | Kharik Bazar | Basic Sch. Teldih* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
13 | GH-32-3 | 2009-10 | Bhagalpur | Ishmailpur | M.S.Parvatta* | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Land not available. |  | 0
14 | GH-143-1 | 2010-11 | Bhagalpur | Pirpaiti | M.S, Simanpur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
15 | GH-143-2 | 2010-11 | Bhagalpur | Kahalgaon | R. S. H.S, Rampur | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
16 | GH-143-3 | 2010-11 | Bhagalpur | Sabour | H.S, Mamalkha | 475 dated 03.11.2011 | 158 SBD OF2013-14 (26.11.2013) | [9 empty] | 1 | Inaugurated | 2015-07-20 | 13223465
17 | GH-144-1 | 2010-11 | Bhagalpur | Goradih | M.S, Goradih | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852
18 | GH-144-2 | 2010-11 | Bhagalpur | Sultanganj | K.N.S.M.H.S, Sultanganj | 475 dated 03.11.2011 | 136 SBD of 2013-14 (22.10.2013) | [9 empty] | 1 | Inaugurated | 2015-07-14 | 13625852
19 | GH-145-1 | 2010-11 | Bhagalpur | Bihpur | H.S, Jairampur | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852
20 | GH-145-2 | 2010-11 | Bhagalpur | Naugachhia | H.S, Sahu Parbatta | 475 dated 03.11.2011 | 143 SBD OF 4 (30.10.2013) | [9 empty] | 1 | Inaugurated | 2014-05-17 | 14479852
21 | GH-146-1 | 2010-11 | Bhagalpur | Gopalpur | Proj. Girls H.S, Saidpur | 475 dated 03.11.2011 | 37 SBD OF 2013-14 (10.6.2013) | [9 empty] | 1 | Inaugurated | 2014-02-08 | 14473004
22 | GH-147-1 | 2010-11 | Bhagalpur | Shahkund | Proj. H.S, Shahkund | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395969
23 | GH-147-2 | 2010-11 | Bhagalpur | Jagdishpur | Proj. Girls H.S, Jagdishpur | 475 dated 03.11.2011 | 65 SBD OF 2013-14 (26.7.2013) | [9 empty] | 1 | Inaugurated | 2014-07-24 | 12395970
24 | GH-07-1 | 2009-10 | Bhojpur | Agioan | D.N.H.S., Gorpa | BMSP/INF-253/2012-867 | 25 SBD of 2013-14/ 10.05.2013 | [8 empty] | 1 |  |  |  | 8764831
25 | GH-08-1 | 2009-10 | Bhojpur | Jagdishpur | Janta H.S., Baligaw | BMSP/INF-253/2012-867 | 22 SBD of 2013-14/ 24.04.2013 | [8 empty] | 1 |  |  |  | 10754003
26 | GH-109-1 | 2010-11 | Buxar | Rajpur | H.S.Rajpur Compound | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 15.03.2017 | 11860829
27 | GH-109-2 | 2010-11 | Buxar | Itarhi | H.S.Itarhi | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 |  | 28.02.2017 | 14826037
28 | GH-109-3 | 2010-11 | Buxar | Nawanagar | H.S. Nawanagar | 475 dated 03.11.2011 | 03.07.2014 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 14826037
29 | GH-133-1 | 2010-11 | Darbhanga | Keoti | R. S. H.S, Keoti | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009
30 | GH-133-2 | 2010-11 | Darbhanga | Ghanshyampur | H.S, Pohadidibela | 475 dated 03.11.2011 | 20.7.2013 | [9 empty] | 1 | Inaugurated | 15.5.15 | 15694009
31 | GH-134-1 | 2010-11 | Darbhanga | Kusheswara | M.S, Kushe .Sthan | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773087
32 | GH-134-2 | 2010-11 | Darbhanga | Hanuman Nagar | G..H. S.Kolhanta Patori | 475 dated 03.11.2011 | 27.6.2013 | [9 empty] | 1 | Inaugurated | 20.6.15 | 15773086
33 | GH-135-1 | 2010-11 | Darbhanga | Gora Bauram | H.S, Gourabauram | 475 dated 03.11.2011 | 26.7.2013 | [6 empty] | 1 | [5 empty] | 4834375
34 | GH-135-2 | 2010-11 | Darbhanga | Manigachhi | H.S, Balour | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582
35 | GH-135-3 | 2010-11 | Darbhanga | Tardih | H.S, Narainpur | 475 dated 03.11.2011 | 26.7.2013 | [9 empty] | 1 | Inaugurated |  | 16114582
36 | GH-116-1 | 2010-11 | East Champaran | Chakiya | K.G.B.N., Chakiya | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | 1 | [9 empty] | Land not available |  | 0
37 | GH-116-2 | 2010-11 | East Champaran | Kalyanpur | K.G.B.N., Kalyanpur | 475 dated 03.11.2011 | 176 SBD of 2013-14 (3.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14156805
38 | GH-117-1 | 2010-11 | East Champaran | Dhaka | K.G.B.N., Dhaka | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669947
39 | GH-117-2 | 2010-11 | East Champaran | Ghorasahan | K.G.B.N.,Ghorasahan | 475 dated 03.11.2011 | 216 SBD of 2013-14 (31.12.2013) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14669946
40 | GH-118-1 | 2010-11 | East Champaran | Kesariya | K.G.B.N., Kesariya | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 | Inaugurated 16.07.2016 | 31.3.2016 | 12987881
41 | GH-118-2 | 2010-11 | East Champaran | Kotwa | K.G.B.N., Kotwa | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [9 empty] | 1 |  | 31.3.2016 | 12987881
42 | GH-118-3 | 2010-11 | East Champaran | Sangrampur | K.G.B.N., Sangrampur | 475 dated 03.11.2011 | 11 SBD of 2014-15 (16.5.2014) | [8 empty] | 1 |  |  | 31.3.2016 | 10390304
43 | GH-119-1 | 2010-11 | East Champaran | Madhuwan | K.G.B.N., Madhuwan | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
44 | GH-119-2 | 2010-11 | East Champaran | Mehsi | K.G.B.N., Mehsi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
45 | GH-119-3 | 2010-11 | East Champaran | Tetariya | K.G.B.N., Tetariya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Start |  | 0
46 | GH-120-1 | 2010-11 | East Champaran | Ramgharwa | K.G.B.N., Ramgharwa | 475 dated 03.11.2011 | 226 SBD of 2014-15 (04.08.2014 | [8 empty] | 1 |  |  | 31.3.2016 | 10128657
47 | GH-129-1 | 2010-11 | Gopalganj | Baikunthpur | H.S, Sirsa | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-09-30 | 13648071
48 | GH-129-2 | 2010-11 | Gopalganj | Sidhwaliya | H.S, Mahamadpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-09-30 | 13648072
49 | GH-129-3 | 2010-11 | Gopalganj | Manjha | H.S, Manjha(old) H/s Dharm Parsa(New) | 475 dated 03.11.2011 | [10 empty] | 1 | Handover | 2015-09-30 | 13648071
50 | GH-130-1 | 2010-11 | Gopalganj | Panchdewari | H.S, Jamunaha Bazar | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated |  | 14408719
51 | GH-130-2 | 2010-11 | Gopalganj | Bhorey | H.S, Bhore | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 11526975
52 | GH-131-1 | 2010-11 | Gopalganj | Uchakagaon | H.S, Uchakagaon | 475 dated 03.11.2011 | [9 empty] | 1 |  |  |  | 13375616
53 | GH-131-2 | 2010-11 | Gopalganj | Kateya | Kanya H.S, Kateya(old) G.A H/S Kateya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Land Dispute |  | 0
54 | GH-132-1 | 2010-11 | Gopalganj | Kuchaikote | H.S, Sonekola | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-03-20 | 14619495
55 | GH-132-2 | 2010-11 | Gopalganj | Gopalganj | S.S Girls Inter School, Gopalganj | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 2015-03-20 | 14619495
56 | GH-150-1 | 2010-11 | Jamui | Khaira | Project G.H.S, Khaira | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-09-20 | 11102710
57 | GH-150-2 | 2010-11 | Jamui | Sono | Project H.S, Sona | 475 dated 03.11.2011 | 86 SBD 2013-14 (26.8.2013) | [9 empty] | 1 | Inaugurated | 2015-02-25 | 11102709
58 | GH-113-1 | 2010-11 | Jehanabad | Jehanabad | H.S., Jehanabad | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
59 | GH-113-2 | 2010-11 | Jehanabad | Kako | H.S. Pali Bazar | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
60 | GH-113-3 | 2010-11 | Jehanabad | Ghosi | H.S. Ghosi | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started. EMD to be returned |  | 0
61 | GH-114-1 | 2010-11 | Jehanabad | Ratni Faridpur | H.S. Dayalbagh, Nehalpur | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not started EMD to be returned |  | 0
62 | GH-114-2 | 2010-11 | Jehanabad | Makhdumpur | S.S. Tehta | 475 dated 03.11.2011 |  | 1 | [9 empty] | Low land. EMD to be returned |  | 0
63 | GH-115-1 | 2010-11 | Jehanabad | Hulashganj | H.S. Hulashganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Local problem. EMD to be returned |  | 0
64 | GH-115-2 | 2010-11 | Jehanabad | Modanganj | D.N.H.S. Bandhuganj | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not Started. EMD to be returned |  | 0
65 | GH-111-1 | 2010-11 | Kaimur | Durgawati | K.G.B.V. Compound | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14150475
66 | GH-111-2 | 2010-11 | Kaimur | Adhaura | H. S. Adhaura | 475 dated 03.11.2011 | 18.11.2013 | [9 empty] | 1 | Inaugurated | 31.01.2017 | 14150474
67 | GH-27-1 | 2009-10 | Katihar | Kadwa | N.C.C. Smarak H.S Balia Belon | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 13455545
68 | GH-27-2 | 2009-10 | Katihar | Balrampur | S.S., High School, Telta | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2016-01-15 | 13455546
69 | GH-27-3 | 2009-10 | Katihar | Sameli | D.G.H.S., Krishna Nagar | BMSP/INF-253/2012-867 | 83 SBD of 2013-2014 26.08.2013 | [9 empty] | 1 | Inaugurated | 2015-02-04 | 13455545
70 | GH-28-1 | 2009-10 | Katihar | Manihari | B.P.S.P.H.S., Manihari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-12-28 | 14782767
71 | GH-28-2 | 2009-10 | Katihar | Azamnagar | H.S., Salmari | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | [9 empty] | 1 | Inaugurated | 2014-11-28 | 14782767
72 | GH-28-3 | 2009-10 | Katihar | Pranpur | M.S., Bastol | BMSP/INF-253/2012-867 | 115 SBD of 2013-2014 23.08.2013 | 1 | [9 empty] | Land Dispute |  | 0
73 | GH-29-1 | 2009-10 | Katihar | Falka | B.S.M.High School, Pothiya | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780
74 | GH-29-2 | 2009-10 | Katihar | Kursela | Sampat Raj Devi Girl's H.S., Kursela | BMSP/INF-253/2012-867 | 28 SBD of 2013-2014 17.05.2013 | [8 empty] | 1 |  |  |  | 12242780
75 | GH-34-1 | 2009-10 | Lakhisarai | Surajgarha | Project K. K.H., Surajgarha | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | 1 | [9 empty] | Land not available |  | 0
76 | GH-34-2 | 2009-10 | Lakhisarai | Pipariya | M.M.P. H.S., Walipur | BMSP/INF-253/2012-867 | 428 SBD of 2014-15 (06.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11286461
77 | GH-35-1 | 2009-10 | Lakhisarai | Halsi | High School, Halsi | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [8 empty] | 1 |  |  |  | 10390217
78 | GH-35-2 | 2009-10 | Lakhisarai | Ramgarh Chowk | D.M H.S., Sharma | BMSP/INF-253/2012-867 | 120 SBD 2014-15 20.06.2014 | [6 empty] | 1 | [5 empty] | 3896331
79 | GH-151-1 | 2010-11 | Lakhisarai | Lakhisarai | M.V.M H.S.Nayatola, Lakhisarai | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. PPO R.M.S.A |  | 0
80 | GH-151-2 | 2010-11 | Lakhisarai | Barahiya | S.R.R.S Girls H.S, Barahiya | 475 dated 03.11.2011 |  | 1 | [9 empty] | Dropped. Land problem |  | 0
81 | GH-14-1 | 2009-10 | Madhubani | Benipatti | B.J.J.H.S. Adher* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754
82 | GH-14-2 | 2009-10 | Madhubani | Bisfi | H.S. Parsauni* | BMSP/INF-253/2012-867 | 16.3.2013 | [8 empty] | 1 |  |  |  | 12600754
83 | GH-15-1 | 2009-10 | Madhubani | Madhepur | H.S. Madhepur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063
84 | GH-15-2 | 2009-10 | Madhubani | Lakhanaur | P Girl H.S. Lakhanaur* | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168063
85 | GH-15-3 | 2009-10 | Madhubani | Andarathari | M.S., Andarathari | BMSP/INF-253/2012-867 | 15.7.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 11168062
86 | GH-16-1 | 2009-10 | Madhubani | Rajnagar | R. H.S.Raj Nagar* | BMSP/INF-253/2012-867 | 02.12.13 | 1 | [9 empty] | Required land 125'x100' available land50'x25' |  | 0
87 | GH-16-2 | 2009-10 | Madhubani | Pandaul | Anup Lal Project Girls H.S. Barmotra Pandaul* | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084
88 | GH-16-3 | 2009-10 | Madhubani | Babubarhi | M.S., Bhupatti | BMSP/INF-253/2012-867 | 02.12.13 | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 14946084
89 | GH-17-1 | 2009-10 | Madhubani | Ladania | M.S., Ladania Girl's | BMSP/INF-253/2012-867 | 20.8.2013 | 1 | [9 empty] | Land not available |  | 0
90 | GH-17-2 | 2009-10 | Madhubani | Jainagar | M.S., Dullipatti | BMSP/INF-253/2012-867 | 20.8.2013 | [9 empty] | 1 | Inaugurated | 24.11.15 | 15076496
91 | GH-18-1 | 2009-10 | Madhubani | Basopatti | H.S. Basopatti * | BMSP/INF-253/2012-867 | 15.07.13 | [9 empty] | 1 |  |  | 10783387
92 | GH-18-2 | 2009-10 | Madhubani | Madhwapur | H.S. Madhwapur* | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709
93 | GH-18-3 | 2009-10 | Madhubani | Ghoghardiha | H.S., Dewadh | BMSP/INF-253/2012-867 | 15.07.13 | [8 empty] | 1 |  |  |  | 8626709
94 | GH-136-1 | 2010-11 | Madhubani | Kaulahi | H.S, Kaulahi | 475 dated 03.11.2011 | 02.12.13 | 1 | [9 empty] | Land Dispute |  | 0
95 | GH-136-2 | 2010-11 | Madhubani | Harlakhi | H.S, Umgaun | 475 dated 03.11.2011 | 02.12.13 | [9 empty] | 1 | Inaugurated | 22.1.15 | 15632869
96 | GH-33-1 | 2009-10 | Munger | Haveli Kharagpur | Govt.+2 H.S., Haweli Kharagpur | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459708
97 | GH-33-2 | 2009-10 | Munger | Dharahara | K.R.S.K.H H.S., Dharahra | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | 1 | [9 empty] | Land not available |  | 0
98 | GH-33-3 | 2009-10 | Munger | Tetiabamber | Jagannath H.S Tetia Bamber | BMSP/INF-253/2012-867 | 57 SBD OF2013-14 (19.7.2013) | [9 empty] | 1 | Inaugurated |  | 11459707
99 | GH-149-1 | 2010-11 | Munger | Tarapur | M.S, Tarapur | 475 dated 03.11.2011 | 104 SBD 2013-14 (11.9.2013) | [6 empty] | 1 | [5 empty] | 6098553
100 | GH-101-1 | 2010-11 | Patna | Daniyawa | Rajkiyakrit H.S., Sigariyawa | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated 16.07.2016 | 30.04.2016 | 13865367
101 | GH-101-2 | 2010-11 | Patna | Khusrupur | Rajkiyakrit Mahadeo H.S., Fatuwa, Khusrupur | 475 dated 03.11.2011 | 108 SBD of 2013-14/ 18.09.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 13865367
102 | GH-102-1 | 2010-11 | Patna | Bakhtiyarpur | Rajkiyakrit H.S., Salimpur | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | 1 | [9 empty] | Land not available. Site to be changed |  | 0
103 | GH-102-2 | 2010-11 | Patna | Belchhi | Rajkiyakrit H.S., Saksohar | 475 dated 03.11.2011 | 203 SBD of 2013-14/ 13.01.14 | [8 empty] | 1 |  | Flooring (DEBAR) |  | 11920568
104 | GH-103-1 | 2010-11 | Patna | Paliganj | Rajkiyakrit H.S., Paliganj | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  |  |  | 15692151
105 | GH-103-2 | 2010-11 | Patna | Dulhin Bazar | Banshidhari H.S., Bharatpura | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [8 empty] | 1 |  | DEBAR |  | 12553720
106 | GH-103-3 | 2010-11 | Patna | Bikram | Parwati H.S., Bikram | 475 dated 03.11.2011 | 135 SBD of 2013-14/ 10.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 12553721
107 | GH-104-1 | 2010-11 | Patna | Masaurih | Smt. Girija Kuwar H.S., Masaurih | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 | DEBAR | 08.03.17 | 11571154
108 | GH-104-2 | 2010-11 | Patna | Punpun | Sahid Ramanand R. Govind H.S., Punpun | 475 dated 03.11.2011 | 137 SBD of 2013-14/ 22.10.2013 | [9 empty] | 1 |  | 05.03.17 | 11571153
109 | GH-105-1 | 2010-11 | Patna | Patna Sadar (Gramin) | Rajkiyakrit Mahanth Hanuman Sharan H.S.School,Rajapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | 1 | [9 empty] | Land Dispute |  | 0
110 | GH-105-2 | 2010-11 | Patna | Danapur | Baldeo Senior Secondary School, Danapur | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 | Inaugurated | 06.04.2016 | 13012761
111 | GH-105-3 | 2010-11 | Patna | Maner | Rajkiyakrit H/S, Maner | 475 dated 03.11.2011 | 230 SBD of 2013-14 / 03.03.2014 | [9 empty] | 1 |  | 24.12.16 | 13012761
112 | GH-106-1 | 2010-11 | Patna | Mokama | Railway Aided H.S., Mokama | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488
113 | GH-106-2 | 2010-11 | Patna | Ghoswari | Rajkiyakrit H.S., Kumhra | 475 dated 03.11.2011 | 159 SBD of 2013-14/ 26.11.2013 | [9 empty] | 1 | Inaugurated | 30.06.2015 | 14902488
114 | GH-107-1 | 2010-11 | Patna | Barh | Rajkiyakrit Anugrah Narayan Singh Senior Secondary School, Barh | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | [9 empty] | 1 | Inaugurated | 30.04.2016 | 14329584
115 | GH-107-2 | 2010-11 | Patna | Pandarak | Laxmi Narayan Rajbanshi H.S., Dhibar | 475 dated 03.11.2011 | 121 SBD 0f 2013-14/ 4.10.2013 | 1 | [9 empty] | Sufficient land not available |  | 0
116 | GH-108-1 | 2010-11 | Patna | Naubatpur | Rajkiyakrit H.S., Amarpura | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961
117 | GH-108-2 | 2010-11 | Patna | Sampatchak | Gramin S.S.School Chakbairiya, Patna | 475 dated 03.11.2011 | 54 SBD 0f 2013-14/ 19.7.2013 | [9 empty] | 1 | Inaugurated | 30.09.2015 | 14166961
118 | GH-22-1 | 2009-10 | Purnea | Dhamdaha | H.S., Dhamdaha | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808
119 | GH-22-2 | 2009-10 | Purnea | Rupouli | Project Girl's H.S., Rupouli | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742808
120 | GH-22-3 | 2009-10 | Purnea | Bhawanipur | H.S., Bhawanipur | BMSP/INF-253/2012-867 | 82 SBD OF 2013-14 (22.8.2013) | [8 empty] | 1 |  |  |  | 11742809
121 | GH-23-1 | 2009-10 | Purnea | Barharakothi | Shyama H.S., Bhatotar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679264
122 | GH-23-2 | 2009-10 | Purnea | K. Nagar | H.S., Champanagar | BMSP/INF-253/2012-867 | 36 SBD OF 2013-14 (3.6.13) | [8 empty] | 1 |  |  |  | 11679263
123 | GH-24-1 | 2009-10 | Purnea | Purnia East | Proj. Girl's H.S., Ranipatra | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | 1 | [9 empty] | Land not available |  | 0
124 | GH-24-2 | 2009-10 | Purnea | Jalalgarh | N.D Rungata H.S., Jalalgarh | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509025
125 | GH-24-3 | 2009-10 | Purnea | Kasba | Kalanand H.S., Garabnaili | BMSP/INF-253/2012-867 | 197 SBD OF 2013-14 (30.12.13) | [9 empty] | 1 | Inaugurated | 2015-02-09 | 13509024
126 | GH-25-1 | 2009-10 | Purnea | Dagarua | Abul Kalam H.S., Ichalo | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start. Agreement not done |  | 0
127 | GH-25-2 | 2009-10 | Purnea | Srinagar | Govt. S.S., Srinagar | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0
128 | GH-25-3 | 2009-10 | Purnea | Baisi | Proj. Girl's School Baisi | BMSP/INF-253/2012-867 |  | 1 | [9 empty] | Not Start |  | 0
129 | GH-26-1 | 2009-10 | Purnea | Baisa | H.S., Rauta | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541239
130 | GH-26-2 | 2009-10 | Purnea | Amour | Project Girl's School, Amour | BMSP/INF-253/2012-867 | 192 SBD OF 2013-14 (17.12.13) | [8 empty] | 1 |  |  |  | 8541238
131 | GH-110-1 | 2010-11 | Rohtas | Chenari | Middle School, Khurmabad, Chenari | 475 dated 03.11.2011 | 190 SBD of 2013-14/ 16.12.13 | [9 empty] | 1 | Inaugurated | 30.08.2015 | 13987787
132 | GH-141-1 | 2010-11 | Saharsa | Kahra | Govt. Girls H. S, Saharsa | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981
133 | GH-141-2 | 2010-11 | Saharsa | Saur Bazar | Gajadhar Sahu H.S, Saur Bazar | 475 dated 03.11.2011 | 49 SBD OF2013-14 (9.7.2013) | [9 empty] | 1 | Inaugurated | 30.03.15 | 13907981
134 | GH-142-1 | 2010-11 | Saharsa | Salkhua | H.S, Salkhua | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | 1 | [9 empty] | Land not available. |  | 0
135 | GH-142-2 | 2010-11 | Saharsa | Sonbarsa | Sir Hariballabh Inst. | 475 dated 03.11.2011 | 208 SBD OF2013-14 (16.1.2014) | [9 empty] | 1 |  |  | 12885961
136 | GH-19-1 | 2009-10 | Samastipur | Singhia | K.G., Academy, Singhia | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available (required land 125'x100' avlaible land22'x11') |  | 0
137 | GH-19-2 | 2009-10 | Samastipur | Bithan | H.S., Bithan | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 30.9.15 | 14010421
138 | GH-20-1 | 2009-10 | Samastipur | Warisnagar | M.S., Hajpurwa, Warisnagar | BMSP/INF-253/2012-867 | 24.04.13 | [9 empty] | 1 | Inaugurated | 23.10.15 | 15193375
139 | GH-20-2 | 2009-10 | Samastipur | Marwa | H.S., Morwa | BMSP/INF-253/2012-867 | 24.04.13 | 1 | [9 empty] | Land not available. (required land 125'x100' avlaible landx18'x13') |  | 0
140 | GH-137-1 | 2010-11 | Samastipur | Kalyanpur | K.G.B.V, Kalyanpur | 475 dated 03.11.2011 | 27.01.14 | 1 | [9 empty] | Land not available |  | 0
141 | GH-137-2 | 2010-11 | Samastipur | Pusa | Girls Int. Sch. Pusa | 475 dated 03.11.2011 | 27.01.14 | [9 empty] | 1 | Inaugurated | 15.12.15 | 14509763
142 | GH-138-1 | 2010-11 | Samastipur | Ujiarpur | B.R.C, Ujiarpur Campus | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739
143 | GH-138-2 | 2010-11 | Samastipur | Sarayranjan | H.S, Bathua Bujurg | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405739
144 | GH-138-3 | 2010-11 | Samastipur | Samastipur | M. I. S. Samastipur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated | 28.2.16 | 13405740
145 | GH-139-1 | 2010-11 | Samastipur | Vidyapati Nagar | I.Sch.Vidyapati Nagar N | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
146 | GH-139-2 | 2010-11 | Samastipur | Bibhutipur | M.S, Sirsi | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
147 | GH-139-3 | 2010-11 | Samastipur | Dalsingh Sarai | C.H. I. S.Dalsingh Sarai | 475 dated 03.11.2011 | 13.12.2014 | [9 empty] | 1 | Inaugurated | 12.9.15 | 13241591
148 | GH-140-1 | 2010-11 | Samastipur | Hasanpur | N.H.S, Hasanpur Road | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268
149 | GH-140-2 | 2010-11 | Samastipur | Sihivaji nagar | H.S, Shivaji Nagar | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648268
150 | GH-140-3 | 2010-11 | Samastipur | Khanpur | I.Sch. Siropatti Khatu | 475 dated 03.11.2011 | 04.10.13 | [9 empty] | 1 | Inaugurated | 18.3.16 | 14648267
151 | GH-12-1 | 2009-10 | Saran | Marhourah | U.M.S., Awari, Marhourah | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | [9 empty] | 1 | Inaugurated |  | 11673134
152 | GH-12-2 | 2009-10 | Saran | Taraiyan | M.S., Gawandary, Taria | BMSP/INF-253/2012-867 | 20 SBD of 2014-2015 20.05.2014 | 1 | [9 empty] | Location changed & But Land Problem |  | 0
153 | GH-13-1 | 2009-10 | Saran | Parsa | M.S., Bishnupur, Parsa | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | [9 empty] | 1 | Inaugurated. Handover | 2015-07-17 | 13994126
154 | GH-13-2 | 2009-10 | Saran | Ishuapur | U.M.S., Satasi, Ishuapur | BMSP/INF-253/2012-867 | 48 SBD of 2013-2014 8.07.2013 | 1 | [9 empty] | Land problem |  | 0
155 | GH-126-1 | 2010-11 | Saran | Garkha | MS Chainpur Bhaiswara | 475 dated 03.11.2011 | [10 empty] | 1 |  | 2015-12-31 | 14183475
156 | GH-126-2 | 2010-11 | Saran | Maker | UMS Baghakol | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-31 | 14183475
157 | GH-01-1 | 2009-10 | Sitamarhi | Parihar | S.G.H.S., Parihar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
158 | GH-01-2 | 2009-10 | Sitamarhi | Sonbarsa | H.S., Bhutahi | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
159 | GH-01-3 | 2009-10 | Sitamarhi | Bathnaha | H.S., Yogibana Bazar | BMSP/INF-253/2012-867 | 122 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14659623
160 | GH-02-1 | 2009-10 | Sitamarhi | Parsauni | H.S., Parsauni Chowk | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029
161 | GH-02-2 | 2009-10 | Sitamarhi | Riga | H.S., Rewasi | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022030
162 | GH-02-3 | 2009-10 | Sitamarhi | Belsand | H.S., Belsand | BMSP/INF-253/2012-867 | 529 SBD OF 14-15 (17.12.14 | [9 empty] | 1 | Inaugurated 16.07.2016 | 19.3.16 | 16022029
163 | GH-3-1 | 2009-10 | Sitamarhi | Bairgania | Jaurimal H.S., Bairgania | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP (Letter given)/13/12/2014 |  | 4751468
164 | GH-3-2 | 2009-10 | Sitamarhi | Suppi | H.S., Suppi | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/12-04-2015 |  | 4751467
165 | GH-3-3 | 2009-10 | Sitamarhi | Majarganj | H.S., Majarganj | BMSP/INF-253/2012-867 | 500 SDB OF 14-15 (12.12.14) | [5 empty] | 1 |  |  |  |  | STOP/5-12-2014 |  | 4751468
166 | GH-4-1 | 2009-10 | Sitamarhi | Sursand | Saryu H.S., Sursand | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [8 empty] | 1 |  |  |  | 13056903
167 | GH-4-2 | 2009-10 | Sitamarhi | Pupri | Proj. H.S., Pupri | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | 1 | [9 empty] | small land |  | 0
168 | GH-4-3 | 2009-10 | Sitamarhi | Choraut | H.S., Choraut | BMSP/INF-253/2012-867 | 429 SBD OF 14-15 (6.11.14) | [9 empty] | 1 |  |  | 16321128
169 | GH-5-1 | 2009-10 | Sitamarhi | Bajpatti | H.S., Bajpatti | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
170 | GH-5-2 | 2009-10 | Sitamarhi | Nanpur | H.S., Janipur | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
171 | GH-5-3 | 2009-10 | Sitamarhi | Bokhra | H.S., Kharka | BMSP/INF-253/2012-867 | 123 SBD OF 2012-13(16.3.2013) | [9 empty] | 1 | Inaugurated | 30.4.16 | 14935363
172 | GH-6-1 | 2009-10 | Sitamarhi | Dumra | K.G.H.S., Dumra | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673297
173 | GH-6-2 | 2009-10 | Sitamarhi | Runni saidpur | H.S., Morsand | BMSP/INF-253/2012-867 | 124 SBD OF 2012-13(16.3.2013) | [8 empty] | 1 |  | plaster internal |  | 12673296
174 | GH-127-1 | 2010-11 | Siwan | Maharajganj | H.S.Sikatiya | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881
175 | GH-127-2 | 2010-11 | Siwan | Barhariya | Sri Krishan H.S. Kailgarh | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778882
176 | GH-127-3 | 2010-11 | Siwan | Bhagwanpur Hatt | S.S. High School, Bhagawanpur Hatt | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-08-06 | 13778881
177 | GH-128-1 | 2010-11 | Siwan | Goreya Kothi | Narayan Karmayogi H.S, Goreyakothi | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
178 | GH-128-2 | 2010-11 | Siwan | Basantpur | H.S, Basantpur | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
179 | GH-128-3 | 2010-11 | Siwan | Dharaunda | G.S. H.S, Ujaini | 475 dated 03.11.2011 | [10 empty] | 1 | Inaugurated. Handover | 2015-12-28 | 12873620
180 | GH-21-1 | 2009-10 | Supaul | Raghopur | M.S., Kajayan, Raghopur | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265108
181 | GH-21-2 | 2009-10 | Supaul | Pratapganj | Public H.S., Pratapganj | BMSP/INF-253/2012-867 | 11 SBD of 2013-2014 20-04-2013 | [9 empty] | 1 | Inaugurated | 16.07.2015 | 12265107
182 | GH-121-1 | 2010-11 | Vaishali | Rajapakar | H.S.,Rajapakar | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | 1 | [11 empty] | 0
183 | GH-121-2 | 2010-11 | Vaishali | Mahua | M.S. Singhara | 475 dated 03.11.2011 | 69 SBD OF2013-14 (30.7.2013) | [9 empty] | 1 | Inaugurated | 18.5.15 | 14587944
184 | GH-122-1 | 2010-11 | Vaishali | Raghopur | B.S.J.S.H.S.Fatehpur, Vaishali | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Land problem |  | 0
185 | GH-122-2 | 2010-11 | Vaishali | Bidupur | S.S.V.M.H.S., Ramdauli | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | [9 empty] | 1 | Inaugurated | 28.4.16 | 13567869
186 | GH-122-3 | 2010-11 | Vaishali | Deshri | H.S. Bhataulla | 475 dated 03.11.2011 | 109 SBD OF2013-14 (18.9.2013) | 1 | [9 empty] | Dismantling |  | 0
187 | GH-123-1 | 2010-11 | Vaishali | Patepur | S.R.C.H.S.,Patepur, Vaishali | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 13868106
188 | GH-123-2 | 2010-11 | Vaishali | Lalganj | G.A.H/S, Lalganj | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0
189 | GH-123-3 | 2010-11 | Vaishali | Goraul | H.S., Goraul | 475 dated 03.11.2011 | 462 SBD OF 14-15 (18.11.14) | 1 | [9 empty] | Land in Field Area Headmaster Objecting To Construct |  | 0
190 | GH-124-1 | 2010-11 | Vaishali | Vaishali | S.M.T.H.S., Vaishali | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | 1 | [9 empty] | No apparoch road |  | 0
191 | GH-124-2 | 2010-11 | Vaishali | Bhagwanpur | M.S.Ratnapura Bhagwanpur | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [9 empty] | 1 | Inaugurated 16.07.2016 |  | 26954587
192 | GH-124-3 | 2010-11 | Vaishali | Chehrakala | B.N. High School, Sehan * | 475 dated 03.11.2011 | 253 SBD OF 2014-15(11.08.14) | [8 empty] | 1 |  |  |  | 0
193 | GH-125-1 | 2010-11 | West Champaran | Bagha-1 | R.S.H.S. Parsuniform | 475 dated 03.11.2011 |  | 1 | [9 empty] | Not start |  | 0
Total No. of Schools (Girls Hostel) 2009-10 & 2010-11 |  |  |  |  | 193 |  |  | 47 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 27 | 113

## Sheet4
Summary Report of Physical and Financial Status of Girls Hostel 2009-10 & 2010-11
SL. No. | District Name | Girls Hostel 2009-10 | [11 empty] | Girls Hostel 2010-11 | [11 empty] | Girls Hostel 2009-10 & 2010-11
|  | Not Started | Lay-outed | Foundationd | Plinth | GF-LL | GF-RL | FF-LL2 | FF-RL | Finishing | Inprogress | Completed | Sum of Total Completion Cost | Not Started | Lay-outed | Foundationd | Plinth | GF-LL | GF-RL | FF-LL2 | FF-RL | Finishing | Inprogress | Completed | Sum of Total Completion Cost | Not Started | Lay-outed | Foundationd | Plinth | GF-LL | GF-RL | FF-LL2 | FF-RL | Finishing | Inprogress | Completed | Sum of Total Completion Cost
1 | Arwal | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2 | 24358041 | [9 empty] | 0 | 2 | 24358041
2 | Aurangabad | 2 | [8 empty] | 0 | 2 | 27325759 | 0 | [8 empty] | 0 | 0 | 0 | 2 | [8 empty] | 0 | 2 | 27325759
3 | Banka | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 13168871 | [9 empty] | 0 | 1 | 13168871
4 | Bhagalpur | 4 | [8 empty] | 0 | 2 | 24766040 | 0 | [8 empty] | 0 | 10 | 135146746 | 4 | [8 empty] | 0 | 12 | 159912786
5 | Bhojpur | 0 | [7 empty] | 2 | 2 | 0 | 19518834 | 0 | [8 empty] | 0 | 0 | 0 | [8 empty] | 2 | 2 |  | 19518834
6 | Buxar | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3 | 41512903 | [9 empty] | 0 | 3 | 41512903
7 | Darbhanga | 0 | [8 empty] | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  | 1 | 6 | 99997730 | [6 empty] | 1 |  |  | 1 | 6 | 99997730
8 | East Champaran | 0 | [8 empty] | 0 | 0 | 0 | 4 | [7 empty] | 2 | 2 | 5 | 89991421 | 4 | [7 empty] | 2 | 2 | 5 | 89991421
9 | Gopalganj | 0 | [8 empty] | 0 | 0 | 0 | 1 | [7 empty] | 2 | 2 | 6 | 109494514 | 1 | [7 empty] | 2 | 2 | 6 | 109494514
10 | Jamui | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2 | 22205419 | [9 empty] | 0 | 2 | 22205419
11 | Jehanabad | 0 | [8 empty] | 0 | 0 | 0 | 7 | [8 empty] | 0 | 0 | 0 | 7 | [8 empty] | 0 |  | 0
12 | Kaimur | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2 | 28300949 | [9 empty] | 0 | 2 | 28300949
13 | Katihar | 1 | [7 empty] | 2 | 2 | 5 | 94417730 | 0 | [8 empty] | 0 | 0 | 0 | 1 | [7 empty] | 2 | 2 | 5 | 94417730
14 | Lakhisarai | 1 | [5 empty] | 1 |  | 1 | 2 | 1 | 25573009 | 2 | [8 empty] | 0 | 0 | 0 | 3 | [5 empty] | 1 |  | 1 | 2 | 1 | 25573009
15 | Madhubani | 2 | [7 empty] | 4 | 4 | 7 | 131711165 | 1 | [8 empty] | 0 | 1 | 15632869 | 3 | [7 empty] | 4 | 4 | 8 | 147344034
16 | Munger | 1 | [8 empty] | 0 | 2 | 22919415 | 0 | [5 empty] | 1 |  |  | 1 | 0 | 6098553 | 1 | [5 empty] | 1 |  |  | 1 | 2 | 29017968
17 | Patna | 0 | [8 empty] | 0 | 0 | 0 | 3 | [7 empty] | 3 | 3 | 12 | 202087205 | 3 | [7 empty] | 3 | 3 | 12 | 202087205
18 | Purnea | 4 | [7 empty] | 7 | 7 | 2 | 102687478 | 0 | [8 empty] | 0 | 0 | 0 | 4 | [7 empty] | 7 | 7 | 2 | 102687478
19 | Rohtas | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 13987787 | [9 empty] | 0 | 1 | 13987787
20 | Saharsa | 0 | [8 empty] | 0 | 0 | 0 | 1 | [8 empty] | 0 | 3 | 40701923 | 1 | [8 empty] | 0 | 3 | 40701923
21 | Samastipur | 2 | [8 empty] | 0 | 2 | 29203796 | 1 | [8 empty] | 0 | 10 | 138396557 | 3 | [8 empty] | 0 | 12 | 167600353
22 | Saran | 2 | [8 empty] | 0 | 2 | 25667260 | 0 | [8 empty] | 0 | 2 | 28366950 | 2 | [8 empty] | 0 | 4 | 54034210
23 | Sitamarhi | 1 |  |  |  |  | 3 |  |  | 3 | 6 | 10 | 205830073 | 0 | [8 empty] | 0 | 0 | 0 | 1 |  |  |  |  | 3 |  |  | 3 | 6 | 10 | 205830073
24 | Siwan | 0 | [8 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 6 | 79957504 | [9 empty] | 0 | 6 | 79957504
25 | Supaul | 0 | [8 empty] | 0 | 2 | 24530215 | 0 | [8 empty] | 0 | 0 | 0 | [9 empty] | 0 | 2 | 24530215
26 | Vaishali | 0 | [8 empty] | 0 | 0 | 0 | 6 | [7 empty] | 1 | 1 | 4 | 68978506 | 6 | [7 empty] | 1 | 1 | 4 | 68978506
27 | West Champaran | 0 | [8 empty] | 0 | 0 | 0 | 1 | [8 empty] | 0 | 0 | 0 | 1 | [8 empty] | 0 |  | 0
Grand Total |  | 20 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 19 | 23 | 37 | 734150774 | 27 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 8 | 10 | 76 | 1158384448 | 47 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 27 | 33 | 113 | 1892535222
80