## USSS (2011-12)
BSEIDC Ltd., Patna
Physical Status of USSS (2011-12)
S.N. | Group No. |  |  |  | Division | Name of District | Name of Block | S.N. | Name of School |  | Name of Agency | Retrender | Tender Process | Physical Status | [10 empty] | Remarks | Session
|  | BMSP Portion Expenses | State Govt.Portion Expenses | Total Expenses | [5 empty] | Agreement No. |  |  |  | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | Date of Completion
[18 empty] | LL | RL | LL | RL
1 | USSS-26 (A) |  |  |  | Patna East | Nalanda |  | 1 | Middle School, Basuan |  | No bidder | 1 | [12 empty] | Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
2 | USSS-26 (B) |  |  |  | Patna East | Nalanda |  | 2 | Middle School, Malikpur |  | DHARMENDRA KUMAR 9771493663 |  |  | 1 | [10 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
3 | USSS-26 (C) |  |  |  | Patna East | Nalanda |  | 3 | Middle School, Mohaddinpur |  | ANJANI KUMAR. 7033094100, 9204611556 |  |  | 1 | [10 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
4 | USSS-26 (D) |  |  |  | Patna East | Nalanda |  | 4 | Middle School, Jagdishpur Tayari |  | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 |  |  |  | 1 | [9 empty] | E/W | 2011-12
5 | USSS-26 (E) |  |  |  | Patna East | Nalanda |  | 5 | Middle School, Puraini |  | DHARMENDRA KUMAR 9771493663 |  |  | 1 | [10 empty] | LOA Issue. Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-578 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
6 | USSS-26 (F) |  |  |  | Patna East | Nalanda |  | 6 | Middle School, Lodipur |  | Tender Process |  | 1 | [11 empty] | Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-577 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
7 | USSS-27 (A) |  |  |  | Patna East | Patna |  | 1 | Middle School, Diwra |  | SRI SACHCHIDA NAND SINGH 9631260151 |  |  |  | 1 | [9 empty] | E/W start (Place को लेकर स्थानीय लोगों द्वारा Dispute) | 2011-12
8 | USSS-27 (B) |  |  |  | Patna East | Patna |  | 2 | Middle School, Samstichak |  | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 |  |  |  |  | 1 | [8 empty] | Fondation PCC | 2011-12
9 | USSS-27 (C) |  |  |  | Patna East | Patna |  | 3 | Middle School, Pirbarhouna |  | RANA CONSTRUCTION 9334104328 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
10 | USSS-27 (D) |  |  |  | Patna East | Patna |  | 4 | Middle School, Gangachak |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
11 | USSS-28-1 |  |  |  | Patna East | Patna |  | 1 | Middle School, Karai |  | Shilendra kumar |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-582 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
12 | USSS-29-1 |  |  |  | Patna East | Bhojpur | Barhara | 1 | Govt. Middle School, Kudariya Parshurampur |  | Narendra kumar |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
13 | USSS-29-2 |  |  |  | Patna East | Bhojpur | Barhara | 2 | Upgraded Middle School, Paiga |  | Narendra kumar |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
14 | USSS-29-3 |  |  |  | Patna East | Bhojpur | Ara | 3 | Upgraded Middle School, Barouli |  | Narendra kumar |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
15 | USSS-29-4 |  |  |  | Patna East | Bhojpur | Ara | 4 | Middle School, Barka Dumra |  | Narendra kumar |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
16 | USSS-29-5 |  |  |  | Patna East | Bhojpur | Garahni | 5 | Upgraded Middle School, Dadiyabag |  | Narendra kumar |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
17 | USSS-29-6 |  |  |  | Patna East | Bhojpur | Koielwar | 6 | Upgraded Middle School, Bhoparpur |  | Tender Process |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-584 /20.11.16 द्वारा अनुरोध किया गया. 46/2013-19 | 2011-12
18 | USSS-30-1 |  |  |  | Patna East | Bhojpur | Tarari | 1 | Middle School, Sara |  | Narendra kumar |  |  |  |  | 1 | [8 empty] | E/W | 2011-12
19 | USSS-30-2 |  |  |  | Patna East | Bhojpur | Tarari | 2 | Middle School, Bhakura |  | Narendra kumar |  |  |  |  | 1 | [8 empty] | E/w | 2011-12
20 | USSS-30-3 |  |  |  | Patna East | Bhojpur | Pero | 3 | Middle School, Dhanpura |  | Narendra kumar |  |  |  |  | 1 | [8 empty] | E/w | 2011-12
21 | USSS-30-4 |  |  |  | Patna East | Bhojpur | Sahar | 4 | Middle School, Perhap |  | Narendra kumar |  |  | 1 | [10 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
22 | USSS-30-5 |  |  |  | Patna East | Bhojpur | Sahar | 5 | Middle School, Nonuar |  | Narendra kumar |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-580 /20.11.16 तथा DEO से पत्रांक 661 दिनांक 24.12.16 द्वारा अनुरोध किया गया है | 2011-12
23 | USSS-30-6 |  |  |  | Patna East | Bhojpur | Sahar | 6 | Middle School, Purhara |  | Tender Process | 1 | [12 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
24 | USSS-31 (A) |  |  |  | Patna West | Buxar | ब्रहम्‍पुर | 1 | Middle School, Bhadwar |  | Sanjay Kumar Tiwary |  |  |  |  | 1 | [9 empty] | 2011-12
25 | USSS-31 (B) |  |  |  | Patna West | Buxar | ब्रहम्‍पुर | 2 | Girl Middle School, Akrasi |  | Satyam Enterprises |  |  | 1 | [10 empty] | LOA Issue. Low land about 4'. | 2011-12
26 | USSS-32-1 | 5812000 | 3164852 | 8976852 | Patna West | Kaimur Bhabhua | चैनपुर | 1 | Middle School, Dhardihan |  | KRISHNA | [10 empty] | 1 |  |  |  | 2011-12
27 | USSS-32-2 |  |  | 0 | Patna West | Kaimur Bhabhua | चॉंद | 2 | Upgraded Middle School, Chouri |  | KRISHNA |  |  | 1 | [10 empty] | Encrochment | 2011-12
28 | USSS-32-3 | 5812000 | 4749002 | 10561002 | Patna West | Kaimur Bhabhua | भगवानपुर | 3 | Middle School, Dadar |  | KRISHNA | [11 empty] | 1 |  | Handover | 2011-12
29 | USSS-32-4 | 5812000 | 3164852 | 8976852 | Patna West | Kaimur Bhabhua | रामपुर | 4 | Middle School, Lohandi |  | KRISHNA | [10 empty] | 1 |  |  |  | 2011-12
30 | USSS-32-5 | 5808552 | 0 | 5808552 | Patna West | Kaimur Bhabhua | मोहनियॉं | 5 | Middle School, Badhani |  | KRISHNA | [9 empty] | 1 |  |  |  |  | 2011-12
31 | USSS-33 (A) |  |  | 0 | Patna West | Rohtas | दावत | 1 | Middle School, Parmdiha |  | RAJENDRA SINGH 9430226175 |  |  |  |  | 1 | [9 empty] | 2011-12
32 | USSS-33 (B) |  |  | 0 | Patna West | Rohtas | नोखा | 2 | Middle School, Hathini |  | ARSA INFRATECH PRIVATE LIMITED 9308676177 |  |  | 1 | [10 empty] | LOA Issue. Land not available. | 2011-12
33 | USSS-33 (C) |  |  | 0 | Patna West | Rohtas | काराकाट | 3 | Middle School, Itdhiyan |  | A B CONSTRUCTION 7250583221 | [5 empty] | 1 | [7 empty] | LOA Issue | 2011-12
34 | USSS-34-1 | 5812000 | 3160285 | 8972285 | Patna West | Rohtas | अकोढ़ीगोला | 1 | Middle School, Gobardhanpur |  | SHALINI SINGH | [10 empty] | 1 |  |  |  | 2011-12
35 | USSS-34-2 | 5812000 | 4743630 | 10555630 | Patna West | Rohtas | डिहरी | 2 | Middle School, Tandwa |  | SHALINI SINGH | [11 empty] | 1 |  |  | 2011-12
36 | USSS-34-3 | 5812000 | 4743630 | 10555630 | Patna West | Rohtas | काराकाट | 3 | Middle School, Danwar |  | SHALINI SINGH | [11 empty] | 1 |  |  | 2011-12
37 | USSS-35 (A) |  |  | 0 | Patna West | Rohtas | करहगर | 1 | Upgraded Middle School, Rehari |  | ANIL RAY 9507466444 |  |  |  |  | 1 | [9 empty] | 2011-12
38 | USSS-35 (B) |  |  | 0 | Patna West | Rohtas | Rohtas | 2 | Middle School, Majhiyawan |  | UDAY KUMAR 9955691188 |  |  | 1 | [10 empty] | LOA Issue. Less land and dispute | 2011-12
39 | USSS-35-3 |  |  | 0 | Patna West | Rohtas |  | 3 | Middle School, Ghordihi |  | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [12 empty] | Tender Process | 2011-12
40 | USSS-36 (A) |  |  | 0 | Magadh | Jahanabad |  | 1 | Middle School, Ahiyasa |  | PRAVEEN KUMAR 7033712900 | [5 empty] | 1 | [8 empty] | 2011-12
41 | USSS-36 (B) |  |  | 0 | Magadh | Jahanabad |  | 2 | Middle School,Sewnon |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
42 | USSS-36 (C) |  |  | 0 | Magadh | Jahanabad |  | 3 | Middle School, Dewra |  | PRAVEEN KUMAR 7033712900 | [6 empty] | 1 | [7 empty] | 2011-12
43 | USSS-37 (A) |  |  | 0 | Magadh | Aurangabad |  | 1 | Middle School, Kusumbasdiha |  | DHANANJAY KUMAR SINGH 9931845497 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
44 | USSS-37 (B) |  |  | 0 | Magadh | Aurangabad |  | 2 | Middle School, Pandu |  | DHANANJAY KUMAR SINGH 9931845497 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
45 | USSS-38-1 |  |  | 0 | Magadh | Aurangabad |  | 1 | Middle School, Gamharia |  | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
46 | USSS-38-2 |  |  | 0 | Magadh | Aurangabad |  | 2 | Middle School,Sondiha |  | MS MATESHWARI CONSTRUCTION, 7766886737 | [6 empty] | 1 | [7 empty] | 2011-12
47 | USSS-38-3 |  |  | 0 | Magadh | Aurangabad |  | 3 | Middle School, Raslpur |  | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
48 | USSS-39-1 |  |  | 0 | Magadh | Aurangabad |  | 1 | Middle School, Chourahi |  | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
49 | USSS-39-2 |  |  | 0 | Magadh | Aurangabad |  | 2 | Middle School, Sonbarsa |  | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
50 | USSS-39-3 |  |  | 0 | Magadh | Aurangabad |  | 3 | Middle School, Dandwan |  | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
51 | USSS-40 (A) |  |  | 0 | Magadh | Aurangabad |  | 1 | Middle School, Meh |  | MANOJ SINGH, 9939822131, 7033944511 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
52 | USSS-40 (B) |  |  | 0 | Magadh | Aurangabad |  | 2 | Middle School, Tamoli |  | MANOJ SINGH, 9939822131, 7033944511 | [5 empty] | 1 | [8 empty] | 2011-12
53 | USSS-41 (A) |  |  | 0 | Magadh | Gaya |  | 1 | Middle School, Shyamnagar Nima |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
54 | USSS-41 (B) |  |  | 0 | Magadh | Gaya |  | 2 | Middle School, Khajuria |  | NAGENDRA SINGH 9631326479 | [5 empty] | 1 | [8 empty] | 2011-12
55 | USSS-41 (C) |  |  | 0 | Magadh | Gaya |  | 3 | Middle School, Parsawan Khurd |  | SURENDRA KUMAR 9128027943 |  |  |  |  | 1 | [9 empty] | 2011-12
56 | USSS-41 (D) |  |  | 0 | Magadh | Gaya |  | 4 | Middle School, Belauti |  | SANJAY KUMAR SINGH 9973456006 | [5 empty] | 1 | [8 empty] | 2011-12
57 | USSS-41 (E) |  |  | 0 | Magadh | Gaya |  | 5 | Middle School,Bindhua |  | MRITUNJAY KUMAR SINGH 9097394660 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
58 | USSS-42 (A) |  |  | 0 | Magadh | Gaya |  | 1 | Middle School, Sondiha |  | SANJAY KUMAR SINGH 9973456006 |  |  |  |  | 1 | [9 empty] | 2011-12
59 | USSS-42 (B) |  |  | 0 | Magadh | Gaya |  | 2 | Middle School, Angara |  | NARENDRA YADAB 99315315191 |  |  |  |  | 1 | [9 empty] | 2011-12
60 | USSS-42 (C) |  |  | 0 | Magadh | Gaya |  | 3 | Middle School, Punakalan |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
61 | USSS-42 (D) |  |  | 0 | Magadh | Gaya |  | 4 | Middle School, Noni |  | RAVIN KUMAR 8797253525 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
62 | USSS-43-1 | 5812000 | 5163904 | 10975904 | Magadh | Gaya |  | 1 | Upgraded Middle School, Pater |  | Mithlesh Kumar Singh, 9931471924 | [11 empty] | 1 |  |  | 2011-12
63 | USSS-43-2 |  |  | 0 | Magadh | Gaya |  | 2 | Middle School, Bitho |  | Mithlesh Kumar Singh, 9931471924 |  |  | 1 | [10 empty] | Local Dispute | 2011-12
64 | USSS-44 (A) |  |  | 0 | Magadh | Nawada |  | 1 | Middle School, Bardhauna |  | RAJNISH VATS 8051666426 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
65 | USSS-44 (B) |  |  | 0 | Magadh | Nawada |  | 2 | Upgraded Middle School, Puraini |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
66 | USSS-44 (C) |  |  | 0 | Magadh | Nawada |  | 3 | Middle School, Kalound |  | SUDHIR KUMAR 9430411061 | [9 empty] | 1 |  |  |  |  | 2011-12
67 | USSS-44 (D) |  |  | 0 | Magadh | Nawada |  | 4 | Middle School, Paingari |  | SUDHIR KUMAR 9430411061 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
68 | USSS-44 (E) |  |  | 0 | Magadh | Nawada |  | 5 | Upgraded Middle School, Bhatta |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
69 | USSS-17 (A) |  |  | 0 | Bhagalpur | Bhagalpur |  | 1 | Middle School Kishanpur |  | Dayanand Singh |  |  | 1 | [10 empty] | LOA Issue | 2011-12
70 | USSS-17 (B) |  |  | 0 | Bhagalpur | Bhagalpur |  | 2 | Middle School Tarchha |  | Retender |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
71 | USSS-18-1 |  |  | 0 | Bhagalpur | Bhagalpur |  | 1 | Middle School Ghanshyamchak |  | Retender |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
72 | USSS-19-1 | 5812000 | 5981953 | 11793953 | Bhagalpur | Bhagalpur |  | 1 | Middle School Kalgiganj |  | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 2011-12
73 | USSS-19-2 | 5812000 | 5981953 | 11793953 | Bhagalpur | Bhagalpur |  | 2 | Middle School Dayalpur |  | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 2011-12
74 | USSS-19-3 | 5812000 | 5981953 | 11793953 | Bhagalpur | Bhagalpur |  | 3 | Middle School Siya |  | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 2011-12
75 | USSS-19-4 | 5812000 | 5981954 | 11793954 | Bhagalpur | Bhagalpur |  | 4 | Middle School Kishunichak |  | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 2011-12
76 | USSS-20 (A) |  |  | 0 | Bhagalpur | Banka |  | 1 | Middle School kairi |  | Kundan Kumar Singh | [14 empty] | 2011-12
77 | USSS-20 (B) |  |  | 0 | Bhagalpur | Banka |  | 2 | Middle School Bank |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
78 | USSS-20 (C) |  |  | 0 | Bhagalpur | Banka |  | 3 | Middle School Pathdda |  | Lalan Kumar |  |  | 1 | [10 empty] | LOA Issue | 2011-12
79 | USSS-21 (A) |  |  | 0 | Munger | Munger |  | 1 | Middle School Harinmar Bishunpur |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
80 | USSS-21 (B) |  |  | 0 | Munger | Munger |  | 2 | Middle School Manik Mandal Tola |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
81 | USSS-21 (C) |  |  | 0 | Munger | Munger |  | 3 | Middle School Kalyanpur |  | ANIL KUMAR SINGH 9570904951 |  |  | 1 | [11 empty] | 2011-12
82 | USSS-21 (D) |  |  | 0 | Munger | Munger |  | 4 | Middle School Teghara |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
83 | USSS-21 (E) |  |  | 0 | Munger | Munger |  | 5 | Middle School Dhudhaladih |  | No bidder | 1 | [12 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
84 | USSS-22 (A) |  |  | 0 | Munger | Munger |  | 1 | Middle School Ramcharit Maidan |  | DIGBIJAY KUMAR 8084371876 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
85 | USSS-22 (B) |  |  | 0 | Munger | Munger |  | 2 | Middle School Madhura / Katiyari |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
86 | USSS-22 (C) |  |  | 0 | Munger | Munger |  | 3 | Middle School, Dhobai |  | Retender | 1 | [12 empty] | Retender | 2011-12
87 | USSS-22 (D) |  |  | 0 | Munger | Munger |  | 4 | Middle School Nabgoi |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
88 | USSS-23-1 | 5812000 | 3214909 | 9026909 | Munger | Lakhisarai |  | 1 | Middle School, Bahachha |  | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 2011-12
89 | USSS-23-2 | 5812000 | 3214909 | 9026909 | Munger | Lakhisarai |  | 2 | Middle School Tarhari |  | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 2011-12
90 | USSS-23-3 | 5812000 | 3214909 | 9026909 | Munger | Lakhisarai |  | 3 | Middle School Nongarh |  | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 2011-12
91 | USSS-23-4 | 3610762 | 0 | 3610762 | Munger | Lakhisarai |  | 4 | Upgraded Middle School Surari |  | SUGEET KUMAR,9504681342 | [7 empty] | 1 | [6 empty] | 2011-12
92 | USSS-24 (A) |  |  | 0 | Munger | Lakhisarai |  | 1 | Upgraded Middle School Bihraura |  | MS BALRAM KUMAR 9430065800 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
93 | USSS-24 (B) |  |  | 0 | Munger | Lakhisarai |  | 2 | Middle School Pokhrama |  | SAI HIGHWAY AND BUILDERS PVT LTD 9771455967 | [5 empty] | 1 | [8 empty] | 2011-12
94 | USSS-24 (C) |  |  | 0 | Munger | Lakhisarai |  | 3 | Upgraded Middle School Dhoni Kundi |  | MONEY CONSTRUCTION PRIVATE LIMITED 9386596373 | [6 empty] | 1 | [7 empty] | 2011-12
95 | USSS-25-1 | 5812000 | 2975379 | 8787379 | Munger | ks[kiqjk |  | 1 | Middle School, Akrama |  | Epitome Construction Pvt Ltd,8935825344 | [10 empty] | 1 |  |  |  | 2011-12
96 | USSS-25-2 | 4652144 | 0 | 4652144 | Munger | Sheikhpur |  | 2 | Upgraded Middle School, Diha |  | Epitome Construction Pvt Ltd,8935825344 | [7 empty] | 1 | [5 empty] | WORK STOPPED BY DIST ADMN (upto FF sill lv) | 2011-12
97 | USSS-25-3 | 5812000 | 4526093 | 10338093 | Munger | Sheikhpur |  | 3 | Middle School, Kutout |  | Epitome Construction Pvt Ltd,8935825344 | [11 empty] | 1 |  |  | 2011-12
98 | USSS-45 (A) |  |  | 0 | Munger | Jamaui |  | 1 | Upgraded Middle School, Harla |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
99 | USSS-45 (B) |  |  | 0 | Munger | Jamaui |  | 2 | Middle School, Kairakado |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
100 | USSS-45 (C) |  |  | 0 | Munger | Jamaui |  | 3 | Middle School, Shobhakhan |  | Anil Singh |  |  |  |  | 1 | [9 empty] | 2011-12
101 | USSS-45 (D) |  |  | 0 | Munger | Jamaui |  | 4 | Middle School, Abgila Chourasa |  | NATHUNI YADAV 9931012527 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
102 | USSS-47 (A) |  |  | 0 | Munger | Munger | Birpur | 1 | Middle School Parra |  | MS KUMAR TRADING COMPANY 9431276100 | [5 empty] | 1 | [8 empty] | 2011-12
103 | USSS-47 (B) |  |  | 0 | Munger | Munger | Bakhari | 2 | Middle School Lauchhe |  | No bidder | 1 | [12 empty] | NIT-46 (2015-16). Retender | 2011-12
104 | USSS-47 (C) |  |  | 0 | Munger | Munger | Birpur | 3 | Middle School Kharmauli |  | MS BALRAM KUMAR 9430065800 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
105 | USSS-47 (D) |  |  | 0 | Munger | Munger | Sahebpur Kamal | 4 | Middle School Hira Tol |  | RAM NIWAS KUMAR 9431067357 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
106 | USSS-47 (E) |  |  | 0 | Munger | Munger | Mansurchak | 5 | Middle School Makdhampur |  | No bidder | 1 | [12 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
107 | USSS-48-1 |  |  | 0 | Munger | Munger | Begusarai | 1 | Middle School Akaha |  | RAM NARESH SHARMA 9430088029 |  |  |  | 1 | [10 empty] | 2011-12
108 | USSS-48-2 |  |  | 0 | Munger | Munger | Begusarai | 2 | Middle School Bhitsari |  | Tender Process | 1 | [12 empty] | Retender | 2011-12
109 | USSS-10 (A) |  |  | 0 | Kosi | Saharsa |  | 1 | Middle School Dhamsaina |  | JIWAN LAXMI CONSTRUCTION PVT LTD 9431089386 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
110 | USSS-6 (A) |  |  | 0 | Purnea | Araria |  | 1 | Middle School Mangalwar Chariya |  | Shining Madhusudan Construction |  |  | 1 | [10 empty] | LOA Issue | 2011-12
111 | USSS-6 (B) |  |  | 0 | Purnea | Araria |  | 2 | Middle School Maldwar East |  | WALKS n WALKS MANAGE PRIVATE LIMITED 8434514666 |  |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
112 | USSS-7-1 |  |  | 0 | Purnea | Kishanganj |  | 1 | Middle School Daula |  | BIRENDRA KUMAR SINGH,9473440405 |  |  | 1 | [10 empty] | H.M. not giving permission to construct the building | 2011-12
113 | USSS-8 (A) |  |  | 0 | Purnea | Purnea |  | 1 | Middle School Rupauli |  | Walks n Walks Manage Pvt. Ltd. |  |  | 1 | [10 empty] | LOA Issue | 2011-12
114 | USSS-8 (B) |  |  | 0 | Purnea | Purnea |  | 2 | Middle School Rampur Tilak East |  | Tender Process |  | 1 | [11 empty] | Double Scheme | 2011-12
115 | USSS-8 (C) |  |  | 0 | Purnea | Purnea |  | 3 | Middle School ,Mahendra Nagar Diyara |  | Tender Process | 1 | [12 empty] | Retender | 2011-12
116 | USSS-9-1 | 5812000 | 4176042 | 9988042 | Purnea | Katihar |  | 1 | Middle School Belwa |  | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  |  | 2011-12
117 | USSS-9-2 | 5287789 | 0 | 5287789 | Purnea | Katihar |  | 2 | Middle School Kharsauta |  | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | FF sill level | 2011-12
118 | USSS-9-3 | 5812000 | 4176042 | 9988042 | Purnea | Katihar |  | 3 | Middle School Kalyan Gaon |  | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  |  | 2011-12
119 | USSS-9-4 | 5812000 | 1825914 | 7637914 | Purnea | Katihar |  | 4 | Middle School Rampur |  | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  |  | 2011-12
120 | USSS-4 (A) |  |  | 0 | Tirhut East | Sitamarhi |  | 1 | Middle School Sutihara |  | Shashi Kant Singh |  |  | 1 | [10 empty] | LOA Issue | 2011-12
121 | USSS-4 (B) |  |  | 0 | Tirhut East | Sitamarhi |  | 2 | Middle School Bhantawari |  | Shashi Kant Singh 9771952932 |  |  |  |  | 1 | [9 empty] | 2011-12
122 | USSS-4 (C) |  |  | 0 | Tirhut East | Sitamarhi |  | 3 | Middle School Rajwara |  | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 | [6 empty] | 1 | [7 empty] | 2011-12
123 | USSS-12-1 | 5812000 | 4124538 | 9936538 | Tirhut East | Muzaffarpur |  | 1 | Middle School Bariyarpur |  | S R CONSTRUCTIONS PVT LTD, 7739441850 | [11 empty] | 1 |  |  | 2011-12
124 | USSS-12-2 |  | 0 | 0 | Tirhut East | Muzaffarpur |  | 2 | Middle School Dhabauli |  | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [10 empty] | Land Dispute | 2011-12
125 | USSS-12-3 |  | 0 | 0 | Tirhut East | Muzaffarpur |  | 3 | Middle School Lakhanpur |  | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [10 empty] | Land Dispute | 2011-12
126 | USSS-13 (A) |  |  | 0 | Tirhut East | Muzaffarpur |  | 1 | Middle School Bhatauna |  | VIJAY KUMAR SHAHI 9507385720 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
127 | USSS-13 (B) |  |  | 0 | Tirhut East | Muzaffarpur |  | 2 | Middle School Sirkohiya |  | DEVENDRA KUMAR 9708256685 |  |  |  | 1 | [10 empty] | 2011-12
128 | USSS-15 (A) |  |  | 0 | Tirhut East | Vaishali |  | 1 | Upgraded Middle School Panapur Silaut |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
129 | USSS-15 (B) |  |  | 0 | Tirhut East | Vaishali |  | 2 | Upgraded Middle School Totha |  | SACHIN CONSTRUCTION |  |  | 1 | [10 empty] | LOA Issue | 2011-12
130 | USSS-15 (C) |  |  | 0 | Tirhut East | Vaishali |  | 3 | Middle School Shital Bhakurhar |  | GAJENDRA PATEL 9708793426 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
131 | USSS-1 (A) |  |  | 0 | Tirhut West | West Champaran |  | 1 | Govt. Middle School Kumhiya |  | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
132 | USSS-1 (B) |  |  | 0 | Tirhut West | West Champaran |  | 2 | Middle School Panchgawa |  | SHARDA CHANDEL CONTRACT PVT 9792083771 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
133 | USSS-1 (C) |  |  | 0 | Tirhut West | West Champaran |  | 3 | Middle School Donwar |  | MOHD SHAFIQUE 9939886786 | [5 empty] | 1 | [8 empty] | 2011-12
134 | USSS-1 (D) |  |  | 0 | Tirhut West | West Champaran |  | 4 | Ugraded middle school malahi tola |  | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
135 | USSS-2-1 |  | 0 | 0 | Tirhut West | East Champaran |  | 1 | Middle School Mali |  | ASIANA CONSTRACT PVT LTD, 9431088485 |  |  | 1 | [10 empty] | Not Start | 2011-12
136 | USSS-2-2 | 5812000 | 4773711 | 10585711 | Tirhut West | East Champaran |  | 2 | Middle School Chand parsa |  | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  |  | 2011-12
137 | USSS-2-3 | 5812000 | 4773711 | 10585711 | Tirhut West | East Champaran |  | 3 | Middle School Sitalpur |  | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  |  | 2011-12
138 | USSS-3 (A) |  |  | 0 | Tirhut West | Sheohar |  | 1 | Middle School Dhankaul |  | SHEEL CONSTRUCTION 9430081574 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
139 | USSS-3 (B) |  |  | 0 | Tirhut West | Sheohar |  | 2 | Middle School Narayanpur |  | Shashi Kant Singh 9771952932 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
140 | USSS-3 (C) |  |  | 0 | Tirhut West | Sheohar |  | 3 | Middle School Khairadarp |  | Shashi Kant Singh 9771952932 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
141 | USSS-5-1 | 5812000 | 6160534 | 11972534 | Darbhanga | Madhubani |  | 1 | Govt. Middle School Rudrapur |  | Kamlesh Kumar 934808205 | [11 empty] | 1 |  | inugurated | 2011-12
142 | USSS-5-2 | 5812000 | 4364654 | 10176654 | Darbhanga | Madhubani |  | 2 | Govt. Middle School Bhatra Ghat |  | Kamlesh Kumar 934808205 | [10 empty] | 1 |  |  |  | 2011-12
143 | USSS-11 (A) |  |  | 0 | Darbhanga | Darbhanga |  | 1 | Upgraded Middle School Raj kharwar |  | ASHOK KUMAR YADAV 9386050569 | 1 | [12 empty] | Tender Process | 2011-12
144 | USSS-11 (B) |  |  | 0 | Darbhanga | Darbhanga |  | 2 | Upgraded Middle School Tilkeshwar Sthan |  | ASHOK KUMAR YADAV 9386050569 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
145 | USSS-11 (C) |  |  | 0 | Darbhanga | Darbhanga |  | 3 | Upgraded Middle School Raipur |  | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 |  |  | 1 | [10 empty] | LOA Issue | 2011-12
146 | USSS-16-1 |  |  | 0 | Darbhanga | Samastipur |  | 1 | Middle School Isar Tola |  | Tender Process |  | 1 | [11 empty] | NIT-46 (2015-16) | 2011-12
147 | USSS-14-1 | 5812000 | 3471854 | 9283854 | Saran | Siwan |  | 1 | Middle School Sahadulpur |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  |  | 2011-12
148 | USSS-14-2 |  | 0 |  | Saran | Siwan |  | 2 | Middle School Gamiyar |  | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [10 empty] | Land not available | 2011-12
149 | USSS-14-3 | 5812000 | 5110181 | 10922181 | Saran | Siwan |  | 3 | Middle School Daraunda |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 2011-12
150 | USSS-14-4 | 5812000 | 5110181 | 10922181 | Saran | Siwan |  | 4 | Middle School, Baluya |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 2011-12
151 | USSS-14-5 | 5812000 | 5110181 | 10922181 | Saran | Siwan |  | 5 | Middle School Barka Manjha |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 2011-12
152 | USSS-46-1 | 608043 | 0 | 608043 | Saran | Siwan |  | 1 | Middle School Sikatiya |  | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [11 empty] | 2011-12
153 | USSS-46-2 | 5812000 | 876410 | 6688410 | Saran | Siwan |  | 2 | Middle School Kilpur |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [9 empty] | 1 |  |  |  |  | 2011-12
154 | USSS-46-3 | 5812000 | 4524633 | 10336633 | Saran | Siwan |  | 3 | Middle School Pratapur |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  |  | 2011-12
155 | USSS-46-4 |  |  |  | Saran | Siwan |  | 4 | Middle School Shivpur Sakra |  | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [10 empty] | Land Problem | 2011-12
156 | USSS-46-5 | 5812000 | 4524633 | 10336633 | Saran | Siwan |  | 5 | Middle School Balaipur |  | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  |  | 2011-12
Total No. of USSS (2011-12) | [7 empty] | 156 |  |  |  | 10 | 20 | 61 | 4 | 12 | 8 | 4 | 3 | 0 | 4 | 15 | 14
[9 empty] | USSS 2011-12 | [5 empty] | 4 | 12 | 8 | 4 | 3 | 0 | 4 | 15 | 14
[9 empty] | USSS 2013-14 | [5 empty] | 2 | 3 | 6 | 2 | 12 | 3 | 17 | 59 | 71
[15 empty] | 6 | 15 | 14 | 6 | 15 | 3 | 21 | 74 | 85
Note on L114: Cancel

## USSS (2011-12) (2) (hidden)
BSEIDC Ltd., Patna
Physical Status of USSS (2011-12)
S.N. | Group No. |  |  |  | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Retrender | Tender Process | Session Year/Sanction Order No. | Agreement No. | Physical Status | [10 empty] | Remarks | Session
|  | BMSP Portion Expenses | State Govt.Portion Expenses | Total Expenses | [10 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | Date of Completion
[19 empty] | LL | RL | LL | RL
1 | USSS-26 (A) |  |  |  | Patna East | ukyUnk |  | 1 | Middle School, Basuan | No bidder | 1 | [14 empty] | Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
2 | USSS-26 (B) |  |  |  | Patna East | ukyUnk |  | 2 | Middle School, Malikpur | DHARMENDRA KUMAR 9771493663 |  |  |  |  | 1 | [10 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
3 | USSS-26 (C) |  |  |  | Patna East | ukyUnk |  | 3 | Middle School, Mohaddinpur | ANJANI KUMAR. 7033094100, 9204611556 |  |  |  |  | 1 | [10 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया | 2011-12
4 | USSS-26 (D) |  |  |  | Patna East | ukyUnk |  | 4 | Middle School, Jagdishpur Tayari | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 | [5 empty] | 1 | [9 empty] | E/W | 2011-12
5 | USSS-26 (E) |  |  |  | Patna East | ukyUnk |  | 5 | Middle School, Puraini | DHARMENDRA KUMAR 9771493663 |  |  |  |  | 1 | [10 empty] | LOA Issue. Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-578 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
6 | USSS-26 (F) |  |  |  | Patna East | ukyUnk |  | 6 | Middle School, Lodipur | Tender Process |  | 1 | [13 empty] | Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-577 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
7 | USSS-27 (A) |  |  |  | Patna East | iVuk |  | 1 | Middle School, Diwra | SRI SACHCHIDA NAND SINGH 9631260151 | [5 empty] | 1 | [9 empty] | E/W start (Place को लेकर स्थानीय लोगों द्वारा Dispute) | 2011-12
8 | USSS-27 (B) |  |  |  | Patna East | iVuk |  | 2 | Middle School, Samstichak | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 | [6 empty] | 1 | [8 empty] | Fondation PCC | 2011-12
9 | USSS-27 (C) |  |  |  | Patna East | iVuk |  | 3 | Middle School, Pirbarhouna | RANA CONSTRUCTION 9334104328 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
10 | USSS-27 (D) |  |  |  | Patna East | iVuk |  | 4 | Middle School, Gangachak | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
11 | USSS-28-1 |  |  |  | Patna East | iVuk |  | 1 | Middle School, Karai | Shilendra kumar |  |  |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-582 /20.11.16 द्वारा अनुरोध किया गया है | 2011-12
12 | USSS-29-1 |  |  |  | Patna East | Hkkstiqj | Barhara | 1 | Govt. Middle School, Kudariya Parshurampur | Narendra kumar |  |  |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
13 | USSS-29-2 |  |  |  | Patna East | Hkkstiqj | Barhara | 2 | Upgraded Middle School, Paiga | Narendra kumar |  |  |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
14 | USSS-29-3 |  |  |  | Patna East | Hkkstiqj | Ara | 3 | Upgraded Middle School, Barouli | Narendra kumar |  |  |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
15 | USSS-29-4 |  |  |  | Patna East | Hkkstiqj | Ara | 4 | Middle School, Barka Dumra | Narendra kumar |  |  |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
16 | USSS-29-5 |  |  |  | Patna East | Hkkstiqj | Garahni | 5 | Upgraded Middle School, Dadiyabag | Narendra kumar |  |  |  |  | 1 | [10 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) | 2011-12
17 | USSS-29-6 |  |  |  | Patna East | Hkkstiqj | Koielwar | 6 | Upgraded Middle School, Bhoparpur | Tender Process |  |  |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-584 /20.11.16 द्वारा अनुरोध किया गया. 46/2013-19 | 2011-12
18 | USSS-30-1 |  |  |  | Patna East | Hkkstiqj | Tarari | 1 | Middle School, Sara | Narendra kumar | [6 empty] | 1 | [8 empty] | E/W | 2011-12
19 | USSS-30-2 |  |  |  | Patna East | Hkkstiqj | Tarari | 2 | Middle School, Bhakura | Narendra kumar | [6 empty] | 1 | [8 empty] | E/w | 2011-12
20 | USSS-30-3 |  |  |  | Patna East | Hkkstiqj | Pero | 3 | Middle School, Dhanpura | Narendra kumar | [6 empty] | 1 | [8 empty] | E/w | 2011-12
21 | USSS-30-4 |  |  |  | Patna East | Hkkstiqj | Sahar | 4 | Middle School, Perhap | Narendra kumar |  |  |  |  | 1 | [10 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
22 | USSS-30-5 |  |  |  | Patna East | Hkkstiqj | Sahar | 5 | Middle School, Nonuar | Narendra kumar |  |  |  |  | 1 | [10 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-580 /20.11.16 तथा DEO से पत्रांक 661 दिनांक 24.12.16 द्वारा अनुरोध किया गया है | 2011-12
23 | USSS-30-6 |  |  |  | Patna East | Hkkstiqj | Sahar | 6 | Middle School, Purhara | Tender Process | 1 | [14 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 | 2011-12
24 | USSS-31 (A) |  |  |  | Patna West | बक्‍सर | ब्रहम्‍पुर | 1 | Middle School, Bhadwar | Sanjay Kumar Tiwary | [6 empty] | 1 | [9 empty] | 2011-12
25 | USSS-31 (B) |  |  |  | Patna West | बक्‍सर | ब्रहम्‍पुर | 2 | Girl Middle School, Akrasi | Satyam Enterprises |  |  |  |  | 1 | [10 empty] | LOA Issue. Low land about 4'. | 2011-12
26 | USSS-32-1 | 5812000 | 3164852 | 8976852 | Patna West | भभुआ कैमूर | चैनपुर | 1 | Middle School, Dhardihan | KRISHNA | [12 empty] | 1 |  |  |  | 2011-12
27 | USSS-32-2 |  |  | 0 | Patna West | भभुआ कैमूर | चॉंद | 2 | Upgraded Middle School, Chouri | KRISHNA |  |  |  |  | 1 | [10 empty] | Encrochment | 2011-12
28 | USSS-32-3 | 5812000 | 4749002 | 10561002 | Patna West | भभुआ कैमूर | भगवानपुर | 3 | Middle School, Dadar | KRISHNA | [13 empty] | 1 |  | Handover | 2011-12
29 | USSS-32-4 | 5812000 | 3164852 | 8976852 | Patna West | भभुआ कैमूर | रामपुर | 4 | Middle School, Lohandi | KRISHNA | [12 empty] | 1 |  |  |  | 2011-12
30 | USSS-32-5 | 5808552 | 0 | 5808552 | Patna West | भभुआ कैमूर | मोहनियॉं | 5 | Middle School, Badhani | KRISHNA | [11 empty] | 1 |  |  |  |  | 2011-12
31 | USSS-33 (A) |  |  | 0 | Patna West | रोहतास | दावत | 1 | Middle School, Parmdiha | RAJENDRA SINGH 9430226175 | [6 empty] | 1 | [9 empty] | 2011-12
32 | USSS-33 (B) |  |  | 0 | Patna West | रोहतास | नोखा | 2 | Middle School, Hathini | ARSA INFRATECH PRIVATE LIMITED 9308676177 |  |  |  |  | 1 | [10 empty] | LOA Issue. Land not available. | 2011-12
33 | USSS-33 (C) |  |  | 0 | Patna West | रोहतास | काराकाट | 3 | Middle School, Itdhiyan | A B CONSTRUCTION 7250583221 | [7 empty] | 1 | [7 empty] | LOA Issue | 2011-12
34 | USSS-34-1 | 5812000 | 3160285 | 8972285 | Patna West | रोहतास | अकोढ़ीगोला | 1 | Middle School, Gobardhanpur | SHALINI SINGH | [13 empty] | 1 |  |  | 2011-12
35 | USSS-34-2 | 5812000 | 4743630 | 10555630 | Patna West | रोहतास | डिहरी | 2 | Middle School, Tandwa | SHALINI SINGH | [13 empty] | 1 |  |  | 2011-12
36 | USSS-34-3 | 5812000 | 4743630 | 10555630 | Patna West | रोहतास | काराकाट | 3 | Middle School, Danwar | SHALINI SINGH | [13 empty] | 1 |  |  | 2011-12
37 | USSS-35 (A) |  |  | 0 | Patna West | रोहतास | करहगर | 1 | Upgraded Middle School, Rehari | ANIL RAY 9507466444 | [6 empty] | 1 | [9 empty] | 2011-12
38 | USSS-35 (B) |  |  | 0 | Patna West | रोहतास | रोहतास | 2 | Middle School, Majhiyawan | UDAY KUMAR 9955691188 |  |  |  |  | 1 | [10 empty] | LOA Issue. Less land and dispute | 2011-12
39 | USSS-35-3 |  |  | 0 | Patna West | रोहतास |  | 3 | Middle School, Ghordihi | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [14 empty] | Tender Process | 2011-12
40 | USSS-36 (A) |  |  | 0 | Magadh | tgkukckn |  | 1 | Middle School, Ahiyasa | PRAVEEN KUMAR 7033712900 | [7 empty] | 1 | [8 empty] | 2011-12
41 | USSS-36 (B) |  |  | 0 | Magadh | tgkukckn |  | 2 | Middle School,Sewnon | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
42 | USSS-36 (C) |  |  | 0 | Magadh | tgkukckn |  | 3 | Middle School, Dewra | PRAVEEN KUMAR 7033712900 | [8 empty] | 1 | [7 empty] | 2011-12
43 | USSS-37 (A) |  |  | 0 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Kusumbasdiha | DHANANJAY KUMAR SINGH 9931845497 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
44 | USSS-37 (B) |  |  | 0 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Pandu | DHANANJAY KUMAR SINGH 9931845497 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
45 | USSS-38-1 |  |  | 0 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Gamharia | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
46 | USSS-38-2 |  |  | 0 | Magadh | vkSjaaxkckn |  | 2 | Middle School,Sondiha | MS MATESHWARI CONSTRUCTION, 7766886737 | [8 empty] | 1 | [7 empty] | 2011-12
47 | USSS-38-3 |  |  | 0 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Raslpur | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
48 | USSS-39-1 |  |  | 0 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Chourahi | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
49 | USSS-39-2 |  |  | 0 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Sonbarsa | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
50 | USSS-39-3 |  |  | 0 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Dandwan | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  |  |  | 1 | [10 empty] | Insufficient Land | 2011-12
51 | USSS-40 (A) |  |  | 0 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Meh | MANOJ SINGH, 9939822131, 7033944511 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
52 | USSS-40 (B) |  |  | 0 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Tamoli | MANOJ SINGH, 9939822131, 7033944511 | [7 empty] | 1 | [8 empty] | 2011-12
53 | USSS-41 (A) |  |  | 0 | Magadh | x;k |  | 1 | Middle School, Shyamnagar Nima | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
54 | USSS-41 (B) |  |  | 0 | Magadh | x;k |  | 2 | Middle School, Khajuria | NAGENDRA SINGH 9631326479 | [7 empty] | 1 | [8 empty] | 2011-12
55 | USSS-41 (C) |  |  | 0 | Magadh | x;k |  | 3 | Middle School, Parsawan Khurd | SURENDRA KUMAR 9128027943 | [6 empty] | 1 | [9 empty] | 2011-12
56 | USSS-41 (D) |  |  | 0 | Magadh | x;k |  | 4 | Middle School, Belauti | SANJAY KUMAR SINGH 9973456006 | [7 empty] | 1 | [8 empty] | 2011-12
57 | USSS-41 (E) |  |  | 0 | Magadh | x;k |  | 5 | Middle School,Bindhua | MRITUNJAY KUMAR SINGH 9097394660 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
58 | USSS-42 (A) |  |  | 0 | Magadh | x;k |  | 1 | Middle School, Sondiha | SANJAY KUMAR SINGH 9973456006 | [6 empty] | 1 | [9 empty] | 2011-12
59 | USSS-42 (B) |  |  | 0 | Magadh | x;k |  | 2 | Middle School, Angara | NARENDRA YADAB 99315315191 | [6 empty] | 1 | [9 empty] | 2011-12
60 | USSS-42 (C) |  |  | 0 | Magadh | x;k |  | 3 | Middle School, Punakalan | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
61 | USSS-42 (D) |  |  | 0 | Magadh | x;k |  | 4 | Middle School, Noni | RAVIN KUMAR 8797253525 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
62 | USSS-43-1 | 5812000 | 5163904 | 10975904 | Magadh | x;k |  | 1 | Upgraded Middle School, Pater | Mithlesh Kumar Singh, 9931471924 | [13 empty] | 1 |  |  | 2011-12
63 | USSS-43-2 |  |  | 0 | Magadh | x;k |  | 2 | Middle School, Bitho | Mithlesh Kumar Singh, 9931471924 |  |  |  |  | 1 | [10 empty] | Local Dispute | 2011-12
64 | USSS-44 (A) |  |  | 0 | Magadh | uoknk |  | 1 | Middle School, Bardhauna | RAJNISH VATS 8051666426 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
65 | USSS-44 (B) |  |  | 0 | Magadh | uoknk |  | 2 | Upgraded Middle School, Puraini | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
66 | USSS-44 (C) |  |  | 0 | Magadh | uoknk |  | 3 | Middle School, Kalound | SUDHIR KUMAR 9430411061 | [11 empty] | 1 |  |  |  |  | 2011-12
67 | USSS-44 (D) |  |  | 0 | Magadh | uoknk |  | 4 | Middle School, Paingari | SUDHIR KUMAR 9430411061 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
68 | USSS-44 (E) |  |  | 0 | Magadh | uoknk |  | 5 | Upgraded Middle School, Bhatta | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
69 | USSS-17 (A) |  |  | 0 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kishanpur | Dayanand Singh |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
70 | USSS-17 (B) |  |  | 0 | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Tarchha | Retender |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
71 | USSS-18-1 |  |  | 0 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Ghanshyamchak | Retender |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
72 | USSS-19-1 | 5812000 | 5981953 | 11793953 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kalgiganj | MS Rungta Enterprises, 9431265821 | [13 empty] | 1 |  |  | 2011-12
73 | USSS-19-2 | 5812000 | 5981953 | 11793953 | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Dayalpur | MS Rungta Enterprises, 9431265821 | [13 empty] | 1 |  |  | 2011-12
74 | USSS-19-3 | 5812000 | 5981953 | 11793953 | Bhagalpur | Hkkxyiqj |  | 3 | Middle School Siya | MS Rungta Enterprises, 9431265821 | [13 empty] | 1 |  |  | 2011-12
75 | USSS-19-4 | 5812000 | 5981954 | 11793954 | Bhagalpur | Hkkxyiqj |  | 4 | Middle School Kishunichak | MS Rungta Enterprises, 9431265821 | [13 empty] | 1 |  |  | 2011-12
76 | USSS-20 (A) |  |  | 0 | Bhagalpur | ckadk |  | 1 | Middle School kairi | Kundan Kumar Singh | [16 empty] | 2011-12
77 | USSS-20 (B) |  |  | 0 | Bhagalpur | ckadk |  | 2 | Middle School Bank | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
78 | USSS-20 (C) |  |  | 0 | Bhagalpur | ckadk |  | 3 | Middle School Pathdda | Lalan Kumar |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
79 | USSS-21 (A) |  |  | 0 | Munger | ewaxsj |  | 1 | Middle School Harinmar Bishunpur | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
80 | USSS-21 (B) |  |  | 0 | Munger | ewaxsj |  | 2 | Middle School Manik Mandal Tola | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
81 | USSS-21 (C) |  |  | 0 | Munger | ewaxsj |  | 3 | Middle School Kalyanpur | ANIL KUMAR SINGH 9570904951 |  |  |  |  | 1 | [11 empty] | 2011-12
82 | USSS-21 (D) |  |  | 0 | Munger | ewaxsj |  | 4 | Middle School Teghara | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
83 | USSS-21 (E) |  |  | 0 | Munger | ewaxsj |  | 5 | Middle School Dhudhaladih | No bidder | 1 | [14 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
84 | USSS-22 (A) |  |  | 0 | Munger | ewaxsj |  | 1 | Middle School Ramcharit Maidan | DIGBIJAY KUMAR 8084371876 | [6 empty] | 1 | [9 empty] | 2011-12
85 | USSS-22 (B) |  |  | 0 | Munger | ewaxsj |  | 2 | Middle School Madhura / Katiyari | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
86 | USSS-22 (C) |  |  | 0 | Munger | ewaxsj |  | 3 | Middle School, Dhobai | Retender | 1 | [14 empty] | Retender | 2011-12
87 | USSS-22 (D) |  |  | 0 | Munger | ewaxsj |  | 4 | Middle School Nabgoi | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
88 | USSS-23-1 | 5812000 | 3214909 | 9026909 | Munger | y[khljk; |  | 1 | Middle School, Bahachha | SUGEET KUMAR,9504681342 |  |  |  | 691 SBD OF 14-15 (14.02.15) | [8 empty] | 1 |  |  |  | 2011-12
89 | USSS-23-2 | 5812000 | 3214909 | 9026909 | Munger | y[khljk; |  | 2 | Middle School Tarhari | SUGEET KUMAR,9504681342 |  |  |  | 691 SBD OF 14-15 (14.02.15) | [8 empty] | 1 |  |  |  | 2011-12
90 | USSS-23-3 | 5812000 | 3214909 | 9026909 | Munger | y[khljk; |  | 3 | Middle School Nongarh | SUGEET KUMAR,9504681342 |  |  |  | 691 SBD OF 14-15 (14.02.15) | [8 empty] | 1 |  |  |  | 2011-12
91 | USSS-23-4 | 3610762 | 0 | 3610762 | Munger | y[khljk; |  | 4 | Upgraded Middle School Surari | SUGEET KUMAR,9504681342 |  |  |  | 691 SBD OF 14-15 (14.02.15) | [5 empty] | 1 | [6 empty] | 2011-12
92 | USSS-24 (A) |  |  | 0 | Munger | y[khljk; |  | 1 | Upgraded Middle School Bihraura | MS BALRAM KUMAR 9430065800 | [5 empty] | 1 | [10 empty] | 2011-12
93 | USSS-24 (B) |  |  | 0 | Munger | y[khljk; |  | 2 | Middle School Pokhrama | SAI HIGHWAY AND BUILDERS PVT LTD 9771455967 | [7 empty] | 1 | [8 empty] | 2011-12
94 | USSS-24 (C) |  |  | 0 | Munger | y[khljk; |  | 3 | Upgraded Middle School Dhoni Kundi | MONEY CONSTRUCTION PRIVATE LIMITED 9386596373 | [9 empty] | 1 | [6 empty] | 2011-12
95 | USSS-25-1 | 5812000 | 2975379 | 8787379 | Munger | 'ks[kiqjk |  | 1 | Middle School, Akrama | Epitome Construction Pvt Ltd,8935825344 |  |  |  | 692 SBD OF 14-15 (14.02.15) | [8 empty] | 1 |  |  |  | 2011-12
96 | USSS-25-2 | 4652144 | 0 | 4652144 | Munger | 'ks[kiqjk |  | 2 | Upgraded Middle School, Diha | Epitome Construction Pvt Ltd,8935825344 |  |  |  | 692 SBD OF 14-15 (14.02.15) | [5 empty] | 1 | [5 empty] | WORK STOPPED BY DIST ADMN (upto FF sill lv) | 2011-12
97 | USSS-25-3 | 5812000 | 4526093 | 10338093 | Munger | 'ks[kiqjk |  | 3 | Middle School, Kutout | Epitome Construction Pvt Ltd,8935825344 |  |  |  | 692 SBD OF 14-15 (14.02.15) | [9 empty] | 1 |  |  | 2011-12
98 | USSS-45 (A) |  |  | 0 | Munger | tewbZ |  | 1 | Upgraded Middle School, Harla | Sudesh & Co | [6 empty] | 1 | [9 empty] | 2011-12
99 | USSS-45 (B) |  |  | 0 | Munger | tewbZ |  | 2 | Middle School, Kairakado | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
100 | USSS-45 (C) |  |  | 0 | Munger | tewbZ |  | 3 | Middle School, Shobhakhan | Anil Singh | [6 empty] | 1 | [9 empty] | 2011-12
101 | USSS-45 (D) |  |  | 0 | Munger | tewbZ |  | 4 | Middle School, Abgila Chourasa | NATHUNI YADAV 9931012527 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
102 | USSS-47 (A) |  |  | 0 | Munger | Munger | Birpur | 1 | Middle School Parra | MS KUMAR TRADING COMPANY 9431276100 | [8 empty] | 1 | [7 empty] | 2011-12
103 | USSS-47 (B) |  |  | 0 | Munger | Munger | Bakhari | 2 | Middle School Lauchhe | No bidder | 1 | [14 empty] | NIT-46 (2015-16). Retender | 2011-12
104 | USSS-47 (C) |  |  | 0 | Munger | Munger | Birpur | 3 | Middle School Kharmauli | MS BALRAM KUMAR 9430065800 | [6 empty] | 1 | [9 empty] | 2011-12
105 | USSS-47 (D) |  |  | 0 | Munger | Munger | Sahebpur Kamal | 4 | Middle School Hira Tol | RAM NIWAS KUMAR 9431067357 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
106 | USSS-47 (E) |  |  | 0 | Munger | Munger | Mansurchak | 5 | Middle School Makdhampur | No bidder | 1 | [14 empty] | No Bidder. NIT-46 (2015-16) | 2011-12
107 | USSS-48-1 |  |  | 0 | Munger | Munger | Begusarai | 1 | Middle School Akaha | RAM NARESH SHARMA 9430088029 | [5 empty] | 1 | [10 empty] | 2011-12
108 | USSS-48-2 |  |  | 0 | Munger | Munger | Begusarai | 2 | Middle School Bhitsari | Tender Process | 1 | [14 empty] | Retender | 2011-12
109 | USSS-10 (A) |  |  | 0 | Kosi | lgjlk |  | 1 | Middle School Dhamsaina | JIWAN LAXMI CONSTRUCTION PVT LTD 9431089386 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
110 | USSS-6 (A) |  |  | 0 | Purnea | vjfj;k |  | 1 | Middle School Mangalwar Chariya | Shining Madhusudan Construction |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
111 | USSS-6 (B) |  |  | 0 | Purnea | vjfj;k |  | 2 | Middle School Maldwar East | WALKS n WALKS MANAGE PRIVATE LIMITED 8434514666 |  |  |  |  | 1 | [10 empty] | NIT-46 (2015-16) | 2011-12
112 | USSS-7-1 |  |  | 0 | Purnea | fd'kuxat |  | 1 | Middle School Daula | BIRENDRA KUMAR SINGH,9473440405 |  |  |  |  | 1 | [10 empty] | H.M. not giving permission to construct the building | 2011-12
113 | USSS-8 (A) |  |  | 0 | Purnea | iwf.kZ;k¡ |  | 1 | Middle School Rupauli | Walks n Walks Manage Pvt. Ltd. |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
114 | USSS-8 (B) |  |  | 0 | Purnea | iwf.kZ;k¡ |  | 2 | Middle School Rampur Tilak East | Tender Process |  | 1 | [13 empty] | Double Scheme | 2011-12
115 | USSS-8 (C) |  |  | 0 | Purnea | iwf.kZ;k¡ |  | 3 | Middle School ,Mahendra Nagar Diyara | Tender Process | 1 | [14 empty] | Retender | 2011-12
116 | USSS-9-1 | 5812000 | 4176042 | 9988042 | Purnea | dfVgkj |  | 1 | Middle School Belwa | BIRENDRA KUMAR SINGH, 9473440405 | [12 empty] | 1 |  |  |  | 2011-12
117 | USSS-9-2 | 5287789 | 0 | 5287789 | Purnea | dfVgkj |  | 2 | Middle School Kharsauta | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 | [5 empty] | FF sill level | 2011-12
118 | USSS-9-3 | 5812000 | 4176042 | 9988042 | Purnea | dfVgkj |  | 3 | Middle School Kalyan Gaon | BIRENDRA KUMAR SINGH, 9473440405 | [12 empty] | 1 |  |  |  | 2011-12
119 | USSS-9-4 | 5812000 | 1825914 | 7637914 | Purnea | dfVgkj |  | 4 | Middle School Rampur | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1 |  |  |  |  | 2011-12
120 | USSS-4 (A) |  |  | 0 | Tirhut East | lhrke<+h |  | 1 | Middle School Sutihara | Shashi Kant Singh |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
121 | USSS-4 (B) |  |  | 0 | Tirhut East | lhrke<+h |  | 2 | Middle School Bhantawari | Shashi Kant Singh 9771952932 | [6 empty] | 1 | [9 empty] | 2011-12
122 | USSS-4 (C) |  |  | 0 | Tirhut East | lhrke<+h |  | 3 | Middle School Rajwara | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 | [8 empty] | 1 | [7 empty] | 2011-12
123 | USSS-12-1 | 5812000 | 4124538 | 9936538 | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bariyarpur | S R CONSTRUCTIONS PVT LTD, 7739441850 | [13 empty] | 1 |  |  | 2011-12
124 | USSS-12-2 |  | 0 | 0 | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Dhabauli | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  |  |  | 1 | [10 empty] | Land Dispute | 2011-12
125 | USSS-12-3 |  | 0 | 0 | Tirhut East | eqt¶Qjiqj |  | 3 | Middle School Lakhanpur | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  |  |  | 1 | [10 empty] | Land Dispute | 2011-12
126 | USSS-13 (A) |  |  | 0 | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bhatauna | VIJAY KUMAR SHAHI 9507385720 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
127 | USSS-13 (B) |  |  | 0 | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Sirkohiya | DEVENDRA KUMAR 9708256685 | [5 empty] | 1 | [10 empty] | 2011-12
128 | USSS-15 (A) |  |  | 0 | Tirhut East | oS'kkyh |  | 1 | Upgraded Middle School Panapur Silaut | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
129 | USSS-15 (B) |  |  | 0 | Tirhut East | oS'kkyh |  | 2 | Upgraded Middle School Totha | SACHIN CONSTRUCTION |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
130 | USSS-15 (C) |  |  | 0 | Tirhut East | oS'kkyh |  | 3 | Middle School Shital Bhakurhar | GAJENDRA PATEL 9708793426 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
131 | USSS-1 (A) |  |  | 0 | Tirhut West | if'pe pEikj.k |  | 1 | Govt. Middle School Kumhiya | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
132 | USSS-1 (B) |  |  | 0 | Tirhut West | if'pe pEikj.k |  | 2 | Middle School Panchgawa | SHARDA CHANDEL CONTRACT PVT 9792083771 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
133 | USSS-1 (C) |  |  | 0 | Tirhut West | if'pe pEikj.k |  | 3 | Middle School Donwar | MOHD SHAFIQUE 9939886786 | [7 empty] | 1 | [8 empty] | 2011-12
134 | USSS-1 (D) |  |  | 0 | Tirhut West | if'pe pEikj.k |  | 4 | Ugraded middle school malahi tola | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
135 | USSS-2-1 |  | 0 | 0 | Tirhut West | iwohZ pEikj.k |  | 1 | Middle School Mali | ASIANA CONSTRACT PVT LTD, 9431088485 |  |  |  |  | 1 | [10 empty] | Not Start | 2011-12
136 | USSS-2-2 | 5812000 | 4773711 | 10585711 | Tirhut West | iwohZ pEikj.k |  | 2 | Middle School Chand parsa | ASIANA CONSTRACT PVT LTD, 9431088485 | [12 empty] | 1 |  |  |  | 2011-12
137 | USSS-2-3 | 5812000 | 4773711 | 10585711 | Tirhut West | iwohZ pEikj.k |  | 3 | Middle School Sitalpur | ASIANA CONSTRACT PVT LTD, 9431088485 | [12 empty] | 1 |  |  |  | 2011-12
138 | USSS-3 (A) |  |  | 0 | Tirhut West | f'kogj |  | 1 | Middle School Dhankaul | SHEEL CONSTRUCTION 9430081574 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
139 | USSS-3 (B) |  |  | 0 | Tirhut West | f'kogj |  | 2 | Middle School Narayanpur | Shashi Kant Singh 9771952932 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
140 | USSS-3 (C) |  |  | 0 | Tirhut West | f'kogj |  | 3 | Middle School Khairadarp | Shashi Kant Singh 9771952932 |  |  |  |  | 1 | [10 empty] | LOA Issue | 2011-12
141 | USSS-5-1 | 5812000 | 6160534 | 11972534 | Darbhanga | e/kqcuh |  | 1 | Govt. Middle School Rudrapur | Kamlesh Kumar 934808205 | [13 empty] | 1 | 2015-05-10 | inugurated | 2011-12
142 | USSS-5-2 | 5812000 | 4364654 | 10176654 | Darbhanga | e/kqcuh |  | 2 | Govt. Middle School Bhatra Ghat | Kamlesh Kumar 934808205 | [12 empty] | 1 |  |  |  | 2011-12
143 | USSS-11 (A) |  |  | 0 | Darbhanga | njHkaxk |  | 1 | Upgraded Middle School Raj kharwar | ASHOK KUMAR YADAV 9386050569 | [5 empty] | 1 | [10 empty] | 2011-12
144 | USSS-11 (B) |  |  | 0 | Darbhanga | njHkaxk |  | 2 | Upgraded Middle School Tilkeshwar Sthan | ASHOK KUMAR YADAV 9386050569 | [5 empty] | 1 | [10 empty] | 2011-12
145 | USSS-11 (C) |  |  | 0 | Darbhanga | njHkaxk |  | 3 | Upgraded Middle School Raipur | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 | [6 empty] | 1 | [9 empty] | 2011-12
146 | USSS-16-1 |  |  | 0 | Darbhanga | leLrhiqj |  | 1 | Middle School Isar Tola | Tender Process |  | 1 | [13 empty] | NIT-46 (2015-16) | 2011-12
147 | USSS-14-1 | 5812000 | 3471854 | 9283854 | Saran | lhoku |  | 1 | Middle School Sahadulpur | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 121 SBD OF 2015-16 (17.06.15) | [8 empty] | 1 |  |  |  | 2011-12
148 | USSS-14-2 |  | 0 |  | Saran | lhoku |  | 2 | Middle School Gamiyar | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 121 SBD OF 2015-16 (17.06.15) | 1 | [10 empty] | Land not available | 2011-12
149 | USSS-14-3 | 5812000 | 5110181 | 10922181 | Saran | lhoku |  | 3 | Middle School Daraunda | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 121 SBD OF 2015-16 (17.06.15) | [9 empty] | 1 |  |  | 2011-12
150 | USSS-14-4 | 5812000 | 5110181 | 10922181 | Saran | lhoku |  | 4 | Middle School, Baluya | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 121 SBD OF 2015-16 (17.06.15) | [9 empty] | 1 |  |  | 2011-12
151 | USSS-14-5 | 5812000 | 5110181 | 10922181 | Saran | lhoku |  | 5 | Middle School Barka Manjha | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 121 SBD OF 2015-16 (17.06.15) | [9 empty] | 1 |  |  | 2011-12
152 | USSS-46-1 | 608043 | 0 | 608043 | Saran | lhoku |  | 1 | Middle School Sikatiya | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  |  | 1 | [11 empty] | 2011-12
153 | USSS-46-2 | 5812000 | 876410 | 6688410 | Saran | lhoku |  | 2 | Middle School Kilpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  |  |  | 2011-12
154 | USSS-46-3 | 5812000 | 4524633 | 10336633 | Saran | lhoku |  | 3 | Middle School Pratapur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [12 empty] | 1 |  |  |  | 2011-12
155 | USSS-46-4 |  |  |  | Saran | lhoku |  | 4 | Middle School Shivpur Sakra | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  |  | 1 | [10 empty] | Land Problem | 2011-12
156 | USSS-46-5 | 5812000 | 4524633 | 10336633 | Saran | lhoku |  | 5 | Middle School Balaipur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [12 empty] | 1 |  |  |  | 2011-12
Total No. of USSS (2011-12) | [7 empty] | 156 |  |  | 10 | 20 |  |  | 56 | 7 | 16 | 7 | 4 | 4 | 0 | 4 | 14 | 15
[9 empty] | USSS 2011-12 | [6 empty] | 7 | 16 | 7 | 4 | 4 | 0 | 4 | 14 | 15
[9 empty] | USSS 2013-14 | [6 empty] | 2 | 3 | 6 | 2 | 11 | 4 | 17 | 57 | 73
[16 empty] | 9 | 19 | 13 | 6 | 15 | 4 | 21 | 71 | 88
Note on K114: Cancel

## USSS (2011-12) (3)
BSEIDC Ltd., Patna
Physical Status of USSS (2011-12)
S.N. | Group No. | Name of District | Name of Block | Name of School | Name of Agency | Retrender | Tender Process | Physical Status | [9 empty] | Remarks |  |  | Division | Session
[8 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete |  | Date of Completion | Total Expenses
[12 empty] | LL | RL | LL | RL
1 | USSS-26 (A) | Nalanda |  | Middle School, Basuan | No bidder | 1 | [11 empty] | Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया |  |  | Patna East | 2011-12
2 | USSS-26 (B) | Nalanda |  | Middle School, Malikpur | DHARMENDRA KUMAR 9771493663 | [7 empty] | 1 | [7 empty] | Patna East | 2011-12
3 | USSS-26 (C) | Nalanda |  | Middle School, Mohaddinpur | ANJANI KUMAR. 7033094100, 9204611556 |  |  | 1 | [9 empty] | LOA Issue. Land Available DEO से पत्रांक 660 दिनांक 24.12.16 द्वारा अनुरोध किया गया |  |  | Patna East | 2011-12
4 | USSS-26 (D) | Nalanda |  | Middle School, Jagdishpur Tayari | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 | [7 empty] | 1 | [7 empty] | Patna East | 2011-12
5 | USSS-26 (E) | Nalanda |  | Middle School, Puraini | DHARMENDRA KUMAR 9771493663 |  |  | 1 | [9 empty] | LOA Issue. Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-578 /20.11.16 द्वारा अनुरोध किया गया है |  |  | Patna East | 2011-12
6 | USSS-26 (F) | Nalanda |  | Middle School, Lodipur | Anjani Kumar |  |  | 1 | [9 empty] | Land not available, स्थल उपलब्ध कराने हेतु HM से L.No.-577 /20.11.16 द्वारा अनुरोध किया गया है |  |  | Patna East | 2011-12
7 | USSS-27 (A) | Patna |  | Middle School, Diwra | SRI SACHCHIDA NAND SINGH 9631260151 | [10 empty] | 1 |  |  |  |  | Patna East | 2011-12
8 | USSS-27 (B) | Patna |  | Middle School, Samstichak | JITENDRA KUMAR MOB NO. 9835205052 AND 9507186981 | [7 empty] | 1 | [7 empty] | Patna East | 2011-12
9 | USSS-27 (C) | Patna |  | Middle School, Pirbarhouna | RANA CONSTRUCTION 9334104328 |  |  | 1 | [9 empty] | LOA Issue. Available Land 40'-0" x 120'-0" |  |  | Patna East | 2011-12
10 | USSS-27 (D) | Patna |  | Middle School, Gangachak | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  |  | Patna East | 2011-12
11 | USSS-28-1 | Patna |  | Middle School, Karai | Shilendra kumar |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-582 /20.11.16 द्वारा अनुरोध किया गया है |  |  | Patna East | 2011-12
12 | USSS-29-1 | Bhojpur | Barhara | Govt. Middle School, Kudariya Parshurampur | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) |  |  | Patna East | 2011-12
13 | USSS-29-2 | Bhojpur | Barhara | Upgraded Middle School, Paiga | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) |  |  | Patna East | 2011-12
14 | USSS-29-3 | Bhojpur | Ara | Upgraded Middle School, Barouli | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) |  |  | Patna East | 2011-12
15 | USSS-29-4 | Bhojpur | Ara | Middle School, Barka Dumra | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) |  |  | Patna East | 2011-12
16 | USSS-29-5 | Bhojpur | Garahni | Upgraded Middle School, Dadiyabag | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 (DEO से पत्रांक 661 दिनांक 24.12.16) |  |  | Patna East | 2011-12
17 | USSS-29-6 | Bhojpur | Koielwar | Upgraded Middle School, Bhoparpur | Narendra Kumar |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-584 /20.11.16 द्वारा अनुरोध किया गया. 46/2013-19 |  |  | Patna East | 2011-12
18 | USSS-30-1 | Bhojpur | Tarari | Middle School, Sara | Narendra kumar |  |  |  |  | 1 | [7 empty] | GL |  |  | Patna East | 2011-12
19 | USSS-30-2 | Bhojpur | Tarari | Middle School, Bhakura | Narendra kumar |  |  |  |  | 1 | [7 empty] | Foundation RCC |  |  | Patna East | 2011-12
20 | USSS-30-3 | Bhojpur | Pero | Middle School, Dhanpura | Narendra kumar |  |  |  |  | 1 | [7 empty] | 75% of footing casted, now water logging |  |  | Patna East | 2011-12
21 | USSS-30-4 | Bhojpur | Sahar | Middle School, Perhap | Narendra kumar |  |  | 1 | [9 empty] | DEO से पत्रांक 661 दिनांक 24.12.16 |  |  | Patna East | 2011-12
22 | USSS-30-5 | Bhojpur | Sahar | Middle School, Nonuar | Narendra kumar |  |  | 1 | [9 empty] | स्थल उपलब्ध कराने हेतु HM से L.No.-580 /20.11.16 तथा DEO से पत्रांक 661 दिनांक 24.12.16 द्वारा अनुरोध किया गया है |  |  | Patna East | 2011-12
23 | USSS-30-6 | Bhojpur | Sahar | Middle School, Purhara | Narendra Kumar |  |  |  |  | 1 | [7 empty] | Foundation RCC |  |  | Patna East | 2011-12
24 | USSS-31 (A) | Buxar | ब्रहम्‍पुर | Middle School, Bhadwar | Sanjay Kumar Tiwary |  |  |  |  | 1 | [10 empty] | Patna West | 2011-12
25 | USSS-31 (B) | Buxar | ब्रहम्‍पुर | Girl Middle School, Akrasi | Satyam Enterprises | [6 empty] | 1 | [8 empty] | Patna West | 2011-12
26 | USSS-32-1 | Bhabhua Kaimur | चैनपुर | Middle School, Dhardihan | KRISHNA | [10 empty] | 1 |  |  |  | 8976852 | Patna West | 2011-12
27 | USSS-32-2 | Bhabhua Kaimur | चॉंद | Upgraded Middle School, Chouri | KRISHNA | [5 empty] | 1 | [6 empty] | Encrochment |  | 0 | Patna West | 2011-12
28 | USSS-32-3 | Bhabhua Kaimur | भगवानपुर | Middle School, Dadar | KRISHNA | [11 empty] | 1 | Handover |  | 10561002 | Patna West | 2011-12
29 | USSS-32-4 | Bhabhua Kaimur | रामपुर | Middle School, Lohandi | KRISHNA | [10 empty] | 1 |  |  |  | 8976852 | Patna West | 2011-12
30 | USSS-32-5 | Bhabhua Kaimur | मोहनियॉं | Middle School, Badhani | KRISHNA | [9 empty] | 1 |  |  |  |  | 5808552 | Patna West | 2011-12
31 | USSS-33 (A) | Rohtas | दावत | Middle School, Parmdiha | RAJENDRA SINGH 9430226175 | [7 empty] | 1 | [6 empty] | 0 | Patna West | 2011-12
32 | USSS-33 (B) | Rohtas | नोखा | Middle School, Hathini | ARSA INFRATECH PRIVATE LIMITED 9308676177 | [5 empty] | 1 | [8 empty] | 0 | Patna West | 2011-12
33 | USSS-33 (C) | Rohtas | काराकाट | Middle School, Itdhiyan | A B CONSTRUCTION 7250583221 | [10 empty] | 1 |  |  |  | 0 | Patna West | 2011-12
34 | USSS-34-1 | Rohtas | अकोढ़ीगोला | Middle School, Gobardhanpur | SHALINI SINGH | [11 empty] | 1 |  |  | 8972285 | Patna West | 2011-12
35 | USSS-34-2 | Rohtas | डिहरी | Middle School, Tandwa | SHALINI SINGH | [11 empty] | 1 |  |  | 10555630 | Patna West | 2011-12
36 | USSS-34-3 | Rohtas | काराकाट | Middle School, Danwar | SHALINI SINGH | [11 empty] | 1 |  |  | 10555630 | Patna West | 2011-12
37 | USSS-35 (A) | Rohtas | करहगर | Upgraded Middle School, Rehari | ANIL RAY 9507466444 | [7 empty] | 1 | [6 empty] | 0 | Patna West | 2011-12
38 | USSS-35 (B) | Rohtas | Rohtas | Middle School, Majhiyawan | UDAY KUMAR 9955691188 | [9 empty] | 1 |  |  |  |  | 0 | Patna West | 2011-12
39 | USSS-35-3 | Rohtas |  | Middle School, Ghordihi | SAB CONSTUCTION |  |  |  | 1 | [10 empty] | 0 | Patna West | 2011-12
40 | USSS-36 (A) | Jahanabad |  | Middle School, Ahiyasa | PRAVEEN KUMAR 7033712900 | [8 empty] | 1 | [5 empty] | 0 | Magadh | 2011-12
41 | USSS-36 (B) | Jahanabad |  | Middle School,Sewnon | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Magadh | 2011-12
42 | USSS-36 (C) | Jahanabad |  | Middle School, Dewra | PRAVEEN KUMAR 7033712900 | [9 empty] | 1 |  |  |  |  | 0 | Magadh | 2011-12
43 | USSS-37 (A) | Aurangabad |  | Middle School, Kusumbasdiha | DHANANJAY KUMAR SINGH 9931845497 |  |  |  |  | 1 | [9 empty] | 0 | Magadh | 2011-12
44 | USSS-37 (B) | Aurangabad |  | Middle School, Pandu | DHANANJAY KUMAR SINGH 9931845497 |  |  | 1 | [9 empty] | LOA Issue. Land not available |  | 0 | Magadh | 2011-12
45 | USSS-38-1 | Aurangabad |  | Middle School, Gamharia | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land. |  | 0 | Magadh | 2011-12
46 | USSS-38-2 | Aurangabad |  | Middle School,Sondiha | MS MATESHWARI CONSTRUCTION, 7766886737 | [7 empty] | 1 | [6 empty] | 0 | Magadh | 2011-12
47 | USSS-38-3 | Aurangabad |  | Middle School, Raslpur | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land |  | 0 | Magadh | 2011-12
48 | USSS-39-1 | Aurangabad |  | Middle School, Chourahi | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land |  | 0 | Magadh | 2011-12
49 | USSS-39-2 | Aurangabad |  | Middle School, Sonbarsa | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land |  | 0 | Magadh | 2011-12
50 | USSS-39-3 | Aurangabad |  | Middle School, Dandwan | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Insufficient Land |  | 0 | Magadh | 2011-12
51 | USSS-40 (A) | Aurangabad |  | Middle School, Meh | MANOJ SINGH, 9939822131, 7033944511 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Magadh | 2011-12
52 | USSS-40 (B) | Aurangabad |  | Middle School, Tamoli | MANOJ SINGH, 9939822131, 7033944511 | [7 empty] | 1 | [6 empty] | 0 | Magadh | 2011-12
53 | USSS-41 (A) | Gaya |  | Middle School, Shyamnagar Nima | AZAD CONSTRUCTION |  |  | 1 | [9 empty] | Not Started |  | 0 | Magadh | 2011-12
54 | USSS-41 (B) | Gaya |  | Middle School, Khajuria | NAGENDRA SINGH 9631326479 | [7 empty] | 1 | [6 empty] | 0 | Magadh | 2011-12
55 | USSS-41 (C) | Gaya |  | Middle School, Parsawan Khurd | SURENDRA KUMAR 9128027943 | [7 empty] | 1 | [6 empty] | 0 | Magadh | 2011-12
56 | USSS-41 (D) | Gaya |  | Middle School, Belauti | SANJAY KUMAR SINGH 9973456006 | [5 empty] | 1 | [8 empty] | 0 | Magadh | 2011-12
57 | USSS-41 (E) | Gaya |  | Middle School,Bindhua | MRITUNJAY KUMAR SINGH 9097394660 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Magadh | 2011-12
58 | USSS-42 (A) | Gaya |  | Middle School, Sondiha | SANJAY KUMAR SINGH 9973456006 |  |  |  |  | 1 | [9 empty] | 0 | Magadh | 2011-12
59 | USSS-42 (B) | Gaya |  | Middle School, Angara | NARENDRA YADAB 99315315191 |  |  |  |  | 1 | [9 empty] | 0 | Magadh | 2011-12
60 | USSS-42 (C) | Gaya |  | Middle School, Punakalan | Narendra Yadab |  |  | 1 | [9 empty] | N.O.C. not available |  | 0 | Magadh | 2011-12
61 | USSS-42 (D) | Gaya |  | Middle School, Noni | RAVIN KUMAR 8797253525 |  |  |  |  | 1 | [9 empty] | 0 | Magadh | 2011-12
62 | USSS-43-1 | Gaya |  | Upgraded Middle School, Pater | Mithlesh Kumar Singh, 9931471924 | [11 empty] | 1 |  |  | 10975904 | Magadh | 2011-12
63 | USSS-43-2 | Gaya |  | Middle School, Bitho | Mithlesh Kumar Singh, 9931471924 |  |  | 1 | [9 empty] | Local Dispute |  | 0 | Magadh | 2011-12
64 | USSS-44 (A) | Nawada |  | Middle School, Bardhauna | RAJNISH VATS 8051666426 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Magadh | 2011-12
65 | USSS-44 (B) | Nawada |  | Upgraded Middle School, Puraini | Sudhir Kumar |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Magadh | 2011-12
66 | USSS-44 (C) | Nawada |  | Middle School, Kalound | SUDHIR KUMAR 9430411061 | [9 empty] | 1 |  |  |  |  | 0 | Magadh | 2011-12
67 | USSS-44 (D) | Nawada |  | Middle School, Paingari | SUDHIR KUMAR 9430411061 |  |  | 1 | [9 empty] | Not Started |  | 0 | Magadh | 2011-12
68 | USSS-44 (E) | Nawada |  | Upgraded Middle School, Bhatta | Rajnish Vats |  |  | 1 | [9 empty] | Not Started |  | 0 | Magadh | 2011-12
69 | USSS-17 (A) | Bhagalpur |  | Middle School Kishanpur | Dayanand Singh | [6 empty] | 1 | [7 empty] | 0 | Bhagalpur | 2011-12
70 | USSS-17 (B) | Bhagalpur |  | Middle School Tarchha | Dayanand Singh |  |  | 1 | [9 empty] | Not Strated |  | 0 | Bhagalpur | 2011-12
71 | USSS-18-1 | Bhagalpur |  | Middle School Ghanshyamchak | DAYANAND SINGH |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Bhagalpur | 2011-12
72 | USSS-19-1 | Bhagalpur |  | Middle School Kalgiganj | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 11793953 | Bhagalpur | 2011-12
73 | USSS-19-2 | Bhagalpur |  | Middle School Dayalpur | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 11793953 | Bhagalpur | 2011-12
74 | USSS-19-3 | Bhagalpur |  | Middle School Siya | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 11793953 | Bhagalpur | 2011-12
75 | USSS-19-4 | Bhagalpur |  | Middle School Kishunichak | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  |  | 11793954 | Bhagalpur | 2011-12
76 | USSS-20 (A) | Banka |  | Middle School kairi | Kundan Kumar Singh | [7 empty] | 1 | [6 empty] | 0 | Bhagalpur | 2011-12
77 | USSS-20 (B) | Banka |  | Middle School Bank | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Bhagalpur | 2011-12
78 | USSS-20 (C) | Banka |  | Middle School Pathdda | Lalan Kumar |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Bhagalpur | 2011-12
79 | USSS-21 (A) | Munger |  | Middle School Harinmar Bishunpur | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Munger | 2011-12
80 | USSS-21 (B) | Munger |  | Middle School Manik Mandal Tola | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Munger | 2011-12
81 | USSS-21 (C) | Munger |  | Middle School Kalyanpur | ANIL KUMAR SINGH 9570904951 |  |  | 1 | [9 empty] | Insufficient Land |  | 0 | Munger | 2011-12
82 | USSS-21 (D) | Munger |  | Middle School Teghara | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Munger | 2011-12
83 | USSS-21 (E) | Munger |  | Middle School Dhudhaladih | No bidder | 1 | [11 empty] | No Bidder. NIT-46 (2015-16) |  | 0 | Munger | 2011-12
84 | USSS-22 (A) | Munger |  | Middle School Ramcharit Maidan | DIGBIJAY KUMAR 8084371876 | [5 empty] | 1 | [8 empty] | 0 | Munger | 2011-12
85 | USSS-22 (B) | Munger |  | Middle School Madhura / Katiyari | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Munger | 2011-12
86 | USSS-22 (C) | Munger |  | Middle School, Dhobai | Retender | 1 | [11 empty] | Retender |  | 0 | Munger | 2011-12
87 | USSS-22 (D) | Munger |  | Middle School Nabgoi | Rajendra Pd |  |  | 1 | [9 empty] | Not Started |  | 0 | Munger | 2011-12
88 | USSS-23-1 | Lakhisarai |  | Middle School, Bahachha | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 9026909 | Munger | 2011-12
89 | USSS-23-2 | Lakhisarai |  | Middle School Tarhari | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 9026909 | Munger | 2011-12
90 | USSS-23-3 | Lakhisarai |  | Middle School Nongarh | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  |  | 9026909 | Munger | 2011-12
91 | USSS-23-4 | Lakhisarai |  | Upgraded Middle School Surari | SUGEET KUMAR,9504681342 | [7 empty] | 1 | [6 empty] | 3610762 | Munger | 2011-12
92 | USSS-24 (A) | Lakhisarai |  | Upgraded Middle School Bihraura | MS BALRAM KUMAR 9430065800 |  |  |  |  | 1 | [9 empty] | 0 | Munger | 2011-12
93 | USSS-24 (B) | Lakhisarai |  | Middle School Pokhrama | SAI HIGHWAY AND BUILDERS PVT LTD 9771455967 | [7 empty] | 1 | [6 empty] | 0 | Munger | 2011-12
94 | USSS-24 (C) | Lakhisarai |  | Upgraded Middle School Dhoni Kundi | MONEY CONSTRUCTION PRIVATE LIMITED 9386596373 | [8 empty] | 1 | [5 empty] | 0 | Munger | 2011-12
95 | USSS-25-1 | ks[kiqjk |  | Middle School, Akrama | Epitome Construction Pvt Ltd,8935825344 | [10 empty] | 1 |  |  |  | 8787379 | Munger | 2011-12
96 | USSS-25-2 | Sheikhpura |  | Upgraded Middle School, Diha | Epitome Construction Pvt Ltd,8935825344 | [7 empty] | 1 |  |  |  |  | WORK STOPPED BY DIST ADMN (upto FF sill lv) |  | 4652144 | Munger | 2011-12
97 | USSS-25-3 | Sheikhpura |  | Middle School, Kutout | Epitome Construction Pvt Ltd,8935825344 | [11 empty] | 1 |  |  | 10338093 | Munger | 2011-12
98 | USSS-45 (A) | Jamaui |  | Upgraded Middle School, Harla | Sudesh & Co | [7 empty] | 1 | [6 empty] | 0 | Munger | 2011-12
99 | USSS-45 (B) | Jamaui |  | Middle School, Kairakado | Double Scheme |  |  | 1 | [9 empty] | Double Scheme. Match to SSS 184 |  | 0 | Munger | 2011-12
100 | USSS-45 (C) | Jamaui |  | Middle School, Shobhakhan | Anil Singh | [6 empty] | 1 | [7 empty] | 0 | Munger | 2011-12
101 | USSS-45 (D) | Jamaui |  | Middle School, Abgila Chourasa | NATHUNI YADAV 9931012527 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Munger | 2011-12
102 | USSS-47 (A) | Munger | Birpur | Middle School Parra | MS KUMAR TRADING COMPANY 9431276100 | [7 empty] | 1 | [6 empty] | 0 | Munger | 2011-12
103 | USSS-47 (B) | Munger | Bakhari | Middle School Lauchhe | Retender | 1 | [11 empty] | NIT-46 (2015-16). Retender |  | 0 | Munger | 2011-12
104 | USSS-47 (C) | Munger | Birpur | Middle School Kharmauli | MS BALRAM KUMAR 9430065800 | [5 empty] | 1 | [8 empty] | 0 | Munger | 2011-12
105 | USSS-47 (D) | Munger | Sahebpur Kamal | Middle School Hira Tol | RAM NIWAS KUMAR 9431067357 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Munger | 2011-12
106 | USSS-47 (E) | Munger | Mansurchak | Middle School Makdhampur | Retender | 1 | [11 empty] | No Bidder. NIT-46 (2015-16) |  | 0 | Munger | 2011-12
107 | USSS-48-1 | Munger | Begusarai | Middle School Akaha | RAM NARESH SHARMA 9430088029 | [5 empty] | 1 | [8 empty] | 0 | Munger | 2011-12
108 | USSS-48-2 | Munger | Begusarai | Middle School Bhitsari | Tender Process | 1 | [11 empty] | Tender Process |  | 0 | Munger | 2011-12
109 | USSS-10 (A) | Saharsa |  | Middle School Dhamsaina | JIWAN LAXMI CONSTRUCTION PVT LTD 9431089386 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Kosi | 2011-12
110 | USSS-6 (A) | Araria |  | Middle School Mangalwar Chariya | Shining Madhusudan Construction |  |  |  | 1 | [10 empty] | 0 | Purnea | 2011-12
111 | USSS-6 (B) | Araria |  | Middle School Maldwar East | WALKS n WALKS MANAGE PRIVATE LIMITED 8434514666 |  |  | 1 | [9 empty] | NIT-46 (2015-16) |  | 0 | Purnea | 2011-12
112 | USSS-7-1 | Kishanganj |  | Middle School Daula | BIRENDRA KUMAR SINGH,9473440405 |  |  | 1 | [9 empty] | H.M. not giving permission to construct the building |  | 0 | Purnea | 2011-12
113 | USSS-8 (A) | Purnea |  | Middle School Rupauli | Walks n Walks Manage Pvt. Ltd. |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Purnea | 2011-12
114 | USSS-8 (B) | Purnea |  | Middle School Rampur Tilak East | Tender Process |  | 1 | [10 empty] | Double Scheme |  | 0 | Purnea | 2011-12
115 | USSS-8 (C) | Purnea |  | Middle School ,Mahendra Nagar Diyara | Tender Process | 1 | [11 empty] | Retender |  | 0 | Purnea | 2011-12
116 | USSS-9-1 | katihar |  | Middle School Belwa | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1 |  |  | 9988042 | Purnea | 2011-12
117 | USSS-9-2 | katihar |  | Middle School Kharsauta | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 |  |  |  |  | FF sill level |  | 5287789 | Purnea | 2011-12
118 | USSS-9-3 | katihar |  | Middle School Kalyan Gaon | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  |  | 9988042 | Purnea | 2011-12
119 | USSS-9-4 | katihar |  | Middle School Rampur | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  |  | 7637914 | Purnea | 2011-12
120 | USSS-4 (A) | Sitamarhi |  | Middle School Sutihara | Shashi Kant Singh |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut East | 2011-12
121 | USSS-4 (B) | Sitamarhi |  | Middle School Bhantawari | Shashi Kant Singh 9771952932 | [5 empty] | 1 | [8 empty] | 0 | Tirhut East | 2011-12
122 | USSS-4 (C) | Sitamarhi |  | Middle School Rajwara | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 | [7 empty] | 1 | [6 empty] | 0 | Tirhut East | 2011-12
123 | USSS-12-1 | Muzaffarpur |  | Middle School Bariyarpur | S R CONSTRUCTIONS PVT LTD, 7739441850 | [11 empty] | 1 |  |  | 9936538 | Tirhut East | 2011-12
124 | USSS-12-2 | Muzaffarpur |  | Middle School Dhabauli | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | Land Dispute |  | 0 | Tirhut East | 2011-12
125 | USSS-12-3 | Muzaffarpur |  | Middle School Lakhanpur | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | Land Dispute |  | 0 | Tirhut East | 2011-12
126 | USSS-13 (A) | Muzaffarpur |  | Middle School Bhatauna | VIJAY KUMAR SHAHI 9507385720 |  |  |  |  | 1 | [9 empty] | 0 | Tirhut East | 2011-12
127 | USSS-13 (B) | Muzaffarpur |  | Middle School Sirkohiya | DEVENDRA KUMAR 9708256685 |  |  |  |  | 1 | [9 empty] | 0 | Tirhut East | 2011-12
128 | USSS-15 (A) | Vaishali |  | Upgraded Middle School Panapur Silaut | Tender Process |  | 1 | [10 empty] | NIT-46 (2015-16) |  | 0 | Tirhut East | 2011-12
129 | USSS-15 (B) | Vaishali |  | Upgraded Middle School Totha | SACHIN CONSTRUCTION |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut East | 2011-12
130 | USSS-15 (C) | Vaishali |  | Middle School Shital Bhakurhar | GAJENDRA PATEL 9708793426 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut East | 2011-12
131 | USSS-1 (A) | West Champaran |  | Govt. Middle School Kumhiya | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut West | 2011-12
132 | USSS-1 (B) | West Champaran |  | Middle School Panchgawa | SHARDA CHANDEL CONTRACT PVT 9792083771 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut West | 2011-12
133 | USSS-1 (C) | West Champaran |  | Middle School Donwar | MOHD SHAFIQUE 9939886786 | [7 empty] | 1 | [6 empty] | 0 | Tirhut West | 2011-12
134 | USSS-1 (D) | West Champaran |  | Ugraded middle school malahi tola | MATA VAISHNO AND CHANDEL CONSTRUCTION PVT LTD 7091739151 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut West | 2011-12
135 | USSS-2-1 | East Champaran |  | Middle School Mali | ASIANA CONSTRACT PVT LTD, 9431088485 |  |  | 1 | [9 empty] | Not Start |  | 0 | Tirhut West | 2011-12
136 | USSS-2-2 | East Champaran |  | Middle School Chand parsa | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  |  | 10585711 | Tirhut West | 2011-12
137 | USSS-2-3 | East Champaran |  | Middle School Sitalpur | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  |  | 10585711 | Tirhut West | 2011-12
138 | USSS-3 (A) | Sheohar |  | Middle School Dhankaul | SHEEL CONSTRUCTION 9430081574 | [5 empty] | 1 | [8 empty] | 0 | Tirhut West | 2011-12
139 | USSS-3 (B) | Sheohar |  | Middle School Narayanpur | Shashi Kant Singh 9771952932 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut West | 2011-12
140 | USSS-3 (C) | Sheohar |  | Middle School Khairadarp | Shashi Kant Singh 9771952932 |  |  | 1 | [9 empty] | LOA Issue |  | 0 | Tirhut West | 2011-12
141 | USSS-5-1 | Madhubani |  | Govt. Middle School Rudrapur | Kamlesh Kumar 934808205 | [11 empty] | 1 | inugurated |  | 11972534 | Darbhanga | 2011-12 | 2015-10-05
142 | USSS-5-2 | Madhubani |  | Govt. Middle School Bhatra Ghat | Kamlesh Kumar 934808205 | [10 empty] | 1 |  |  |  | 10176654 | Darbhanga | 2011-12
143 | USSS-11 (A) | Darbhanga |  | Upgraded Middle School Raj kharwar | ASHOK KUMAR YADAV 9386050569 |  |  |  | 1 | [10 empty] | 0 | Darbhanga | 2011-12
144 | USSS-11 (B) | Darbhanga |  | Upgraded Middle School Tilkeshwar Sthan | ASHOK KUMAR YADAV 9386050569 |  |  |  | 1 | [10 empty] | 0 | Darbhanga | 2011-12
145 | USSS-11 (C) | Darbhanga |  | Upgraded Middle School Raipur | AKSHIT ENGINEERING AND CONSTRUCTION PRIVATE LIMITED 08227896001 |  |  |  |  | 1 | [9 empty] | 0 | Darbhanga | 2011-12
146 | USSS-16-1 | Samastipur |  | Middle School Isar Tola | Rohan Construction |  |  |  | 1 | [10 empty] | 0 | Darbhanga | 2011-12
147 | USSS-14-1 | Siwan |  | Middle School Sahadulpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  |  | 9283854 | Saran | 2011-12
148 | USSS-14-2 | Siwan |  | Middle School Gamiyar | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land not available |  |  | Saran | 2011-12
149 | USSS-14-3 | Siwan |  | Middle School Daraunda | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 10922181 | Saran | 2011-12
150 | USSS-14-4 | Siwan |  | Middle School, Baluya | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 10922181 | Saran | 2011-12
151 | USSS-14-5 | Siwan |  | Middle School Barka Manjha | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 10922181 | Saran | 2011-12
152 | USSS-46-1 | Siwan |  | Middle School Sikatiya | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [11 empty] | 608043 | Saran | 2011-12
153 | USSS-46-2 | Siwan |  | Middle School Kilpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [9 empty] | 1 |  |  |  |  | 6688410 | Saran | 2011-12
154 | USSS-46-3 | Siwan |  | Middle School Pratapur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  |  | 10336633 | Saran | 2011-12
155 | USSS-46-4 | Siwan |  | Middle School Shivpur Sakra | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land Problem |  |  | Saran | 2011-12
156 | USSS-46-5 | Siwan |  | Middle School Balaipur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [10 empty] | 1 |  |  |  | 10336633 | Saran | 2011-12
Total No. of USSS (2011-12) | [5 empty] | 7 | 9 | 54 | 5 | 13 | 8 | 3 | 18 | 2 | 6 | 14 | 17
|  |  |  | USSS 2011-12 |  |  |  |  | 5 | 13 | 8 | 3 | 18 | 2 | 6 | 14 | 17
|  |  |  | USSS 2013-14 |  |  |  |  | 2 | 2 | 7 | 2 | 10 | 4 | 11 | 52 | 86
[9 empty] | 7 | 15 | 15 | 5 | 28 | 6 | 17 | 66 | 103
Note on F114: Cancel