## List of State Fund
BSEIDC Ltd., Patna
List of USS (State Fund) 2009-10
S.N. | Group No. | Name of District | Name of Block | Name of School | Name of Agency | Physical Status | [9 empty] | Remarks | Division | Session
[6 empty] | Not Start | Layout | Foundation | PL | Grd floor |  | 1st Floor |  | Finishing | Complete
[10 empty] | LL | RL | LL | RL
1 | USS-219-1 | Bhojpur | cjgkjk | dqnfj;k ij'kqjke eŒ foŒ] | Sudarshan Mahto, At- Jagdishpur, Arrah 8092775732 | [9 empty] | 1 | Inaugurated | Patna East | 2009-10
2 | USS-218-1 | Rohtas | fnukjk | eŒ foŒ fnukjk 8294218392 | Sudarshan Mahto, At- Jagdishpur, Arrah 8092775732 | 1 | [9 empty] | Land not available, earnest money refund | Patna West | 2009-10
3 | USS-221-1 | Banka | pdeqfu;k | eŒ foŒ] pdeqfu;k | D.P.Maheshwari Construction India Pvt. Ltd. 9162255747 | [7 empty] | 1 |  |  | FFRC | Bhagalpur | 2009-10
4 | USS-213-1 | Shekhpura | gFkh;kok¡ | mRŒ eŒ foŒ] jke jk;iqj 8757419360 9431474761 | Arbind Prasad, Purankama, P.O.+ Distt.- Sheikhpura, Bihar 9431258802 | [9 empty] | 1 |  | Munger | 2009-10
5 | USS-214-1 | Begusarai | cfy;k | dykorh egknso eŒ foŒ] cjoh/kh | Raja Enterprises & Co. 9431694183 (19.10.2012) | 1 | [9 empty] | No Land | Munger | 2009-10
6 | USS-215-1 | Munger | eklqexat] Hkkxyiqj | mnkMhg eŒ foŒ | D.P.Maheshwari Construction India Pvt. Ltd. 9162255747 | [8 empty] | 1 |  |  | Munger | 2009-10
7 | USS-201-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] pdyk?kkV 7250532741 | Md. Shafique Alam, Dhanpura, Kishanganj, 9431259842 (16.05.2012) | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
8 | USS-201-2 | Kishanganj | fd'kuxat | e/; fo¦ky;] xkNikMk+ 9973279595 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
9 | USS-201-3 | Kishanganj | fd'kuxat | e/; fo¦ky;] nkSyk 8987031909 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
10 | USS-201-4 | Kishanganj | fd'kuxat | e/; fo¦ky;] eghuxk¡o 7549846854 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
11 | USS-201-5 | Kishanganj | fd'kuxat | e/; fo¦ky;] cssyok] dk'khiqj 9470077789 | Md. Shafique Alam | 1 | [9 empty] | No Land Proposal for drop by E.E. letterno.-264/15Dt.-27.01.2015 | Purnea | 2009-10
12 | USS-202-1 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] cSfj;k 8292434525 | M/S Bala Jee Construction, Co-Operative Colony, Purnea, 9006169540 (16.05.2012) | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
13 | USS-202-2 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] cSxuk 9939791780 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
14 | USS-202-3 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] lqfg;k jgeriqj 8544018037 | M/S Bala Jee Construction | 1 | [9 empty] | Land not available | Purnea | 2009-10
15 | USS-202-4 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] dekrh 8757640064 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
16 | USS-202-5 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] csuqx<+ 9801048554 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
17 | USS-203-1 | Kishanganj | fnX?kycSad | e/; fo¦ky;] fla/khekjh 8986097091 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
18 | USS-203-2 | Kishanganj | fnX?kycSad | e/; fo¦ky;] tj>qyk 9973230476 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
19 | USS-203-3 | Kishanganj | fnX?kycSad | e/; fo¦ky;] dqjgSyh 9661248448 | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
20 | USS-203-4 | Kishanganj | fnX?kycSad | e/; fo¦ky;] dVgyckMh | Md. Shafique Alam | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
21 | USS-204-1 | Kishanganj | Ckgknqjxat | e/; fo¦ky;] nsfl;kVksyh 9934444776 | Md. Shafique Alam | 1 | [9 empty] | Land not Available | Purnea | 2009-10
22 | USS-204-2 | Kishanganj | Ckgknqjxat | e/; fo¦ky;] [skryckMh | Md. Shafique Alam | 1 | [9 empty] | Land not Available | Purnea | 2009-10
23 | USS-204-3 | Kishanganj | Ckgknqjxat | e/; fo¦ky;] yksgkxkMkgkV 9955726430 | Md. Shafique Alam | 1 | [9 empty] | Land not Available | Purnea | 2009-10
24 | USS-204-4 | Kishanganj | Ckgknqjxat | e/; fo¦ky;] egs'kcFkuk 9973612231 | Md. Shafique Alam | 1 | [9 empty] | Land not Available | Purnea | 2009-10
25 | USS-205-1 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] /kuirxat 9430017157 | Birendra Kumar | [9 empty] | 1 | . | Purnea | 2009-10
26 | USS-205-2 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] gYnh[kksMk+ 9470077991 | Birendra Kumar | [9 empty] | 1 | . | Purnea | 2009-10
27 | USS-205-3 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] eksnksg 9470611886 | Birendra Kumar | [9 empty] | 1 | . | Purnea | 2009-10
28 | USS-205-4 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] cMhtku 9471276232 | Birendra Kumar | 1 | [10 empty] | Purnea | 2009-10
29 | USS-206-1 | Kishanganj | Bkdqjxat | e/; fo¦ky;] dknksxk¡o 9431002508 | M/S C.S. Construction, Gayatari Nagar, Motihari, Bihar 9473290979/ 8235161126/ 9304566888 | [7 empty] | 1 |  |  |  | Purnea | 2009-10
30 | USS-206-2 | Kishanganj | Bkdqjxat | e/; fo¦ky;] jktkxk¡o 7250327554 | M/S C.S. Construction | [7 empty] | 1 |  |  |  | Purnea | 2009-10
31 | USS-206-3 | Kishanganj | Bkdqjxat | e/; fo¦ky;] jfl;k 9472898877 | M/S C.S. Construction | [9 empty] | 1 | . | Purnea | 2009-10
32 | USS-206-4 | Kishanganj | Bkdqjxat | e/; fo¦ky;] xyxfy;k 9472979439 | M/S C.S. Construction | 1 | [10 empty] | Purnea | 2009-10
33 | USS-207-1 | Kishanganj | iksfB;k | e/; fo¦ky;] dfy;kxat 9661821842 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
34 | USS-207-2 | Kishanganj | iksfB;k | e/; fo¦ky;] jk;iqj 9430948041 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
35 | USS-207-3 | Kishanganj | iksfB;k | e/; fo¦ky;] efj;k 8969807582 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
36 | USS-207-4 | Kishanganj | iksfB;k | e/; fo¦ky;] nyqvkgkV 9801908155 | M/S Bala Jee Construction | [9 empty] | 1 | Inaugurated | Purnea | 2009-10
37 | USS-220-1 | Vaishali | xksjkSy | eŒ foŒ bLykeiqj 9430036055 | M/S Shanti Construction | [9 empty] | 1 | Inaugurated | Tirhut East | 2009-10
38 | USS-208-1 | East Champaran | ckjk pfd;k | eŒ foŒ] ?ku';ke idjh 9431054693 | M/S Babban Singh, Patpariya, Motihari 9431269941 | [9 empty] | 1 |  | Tirhut West | 2009-10
39 | USS-208-2 | East Champaran | lqxkSyh | eŒ foŒ] pSuiqj 9661300867 | M/S Babban Singh, Patpariya, Motihari 9431269941 |  |  |  | 1 | [6 empty] | Not start | Tirhut West | 2009-10
40 | USS-209-1 | West Champaran | oxgk&II | eŒ foŒ] jruiqjok | Mata Vaoshno And Chandel Const.Pvt. Ltd.,P.O.-Dhanaha, Distt.-West Champaran | 1 | [9 empty] | Not start | Tirhut West | 2009-10
41 | USS-216-1 | Darbhanga | yksvke | eŒ foŒ] yksvke 8987280647 | Amrendra Kumar, P.O-Senduari, Distt.-Vaishali. | 1 | [9 empty] | Land not available | Darbhanga | 2009-10
42 | USS-217-1 | Madhubani | [kqVkSuk | eŒ foŒ ,dFFkk 9931014148 9771934377 | Abhisheka, Vill.-Bairbona, P.O. Siswar, P.S.- Khutauna, Dist.- MAdhubani | [6 empty] | 1 |  |  |  |  | Darbhanga | 2009-10
43 | USS-210-1 | Lkkj.k | flrkc fn;kjk | Ckkfydk eŒ foŒ] flrkc fn;kjk 9648348951 | Vinay Pratap Singh, B-401, Sagar Appt., Magistrate Colony, Ashiyana Nagar, Patna 9471867563 | 1 | [9 empty] | Land not available | Saran | 2009-10
44 | USS-211-1 | xksikyxat | mpdkxk¡o | e/; fo¦ky;] dijiqjk | M/S Shri Krishna Const. Company, Sushila Swami Sadan, North Womens College, Gopalganj 9801697295 | [9 empty] | 1 | . | Saran | 2009-10
45 | USS-212-1 | lhoku | uoru | eŒ foŒ]vaXkkSrk 9162360244 | Ashiana Contract Pvt. Ltd., Rajendra Nagar, Gopalganj 9431088485 (18.10.2012) | [9 empty] | 1 | Inaugurated | Saran | 2009-10
Total No. of Schools (USS) State Fund |  |  |  | 45 |  | 13 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 26
| Total No. of Schools |  | 45
| Retender ( No. of Schools) |  | 0
| Contract Awarded |  | 45
| Inaugurated (No. of Schools) |  | 19

## Completed (USS-SF)
BSEIDC Ltd., Patna
Completed List of USS (State Fund) 2009-10
S.N. | Group No. | Name of District | Name of Block | Name of School | Physical Status | Remarks
1 | USS-219-1 | Bhojpur | cjgkjk | dqnfj;k ij'kqjke eŒ foŒ] | Completed | Inaugurated
2 | USS-213-1 | Shekhpura | gFkh;kok¡ | mRŒ eŒ foŒ] jke jk;iqj 8757419360 9431474761 | Completed
3 | USS-201-1 | Kishanganj | fd'kuxat | e/; fo¦ky;] pdyk?kkV 7250532741 | Completed | Inaugurated
4 | USS-201-2 | Kishanganj | fd'kuxat | e/; fo¦ky;] xkNikMk+ 9973279595 | Completed | Inaugurated
5 | USS-201-3 | Kishanganj | fd'kuxat | e/; fo¦ky;] nkSyk 8987031909 | Completed | Inaugurated
6 | USS-201-4 | Kishanganj | fd'kuxat | e/; fo¦ky;] eghuxk¡o 7549846854 | Completed | Inaugurated
7 | USS-202-1 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] cSfj;k 8292434525 | Completed | Inaugurated
8 | USS-202-2 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] cSxuk 9939791780 | Completed | Inaugurated
9 | USS-202-4 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] dekrh 8757640064 | Completed | Inaugurated
10 | USS-202-5 | Kishanganj | Vs<+kxkNh | e/; fo¦ky;] csuqx<+ 9801048554 | Completed | Inaugurated
11 | USS-203-1 | Kishanganj | fnX?kycSad | e/; fo¦ky;] fla/khekjh 8986097091 | Completed | Inaugurated
12 | USS-203-2 | Kishanganj | fnX?kycSad | e/; fo¦ky;] tj>qyk 9973230476 | Completed | Inaugurated
13 | USS-203-3 | Kishanganj | fnX?kycSad | e/; fo¦ky;] dqjgSyh 9661248448 | Completed | Inaugurated
14 | USS-203-4 | Kishanganj | fnX?kycSad | e/; fo¦ky;] dVgyckMh | Completed | Inaugurated
15 | USS-205-1 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] /kuirxat 9430017157 | Completed | HANDOVER
16 | USS-205-2 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] gYnh[kksMk+ 9470077991 | Completed | HAND OVER
17 | USS-205-3 | Kishanganj | dkspk/kkeu | e/; fo¦ky;] eksnksg 9470611886 | Completed | HANDOVER
18 | USS-206-3 | Kishanganj | Bkdqjxat | e/; fo¦ky;] jfl;k 9472898877 | Completed | HANDOVER
19 | USS-207-1 | Kishanganj | iksfB;k | e/; fo¦ky;] dfy;kxat 9661821842 | Completed | Inaugurated
20 | USS-207-2 | Kishanganj | iksfB;k | e/; fo¦ky;] jk;iqj 9430948041 | Completed | Inaugurated
21 | USS-207-3 | Kishanganj | iksfB;k | e/; fo¦ky;] efj;k 8969807582 | Completed | Inaugurated
22 | USS-207-4 | Kishanganj | iksfB;k | e/; fo¦ky;] nyqvkgkV 9801908155 | Completed | Inaugurated
23 | USS-220-1 | Vaishali | xksjkSy | eŒ foŒ bLykeiqj 9430036055 | Completed | Inaugurated
24 | USS-208-1 | East Champaran | ckjk pfd;k | eŒ foŒ] ?ku';ke idjh 9431054693 | Completed
25 | USS-211-1 | xksikyxat | mpdkxk¡o | e/; fo¦ky;] dijiqjk | Completed | Handover
26 | USS-212-1 | lhoku | uoru | eŒ foŒ]vaXkkSrk 9162360244 | Completed | Inaugurated