## AKU (2)
BSEIDC Ltd., Patna
* Project Cost (in Crore):- Rs. 99.04 | [11 empty] | * Time of Completion: 24 Months
Progress Report of Construction of ARYBHATT KNOWLEDGE UNIVERSITY, PATNA
S. No. | Group no. | Name of District | Name of Block | Name of Buildings & Pattern | Image Updated | Agreement No. & Date | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | 3rd Floor |  | 4th Floor |  | 5th Floor |  | 6th Floor |  | Finishing | Complete | Remarks
[10 empty] | LL | RL | LL | RL | LL | RL | LL | RL | LL | RL | LL | RL | LL | RL
1 | AKU-1-1 | PATNA | PATNA SADAR | AKU - V.C. Bungalow & (G+1) | [9 empty] | X | X | X | X | X | X | X | X | X | X | 1
| AKU-1-2 |  |  | AKU - Registrar House & (G+1) | [9 empty] | X | X | X | X | X | X | X | X | X | X | 1
| AKU-1-3 |  |  | AKU - Guest House & (G+2) | [11 empty] | X | X | X | X | X | X | X | X | 1
| AKU-1-4 |  |  | AKU - Staff Quarter & (G+2) | [11 empty] | X | X | X | X | X | X | X | X | 1
| AKU-1-5 |  |  | AKU - Scholar House & (G+3) | [13 empty] | X | X | X | X | X | X | 1 |  |  | X
| AKU-1-6 |  |  | AKU - Block ‘A’ & (G+6) | [19 empty] | 1
| AKU-1-7 |  |  | AKU - Block ‘B’ & (G+6) | [19 empty] | 1
| AKU-1-8 |  |  | AKU - Block ‘C’ & (G+6) | [19 empty] | 1
Total No. of University / Buildings: |  |  |  | 1 / 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0