## Sheet1
BSEIDC Ltd., Patna
Physical Status of Model School 2009-10 & 2010-11
Sl. NO. | Sl. No. | Group no | UDISE CODE | Name of Division | Session | District | Block | SN | Name Of School |  | Physical Status
[10 empty] | Agreement Value | Not Start | LAY OUT | FOUND ATION | PL | Ground Floor |  | First Floor |  | Second Floor |  | FINI SHING | COMP LETE | Remarks
[15 empty] | LL | RL | LL. | RL. | LL. | RL.
1 |  | MS-1 | 10120701210 | Koshi | 2009-10 | सहरसा | सोनबरसा | 1 | High School Sonbarsha | 273.3667 | [10 empty] | 1 |  | Plaster and Kota work
2 |  | MS-1 |  | Koshi | 2009-10 | सहरसा | सोनबरसा | 2 | Govt. Basic School Surath | 273.3667 | [10 empty] | 1 |  | Work Stop.
3 |  | MS-1 | 10120201801 | Koshi | 2009-10 | सहरसा | Attar Kataiya | 3 | High School Menha | 273.3667 | [11 empty] | 1 | Inaugurated
4 |  | MS-2 |  | Koshi | 2009-10 | मधेपुरा | कुमारखंड | 1 | High School Kumarkhand | 272.65 | [10 empty] | 1 |  | All Finishing Works in progress.
5 |  | MS-2 |  | Koshi | 2009-10 | मधेपुरा | मधेपुरा | 2 | Shiv Nandan Pd.+2 School | 272.65 | [11 empty] | 1 | Inaugurated 16.07.2016
6 |  | MS-2 | 10110501823 | Koshi | 2009-10 | मधेपुरा | आलमनगर | 3 | A.K.M. H/S Shah Alam Nagar | 272.65 | [11 empty] | 1 | Inaugurated 16.07.2016
7 |  | MS-3 | 10061102301 | Koshi | 2009-10 | सुपौल | त्रिवेणीगंज | 1 | M/S.Daparkha | 283 | [11 empty] | 1 | Inaugurated
8 |  | MS-3 | 10060108701 | Koshi | 2009-10 | सुपौल | बसंतपुर | 2 | H/S.Hirdya Nagar | 283 | [11 empty] | 1 | Inaugurated 16.07.2016
9 |  | MS-163 |  | Koshi | 2010-11 | सुपौल | किशनपुर | 1 | H/S, Kishanpur | 280.5 | [11 empty] | 1 | Inaugurated 16.07.2016
10 |  | MS-163 | 10061004109 | Koshi | 2010-11 | सुपौल | सुपौल | 2 | H/S, Sukhpur | 280.5 | [11 empty] | 1 | Inaugurated
11 |  | MS-163 | 10060601605 | Koshi | 2010-11 | सुपौल | पिपरा | 3 | Govt. Basic School, Basaha | 280.5 | [11 empty] | 1 | Inaugurated 16.07.2016
12 |  | MS-164 | 10060802813 | Koshi | 2010-11 | सुपौल | राघोपुर | 1 | L.S. H/S, Simrahi Bazar, Raghopur | 285.7033 | [9 empty] | 1 |  |  | Bricks Work
13 |  | MS-164 | 10060700510 | Koshi | 2010-11 | सुपौल | प्रतापगंज | 2 | Public H/S, Pratapganj | 285.7033 | [11 empty] | 1 | Inaugurated 16.07.2016
14 |  | MS-164 |  | Koshi | 2010-11 | सुपौल | छातापुर | 3 | S.S. H/S, Sukhpur. Surpatganj | 285.7033 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-51)
15 |  | MS-165 | 10060902405 | Koshi | 2010-11 | सुपौल | सरायगढ़ भपटियाही | 1 | B.G H/S, Bhaptiyahi | 262.13 | [11 empty] | 1 | Inaugurated 16.07.2016
16 |  | MS-29 | 10140502104 | Tirhut East | 2009-10 | मुजफ्फरपुर | Kurhni | 1 | HS Chhajan Mohini | 263.9833 | [11 empty] | 1 | Inaugurated
17 |  | MS-29 |  | Tirhut East | 2009-10 | मुजफ्फरपुर | सकरा | 2 | Govt. Basic School, Rapeura | 263.9833 | [11 empty] | 1 | Inaugurated
18 |  | MS-29 |  | Tirhut East | 2009-10 | मुजफ्फरपुर | मुशहरी | 3 | H/S.Meghmath | 263.9833 | [11 empty] | 1 | Inaugurated
19 |  | MS-30 | 10181106703 | Tirhut East | 2009-10 | वैशाली | जन्दाहा | 1 | R.B.S.Loma | 256.3404 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-52)
20 |  | MS-30 | 10180804101 | Tirhut East | 2009-10 | वैशाली | पातेपुर | 2 | Govt. Basic School Bardiha | 256.3404 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-53)
21 |  | MS-30 | 10180114701 | Tirhut East | 2009-10 | वैशाली | हाजीपुर | 3 | Govt. Basic School Jagdishpur | 256.3404 | [9 empty] | 1
22 |  | MS-30 | 10180600907 | Tirhut East | 2009-10 | वैशाली | महुआ | 4 | M.S Singhara | 256.3404 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (SL.No.-1)
23 |  | MS-31 | 10181303109 | Tirhut West | 2009-10 | पूर्वी चंपारण | कल्यानपुर | 1 | Govt. Basic School Madhopur Govind | 271.715 | [11 empty] | 1 | Inaugurated
24 |  | MS-31 | 10180705003 | Tirhut West | 2009-10 | पूर्वी चंपारण | चकिया | 2 | B.A.A.P. H/S. Barachakia | 271.715 | [11 empty] | 1 | Inaugurated
25 |  | MS-32 | 10181405301 | Tirhut West | 2009-10 | पश्चिम चम्पारण | बगहा-1 | 1 | Govt. Basic School Patilar | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
26 |  | MS-32 | 10181509803 | Tirhut West | 2009-10 | पश्चिम चम्पारण | नरकटियागंज | 2 | H/S. Mathura Gokhula | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
27 |  | MS-32 | 10181601701 | Tirhut West | 2009-10 | पश्चिम चम्पारण | मझौलिया | 3 | Govt. Basic School Mahna Mirjapur | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
28 |  | MS-33 | 10040403518 | Tirhut East | 2009-10 | सीतामढी | रून्‍नीसैदपुर | 1 | H./S.Morsand | 261.77 | [11 empty] | 1 | Inaugurated
29 |  | MS-33 |  | Tirhut East | 2009-10 | सीतामढी | सोनबरसा | 2 | H/S. Sonbarsha | 261.77 | [11 empty] | 1 | Inaugurated
30 |  | MS-34 | 10030304605 | Tirhut West | 2009-10 | शिवहर | तरियानी | 1 | H.S.Taiyari | 267.8533 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
31 |  | MS-34 | 10030204801 | Tirhut West | 2009-10 | शिवहर | शिवहर | 2 | Govt. Basic School Bishahi | 267.8533 | [10 empty] | 1 |  | Painting done, Inside Finishing going on
32 |  | MS-34 | 10032201804 | Tirhut West | 2009-10 | शिवहर | पुरनहिया | 3 | H/S. Sonoul Sultan | 267.8533 | [10 empty] | 1 |  | Painting done, Inside Finishing going on
33 |  | MS-109 | 10181303109 | Tirhut East | 2010-11 | वैशाली | राघोपुर | 1 | T.R.S.S. H/S Jurawanpur | 266.15 | [11 empty] | 1 | Inaugurated 2017
34 |  | MS-109 | 10180705003 | Tirhut East | 2010-11 | वैशाली | महनार | 2 | Govt. Basic School, Karnauti | 266.15 | [11 empty] | 1 | Inaugurated
35 |  | MS-109 | 10181405301 | Tirhut East | 2010-11 | वैशाली | बिदुपुर | 3 | Govt. Basic School, Chechar | 266.15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
36 |  | MS-110 | 10181509803 | Tirhut East | 2010-11 | वैशाली | वैशाली | 1 | H.S H/S, Chintamanipur | 263.2033 | [11 empty] | 1 | Inaugurated
37 |  | MS-110 | 10181601701 | Tirhut East | 2010-11 | वैशाली | पतेर्ही बेलसर | 2 | Govt. Basic School, Surhattha | 263.2033 | [11 empty] | 1 | Inaugurated
38 |  | MS-110 |  | Tirhut East | 2010-11 | वैशाली | लालगंज | 3 | Govt. Basic School, Michagadh | 263.2033 | [11 empty] | 1 | Inaugurated
39 |  | MS-111 | 10180204501 | Tirhut East | 2010-11 | वैशाली | भगवानपुर | 1 | Govt. Basic School, Warispur | 264.4433 | [11 empty] | 1 | Inaugurated
40 |  | MS-111 | 10180502801 | Tirhut East | 2010-11 | वैशाली | गोरौल | 2 | Govt. Basic School, Kanhauli | 264.4433 | [11 empty] | 1 | Inaugurated
41 |  | MS-111 | 10180401603 | Tirhut East | 2010-11 | वैशाली | चेहरा कलां | 3 | B.N. H/S, Sehan | 264.4433 | [11 empty] | 1 | Inaugurated
42 |  | MS-112 | 10181004002 | Tirhut East | 2010-11 | वैशाली | राजा पाकर | 1 | Govt. Basic School, Narayanpur | 269.39 | [11 empty] | 1 | Inaugurated
43 |  | MS-112 | 10180310702 | Tirhut East | 2010-11 | वैशाली | देसरी | 2 | S.G.B.B.A.S. H/S, Bhatauliya | 269.39 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | L P Mandir on land Old Building to be Dismantle
44 |  | MS-112 | 10181203707 | Tirhut East | 2010-11 | वैशाली | सहदे बुज़ुर्ग | 3 | Gandhi H/S, Sahadai Buzurg | 269.39 | [11 empty] | 1 | Inaugurated
45 |  | MS-120 | 10040702905 | Tirhut East | 2010-11 | सीतामढी | रीगा | 1 | T.R.N.H.S, Sahbajpur Kharsan | 280.0925 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-2)
46 |  | MS-120 | 10040602001 | Tirhut East | 2010-11 | सीतामढी | परसौनी | 2 | Govt. Basic School, Raghopur Bhakhari | 280.0925 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-3)
47 |  | MS-120 | 10040505801 | Tirhut East | 2010-11 | सीतामढी | बेलसंड | 3 | Govt. Basic School, Machi Bhandari | 280.0925 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
48 |  | MS-121 | 10041603802 | Tirhut East | 2010-11 | सीतामढी | नानपुर | 1 | Govt. Basic School, Janipur | 278.6509 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-4)
49 |  | MS-121 | 10041900213 | Tirhut East | 2010-11 | सीतामढी | चोरौत | 2 | S.L.N.S H/S, Chorout | 278.6509 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-54)
50 |  | MS-121 | 10041303813 | Tirhut East | 2010-11 | सीतामढी | सुरसंड | 3 | Saryu H/S, Sursand | 278.6509 | 1 | [11 empty] | Land Dispute
51 |  | MS-122 | 10041405911 | Tirhut East | 2010-11 | सीतामढी | बाजपट्टी | 1 | S.R.P.N. H/S, Bajpatti | 283.4938 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-5)
52 |  | MS-122 | 10040900205 | Tirhut East | 2010-11 | सीतामढी | मेजरगंज | 2 | J.B. H/S, Majorganj | 283.4938 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-55)
53 |  | MS-122 | 10041205313 | Tirhut East | 2010-11 | सीतामढी | परिहार | 3 | S.G. H/S, Parihar | 283.4938 | 1 | [11 empty] | Local dispute
54 |  | MS-123 | 10022101702 | Tirhut West | 2010-11 | पूर्वी चंपारण | पिपराकोठी | 1 | Govt. Basic School, Piprakothi | 261.765 | [11 empty] | 1 | Inaugurated
55 |  | MS-123 |  | Tirhut West | 2010-11 | पूर्वी चंपारण | कोटवा | 2 | H/S, Machh-agargawa | 261.765 | [11 empty] | 1 | Inaugurated
56 |  | MS-124 | 10021503004 | Tirhut West | 2010-11 | पूर्वी चंपारण | मेहसी | 1 | High School, Mehsi | 268.515 | [11 empty] | 1 | Inaugurated 16.07.2016
57 |  | MS-124 | 10021202112 | Tirhut West | 2010-11 | पूर्वी चंपारण | केशरिया | 2 | High School, Kesariya | 268.515 | [11 empty] | 1 | Inaugurated 16.07.2016
58 |  | MS-125 | 10022702714 | Tirhut West | 2010-11 | पूर्वी चंपारण | तुरकौलिया | 1 | S.R.R. H/S, Turkaulia | 262.6233 | [10 empty] | 1
59 |  | MS-125 | 10022506202 | Tirhut West | 2010-11 | पूर्वी चंपारण | सुगौली | 2 | Nand High School, Sugauli | 262.6233 | [11 empty] | 1 | Inaugurated 16.07.2016
60 |  | MS-125 | 10020303404 | Tirhut West | 2010-11 | पूर्वी चंपारण | बंजरिया | 3 | H/S, Mokhlishpur | 262.6233 | [10 empty] | 1
61 |  | MS-126 | 10022302904 | Tirhut West | 2010-11 | पूर्वी चंपारण | रक्सौल | 1 | H/S, Purandara Bhelahi | 279.2697 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-56)
62 |  | MS-126 | 10022202003 | Tirhut West | 2010-11 | पूर्वी चंपारण | रामगढवा | 2 | Govt. Basic School, Siswaniya | 279.2697 | [11 empty] | 1 | Inaugurated 2017
63 |  | MS-126 |  | Tirhut West | 2010-11 | पूर्वी चंपारण | छौङादानो | 3 | H/S, Chhoradano | 279.2697 | [11 empty] | 1 | Inaugurated 16.07.2016
64 |  | MS-127 | 10020104102 | Tirhut West | 2010-11 | पूर्वी चंपारण | आदापुर | 1 | Govt. Basic School, Bhawanati | 288.5047 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-6)
65 |  | MS-127 | 10020902205 | Tirhut West | 2010-11 | पूर्वी चंपारण | घोङासहन | 2 | Govt. Basic School, Bhelwa Circle | 288.5047 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-7)
66 |  | MS-127 | 10020806802 | Tirhut West | 2010-11 | पूर्वी चंपारण | ढाका | 3 | H/S, Dhaka | 288.5047 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-8)
67 |  | MS-128 | 10022001106 | Tirhut West | 2010-11 | पूर्वी चंपारण | फेनहारा | 1 | H/S, Phenhara | 271.5133 | [10 empty] | 1
68 |  | MS-128 | 10020704603 | Tirhut West | 2010-11 | पूर्वी चंपारण | चिरैया | 2 | M.S. H/S, Chiraiya | 271.5133 | [10 empty] | 1
69 |  | MS-128 |  | Tirhut West | 2010-11 | पूर्वी चंपारण | पताहि | 3 | H/S, Patahi | 271.5133 | [10 empty] | 1
70 |  | MS-129 | 10021403202 | Tirhut West | 2010-11 | पूर्वी चंपारण | मधुबन | 1 | H/S, Madhuban | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
71 |  | MS-129 | 10022601505 | Tirhut West | 2010-11 | पूर्वी चंपारण | तेतरिया | 2 | H/S, Tetaria | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
72 |  | MS-129 |  | Tirhut West | 2010-11 | पूर्वी चंपारण | पकङीदयाल | 3 | H/S, Barkawan | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
73 |  | MS-130 |  | Tirhut West | 2010-11 | पूर्वी चंपारण | अरेराज | 1 | H/S, Areraj | 265.3 | [11 empty] | 1 | Inaugurated
74 |  | MS-130 | 10022400113 | Tirhut West | 2010-11 | पूर्वी चंपारण | संग्रामपुर | 2 | H/S, Sangrampur | 265.3 | [11 empty] | 1 | Inaugurated
75 |  | MS-131 | 10021000601 | Tirhut West | 2010-11 | पूर्वी चंपारण | हरसिद्धि | 1 | Govt. Basic School, Kritpur Mathiya | 270.425 | [11 empty] | 1 | Inaugurated 16.07.2016
76 |  | MS-131 | 10021705501 | Tirhut West | 2010-11 | पूर्वी चंपारण | पहाङपुर | 2 | Govt. Basic School, Baluahar Siddhi | 270.425 | [11 empty] | 1 | Inaugurated 2017
77 |  | MS-185 | 10010503103 | Tirhut West | 2010-11 | पश्चिम चम्पारण | बैरिया | 1 | H/S, Bathna |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
78 |  | MS-185 | 10011001619 | Tirhut West | 2010-11 | पश्चिम चम्पारण | ठकराहा | 2 | G.M. H/S, Thakaraha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
79 |  | MS-185 | 10011701605 | Tirhut West | 2010-11 | पश्चिम चम्पारण | भितहां | 3 | H/S. Ajaynagar Rerha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
80 |  | MS-186 | 10010203611 | Tirhut West | 2010-11 | पश्चिम चम्पारण | नौतन | 1 | Janta H/S, Telua |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
81 |  | MS-186 |  | Tirhut West | 2010-11 | पश्चिम चम्पारण | बेतिया | 2 | B.H.S.S, Bettiah |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
82 |  | MS-187 | 10010401102 | Tirhut West | 2010-11 | पश्चिम चम्पारण | योगापट्टी | 1 | Govt. Basic School, Balua | 69.8047 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-57)
83 |  | MS-187 |  | Tirhut West | 2010-11 | पश्चिम चम्पारण | चनपटिया | 2 | Govt. Basic School, Chaubetola | 69.8047 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-58)
84 |  | MS-187 | 10011305404 | Tirhut West | 2010-11 | पश्चिम चम्पारण | सिकटा | 3 | Janta H/S, Sikta | 69.8047 | [11 empty] | 1 | Inaugurated 2017 Bind up List - 81 (S.No.-59)
85 |  | MS-188 | 10011212006 | Tirhut West | 2010-11 | पश्चिम चम्पारण | रामनगर | 1 | H/S, Harinagar | 274.295 | [11 empty] | 1 | Inaugurated 16.07.2016
86 |  | MS-188 | 10010900605 | Tirhut West | 2010-11 | पश्चिम चम्पारण | लौरिया | 2 | A.H. H/S, Bagahi | 274.295 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
87 |  | MS-189 | 10011800409 | Tirhut West | 2010-11 | पश्चिम चम्पारण | पिपरासी | 1 | Govt. Basic School, Manjhariya | 290.425 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-9)
88 |  | MS-189 |  | Tirhut West | 2010-11 | पश्चिम चम्पारण | मधुबनी | 2 | M/S, Tamkuhwa | 290.425 | [10 empty] | 1 |  | plaster done, rest work in progress
89 |  | MS-190 | 10011402902 | Tirhut West | 2010-11 | पश्चिम चम्पारण | गौनाहा | 1 | Govt. Basic School, Bhithakha |  | 1 | [11 empty] | Bind up List - 81 (S.No.-10). Performance security returned.
90 |  | MS-190 |  | Tirhut West | 2010-11 | पश्चिम चम्पारण | मैनाटांड | 2 | R.S. H/S, Rampurwa |  | 1 | [11 empty] | Bind up List - 81 (S.No.-11). Performance security returned.
91 |  | MS-9 | 10130614201 | Darbhanga | 2009-10 | दरभंगा | बहादुरपुर | 1 | Govt. Basic School Ughara | 272.1833 | [11 empty] | 1 | Inaugurated
92 |  | MS-9 |  | Darbhanga | 2009-10 | दरभंगा | बहेरी | 2 | Govt. Basic School Machchhi | 272.1833 | [11 empty] | 1 | Inaugurated
93 |  | MS-9 |  | Darbhanga | 2009-10 | दरभंगा | दरभंगा | 3 | H/S,Atihar | 272.1833 | [11 empty] | 1 | Inaugurated
94 |  | MS-10 | 10050405416 | Darbhanga | 2009-10 | मधुबनी | बेनीपट्टी | 1 | Govt. Basic School Shahpur | 269.825 | [11 empty] | 1 | Inaugurated
95 |  | MS-10 |  | Darbhanga | 2009-10 | मधुबनी | अंधराठाढ़ी | 2 | H/S.Andhra Thari | 269.825 | [11 empty] | 1 | Inaugurated
96 |  | MS-11 | 10191907801 | Darbhanga | 2009-10 | समस्तीपुर | कलयानपुर | 1 | Govt. Basic School,Janardanpur | 263.31 | [11 empty] | 1 | Inaugurated
97 |  | MS-11 |  | Darbhanga | 2009-10 | समस्तीपुर | समस्तीपुर | 2 | Govt. Basic School,Chatauna | 263.31 | [11 empty] | 1 | Inaugurated
98 |  | MS-113 | 10050702404 | Darbhanga | 2010-11 | मधुबनी | बासोपट्टी | 1 | Govt. Basic School, Sukhasi | 285.2691 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-12)
99 |  | MS-113 | 10050505001 | Darbhanga | 2010-11 | मधुबनी | बिस्फी | 2 | Govt. Basic School, Simari | 285.2691 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-13)
100 |  | MS-114 | 10050702704 | Darbhanga | 2010-11 | मधुबनी | हरलाखी | 1 | Govt. Basic School, Hisar | 285.1985 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-14)
101 |  | MS-114 | 10051700101 | Darbhanga | 2010-11 | मधुबनी | मधवापुर | 2 | Govt. Basic School, Rema | 285.1985 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-15)
102 |  | MS-115 | 10050906816 | Darbhanga | 2010-11 | मधुबनी | झंझारपुर | 1 | Kejriwal H/S, Jhanjharpur | 278.0067 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
103 |  | MS-115 | 10051402715 | Darbhanga | 2010-11 | मधुबनी | लखनौर | 2 | High School, Lakhnaur | 278.0067 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
104 |  | MS-115 | 10051601720 | Darbhanga | 2010-11 | मधुबनी | मधेपुर | 3 | High School, Madhepur | 278.0067 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
105 |  | MS-116 | 10050206503 | Darbhanga | 2010-11 | मधुबनी | बाबूबरही | 1 | J.N. H/S, Babubarhi | 279.2203 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-60)
106 |  | MS-116 | 10051800504 | Darbhanga | 2010-11 | मधुबनी | पंडौल | 2 | Govt. Basic School, Maukarampur | 279.2203 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-61)
107 |  | MS-116 | 10052104001 | Darbhanga | 2010-11 | मधुबनी | राजनगर | 3 | Govt. Basic School, Nakati | 279.2203 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-62)
108 |  | MS-117 |  | Darbhanga | 2010-11 | मधुबनी | घोघरडीहा | 1 | High School, Devadh | 289.52 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-15). Inaugurated 16.07.2016.
109 |  | MS-117 | 10051500209 | Darbhanga | 2010-11 | मधुबनी | लौकही | 2 | High School, Laukhi | 289.52 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-63). Inaugurated 16.07.2016.
110 |  | MS-117 | 10051900707 | Darbhanga | 2010-11 | मधुबनी | फुलपरास | 3 | High School, Phulparas | 289.52 | [10 empty] | 1 |  | Inaugurated 16.07.2016
111 |  | MS-118 | 10050801304 | Darbhanga | 2010-11 | मधुबनी | जयनगर | 1 | High School, Jainagar | 285.0467 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-17)
112 |  | MS-118 |  | Darbhanga | 2010-11 | मधुबनी | कलुआही | 2 | High School, Narar | 285.0467 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-64)
113 |  | MS-118 | 10051101201 | Darbhanga | 2010-11 | मधुबनी | खजौली | 3 | High School, Khajauli | 285.0467 | [11 empty] | 1
114 |  | MS-119 | 10051200617 | Darbhanga | 2010-11 | मधुबनी | खुटौना | 1 | High School, Khutauna | 310.2473 | [11 empty] | 1 | Inaugurated 16.07.2016
115 |  | MS-119 | 10051301610 | Darbhanga | 2010-11 | मधुबनी | लदनिया | 2 | High School, Matha Ladania | 310.2473 | [11 empty] | 1 | Inaugurated 16.07.2016
116 |  | MS-196 | 10190503501 | Darbhanga | 2010-11 | समस्तीपुर | उजियारपुर | 1 | Govt. Basic School, Kariyara | 264.5567 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
117 |  | MS-196 | 10191804306 | Darbhanga | 2010-11 | समस्तीपुर | मोरवा | 2 | Govt. Basic School, Mariya | 264.5567 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
118 |  | MS-196 |  | Darbhanga | 2010-11 | समस्तीपुर | रोसरा | 3 | Govt. Basic School, Dharmpur | 264.5567 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
119 |  | MS-197 | 10191503203 | Darbhanga | 2010-11 | समस्तीपुर | दलसिंघसराय | 1 | Govt. Basic School, Salkhani | 263.865 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
120 |  | MS-197 | 10190604802 | Darbhanga | 2010-11 | समस्तीपुर | बिभुतिपुर | 2 | L.L. H/S, Sirsi | 263.865 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
121 |  | MS-198 | 10130903703 | Darbhanga | 2010-11 | दरभंगा | बेनीपुर | 1 | Jayanand H/S. Bahera | 257.498 | [11 empty] | 1 | Inaugurated 16.07.2016
122 |  | MS-198 |  | Darbhanga | 2010-11 | दरभंगा | किरतपुर | 2 | H/S, Rasiyari | 257.498 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available (required land 293'x250' avlaible land25'x15')
123 |  | MS-199 | 10131004002 | Darbhanga | 2010-11 | दरभंगा | घनश्यामपुर | 1 | Janta H/S, Shivnagar Gah | 276.465 | [11 empty] | 1 | Inaugurated
124 |  | MS-199 | 10131701502 | Darbhanga | 2010-11 | दरभंगा | गौरबौरम | 2 | H/S, Azi | 276.465 | [11 empty] | 1 | Inaugurated 16.07.2016
125 |  | MS-200 | 10130202905 | Darbhanga | 2010-11 | दरभंगा | केवटी | 1 | R.J. H/S, Keoti Baubari | 272.08 | [11 empty] | 1 | Bind up List - 81 (S.No.-18) Inaugurated 16.07.2016.
126 |  | MS-200 | 10130101902 | Darbhanga | 2010-11 | दरभंगा | जाले | 2 | Govt. Basic School, Daughara | 272.08 | [11 empty] | 1 | Inaugurated
127 |  | MS-201 | 10131403501 | Darbhanga | 2010-11 | दरभंगा | तारडीह | 1 | Govt. Basic School, Narayanpur | 272.815 | [11 empty] | 1 | Inaugurated 16.07.2016
128 |  | MS-201 | 10130803509 | Darbhanga | 2010-11 | दरभंगा | मनीगाछी | 2 | High School, Nehra | 272.815 | [11 empty] | 1 | Inaugurated 16.07.2016
129 |  | MS-202 | 10130404401 | Darbhanga | 2010-11 | दरभंगा | हायाघाट | 1 | Govt. Basic School, Sree rampur | 277.42 | [11 empty] | 1 | Inaugurated 16.07.2016
130 |  | MS-202 | 10130303701 | Darbhanga | 2010-11 | दरभंगा | सिंघवारा | 2 | Govt. Basic School, Haripur Ladaur | 277.42 | [11 empty] | 1 | Inaugurated
131 |  | MS-202 | 10131300801 | Darbhanga | 2010-11 | दरभंगा | हनुमाननगर | 3 | Govt. Basic School, Goraipatti | 277.42 | [11 empty] | 1 | Inaugurated
132 |  | MS-203 | 10131804005 | Darbhanga | 2010-11 | दरभंगा | कुशेश्वर स्थान पूर्वी | 1 | S.K. H/S, Kusheshwar Asthan |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
133 |  | MS-203 | 10131201603 | Darbhanga | 2010-11 | दरभंगा | कुशेश्वर स्थान | 2 | G.P. H/S, Bhahar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
134 |  | MS-203 | 10131101902 | Darbhanga | 2010-11 | दरभंगा | बिरौल | 3 | Onkar H/S, Supaul Bazar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
135 |  | MS-12 | 10280204803 | Patna East | 2009-10 | पटना | मसौढी | 1 | H/S.Masaurhi |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
136 |  | MS-12 |  | Patna East | 2009-10 | पटना | पुनपुन | 2 | H/S.Punpun |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
137 |  | MS-12 |  | Patna East | 2009-10 | पटना | पालीगंज | 3 | H/S Chandhosh |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
138 |  | MS-13 | 10270104102 | Patna East | 2009-10 | नालंदा | अस्था'वा | 1 | Govt. Basic School, Balwapur | 248.12 | [11 empty] | 1 | Inaugurated 16.07.2016
139 |  | MS-13 | 10271606202 | Patna East | 2009-10 | नालंदा | रहुई | 2 | H/S.Mauriyachak Supasan | 248.12 | [11 empty] | 1
140 |  | MS-13 |  | Patna East | 2009-10 | नालंदा | हिलसा | 3 | H/S.Hilsa | 248.12 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-19)
141 |  | MS-14 | 10290713202 | Patna East | 2009-10 | भोजपुर | पिरो | 1 | Govt. Basic School, Rajaiya | 249.9385 |  |  | 1 | 0 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-20)
142 |  | MS-14 |  | Patna East | 2009-10 | भोजपुर | तरारी | 2 | H/S.Barkagaon | 249.9385 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-21)
143 |  | MS-15 |  | Patna West | 2009-10 | रोहतास | सासाराम | 1 | H/S.Takia | 254.655 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
144 |  | MS-15 | 10320430401 | Patna West | 2009-10 | रोहतास | करहगर | 2 | Govt. Basic School, Sawan Bahar | 254.655 | [11 empty] | 1 | Inaugurated
145 | 1 | MS-108 | 10321500804 | Patna West | 2010-11 | बक्‍सर | ब्रहम्‍पुर | 1 | (+2) B.N. H/S, Brahampur | 264.1167 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-28)
146 | 2 | MS-108 | 10321100115 | Patna West | 2010-11 | बक्‍सर | सिमरी | 2 | (+2) H/S, Simri | 264.1167 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-29)
147 |  | MS-17 | 10321005702 | Patna West | 2009-10 | भभुआ कैमूर | मोहनियॉं | 1 | Govt. Basic School, Mohaniya | 266.0866 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-23)
148 |  | MS-17 | 10321702103 | Patna West | 2009-10 | भभुआ कैमूर | भभुआ | 2 | H/S.Akhlashpur | 266.0866 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-24)
149 |  | MS-17 | 10310707502 | Patna West | 2009-10 | भभुआ कैमूर | दुर्गावती | 3 | H/S.Kampura | 266.0866 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-25)
150 |  | MS-101 |  | Patna East | 2010-11 | पटना | मनेर | 1 | M.Y. H/S, Gorakhatola | 270.8633 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not Available Site changed proposal goes to BMSP
151 |  | MS-101 | 10280502011 | Patna East | 2010-11 | पटना | बिहटा | 2 | R.T.P. H/S, Bihta (Anandpur) | 270.8633 | [10 empty] | 1
152 |  | MS-101 | 10280403603 | Patna East | 2010-11 | पटना | बिक्रम | 3 | D.D.S. H/S, Morlawa | 270.8633 | [11 empty] | 1 | Inaugurated
153 |  | MS-102 | 10280803809 | Patna East | 2010-11 | पटना | दानापुर | 1 | R.G.S.S. School, khagaul | 272.9533 | [11 empty] | 1 | Inaugurated 2017
154 |  | MS-102 | 10280304704 | Patna East | 2010-11 | पटना | दुलिहन बाजार | 2 | Basidhar H/S, Bharatpur | 272.9533 | [11 empty] | 1 | Inaugurated
155 |  | MS-102 | 10280607904 | Patna East | 2010-11 | पटना | नौबतपुर | 3 | Govt. H/S, Amarpur (Chiraura) | 272.9533 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-26)
156 |  | MS-103 | 10281301505 | Patna East | 2010-11 | पटना | धनरूआ | 1 | H/S, Biroiyara | 266.355 | [10 empty] | 1 |  | Inaugurated 2017
157 |  | MS-103 | 10281600205 | Patna East | 2010-11 | पटना | खुसरुपुर | 2 | Mahadeo H/S, Khusrupur | 266.355 | [7 empty] | 1 |  |  |  |  | Inaugurated 2017. Bind up List - 81 (S.No.-65)
158 |  | MS-104 | 10281501303 | Patna East | 2010-11 | पटना | दनियावां | 1 | Rajkiyakrit H/S, Daniyawa | 265.115 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
159 |  | MS-104 | 10281406103 | Patna East | 2010-11 | पटना | फतुहॉ | 2 | A.N.S, H/S, Usfa | 265.115 | [10 empty] | 1 |  | Inaugurated 2017
160 |  | MS-105 | 10282100515 | Patna East | 2010-11 | पटना | बेल्‍छी | 1 | Govt. H/S, Saksohars | 267.5533 | [11 empty] | 1 | Inaugurated
161 |  | MS-105 |  | Patna East | 2010-11 | पटना | मोकामा | 2 | R.A. H/S, Mokama | 267.5533 | [11 empty] | 1 | Inaugurated
162 |  | MS-105 | 10282300103 | Patna East | 2010-11 | पटना | पण्‍डारक | 3 | P.B.M. H/S, Pandark | 267.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
163 |  | MS-106 |  | Patna East | 2010-11 | पटना | घोसवरी | 1 | Govt. H/S, Kurmichak | 268.99 | [10 empty] | 1
164 |  | MS-106 | 10281701505 | Patna East | 2010-11 | पटना | बख्तियारपुर | 2 | Govt. H/S, Sawani | 268.99 | [11 empty] | 1 | Inaugurated
165 |  | MS-106 | 10281800102 | Patna East | 2010-11 | पटना | बाढ | 3 | Govt. H/S, Badhna | 268.99 | [6 empty] | 0 |  |  |  | 1 |  | Bind up List - 81 (S.No.-27)
166 |  | MS-107 | 10302108901 | Patna West | 2010-11 | बक्‍सर | बक्‍सर | 1 | Govt. Basic School, Karhansi | 260.5633 | [11 empty] | 1 | Inaugurated 16.07.2016
167 |  | MS-107 |  | Patna West | 2010-11 | बक्‍सर | चौसा | 2 | Govt. Basic School, Saraiya | 260.5633 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | School not locate
168 |  | MS-107 | 10301500826 | Patna West | 2010-11 | बक्‍सर | डुमरॉंव | 3 | (+2) Raj H/S, Dumraon | 260.5633 | [11 empty] | 1 | Inaugurated 16.07.2016
169 | 3 | MS-108 | 10302201008 | Patna West | 2010-11 | बक्‍सर | केसठ | 3 | (+2) H/S, Kesath | 264.1167 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-30)
170 | 4 | MS-133 | 10230518301 | Bhagalpur | 2010-11 | बांका | रजौन | 1 | Govt. Basic School, Chilkawar | 268.9202 | [11 empty] | 1 | Inaugurated 16.07.2016 | Inaugurated 2017
171 | 5 | MS-133 | 10230910302 | Bhagalpur | 2010-11 | बांका | धोरैया | 2 | Tribhuwan Academy | 268.9202 | [11 empty] | 1 | Inaugurated 16.07.2016 | Inaugurated 2017
172 | 6 | MS-135 |  | Patna East | 2010-11 | भोजपुर | बरहारा | 1 | Govt. Basic School, Barhara | 261.4577 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started. School not locate
173 | 7 | MS-135 | 10290300122 | Patna East | 2010-11 | भोजपुर | बिहिया | 2 | (+2) H/S, Bihia | 261.4577 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-31)
174 |  | MS-136 | 10290404007 | Patna East | 2010-11 | भोजपुर | कोइलवर | 1 | M.B. H/S, Kulhariya | 260.46 | [10 empty] | 1 |  | Inaugurated 2017
175 |  | MS-136 | 10290503608 | Patna East | 2010-11 | भोजपुर | उदवंतनगर | 2 | H/S, Udwant Nagar | 260.46 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land dispute
176 |  | MS-136 |  | Patna East | 2010-11 | भोजपुर | चरपोखरी | 3 | Macha H/S, Barami | 260.46 | [10 empty] | 1 |  | Inaugurated 2017 Bind up List - 81 (S.No.-32).
177 |  | MS-137 | 10290805019 | Patna East | 2010-11 | भोजपुर | साहार | 1 | H/S, Sahar, Bhojpur | 254.915 | [11 empty] | 1 | Inaugurated
178 |  | MS-137 | 10291204615 | Patna East | 2010-11 | भोजपुर | सन्देश | 2 | H/S, Sandesh | 254.915 | [11 empty] | 1 | Inaugurated
179 |  | MS-138 | 10291307710 | Patna East | 2010-11 | भोजपुर | गरहनि | 1 | R.D. H/S, Garhani | 261.065 | [11 empty] | 1 | Inaugurated
180 |  | MS-138 | 10291400102 | Patna East | 2010-11 | भोजपुर | अगिआव | 2 | Govt. Basic School, Agiaon | 261.065 | [11 empty] | 1 | Inaugurated 16.07.2016
181 |  | MS-139 | 10271905903 | Patna East | 2010-11 | नालंदा | सिलाव | 1 | Gandhi h.s.Silaw |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started, Retender
182 |  | MS-139 | 10271704708 | Patna East | 2010-11 | नालंदा | राजगीर | 2 | R.D.H.S. Rajgir |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started, Retender
183 |  | MS-140 | 10271200102 | Patna East | 2010-11 | नालंदा | कतरीसराय | 1 | H.S. Badi | 251.6 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
184 |  | MS-140 | 10270700103 | Patna East | 2010-11 | नालंदा | गिरियक | 2 | H/S, Giriak Adampur | 251.6 | [11 empty] | 1 | Inaugurated
185 |  | MS-141 | 10271303506 | Patna East | 2010-11 | नालंदा | नगरनौसा | 1 | H.S. Nagarnousa | 257.13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land problem water logged 8'-0" deep land
186 |  | MS-141 | 10270503401 | Patna East | 2010-11 | नालंदा | चण्डी | 2 | Govt. Basic School, Kaurnawa | 257.13 | [11 empty] | 1 | Inaugurated
187 |  | MS-142 | 10272000603 | Patna East | 2010-11 | नालंदा | थरथरी | 1 | H/S, Bhathar | 248.765 | [11 empty] | 1 | handover
188 |  | MS-142 | 10271406201 | Patna East | 2010-11 | नालंदा | नुरसराय | 2 | H/S, Noorsarai | 248.765 | [11 empty] | 1 | handover
189 |  | MS-143 | 10271010601 | Patna East | 2010-11 | नालंदा | ईस्लामपुर | 1 | Govt. Basic School, Sanda | 249.4 | [11 empty] | 1 | Inaugurated
190 |  | MS-143 | 10270201009 | Patna East | 2010-11 | नालंदा | बिन्द | 2 | H/S, Eksara | 249.4 | [11 empty] | 1 | Inaugurated
191 |  | MS-143 | 10270602009 | Patna East | 2010-11 | नालंदा | ए'कगरसराय | 3 | S.S. Academy, Ekangarsarai | 249.4 | [11 empty] | 1 | Inaugurated
192 |  | MS-144 | 10270802703 | Patna East | 2010-11 | नालंदा | हरनौत | 1 | Govt. Basic School, Gokulpur Math | 257.7167 | [11 empty] | 1 | Inaugurated 16.07.2016
193 |  | MS-144 | 10271802614 | Patna East | 2010-11 | नालंदा | सरमेरा | 2 | H/S, Sarmera | 257.7167 | [11 empty] | 1 | Inaugurated
194 |  | MS-144 | 10270400409 | Patna East | 2010-11 | नालंदा | बिन्द | 3 | H/S, Bind | 257.7167 | [11 empty] | 1 | Inaugurated
195 |  | MS-145 | 10321500804 | Patna West | 2010-11 | रोहतास | अकोढ़ीगोला | 1 | H.S. Prem Nagar, Akodhigola | 254.4719 | [11 empty] | 1 | Inaugurated
196 |  | MS-145 | 10321100115 | Patna West | 2010-11 | रोहतास | डिहरी | 2 | H.S. Dihri-on-sone, Dehri | 254.4719 | [11 empty] | 1 | Inaugurated
197 |  | MS-146 | 10321005702 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 1 | Govt. Basic School, Kabhai | 269.2706 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-33)
198 |  | MS-146 | 10321702103 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 2 | R.R. H.S. Suryappura | 269.2706 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-66)
199 |  | MS-146 |  | Patna West | 2010-11 | रोहतास | दावत | 3 | R.P.S. H.S.Kabai, Dawath | 269.2706 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-67)
200 |  | MS-147 | 10321826307 | Patna West | 2010-11 | रोहतास | कोचस | 1 | H.S. Kochas | 269.1185 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-68)
201 |  | MS-147 | 10321201703 | Patna West | 2010-11 | रोहतास | दिनारा | 2 | M.H.S. Basdihan, Dinara | 269.1185 | [10 empty] | 1
202 |  | MS-148 | 10320313501 | Patna West | 2010-11 | रोहतास | नोखा | 1 | H.S. Garh Nokha, Nokha | 277.4303 | [11 empty] | 1 | Bind up List - 81 (S.No.-69) Inaugurated 16.07.2016
203 |  | MS-148 | 10320908203 | Patna West | 2010-11 | रोहतास | काराकाट | 2 | S.S.D.H.S. Amauna, Karakat | 277.4303 | [11 empty] | 1 | Bind up List - 81 (S.No.-34) Inaugurated 16.07.2016.
204 |  | MS-148 | 10320800105 | Patna West | 2010-11 | रोहतास | नासरीगंज | 3 | Basant H.S. Itimiha Karma | 277.4303 | [11 empty] | 1 | Inaugurated 16.07.2016
205 |  | MS-149 | 10320515210 | Patna West | 2010-11 | रोहतास | चेनारी | 1 | R.D.G.H.S. Chenari | 261.7963 | [11 empty] | 1 | Inaugurated 16.07.2016
206 |  | MS-149 | 10320600605 | Patna West | 2010-11 | रोहतास | शिवसागर | 2 | S.D.H.S. Sheo Sagar | 261.7963 | [11 empty] | 1 | Inaugurated 16.07.2016
207 |  | MS-150 | 10320207403 | Patna West | 2010-11 | रोहतास | नौहट्टा | 1 | H.S.Boulian | 266.18 | [11 empty] | 1 | Inaugurated
208 |  | MS-151 | 10321415907 | Patna West | 2010-11 | रोहतास | तिलौथु | 1 | H.S.Tilauthu | 251.97 | [11 empty] | 1 | Inaugurated
209 | 8 | MS-16 | 10301800118 | Patna West | 2009-10 | बक्‍सर | राजपुर | 1 | H/S.Rajpur | 279.43 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-22)
210 | 9 | MS-16 |  | Patna West | 2009-10 | बक्‍सर | इटाढी | 2 | Govt. Basic School, Unwas | 279.43 | [10 empty] | 1
211 | 10 | MS-166 | 10090408903 | Purnea | 2010-11 | पूर्णिया | पूर्णिया पूर्व | 1 | Govt. Basic School, Chadirjiganj | 279.8518 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-71)
212 |  | MS-36 | 10090607701 | Purnea | 2009-10 | अररिया | रानीगंज | 1 | H./S.Raniganj | 265.13 | [11 empty] | 1 | Inaugurated 16.07.2016
213 |  | MS-36 | 10090908601 | Purnea | 2009-10 | अररिया | फारबिसगंज | 2 | Govt. Basic School Haripur | 265.13 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-70)
214 |  | MS-36 |  | Purnea | 2009-10 | अररिया | भरगामा | 3 | H/S.Bhargama | 265.13 | [11 empty] | 1 | Inaugurated 16.07.2016
215 |  | MS-37 | 10100404702 | Purnea | 2009-10 | कटिहार | कोढा | 1 | Govt. Basic School, Gorawari | 261.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land litigation . Final bill submitted (Group No.: 37-1,37-2 &37-3)
216 |  | MS-37 |  | Purnea | 2009-10 | कटिहार | कटिहार | 2 | P.T.T.C Musapur | 261.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land litigation
217 |  | MS-37 | 10101600107 | Purnea | 2009-10 | कटिहार | मनिहारी | 3 | H/S.Nawabganj | 261.1 | [11 empty] | 1 | Inaugurated 16.07.2016
218 |  | MS-38 | 10082500908 | Purnea | 2009-10 | किशनगंज | दिघलबैंक | 1 | H/S. Tulsiya | 268.65 | [11 empty] | 1 | Inaugurated
219 |  | MS-38 |  | Purnea | 2009-10 | किशनगंज | ठाकुरगंज | 2 | H/S. Thakurganj | 268.65 | [11 empty] | 1 | Inaugurated
220 | 11 | MS-166 | 10090607701 | Purnea | 2010-11 | पूर्णिया | कृत्यानन्द नगर | 2 | Govt. Basic School, Kalyanpur | 279.8518 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-72)
221 | 12 | MS-166 | 10090908601 | Purnea | 2010-11 | पूर्णिया | कसबा | 3 | Govt. Basic School, Sabdalpur | 279.8518 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-73)
222 | 13 | MS-169 | 10091000602 | Purnea | 2010-11 | पूर्णिया | भवानीपुर | 1 | Govt. Basic School, Barhari | 287.8399 | [11 empty] | 1 | Inaugurated 16.07.2016
223 |  | MS-167 | 10091200103 | Purnea | 2010-11 | पूर्णिया | जलालगढ | 1 | N.D. Rungta H/S, Jalalgarh | 265.5533 | [11 empty] | 1 | Inaugurated | Inaugurated 2017
224 |  | MS-167 | 10091300701 | Purnea | 2010-11 | पूर्णिया | श्रीनगर | 2 | Govt. Basic School, Srinagar | 265.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
225 |  | MS-167 | 10091400106 | Purnea | 2010-11 | पूर्णिया | डगरुआ | 3 | H/S, Soura | 265.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
226 |  | MS-168 | 10090200104 | Purnea | 2010-11 | पूर्णिया | बायसी | 1 | H/S, Baisi | 277.9267 | [11 empty] | 1 | Inaugurated 16.07.2016
227 |  | MS-168 | 10090100104 | Purnea | 2010-11 | पूर्णिया | वैसा | 2 | T.N.H/S, Piyaji | 277.9267 | [11 empty] | 1 | Inaugurated
228 | 14 | MS-169 | 10090806502 | Purnea | 2010-11 | पूर्णिया | रूपौली | 2 | Govt. Basic School, Sapaha | 287.8399 | [11 empty] | 1 | Inaugurated 16.07.2016
229 | 15 | MS-35 | 10091102005 | Purnea | 2009-10 | पूर्णिया | धमदाहा | 1 | Govt. Basic School Purandaha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
230 |  | MS-170 | 10100700407 | Purnea | 2010-11 | कटिहार | समेली | 1 | D.G. H/S, Krishna Ngr | 266.0706 | [11 empty] | 1 | Inaugurated 16.07.2016
231 |  | MS-170 | 10101200106 | Purnea | 2010-11 | कटिहार | आजमनगर | 2 | R.K. H/S, Azam Ngr | 266.0706 | 1 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | LAND PROBLEM. (villagers claiming the land as raiyati after layout)
232 |  | MS-171 | 10100802901 | Purnea | 2010-11 | कटिहार | फलका | 1 | Govt. Basic School, Mangha | 261.711 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-74)
233 |  | MS-171 | 10100500118 | Purnea | 2010-11 | कटिहार | कुर्सेला | 2 | A.P. H/S Ayodhyaganj | 261.711 | [11 empty] | 1 | Inaugurated 16.07.2016
234 |  | MS-172 | 10100200102 | Purnea | 2010-11 | कटिहार | डंडखोरा | 1 | SadaNand H/S, Dumaria |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | Retender
235 |  | MS-7 | 10220214501 | Bhagalpur | 2009-10 | भागलपुर | सन्‍हौला | 1 | Govt. Basic School Bhuriya | 251.0533 | [11 empty] | 1 | Inaugurated
236 |  | MS-7 |  | Bhagalpur | 2009-10 | भागलपुर | कहलगांव | 2 | Govt. Basic School Shobhnathpur | 251.0533 | [11 empty] | 1 | Inaugurated
237 |  | MS-7 |  | Bhagalpur | 2009-10 | भागलपुर | पिरपैती | 3 | Govt. Basic School Panchrukhi | 251.0533 | [11 empty] | 1 | Inaugurated
238 |  | MS-8 | 10230108509 | Bhagalpur | 2009-10 | बांका | कटोरिया | 1 | Govt. Basic School Karjhausa | 245.86 | [11 empty] | 1 | Inaugurated
239 |  | MS-8 |  | Bhagalpur | 2009-10 | बांका | बौंसी | 2 | H/S.Maniyarpur | 245.86 | [11 empty] | 1 | Inaugurated
240 | 16 | MS-35 | 10090502903 | Purnea | 2009-10 | पूर्णिया | बरहरा कोठी | 2 | Govt. Basic School Diwrawanar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started, aggrement not done
241 | 17 | MS-35 | 10090706203 | Purnea | 2009-10 | पूर्णिया | बनमनखी | 3 | Govt. Basic School Dheema |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started, aggrement not done
242 |  | MS-204 |  | Bhagalpur | 2010-11 | भागलपुर | सबौर | 1 | H/S, Parsadih Simri | 255.71 | [11 empty] | 1 | Inaugurated 16.07.2016
243 |  | MS-204 | 10220301805 | Bhagalpur | 2010-11 | भागलपुर | जगदीशपुर | 2 | Loknath H/S, Jagdishpur | 255.71 |  |  |  | . | [7 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-75)
244 |  | MS-204 | 10222300701 | Bhagalpur | 2010-11 | भागलपुर | नाथनगर | 3 | H/S, Shapur | 255.71 | [11 empty] | 1 | Inaugurated 2017
245 |  | MS-205 | 10221602102 | Bhagalpur | 2010-11 | भागलपुर | गोराडीह | 1 | H/S, Jamin Murhan Hat | 267.6047 | [11 empty] | 1 | Inaugurated 2017. handover
246 |  | MS-205 | 10222704602 | Bhagalpur | 2010-11 | भागलपुर | शाहकुण्‍ड | 2 | Govt. Basic School, Hajipur | 267.6047 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-35)
247 |  | MS-205 |  | Bhagalpur | 2010-11 | भागलपुर | सुलतानगंज | 3 | H/S, Karharia | 267.6047 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-76).
248 |  | MS-206 | 10221800308 | Bhagalpur | 2010-11 | भागलपुर | बिहपुर | 1 | M.S. H/S, Bihpur | 257.335 | [11 empty] | 1 | Inaugurated
249 |  | MS-206 | 10222201802 | Bhagalpur | 2010-11 | भागलपुर | खारीक | 2 | Govt. Basic School, Telghi | 257.335 | [11 empty] | 1 | Inaugurated
250 |  | MS-207 | 10222105601 | Bhagalpur | 2010-11 | भागलपुर | नवगछिया | 1 | H/S, Sahu Parbatta | 263.845 | [11 empty] | 1 | Inaugurated 16.07.2016
251 |  | MS-207 | 10221204301 | Bhagalpur | 2010-11 | भागलपुर | गोपालपुर | 2 | Govt. Basic School, Tintanga | 263.845 | [11 empty] | 1 | Inaugurated 16.07.2016
252 |  | MS-24 | 10352200108 | Magadh | 2009-10 | गया | फतेहपुर | 1 | H/S.Fatehpur | 261.2343 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-77)
253 |  | MS-24 | 10352100108 | Magadh | 2009-10 | गया | वजीरगन्ज | 2 | H/S.Wazirgznj | 261.2343 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-36)
254 |  | MS-24 |  | Magadh | 2009-10 | गया | शेरघाटी | 3 | P.T.T.C. Sherghati | 261.2343 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Land not given by H.M.
255 |  | MS-25 | 10341306307 | Magadh | 2009-10 | औरंगाबाद | मदनपुर | 1 | H/S.Beri | 260.8732 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-37)
256 |  | MS-25 |  | Magadh | 2009-10 | औरंगाबाद | नबीनगर | 2 | H/S.Nabinagar | 260.8732 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Not Started,
257 |  | MS-25 | 10341006602 | Magadh | 2009-10 | औरंगाबाद | कुटुम्बा | 3 | Govt. Basic School, Rampur Parsa | 260.8732 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-38)
258 |  | MS-26 |  | Magadh | 2009-10 | जहानाबाद | मखदुमपुर | 1 | Govt. Basic School, Meera Bigha | 245.2 | [10 empty] | 1 |  | plaseter going on
259 |  | MS-26 |  | Magadh | 2009-10 | जहानाबाद | हुलासगंज | 2 | Govt. Basic School, Dogra | 245.2 | [10 empty] | 1 |  | plaster done, rest work in progress
260 |  | MS-27 | 10380606701 | Magadh | 2009-10 | अरवल | करपी | 1 | Govt. Basic School, Pariyahi Bazar | 252.3738 | [10 empty] | 1 |  | Plaster going on
261 |  | MS-27 |  | Magadh | 2009-10 | अरवल | कलेर | 2 | H/S.Kaler | 252.3738 | [10 empty] | 1
262 |  | MS-28 |  | Magadh | 2009-10 | नवादा | सिरदला | 1 | H/S.Sirdala | 245.2067 | [10 empty] | 1 |  | Plaster going on
263 |  | MS-28 |  | Magadh | 2009-10 | नवादा | रजौली | 2 | H/S.Chiraita | 245.2067 | [10 empty] | 1 |  | Plaster going on
264 |  | MS-28 | 10360302401 | Magadh | 2009-10 | नवादा | हिसुआ | 3 | Govt.Basic School Wagodar | 245.2067 | [10 empty] | 1 |  | Plaster going on
265 |  | MS-152 | 10360500301 | Magadh | 2010-11 | अरवल | कुर्था | 1 | H/S, Kurtha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
266 |  | MS-152 | 10361201613 | Magadh | 2010-11 | अरवल | सोनभद्र बंशी सुर्यापूर | 2 | H/S, Khatangi |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
267 |  | MS-153 | 10360802801 | Magadh | 2010-11 | गया | मानपुर | 1 | H.S.Rasalpur | 245.9767 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-39)
268 |  | MS-153 | 10361400502 | Magadh | 2010-11 | गया | बोधगया | 2 | H.S. Bodhgaya | 245.9767 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-78)
269 |  | MS-153 | 10360400504 | Magadh | 2010-11 | गया | बेलागन्ज | 3 | A.H.S. Belaganj | 245.9767 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-40)
270 |  | MS-154 | 10360200108 | Magadh | 2010-11 | गया | टिकारी | 1 | Govt. Basic School, Bhawanpur | 259.0612 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-41)
271 |  | MS-154 | 10361002409 | Magadh | 2010-11 | गया | कोन्च | 2 | G.H.S. Konch | 259.0612 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-42)
272 |  | MS-154 | 10360705810 | Magadh | 2010-11 | गया | परैया | 3 | A.H.S. Paraiya | 259.0612 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-43)
273 |  | MS-155 | 10360109201 | Magadh | 2010-11 | गया | टनकुप्पा | 1 | Govt. Basic School, Makhdumpur |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | Retender
274 |  | MS-155 | 10360605308 | Magadh | 2010-11 | गया | गुरारु | 2 | B.S.H.S. Esmailpur |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
275 |  | MS-156 |  | Magadh | 2010-11 | गया | डॊभी | 1 | Govt. Basic School, Bajaura | 263.173 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-44)
276 |  | MS-156 | 10352300106 | Magadh | 2010-11 | गया | मोहनपुर | 2 | H.S.Mohanpur | 263.173 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-45)
277 |  | MS-156 | 10352405201 | Magadh | 2010-11 | गया | बाराचट्टी | 3 | Govt. Basic School, Pataluka | 263.173 | 1 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | Not Started,
278 |  | MS-157 | 10351503501 | Magadh | 2010-11 | गया | ईमामगन्ज | 1 | Govt. Basic School, Wara |  | 1 | 0 | 0 |  |  |  |  | 0
279 |  | MS-157 | 10351600205 | Magadh | 2010-11 | गया | डुमरीया | 2 | J.H.S. Dumariya |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 |  | MS-158 | 10351300104 | Magadh | 2010-11 | गया | आमस | 1 | H.S. Amas | 262.4687 | [6 empty] | 1 | [5 empty] | Bind up List - 81 (S.No.-46)
281 |  | MS-158 |  | Magadh | 2010-11 | गया | गुरुआ | 2 | H.S. Bharsanthu (Bharaundha) | 262.4687 |  |  |  | 1 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-47)
282 |  | MS-158 | 10350602501 | Magadh | 2010-11 | गया | मोहडा | 3 | Govt. Basic School, Jatian | 262.4687 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Start. (Land given by H.M. Dated - 15.06.15)
283 |  | MS-159 | 10350702101 | Magadh | 2010-11 | गया | अतरी | 1 | H.S.Tetua | 246.16 | [10 empty] | 1
284 |  | MS-159 |  | Magadh | 2010-11 | गया | बथानी | 2 | Govt. Basic School, Rahui | 246.16 | [10 empty] | 1 |  | Inaugurated 2017
285 |  | MS-159 | 10350400106 | Magadh | 2010-11 | गया | खिजरसराय | 3 | H.S. Khijarsarai | 246.16 | [10 empty] | 1
286 |  | MS-160 | 10350900127 | Magadh | 2010-11 | गया | Chandouti | 1 | H.S. Chandaouti | 245.61 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-79)
287 |  | MS-161 | 10330202008 | Magadh | 2010-11 | जहानाबाद | घोसी | 1 | H.S. Ghoshi | 249.55 | [11 empty] | 1 | Inaugurated 2017
288 |  | MS-161 |  | Magadh | 2010-11 | जहानाबाद | जहानाबाद | 2 | H.S.Pandooe | 249.55 | [11 empty] | 1 | Inaugurated 2017
289 |  | MS-162 | 10331200103 | Magadh | 2010-11 | जहानाबाद | मोदनगंज | 1 | H.S. Okari, Modanganj | 249.55 | [11 empty] | 1 | Inaugurated
290 |  | MS-162 | 10330908304 | Magadh | 2010-11 | जहानाबाद | रातनीफरीदपुर | 2 | H.S. Sarta | 249.55 | [11 empty] | 1 | Inaugurated
291 |  | MS-177 | 10360500301 | Magadh | 2010-11 | नवादा | कौवाकोल | 1 | Govt. Basic School, Baraun Bajitpur | 245.0467 | [10 empty] | 1
292 |  | MS-177 | 10361201613 | Magadh | 2010-11 | नवादा | रोह | 2 | Inter School, Roh | 245.0467 | [10 empty] | 1 |  | plaster, flooring going on
293 |  | MS-177 | 10360802801 | Magadh | 2010-11 | नवादा | नारदीगंज | 3 | Govt. Basic School, Nadariganj | 245.0467 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
294 |  | MS-178 | 10361400502 | Magadh | 2010-11 | नवादा | वारिसलिगंज | 1 | Govt. Basic School, Dariyapur | 247.0759 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
295 |  | MS-178 | 10360400504 | Magadh | 2010-11 | नवादा | काशीचक | 2 | Inter School, Chandinawa | 247.0759 | [11 empty] | 1 | Inaugurated 2017
296 |  | MS-179 | 10360200108 | Magadh | 2010-11 | नवादा | गोविन्‍दपुर | 1 | Inter School, Govindpur | 250.4326 | [11 empty] | 1 | Inaugurated 2017
297 |  | MS-179 | 10361002409 | Magadh | 2010-11 | नवादा | पकरीबरावॉं | 2 | Inter School, Pakribarawan | 250.4326 | [11 empty] | 1 | Inaugurated 2017
298 |  | MS-180 | 10360705810 | Magadh | 2010-11 | नवादा | नरहट | 1 | Inter School, Narhat | 262.1334 | [11 empty] | 1 | Inaugurated 16.07.2016
299 |  | MS-180 | 10360109201 | Magadh | 2010-11 | नवादा | अकबरपुर | 2 | Govt. Basic School, Gopalpur | 262.1334 | [11 empty] | 1 | Inaugurated 16.07.2016
300 |  | MS-181 | 10360605308 | Magadh | 2010-11 | नवादा | मेसकौर | 1 | Inter School, Meskaur | 237.81 |  |  | 1 | 0 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-48)
301 |  | MS-182 | 10340307501 | Magadh | 2010-11 | औरंगाबाद | औरंगाबाद | 1 | Govt. M/S, Babhandi | 257.395 | [11 empty] | 1 | Inaugurated 16.07.2016
302 |  | MS-182 | 10341410705 | Magadh | 2010-11 | औरंगाबाद | बारुन | 2 | R.D.B. H/S, Sunderganj | 257.395 | [11 empty] | 1 | Inaugurated 16.07.2016
303 |  | MS-183 | 10341102404 | Magadh | 2010-11 | औरंगाबाद | देव | 1 | Govt. Basic School, Vishnupur | 257.4903 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-49)
304 |  | MS-183 | 10340600110 | Magadh | 2010-11 | औरंगाबाद | रफीगंज | 2 | R.B.R. H/S, Rafiganj | 257.4903 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
305 |  | MS-184 | 10341206202 | Magadh | 2010-11 | औरंगाबाद | हसपुरा | 1 | Govt. Basic School, Dindir | 254.09 | [11 empty] | 1 | Inaugurated 2017. Handover
306 |  | MS-18 | 10240804601 | Munger | 2009-10 | मुंगेर | धरहरा | 1 | Govt. Basic School, Ghatwari | 257.0628 | [10 empty] | 1
307 |  | MS-18 | 10240507001 | Munger | 2009-10 | मुंगेर | हवेली खड़गपुर | 2 | Govt. Basic School, Khand Bihari | 257.0628 | [10 empty] | 1
308 |  | MS-19 | 10371500107 | Munger | 2009-10 | जमुई | चकाई | 1 | H/S.Chakai | 241.98 | [11 empty] | 1
309 |  | MS-19 | 10371301901 | Munger | 2009-10 | जमुई | खैरा | 2 | Govt. Basic School, Dawilgadh | 241.98 | [11 empty] | 1 | Inaugurated 2017
310 |  | MS-19 | 10371708101 | Munger | 2009-10 | जमुई | सोनो | 3 | M/S Batiya | 241.98 | [11 empty] | 1 | Inaugurated 2017
311 |  | MS-20 | 10252502301 | Munger | 2009-10 | लखीसराय | सुर्यगढ़ा | 1 | Govt. Basic School, Kiranpur | 253.495 | [11 empty] | 1 | Inaugurated 2017
312 |  | MS-20 | 10252301808 | Munger | 2009-10 | लखीसराय | हलसी | 2 | H/S. Halsi | 253.495 | [11 empty] | 1
313 |  | MS-21 | 10262904103 | Munger | 2009-10 | शेखपुरा | बरबीघा | 1 | Govt. Basic School Sarba | 240.39 | [11 empty] | 1 | Inaugurated 16.07.2016
314 |  | MS-21 | 10262700701 | Munger | 2009-10 | शेखपुरा | शेखपुरा | 2 | M/S. Sheikhpura | 240.39 | [11 empty] | 1 | Inaugurated 16.07.2016
315 |  | MS-22 | 10372601701 | Munger | 2009-10 | खगड़िया | खगड़िया | 1 | Govt. Basic School ,Durgapur | 270.23 | [11 empty] | 1 | Inaugurated 16.07.2016
316 |  | MS-22 | 10371800109 | Munger | 2009-10 | खगड़िया | गोगरी | 2 | Govt. Basic School ,Basua | 270.23 | [11 empty] | 1 | Inaugurated 16.07.2016
317 |  | MS-23 | 10201001604 | Munger | 2009-10 | बेगूसराय | बेगूसराय | 1 | Govt. Basic School , Ulao | 252.9667 | [11 empty] | 1 | Inaugurated
318 |  | MS-23 | 10201900105 | Munger | 2009-10 | बेगूसराय | गढ़पुरा | 2 | H/S.Mortar | 252.9667 | [11 empty] | 1 | Inaugurated
319 |  | MS-23 | 10201700105 | Munger | 2009-10 | बेगूसराय | नावकोठी | 3 | H/S Samsa | 252.9667 | [11 empty] | 1 | Inaugurated
320 |  | MS-132 | 10261600109 | Munger | 2010-11 | शेखपुरा | चेवाड़ा | 1 | H/S, Chewara | 241.86 | [11 empty] | 1 | Inaugurated
321 |  | MS-134 | 10201601902 | Munger | 2010-11 | बेगूसराय | बलिया | 1 | Govt. H/S, Sadanandpur | 264.955 | [11 empty] | 1 | Inaugurated 2017
322 |  | MS-134 | 10201203301 | Munger | 2010-11 | बेगूसराय | तेघड़ा | 2 | Govt. Basic School, Bajatpur | 264.955 | [11 empty] | 1 | Inaugurated 2017
323 |  | MS-173 | 10371000108 | Munger | 2010-11 | जमुई | जमुई | 1 | Janta H/S, Sataya | 233.6767 | [11 empty] | 1 | Inaugurated 16.07.2016
324 |  | MS-173 | 10371100104 | Munger | 2010-11 | जमुई | सिकन्‍दरा | 2 | J.S.P.S. H/S. Lachhuar | 233.6767 | [11 empty] | 1 | Inaugurated
325 |  | MS-173 | 10371200203 | Munger | 2010-11 | जमुई | इस्लामनगर अलीगंज | 3 | M.R.P. H/S, Tajpur | 233.6767 | [11 empty] | 1 | Inaugurated 16.07.2016
326 |  | MS-174 | 10370902008 | Munger | 2010-11 | जमुई | बरहट | 1 | Govt. Basic School, Barhat | 238.24 | [11 empty] | 1 | Inaugurated 16.07.2016
327 |  | MS-174 | 10372601701 | Munger | 2010-11 | जमुई | लक्ष्‍मीपुर | 2 | Govt. Basic School, Kajinhara | 238.24 | [11 empty] | 1 | Inaugurated 16.07.2016
328 |  | MS-175 | 10371800109 | Munger | 2010-11 | जमुई | गिद्धौर | 1 | M.C.Vidya Mandir, Gidhour | 227.535 | [11 empty] | 1 | Inaugurated 16.07.2016
329 |  | MS-175 | 10371900109 | Munger | 2010-11 | जमुई | झाझा | 2 | M.G.S. H/S, Jhajha | 227.535 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No Land. Drop
330 |  | MS-176 | 10210500118 | Munger | 2010-11 | खगड़िया | बेलदौर | 1 | Gandhi H/S, Beldaur | 270.2833 | [10 empty] | 1
331 |  | MS-176 |  | Munger | 2010-11 | खगड़िया | मानसी | 2 | Gandhi H/S, Mansi | 270.2833 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | No Land. Drop
332 |  | MS-176 | 10210402102 | Munger | 2010-11 | खगड़िया | चौथम | 3 | Brahma H/S, Pipra | 270.2833 | [10 empty] | 1
333 |  | MS-208 | 10252601404 | Munger | 2010-11 | लखीसराय | रामगढ़ चौक | 1 | Govt. Basic School, Nandnama | 257.8893 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-80)
334 |  | MS-208 |  | Munger | 2010-11 | लखीसराय | चानन | 2 | R.S. +2 H.S., Mananpur | 257.8893 | [11 empty] | 1 | Inaugurated 2017. Bind up List - 81 (S.No.-81)
335 |  | MS-209 | 10252400214 | Munger | 2010-11 | लखीसराय | पिपरिया | 1 | M.R.M.P. +2 H.S., Ramchandrapur | 260.2802 | [11 empty] | 1 | Inaugurated 2017
336 |  | MS-209 |  | Munger | 2010-11 | लखीसराय | बड़हिया | 2 | Govt. Basic School, Bispur | 260.2802 | [11 empty] | 1 | Inaugurated 2017
337 |  | MS-4 | 10171203301 | Saran | 2009-10 | सारण | मांझी | 1 | M/S. Tajpur | 259.8067 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-50)
338 |  | MS-4 |  | Saran | 2009-10 | सारण | गरखा | 2 | H/S. Rampur Birbhan | 259.8067 | [11 empty] | 1 | Inaugurated
339 |  | MS-4 | 10170402201 | Saran | 2009-10 | सारण | दरियापुर | 3 | Govt. Basic School Bhagwanpur | 259.8067 | [11 empty] | 1 | Inaugurated
340 |  | MS-5 |  | Saran | 2009-10 | सिवान | पचरुखी | 1 | H/S.Pachrukhi | 264.9533 | [11 empty] | 1 | Inaugurated
341 |  | MS-5 | 10160110002 | Saran | 2009-10 | सिवान | आन्दर | 2 | Govt. Basic School Jayjor | 264.9533 | [11 empty] | 1 | Inaugurated
342 |  | MS-5 | 10161404801 | Saran | 2009-10 | सिवान | रघुनाथपुर | 3 | Govt. Basic School Sarhara | 264.9533 | [11 empty] | 1 | Inaugurated
343 |  | MS-6 | 10150800107 | Saran | 2009-10 | गोपालगंज | उचकागांव | 1 | H/S.Rahua Jamsar | 268.38 | [11 empty] | 1 | Inaugurated
344 |  | MS-6 |  | Saran | 2009-10 | गोपालगंज | बरौली | 2 | H/S.Sher | 268.38 | [11 empty] | 1 | Inaugurated
345 |  | MS-191 | 10170108901 | Saran | 2010-11 | सारण | अमनौर | 1 | Govt. Basic School, Mandroli |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started. Retender
346 |  | MS-191 | 10171700104 | Saran | 2010-11 | सारण | परसा | 2 | H/S, Parsa |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started. Retender
347 |  | MS-191 | 10171306801 | Saran | 2010-11 | सारण | मढ़ौरा | 3 | Govt. Basic School, Agahara |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started. Retender
348 |  | MS-192 | 10170602101 | Saran | 2010-11 | सारण | एकमा | 1 | Govt. Basic School, Rasulpur |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started. EMD Refund
349 |  | MS-193 | 10161704404 | Saran | 2010-11 | सिवान | हसनपुरा | 1 | C.B. H/S, Usari Dhanauti | 268.925 | [11 empty] | 1 | Inaugurated 16.07.2016
350 |  | MS-193 | 10160603201 | Saran | 2010-11 | सिवान | दरौली | 2 | H/S, Don | 268.925 | [11 empty] | 1 | Inaugurated
351 |  | MS-194 | 10161908001 | Saran | 2010-11 | सिवान | ज़िरादै | 1 | Mahendra H/S, Zeradei | 268.955 | [11 empty] | 1 | Inaugurated
352 |  | MS-194 | 10161601402 | Saran | 2010-11 | सिवान | लकड़ी नबीगंज | 2 | Govt. Basic School, Jalalpur | 268.955 | [11 empty] | 1 | Inaugurated
353 |  | MS-195 | 10161801803 | Saran | 2010-11 | सिवान | नौतन | 1 | H/S, Nawatan | 272.43 | [11 empty] | 1 | Inaugurated
[7 empty] | Total Schools | 353 |  | 85094.2994 | 58 | 0 | 2 | 1 | 0 | 16 | 1 | 21 | 0 | 4 | 54 | 196 |  | 49 | 4 (9-10) | 35 (10-11) | 10 (Duplicate Ing 2017)