## PTEC-22
BSEIDC Ltd., Patna
PROGRESS REPORT OF PTEC
S.No. | SL NO. | Group No. | District | Name Of Institution | S. No. | Name Of Building | Name of Agency with Mo- | Date of Agreement & No | Retender | Tender Process | Physical Status | [11 empty] | Remarks |  | Division
[11 empty] | Not Start | Lay-out | Foundation | PL | Gro |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete |  |  |  | Agreement amount (in Lakh) | Fin. Exp. (in lac) | Financial Achievement (%)
[15 empty] | LL | RL | LL | RL | LL | RL |  |  |  | Scheme
| 1 | P-1 | BHOJPUR | PTEC BIHIYA | 1 | Institutional Building | Dilip Kumar Sharma | 324 SBD OF 2014-2015(12.09.14) | [10 empty] | X | X | 1 |  | Remaining work- Door, Electrical panel RCC drain pipe, window glass etc. | PTEC | Patna East
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  | Remaining work-Iintrenal & External Painting, Main gate, Grill Painting Window glass etc | PTEC | Patna East
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  | Remaining work- Door, Balcony grill, PHE & Electrical fitting, Main gate etc. | PTEC | Patna East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  | Remaining work- Internal Painting, Door, Electrical & PHE fitting etc. | PTEC | Patna East
| 2 | P-2 | PATNA | PTEC MAHENDRU | 1 | Institutional Building | UMAKANT SINGH | 550 SBD OF 14-15 (23.12.14 | [9 empty] | 1 |  |  |  |  | Multi Purpose Hall Roof Slab to be casted, Rest part Final Floor cutting & Internal wall primer work | PTEC | Patna East
[5 empty] | 2 | Boys Hostel | [13 empty] | 1 |  |  | Plaster complete, Floornig, Septic tank & roof treatment works remains | PTEC | Patna East
[5 empty] | 3 | Girls Hostel | [13 empty] | 1 |  |  | Plaster work in progress, Mumty to be casted | PTEC | Patna East
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [5 empty] | X | X | X | X |  |  | Not start | PTEC | Patna East
| 3 | P-3 | PATNA | PTEC MASAURHI | 1 | Institutional Building | ARVIND KUMAR | 694 SBD OF 2014-15 (14.02.15) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Patna East
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Patna East
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Patna East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Patna East
| 4 | P-4 | ROHTAS | PTEC SASARAM | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 59 SBD OF 2014-15 (06.06.14 |  |  | 1 | [11 empty] | Not started due to Archeological area (Tomb of Shershah Suri) | PTEC | Patna West
[5 empty] | 2 | Boys Hostel |  |  |  |  | 1 | [12 empty] | PTEC | Patna West
[5 empty] | 3 | Girls Hostel |  |  |  |  | 1 | [12 empty] | PTEC | Patna West
[5 empty] | 4 | Principal Quarter |  |  |  |  | 1 | [5 empty] | X | X | X | X |  |  |  | PTEC | Patna West
| 5 | P-5 | MUZAFFARPUR | PTEC CHANDWARA | 1 | Institutional Building | Sanjay kumar Singh | 257 SBDOF 2014-15(14.08.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2016 | PTEC | Tirhut East
| 6 | P-6 | MUZAFFARPUR | PTEC PATAHI | 1 | Institutional Building | Rakesh Ranjan | 182 SBD OF 2014-15 (15.07.14) | [13 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
| 7 | P-7 | VAISHALI | PTEC SORHATTHA | 1 | Institutional Building | Vimlesh pd. Singh | 530 SBD OF 14-15 (17.12.14 | [12 empty] | 1 |  | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Tirhut East
| 8 | P-8 | BHAGALPUR | PTEC PHULWARIA | 1 | Institutional Building | Lalan kumar | 397 SBD OF 2014-2014(13.10.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
[5 empty] | 4 | Principal Quarter | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Bhagalpur
| 9 | P-9 | BHAGALPUR | PTEC NAGARPARA | 1 | Institutional Building | SAI HIGHWAY AND BUILDERS PVT. LTD. | 272 SBD OF 2015-16( 02.09.15) | [13 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Bhagalpur
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Bhagalpur
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Bhagalpur
[5 empty] | 4 | Principal Quarter | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Bhagalpur
| 10 | P-10 | AURANGABAD | PTEC SHAHPUR | 1 | Institutional Building | M/S HARIOM CONSTRUCTION | 63 SBD OF 2014-15 (06.06.14) | [7 empty] | 1 | [7 empty] | PTEC | Magadh
[5 empty] | 2 | Boys Hostel | [6 empty] | 1 | [10 empty] | PTEC | Magadh
[5 empty] | 3 | Girls Hostel | [11 empty] | 1 | [5 empty] | PTEC | Magadh
[5 empty] | 4 | Principal Quarter | [9 empty] | 1 | X | X | X | X |  |  |  | PTEC | Magadh
| 11 | P-11 | BEGUSARAI | PTEC VISHNUPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 405 SBD OF 2014-2014(20.10.14) | [10 empty] | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Munger
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Munger
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Munger
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Munger
| 12 | P-12 | SARAN | PTEC BANGRA | 1 | Institutional Building | Indian Progressive construction pvt. Ltd | 4 SBD OF 15-16(01.04.15) | [12 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | PTEC | Saran
| 13 | P-13 | MADHEPURA | PTEC SUKHSAN MANHARA MADHEPURA | 1 | Institutional Building | UMAKANT SINGH | 551 SBD OF 14-15 (23.12.14 | [12 empty] | 1 |  | Inaugurated 16.07.2017 | PTEC | Koshi
[5 empty] | 2 | Boys Hostel | [13 empty] | 1 |  |  | Inaugurated 16.07.2017 | PTEC | Koshi
[5 empty] | 3 | Girls Hostel | [11 empty] | 1 |  |  |  |  | Inaugurated 16.07.2017 | PTEC | Koshi
[5 empty] | 4 | Principal Quarter | [9 empty] | 1 | X | X | X | X |  |  | Inaugurated 16.07.2017 | PTEC | Koshi
| 14 | P-14 | SAMASTIPUR | PTEC RAMPUR JALALPUR | 1 | Institutional Building | M/S SURENDRA PD. SINGH | 482 SBD OF 14-15 (28.11.14) | [13 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
[5 empty] | 4 | Principal Quarter | [15 empty] | 1 | Inaugurated 16.07.2016 | PTEC | Darbhanga
| 15 | P-15 | MADHUBANI | PTEC GHOGHARDIHA | 1 | Institutional Building | Phular Construction | 224 SBD OF 2014-15 (02.08.14 | [13 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Darbhanga
[5 empty] | 2 | Boys Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Darbhanga
[5 empty] | 3 | Girls Hostel | [15 empty] | 1 | Inaugurated 16.07.2017 | PTEC | Darbhanga
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X |  | 1 | Inaugurated 16.07.2017 | PTEC | Darbhanga
| 16 | P-16 | PATNA | PTEC BARH | 1 | Institutional Building | M/S S.K ENTERPRISES | 715 SBD OF 2014-15 (24.02.15) | [9 empty] | 1 |  |  |  |  | RC except Mumty purpose Hall, GF B/W Complete & 1st Floor in progress | PTEC | Patna East
[5 empty] | 2 | Boys Hostel | [13 empty] | 1 |  |  | Plaster Work complete, Kota laying in 1st floor | PTEC | Patna East
[5 empty] | 3 | Girls Hostel | [13 empty] | 1 |  |  | Structure work complete Except Mumty, GF Plater work Complete & 1st floor in progress | PTEC | Patna East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  | intrenal & external plaster | PTEC | Patna East
| 17 | P-17 | GAYA | PTEC SHERGHATI | 1 | Institutional Building | Budha Cons. Pvt. Ltd. | 389 SBD of 2015 -16 | [9 empty] | 1 | [5 empty] | PTEC | Magadh
[5 empty] | 2 | Boys Hostel | [13 empty] | 1 |  |  |  | PTEC | Magadh
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | PTEC | Magadh
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | PTEC | Magadh
| 18 | P-18 | PATNA | PTEC TRAINING COLLEGE GULJARBAG | 1 | Institutional Building | M/S S.K ENTERPRISES | 715 SBD OF 2014-15 (24.02.15) | [10 empty] | X | X | 1 |  | Painting work in progress | PTEC | Patna East
[5 empty] | 2 | Boys Hostel | [13 empty] | 1 |  |  | Internal Plaster complete, External plaster in progress | PTEC | Patna East
[5 empty] | 3 | Girls Hostel | [6 empty] | 1 | [9 empty] | 1st Floor Column Work in progress | PTEC | Patna East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  | Flooring Work complete, Painting work in progress | PTEC | Patna East
| 19 | P-19 | MUZAFFARPUR | PTEC POKHRAIRA | 1 | Institutional Building | M/S C.S CONSTRUCTION | 465 SBD OF 2015-16 (30.03.16) | [12 empty] | 1 |  | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  | Inaugurated 16.07.2017 | PTEC | Tirhut East
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  | Inaugurated 16.07.2017 | PTEC | Tirhut East
| 20 | P-20 | MUNGER | PTEC HAWELI KHARGPUR | 1 | Institutional Building | Budha Infrastructure Private Limited, Hanuman Nagar, Kankarbagh | 388 SBD OF 2015-16 (03.02.16 | [9 empty] | 1 | [5 empty] | PTEC | Munger
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  |  | PTEC | Munger
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | PTEC | Munger
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | PTEC | Munger
| 21 | P-21 | SIWAN | PTEC SIWAN | 1 | Institutional Building | Durga Pratap Singh | 410 SBD OF 2015-16 (17.02.16) | [12 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 2 | Boys Hostel | [14 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 3 | Girls Hostel | [14 empty] | 1 |  |  | PTEC | Saran
[5 empty] | 4 | Principal Quarter | [10 empty] | X | X | X | X | 1 |  |  | PTEC | Saran
| 22 | P-22 | SAMASTIPUR | PTEC SHAHPUR PATORI | 1 | Institutional Building | Tender Process | [13 empty] | 1 |  |  | PTEC | Darbhanga
[5 empty] | 2 | Boys Hostel | [9 empty] | 1 | [7 empty] | PTEC | Darbhanga
[5 empty] | 3 | Girls Hostel | [13 empty] | 1 |  |  |  | PTEC | Darbhanga
[5 empty] | 4 | Principal Quarter | [9 empty] | 1 | X | X | X | X |  |  |  | PTEC | Darbhanga
| Total No. of Institution |  |  |  | 22 |  |  |  | 0 | 0 | 5 | 0 | 2 | 0 | 0 | 5 | 0 | 6 | 0 | 8 | 27 | 35
| Total No. of Institution |  | Name of Institution |  | Total No. of Buildings | Name of Institutional Buildings | Total No. of Buildings |  | Retender | Tender Process | Physical Status
[11 empty] | Not Start | Layout | Foundation | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL | LL | RL
| 22 |  | Primary Teacher Training Institute (PTEC) |  | 22 | Institutional Building |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 8 | 8
[5 empty] | 22 | Boys Hostel |  |  | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 5 | 5 | 9
[5 empty] | 22 | Girls Hostel |  |  | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 6 | 9
[5 empty] | 22 | Principal Quarter |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 8 | 9
| Total No. of Institutional Buildings |  |  |  | 88 |  |  |  | 0 | 0 | 5 | 0 | 2 | 0 | 0 | 5 | 0 | 6 | 0 | 8 | 27 | 35