## Summary all SSSM (hidden)
BSEIDC, PATNA
Summary of all SSSM | [21 empty] | Date:31.07.17
S.N. | EC Name | Name & Designation | Total Sanctioned |  | Contract Awarded (LOA Issued) |  | Agreement done |  | Physical Status | [7 empty] | Summary |  |  |  | Agreement Amount (in Lakh) | Fin. Exp. (in Lac) | Financial Achievent (%) | Remarks
|  |  | No. of Groups | No. of School | No. of Groups | No. of School | No. of Groups | No. of School | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | In-Progress | not start | Inauguration
[12 empty] | LL | RL | LL | RL
1 | EC - 79 | 91 | 69 | 91 | 68 | 90 | 66 | 88 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 14579.638 | 9235.9242 | 63.3481
2 | EC - 86 | 30 | 30 | 30 | 27 | 27 | 23 | 23 | 0 | 1 | 1 | 1 | 5 | 1 | 3 | 6 | 7 | 18 | 5
3 | EC - 96 |  | 18 | 18 | 13 | 13 | 5 | 5 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 9 | 9 | 0
4 | EC - 97 |  | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 2 | 0 |  |  |  |  | 69
5 | EC - 107 |  | 20 | 20 | 11 | 11 | 4 | 4 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 6 | 9 | 5
6 | EC - 110 |  |  | 3 | [13 empty] | 0 | 3 |  |  |  |  | Tender in process (NIT-5)
7 | EC - 122 |  |  | 17 | [13 empty] | 0 | 17 |  |  |  |  | Tender in process (NIT-5)
8 | EC - 127 |  |  | 41 | [13 empty] | 0 | 41 |  |  |  |  | Tender in process (NIT-5)
| Total |  | 142 | 225 | 124 | 146 | 101 | 123 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 14579.638 | 9235.9242 | 63.3481

## List of SSSM (hidden)
BSEIDC Ltd. , Patna
Physical status of SSSM
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Estimated Amount (in Lac) | Time of Completion | Retender | Tender Process | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks | Session | Division
[11 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | SSSM-1-1 | dfVgkj | अमदाबाद | 1 | m0e0fo0 pkek | Umakant Singh, 9431096239 | 342.51 | 15 ekg | [11 empty] | 1 | 91.56 | Inaugurated 2016 | Phase -1 | Purnea
2 | SSSM-1-2 | dfVgkj | अमदाबाद | 2 | e0fo0 turkxksikyiqj | Umakant Singh, 9431096239 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
3 | SSSM-1-3 | dfVgkj | अमदाबाद | 3 | e0fo0 ikjfn;kjk | Umakant Singh, 9431096239 |  |  |  |  | 1 | [10 empty] | LAND MADE AVAILABLE ON THE BANK OF GANGA RIVER. (DANGER OF EROSION) | Phase -1 | Purnea
4 | SSSM-2-1 | dfVgkj | आजमनगर | 1 | e0fo0 fldfV;k | BIRENDRA KUMAR SINGH, 9473440405 | 343.75 | 15 ekg | [10 empty] | 1 |  | 33.03 |  | Phase -1 | Purnea
5 | SSSM-2-2 | dfVgkj | आजमनगर | 2 | m0e0fo0 csyjkgh | BIRENDRA KUMAR SINGH, 9473440405 | [13 empty] | 1 |  | Handover | Phase -1 | Purnea
6 | SSSM-2-3 | dfVgkj | आजमनगर | 3 | m0e0fo0 rs?kM+k | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 | [6 empty] | Phase -1 | Purnea
7 | SSSM-3(A) | dfVgkj | बारसोई | 1 | e0fo0 XokyVksyh | RANA BIRESH PRATAP SINGH, 9430683578 | 115.71 | 15 ekg |  |  | 1 | [10 empty] | 7 FEET DEEP WATER LOGGED LAND MADE AVAILABLE. | Phase -1 | Purnea
8 | SSSM-3(B) | dfVgkj | बारसोई | 1 | e0fo0 [k#vk tehjk | RANA BIRESH PRATAP SINGH,9430683578 | 115.71 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
9 | SSSM-3(C) | dfVgkj | बारसोई | 1 | m0e0fo0 Qqgkxk¡o | R. P. Agarwal , Katihar | 115.71 | 15 ekg |  |  | 1 | [10 empty] | Land not available 14 feet wide 80 feet length land available but it is being used as passage/play ground) letter has been sent to DEO for Land. | Phase -1 | Purnea
10 | SSSM-4(A) | dfVgkj | बलरामपुर | 1 | e0fo0 efydiqj | MUKESH KUMAR, 9431658565 | 115.34 | 15 ekg |  |  | 1 | [10 empty] | Land enchroched, letter has been issued to DEO to solve the problem. | Phase -1 | Purnea
11 | SSSM-4(B) | dfVgkj | बलरामपुर | 1 | e0fo0 Qrsgiqj | Excelent Construction | 115.34 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
12 | SSSM-4(C) | dfVgkj | बलरामपुर | 1 | m0e0fo0 ckywxat fgUnh | R. P. Agarwal , Katihar | 115.34 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
13 | SSSM-5-1 | dfVgkj | फलका | 1 | e0fo0 eks0 uxj jkt/kkuh | BIRENDRA KUMAR SINGH, 9473440405 | 223.83 | 15 ekg |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. USSS-137 on Finishing Stage | Phase -1 | Purnea
14 | SSSM-5-2 | dfVgkj | फलका | 2 | e0fo0 Hkjfl;k | BIRENDRA KUMAR SINGH, 9473440405 | [8 empty] | 1 | [7 empty] | Phase -1 | Purnea
15 | SSSM-6-1 | dfVgkj | कोढ़ा | 1 | vH;kl e0fo0 eqlkiqj | BIRENDRA KUMAR SINGH, 9473440405 | 332.13 | 15 ekg | [9 empty] | 1 |  |  | 21.88 |  | Phase -1 | Purnea
16 | SSSM-6-2 | dfVgkj | कोढ़ा | 2 | e0fo0 [ksfj;k | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. USSS-134 on Finishing Stage | Phase -1 | Purnea
17 | SSSM-6-3 | dfVgkj | कोढ़ा | 3 | e0fo0 fn?kM+h | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. USSS-134 on Finishing Stage | Phase -1 | Purnea
18 | SSSM-7-1 | dfVgkj | प्राणपुर | 1 | m0e0fo0 jkepUnziqj | PANKAJ KUMAR SINGH,9431229327 | 335.36 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
19 | SSSM-7-2 | dfVgkj | प्राणपुर | 2 | e0fo0 egknsoiqj | PANKAJ KUMAR SINGH,9431229327 | [13 empty] | 1 | 74.22 | Inaugurated 2016 | Phase -1 | Purnea
20 | SSSM-7-3 | dfVgkj | प्राणपुर | 3 | e0fo0 cq) uxj | PANKAJ KUMAR SINGH,9431229327 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
21 | SSSM-8-1 | dfVgkj | कटिहार | 1 | m0e0fo0 efu;k | PANKAJ KUMAR SINGH,9431229327 | 221.65 | 15 ekg | [10 empty] | 1 |  | 16.99 |  | Phase -1 | Purnea
22 | SSSM-8-2 | dfVgkj | कटिहार | 2 | e0fo0 cBSyh | PANKAJ KUMAR SINGH,9431229327 | [13 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
23 | SSSM-9-1 | dfVgkj | मनसाही | 1 | jk0e0fo0 eajxh | BIRENDRA KUMAR SINGH, 9473440405 | 222.46 | 15 ekg | [10 empty] | 1 |  | 21.69 |  | Phase -1 | Purnea
24 | SSSM-9-2 | dfVgkj | मनसाही | 2 | vk0e0fo0 jkuhirjk fla/k;k | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 | [6 empty] | Phase -1 | Purnea
25 | SSSM-10-1 | dfVgkj | बरारी | 1 | m0e0fo0 fxnjekjh | BIRENDRA KUMAR SINGH, 9473440405 | 222.01 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Purnea
26 | SSSM-10-2 | dfVgkj | बरारी | 2 | e0fo0 Hk.Mkjry | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | Land not registered in the name of school. | Phase -1 | Purnea
27 | SSSM-11(A) | dfVgkj | मनिहारी | 1 | e0fo0 lqjkikjVky | MS EXCELLENT CONSTRUCTION, 9472021967 | 112.5 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
28 | SSSM-11(B) | dfVgkj | मनिहारी | 1 | e0fo0 dkWVkdks'k | MS EXCELLENT CONSTRUCTION, 9472021967 | 112.5 | 15 ekg |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. USSS-137 on Finishing Stage | Phase -1 | Purnea
29 | SSSM-12(A) | dfVgkj | कदवा | 1 | m0e0fo0 dpkSM+k iwoZ | R. P. Agarwal , Katihar | 112.57 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
30 | SSSM-12(B) | dfVgkj | कदवा | 1 | m0e0fo0 cSnk | MS EXCELLENT CONSTRUCTION,9472021967 | 112.57 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
31 | SSSM-13(A) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 y[kukjs | M/S Excellent Construction | 114 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
32 | SSSM-13(B) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 csydk | MD ARFIN,9006212706 | 114 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
33 | SSSM-13(C) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 ckywVksyk] bLykeiqj | Gajmatia, Khushkibagh | 114 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
34 | SSSM-14(A) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 etxkek | SANJEEV RANJAN SINHA, 9472063463 | 111.74 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
35 | SSSM-14(B) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 yN.kiqj | M/S Excellent Construction | 111.74 | 15 ekg |  |  | 1 | [10 empty] | Donners objection, Letter issued to DPO | Phase -1 | Purnea
36 | SSSM-14(C) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 eksguh | M/S Excellent Construction | 111.74 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
37 | SSSM-15(A) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 lkukiqj | Ashish Anand, Purnea | 112.99 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
38 | SSSM-15(B) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 gjsjkeiqj | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED, 9973239801 | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
39 | SSSM-15(C) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 pjS;k | Bambam Kumar Singh | 112.99 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
40 | SSSM-15(D) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 'kh'kckM+h | Gajmathia | 112.99 | 15 ekg |  |  |  |  | 1 | [9 empty] | Phase -1 | Purnea
41 | SSSM-15(E) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 p¡nokj | HARIMOHAN BISHWAS,9955713757 | 112.99 | 15 ekg |  |  |  | 1 | [9 empty] | Letter issued to contractor to start the work | Phase -1 | Purnea
42 | SSSM-15(F) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 uUnfu;k | Binod Yadav | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
43 | SSSM-16(A) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 Mx#vk | HARIMOHAN BISHWAS,9955713757 | 112.25 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
44 | SSSM-16(B) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 pkSiM+k cyqvk | M/S Excellent Construction | 112.25 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
45 | SSSM-16(C) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 fl;kj[ke | M/S Rana Pratap Singh, Purnea | 112.25 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
46 | SSSM-17-1 | iwf.kZ;k¡ | जलालगढ़ | 1 | e0fo0 efr;kjiqj | DILIP KUMAR, 9631032543 / 9431666265 | 338.09 | 15 ekg | [10 empty] | 1 |  | 58.5 |  | Phase -1 | Purnea
47 | SSSM-17-2 | iwf.kZ;k¡ | जलालगढ़ | 2 | e0fo0 dBSyh | DILIP KUMAR, 9631032543 / 9431666265 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
48 | SSSM-17-3 | iwf.kZ;k¡ | जलालगढ़ | 3 | e0fo0 ,dEck | DILIP KUMAR, 9631032543 / 9431666265 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
49 | SSSM-18-1 | iwf.kZ;k¡ | कृत्यानन्द नगर | 1 | e0fo0 iz[kaM dkWyuh | MS ALAM CONSTR. WORKS & CO, 9199574775 9472103786 | 333.26 | 15 ekg | [7 empty] | 1 |  |  |  |  | 21.07 |  | Phase -1 | Purnea
50 | SSSM-18-2 | iwf.kZ;k¡ | कृत्यानन्द नगर | 2 | e0fo0 izlkniqj csynkjh | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [7 empty] | 1 | [8 empty] | Phase -1 | Purnea
51 | SSSM-18-3 | iwf.kZ;k¡ | कृत्यानन्द नगर | 3 | e0fo0 dk>k x.ks'kiqj | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [9 empty] | 1 | [6 empty] | Phase -1 | Purnea
52 | SSSM-19-1 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 1 | e0fo0 fiijk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | 222.8 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
53 | SSSM-19-2 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 2 | e0fo0 egjktiqj | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [13 empty] | 1 |  | Handover | Phase -1 | Purnea
54 | SSSM-20-1 | iwf.kZ;k¡ | श्रीनगर | 1 | e0fo0 txSyh | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | 224.28 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
55 | SSSM-20-2 | iwf.kZ;k¡ | श्रीनगर | 2 | e0fo0 xaxk Hkou [kks[kk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
56 | SSSM-25-1 | vjfj;k | नरपतगंज | 1 | ,e0,l0 xks[kykiqj ch0,e0,l0 | Kailash Prasad Yadav Constructions Pvt Ltd. , 9431424763 | 353.03 | 15 ekg | [10 empty] | 1 |  | 23.84 |  | Phase -1 | Purnea
57 | SSSM-25-2 | vjfj;k | नरपतगंज | 2 | ,e0,l0 csyk fjQwth | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [13 empty] | 1 |  |  | Phase -1 | Purnea
58 | SSSM-25-3 | vjfj;k | नरपतगंज | 3 | ,e0,l0 pUnk | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
59 | SSSM-26(A) | vjfj;k | रानीगंज | 1 | ,e0,l0 gjhnk,iqj | Krishna Ranjan Kumar, Araria | 114.05 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
60 | SSSM-26(B) | vjfj;k | रानीगंज | 1 | ,e0,l0 ukjk;.kiqj | MD ARFIN, 9006212706 | 114.05 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
61 | SSSM-26(C) | vjfj;k | रानीगंज | 1 | ;w0,e0,l0 nqekfj;k ckyd | MD ARFIN, 9006212706 | 114.05 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
62 | SSSM-27(A) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 vekSuk | KRISHNA RANJAN KUMAR,9939662452 | 116.06 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Purnea
63 | SSSM-27(B) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 iq.kZnkgk | CHANDAN ABHISHEK,9431284224 | 116.06 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
64 | SSSM-28(A) | vjfj;k | सिक्टी | 1 | ,e0,l0 xksjkxPN | Praveen, Araria | 118.43 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
65 | SSSM-28(B) | vjfj;k | सिक्टी | 1 | ;w0,e0,l0 fnefg;k | Md. Iftakhar Alam | 118.43 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
66 | SSSM-29 | vjfj;k | सिक्टी | 1 | ,e0,l0 ispkSyh | KUNAL KUSH | 114.93 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Purnea
67 | SSSM-21(A) | if'pe pEikj.k | सिरिसिया | 1 | e0fo0 fljfl;k | KISHOR KUMAR,8298437834 | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
68 | SSSM-21(B) | if'pe pEikj.k | बेहरा | 1 | e0fo0 >qedk mnwZ | MS SARASWATI COMPANY,9431491241 | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
69 | SSSM-21(C) | if'pe pEikj.k | सूर्यपुर | 1 | mŒ ekŒ foŒ] Hkokuhiqj mnZw | MS SARASWATI COMPANY,9431491241 | 115.98 | 15 ekg | [9 empty] | 1 |  |  |  |  | Phase -1 | Tirhut West
70 | SSSM-22(A) | if'pe pEikj.k | तेलपुर | 1 | m0e0fo0 rsyiqj ckyd | M/S BHATRDWAJ CONSTRUCTION | 115.98 | 15 ekg |  |  | 1 | [10 empty] | Land not available | Phase -1 | Tirhut West
71 | SSSM-22(B) | if'pe pEikj.k | देउरवा | 1 | e0fo0 nsmjok | Ashukla | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
72 | SSSM-22(C) | if'pe pEikj.k | धोबनी धर्मपुर | 1 | m0e0fo0 eqlgjh | SANJAY KUMAR MISHRA, 9546215798 | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
73 | SSSM-22(D) | if'pe pEikj.k | मठिया | 1 | e0fo0 efB;k | AWADHESH SHUKLA, 9431203836 | 115.98 | 15 ekg | [11 empty] | 1 | 14.28 | Inaugurated 2017 | Phase -1 | Tirhut West
74 | SSSM-23(A) | if'pe pEikj.k | रखही | 1 | m0e0fo0 pEikj.k | SHAKAL DEO MISHRA,9006385958 | 115.55 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2017 | Phase -1 | Tirhut West
75 | SSSM-23(B) | if'pe pEikj.k | शेरहवा | 1 | e0fo0 fllok cgqvjok | RAJ KISHORE AKELA,9430642227 | 115.55 | 15 ekg | [11 empty] | 1 | 8.33 | Inaugurated 2017 | Phase -1 | Tirhut West
76 | SSSM-23(C) | if'pe pEikj.k | पुरैनिया हरसरी | 1 | m0e0fo0 dksbZjxkok | SANJAY KUMAR MISHRA, 9546215798 | 115.55 | 15 ekg |  |  | 1 | [10 empty] | Land not available | Phase -1 | Tirhut West
77 | SSSM-24(A) | if'pe pEikj.k | चैहटी | 1 | e0fo0 lkSdV | GYASUL AZAM, 9199932786 | 116.39 | 15 ekg | [10 empty] | 1 |  |  | 50'X80' | Phase -1 | Tirhut West
78 | SSSM-24(B) | if'pe pEikj.k | मधुरि | 1 | m0e0fo0 idqgok iwohZ | GYASUL AZAM, 9199932786 | 116.39 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
79 | SSSM-30-1 | njHkaxk | दरभंगा सदर | 1 | e0fo0 Bdqjfu;k¡ | RAJENDRA PRASAD, 8797539347 | 225.8 | 15 ekg | [11 empty] | 1 | 59.48 | Inaugurated 2016 | Phase -1 | Darbhanga
80 | SSSM-30-2 | njHkaxk | दरभंगा सदर | 2 | e0fo0 da'kh | RAJENDRA PRASAD, 8797539347 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
81 | SSSM-31-1 | njHkaxk | मनीगाछी | 1 | e0fo0 pdfpUrkef.kiqj | S K CONSTRUCTION AND COMPANY,9471006199 | 114.2 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Darbhanga
82 | SSSM-32-1 | njHkaxk | अलीनगर | 1 | mnwZ e0fo0 vyhuxj | AJAY KUMAR PATHAK,9431034060 | 114.27 | 15 ekg | [10 empty] | 1 |  | 21.61 |  | Phase -1 | Darbhanga
83 | SSSM-33-1 | njHkaxk | जाले | 1 | e0fo0 tgkxhj Vksy | SANJAY KUMAR, 8521954601 | 229.19 | 15 ekg | [11 empty] | 1 | 36.79 | Inaugurated 2016 | Phase -1 | Darbhanga
84 | SSSM-33-2 | njHkaxk | जाले | 2 | e0fo0 vfg;kjh xksV | SANJAY KUMAR, 8521954601 | [9 empty] | 1 | [6 empty] | Phase -1 | Darbhanga
85 | SSSM-34(A) | njHkaxk | सिंहवाड़ा | 1 | e0fo0 jktks | BHUSAN KUMAR,9631681894 | 113.32 | 15 ekg | [11 empty] | 1 | 20.33 | Inaugurated 2016 | Phase -1 | Darbhanga
86 | SSSM-34(B) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 cgqvkjk | SachinKhandelwal | 113.32 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
87 | SSSM-34(C) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 xkSjhukFk czgeiqj | SachinKhandelwal | 113.32 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
88 | SSSM-35(A) | njHkaxk | केवटी | 1 | e0fo0 cjgh | OM SHREE CONSTRUCTION, 9934426934 | 112.93 | 15 ekg |  |  |  |  | 1 | [8 empty] | Land Dispute | Phase -1 | Darbhanga
89 | SSSM-35(B) | njHkaxk | केवटी | 1 | m0e0fo0 ykyxat | Rajesh Kumar, 9334374660 | 112.93 | 15 ekg | [10 empty] | 1 |  | 34.09 | Inaugurated 2016 | Phase -1 | Darbhanga
90 | SSSM-36-1 | njHkaxk | किरतपुर | 1 | e0fo0 fdjriqj | OM SHREE CONSTR. BEGUSARAI | 113.75 | 15 ekg | [6 empty] | 1 | [7 empty] | Phase -1 | Darbhanga
91 | SSSM-37-1 | njHkaxk | गौराबौराम | 1 | e0fo0 ckSjke | OM SHREE CONSTR. BEGUSARAI | 114.25 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Darbhanga
92 | SSSM-47(A) | fd'kuxat | cgknqjxat | 1 | e0 fo0 HkheVksyk | KAUSHAL KUMAR | [11 empty] | 1 |  |  |  |  | Phase-2 | Purnea
93 | SSSM-47(B) | fd'kuxat | cgknqjxat | 2 | mŒ eŒ foŒ eaMyVksyk Mksgj | MD ANZAR ALAM | [11 empty] | 1 |  |  |  |  | Phase-2 | Purnea
94 | SSSM-48-1 | fd'kuxat | fd'kuxat | 1 | e0 fo0 ikuhlky | Cancel |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-95 on COMPLETED | Phase-2 | Purnea
95 | SSSM-49(A) | fd'kuxat | dkspk/kkeu | 1 | m0 e0 fo0 dUgS;kckM+h | MANOJ KUMAR | [12 empty] | 1 |  |  |  | Phase-2 | Purnea
96 | SSSM-49(B) | fd'kuxat | dkspk/kkeu | 2 | m0 e0 fo0 eksgjk | BHOLINATH RAY | [6 empty] | 1 | [9 empty] | Phase-2 | Purnea
97 | SSSM-49 ( C) | fd'kuxat | dkspk/kkeu | 3 | m0 e0 fo0 gfjHkk"kk | MD. ZULQUER NAIN | [12 empty] | 1 |  |  |  | Phase-2 | Purnea
98 | SSSM-50 (A) | fd'kuxat | iksfB;k | 1 | m0 e0 fo0 tkyw pkSd | No Bidder |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-96 on Plinth Level | Phase-2 | Purnea
99 | SSSM-50 (B) | fd'kuxat | iksfB;k | 2 | m0 e0 fo0 lksukiwj | WALKS N WALKS | [11 empty] | 1 |  |  |  |  | Phase-2 | Purnea
100 | SSSM-50 ( C) | fd'kuxat | iksfB;k | 3 | m0 e0 fo0 HksykxkNh chjiqj | VATS INFRATECH PVT. LTD. |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-96 on GROUND FLOOR ROOF LEVEL | Phase-2 | Purnea
101 | SSSM-51 | fd'kuxat | VsjkxkPN | 1 | m0 e0 fo0 vkfnoklh Vksyk Hkksjgk | Pawan Kumar Agarwal | [9 empty] | 1 | [6 empty] | Phase-2 | Purnea
102 | SSSM-52 (A) | fd'kuxat | Bkdqjxat | 1 | m0 e0 fo0 ikapxkNh | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR LINTER LEVEL | Phase-2 | Purnea
103 | SSSM-52 (B) | fd'kuxat | Bkdqjxat | 2 | m0 e0 fo0 yks/kk | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR LINTER LEVEL | Phase-2 | Purnea
104 | SSSM-52 ( C) | fd'kuxat | Bkdqjxat | 3 | e0 fo0 csgqyMkaxh | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR ROOF LEVEL | Phase-2 | Purnea
105 | SSSM-38 | lhrke<+h | cktiÍh | 1 | ,e0 ,l0 fcyfg;k | Shree shiva Construction dist- muzaffarpur | [12 empty] | 1 |  |  | External Plaster , Grill Fitting Done Internal Plaster FF Running | Phase-2 | Tirhut East
106 | SSSM-41 | lqikSy | clariqj | 1 | e/; fo¦ky; ujirV~Vh | Madan kumar singh |  |  |  |  | 1 | [10 empty] | Not Started | Phase-2 | Koshi
107 | SSSM-42 (A) | xksikyxat | Fkkos | 1 | ,e0 ,l0 lsejk | PAWAN CONSTRUCTION | [12 empty] | 1 |  |  |  | Phase-2 | Saran
108 | SSSM-42 (B) | xksikyxat | Fkkos | 1 | ;w0 ,e0 ,l0 ukjk;.kiqj | GIRIDHAR GOPAL CONS. |  |  |  |  | 1 | [10 empty] | Land not available | Phase-2 | Saran
109 | SSSM-43 (A) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 lariqj | kumar manash construction |  |  |  |  | 1 | [10 empty] | Land not available | Phase-2 | Saran
110 | SSSM-43 (B) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 'ks[kijlk | Savitri Technocrates pvt. Ltd | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Saran
111 | SSSM-43 (C ) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 dksygqvk | Savitri Technocrates pvt. Ltd | [13 empty] | 1 |  | Inaugurated 2017 | Phase-2 | Saran
112 | SSSM-44 (A) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 gjiqj | sai Highway & builders pvt.ltd | [10 empty] | 1 | [5 empty] | Phase-2 | Saran
113 | SSSM-44 (B) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 ewjkedlwniqj | Cancel |  |  |  |  | 1 | [10 empty] | Double Scheme. Match school name to group no. SSS-352 on COMPLETED | Phase-2 | Saran
114 | SSSM-45 (A) | ckadk | /kqjS;k | 1 | m0 e0 fo0 pyuk | Marcominfra Pvt. Ltd., 9934361315 |  |  |  |  | 1 | [10 empty] | LOA Issue | Phase-2 | Bhagalpur
115 | SSSM-45 (B) | ckadk | /kqjS;k | 2 | m0 e0 fo0 rkfgjiqjk dU;k | Chitragupta construction | [9 empty] | 1 | [5 empty] | DEBAR | Phase-2 | Bhagalpur
116 | SSSM-45 (C ) | ckadk | /kqjS;k | 3 | m0 e0 fo0 vfgjks | Chitragupta construction | [12 empty] | 1 |  |  | G+2, DELAY DUE TO CHANGE IN DRAWING. Second Floor R.L | Phase-2 | Bhagalpur
117 | SSSM-46-1 | Hkkxyiqj | lugkSyk | 1 | e0 fo0 rsyokM+k | Baba Hans Construction | [13 empty] | 1 |  | Inaugurated 2017 | Phase-2 | Bhagalpur
118 | SSSM-39 (A) | e/kqcuh | jfgdk | 1 | ,e0 ,l0 elufx;k | RAMDINESH SINGH |  |  |  |  | 1 | [10 empty] | No Location found | Phase-2 | Darbhanga
119 | SSSM-39 (B) | e/kqcuh | jfgdk | 2 | ,e0 ,l0 eyufx;k | RAMDINESH SINGH | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Darbhanga
120 | SSSM-39 (C ) | e/kqcuh | jfgdk | 3 | ;w0,e0,l0 ckNVksy jkeiqj | RAMDINESH SINGH | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Darbhanga
121 | SSSM-40-1 | e/kqcuh | dyqvkgh | 1 | ,e0 ,l0 eyey | RAMDINESH SINGH | [12 empty] | 1 |  |  |  | Phase-2 | Darbhanga
Total No. of Schools (SSSM) |  |  |  | 121 |  |  |  |  | 0 | 0 | 24 | 1 | 3 | 1 | 2 | 10 | 1 | 5 | 34 | 40 | 557.69

## Phase-1
BSEIDC Ltd. , Patna
Physical status of SSSM (Phase-1)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Physical Status | [9 empty] | Remarks | Session | Division
[9 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[13 empty] | LL | RL | LL | RL
1 | SSSM-1-1 | dfVgkj | अमदाबाद | 1 | m0e0fo0 pkek | Umakant Singh, 9431096239 | [11 empty] | 1 | Completed | Phase -1 | Purnea
2 | SSSM-1-2 | dfVgkj | अमदाबाद | 2 | e0fo0 turkxksikyiqj | Umakant Singh, 9431096239 | [11 empty] | 1 | Completed | Phase -1 | Purnea
3 | SSSM-1-3 | dfVgkj | अमदाबाद | 3 | e0fo0 ikjfn;kjk | Umakant Singh, 9431096239 |  |  | 1 | [9 empty] | LAND MADE AVAILABLE ON THE BANK OF GANGA RIVER. (DANGER OF EROSION) | Phase -1 | Purnea
4 | SSSM-2-1 | dfVgkj | आजमनगर | 1 | e0fo0 fldfV;k | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | Phase -1 | Purnea
5 | SSSM-2-2 | dfVgkj | आजमनगर | 2 | m0e0fo0 csyjkgh | BIRENDRA KUMAR SINGH, 9473440405 | [11 empty] | 1 | Completed | Phase -1 | Purnea
6 | SSSM-2-3 | dfVgkj | आजमनगर | 3 | m0e0fo0 rs?kM+k | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
7 | SSSM-3(A) | dfVgkj | बारसोई | 1 | e0fo0 XokyVksyh | RANA BIRESH PRATAP SINGH, 9430683578 |  |  | 1 | [9 empty] | 7 FEET DEEP WATER LOGGED LAND MADE AVAILABLE. | Phase -1 | Purnea
8 | SSSM-3(B) | dfVgkj | बारसोई | 1 | e0fo0 [k#vk tehjk | RANA BIRESH PRATAP SINGH,9430683578 | [11 empty] | 1 | Completed | Phase -1 | Purnea
9 | SSSM-3(C) | dfVgkj | बारसोई | 1 | m0e0fo0 Qqgkxk¡o | R. P. Agarwal , Katihar |  |  | 1 | [9 empty] | Land not available 14 feet wide 80 feet length land available but it is being used as passage/play ground) letter has been sent to DEO for Land. | Phase -1 | Purnea
10 | SSSM-4(A) | dfVgkj | बलरामपुर | 1 | e0fo0 efydiqj | MUKESH KUMAR, 9431658565 |  |  | 1 | [9 empty] | Land enchroched, letter has been issued to DEO to solve the problem. | Phase -1 | Purnea
11 | SSSM-4(B) | dfVgkj | बलरामपुर | 1 | e0fo0 Qrsgiqj | Excelent Construction | [11 empty] | 1 | Completed | Phase -1 | Purnea
12 | SSSM-4(C) | dfVgkj | बलरामपुर | 1 | m0e0fo0 ckywxat fgUnh | R. P. Agarwal , Katihar | [11 empty] | 1 | Completed | Phase -1 | Purnea
13 | SSSM-5-1 | dfVgkj | फलका | 1 | e0fo0 eks0 uxj jkt/kkuh | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  | Double Scheme. Match school name to group no. USSS-137 on Finishing Stage | Phase -1 | Purnea
14 | SSSM-5-2 | dfVgkj | फलका | 2 | e0fo0 Hkjfl;k | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1 | [6 empty] | Phase -1 | Purnea
15 | SSSM-6-1 | dfVgkj | कोढ़ा | 1 | vH;kl e0fo0 eqlkiqj | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 |  |  |  | Phase -1 | Purnea
16 | SSSM-6-2 | dfVgkj | कोढ़ा | 2 | e0fo0 [ksfj;k | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  | Double Scheme. Match school name to group no. USSS-134 on Finishing Stage | Phase -1 | Purnea
17 | SSSM-6-3 | dfVgkj | कोढ़ा | 3 | e0fo0 fn?kM+h | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  | Double Scheme. Match school name to group no. USSS-134 on Finishing Stage | Phase -1 | Purnea
18 | SSSM-7-1 | dfVgkj | प्राणपुर | 1 | m0e0fo0 jkepUnziqj | PANKAJ KUMAR SINGH,9431229327 | [11 empty] | 1 | Completed | Phase -1 | Purnea
19 | SSSM-7-2 | dfVgkj | प्राणपुर | 2 | e0fo0 egknsoiqj | PANKAJ KUMAR SINGH,9431229327 | [11 empty] | 1 | Completed | Phase -1 | Purnea
20 | SSSM-7-3 | dfVgkj | प्राणपुर | 3 | e0fo0 cq) uxj | PANKAJ KUMAR SINGH,9431229327 | [11 empty] | 1 | Completed | Phase -1 | Purnea
21 | SSSM-8-1 | dfVgkj | कटिहार | 1 | m0e0fo0 efu;k | PANKAJ KUMAR SINGH,9431229327 | [10 empty] | 1 |  |  | Phase -1 | Purnea
22 | SSSM-8-2 | dfVgkj | कटिहार | 2 | e0fo0 cBSyh | PANKAJ KUMAR SINGH,9431229327 | [11 empty] | 1 | Completed | Phase -1 | Purnea
23 | SSSM-9-1 | dfVgkj | मनसाही | 1 | jk0e0fo0 eajxh | BIRENDRA KUMAR SINGH, 9473440405 | [10 empty] | 1 |  |  | Phase -1 | Purnea
24 | SSSM-9-2 | dfVgkj | मनसाही | 2 | vk0e0fo0 jkuhirjk fla/k;k | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
25 | SSSM-10-1 | dfVgkj | बरारी | 1 | m0e0fo0 fxnjekjh | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
26 | SSSM-10-2 | dfVgkj | बरारी | 2 | e0fo0 Hk.Mkjry | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Land not registered in the name of school. | Phase -1 | Purnea
27 | SSSM-11(A) | dfVgkj | मनिहारी | 1 | e0fo0 lqjkikjVky | MS EXCELLENT CONSTRUCTION, 9472021967 | [11 empty] | 1 | Completed | Phase -1 | Purnea
28 | SSSM-11(B) | dfVgkj | मनिहारी | 1 | e0fo0 dkWVkdks'k | MS EXCELLENT CONSTRUCTION, 9472021967 | [11 empty] | 1 | Double Scheme. Match school name to group no. USSS-137 on COMPLETE | Phase -1 | Purnea
29 | SSSM-12(A) | dfVgkj | कदवा | 1 | m0e0fo0 dpkSM+k iwoZ | R. P. Agarwal , Katihar | [11 empty] | 1 | Completed | Phase -1 | Purnea
30 | SSSM-12(B) | dfVgkj | कदवा | 1 | m0e0fo0 cSnk | MS EXCELLENT CONSTRUCTION,9472021967 | [11 empty] | 1 | Completed | Phase -1 | Purnea
31 | SSSM-13(A) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 y[kukjs | M/S Excellent Construction | [11 empty] | 1 | Completed | Phase -1 | Purnea
32 | SSSM-13(B) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 csydk | MD ARFIN,9006212706 | [10 empty] | 1 |  |  | Phase -1 | Purnea
33 | SSSM-13(C) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 ckywVksyk] bLykeiqj | Gajmatia, Khushkibagh | [10 empty] | 1 |  |  | Phase -1 | Purnea
34 | SSSM-14(A) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 etxkek | SANJEEV RANJAN SINHA, 9472063463 | [10 empty] | 1 |  |  | Phase -1 | Purnea
35 | SSSM-14(B) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 yN.kiqj | M/S Excellent Construction |  |  | 1 | [9 empty] | Donners objection, Letter issued to DPO | Phase -1 | Purnea
36 | SSSM-14(C) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 eksguh | M/S Excellent Construction | [11 empty] | 1 | Completed | Phase -1 | Purnea
37 | SSSM-15(A) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 lkukiqj | Ashish Anand, Purnea | [11 empty] | 1 | Completed | Phase -1 | Purnea
38 | SSSM-15(B) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 gjsjkeiqj | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED, 9973239801 | [10 empty] | 1 |  |  | Phase -1 | Purnea
39 | SSSM-15(C) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 pjS;k | Bambam Kumar Singh | [11 empty] | 1 | Completed | Phase -1 | Purnea
40 | SSSM-15(D) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 'kh'kckM+h | Gajmathia |  |  |  |  | 1 | [8 empty] | Phase -1 | Purnea
41 | SSSM-15(E) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 p¡nokj | HARIMOHAN BISHWAS,9955713757 |  |  |  | 1 | [8 empty] | Letter issued to contractor to start the work | Phase -1 | Purnea
42 | SSSM-15(F) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 uUnfu;k | Binod Yadav | [10 empty] | 1 |  |  | Phase -1 | Purnea
43 | SSSM-16(A) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 Mx#vk | HARIMOHAN BISHWAS,9955713757 | [11 empty] | 1 | Completed | Phase -1 | Purnea
44 | SSSM-16(B) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 pkSiM+k cyqvk | M/S Excellent Construction | [11 empty] | 1 | Completed | Phase -1 | Purnea
45 | SSSM-16(C) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 fl;kj[ke | M/S Rana Pratap Singh, Purnea | [11 empty] | 1 | Completed | Phase -1 | Purnea
46 | SSSM-17-1 | iwf.kZ;k¡ | जलालगढ़ | 1 | e0fo0 efr;kjiqj | DILIP KUMAR, 9631032543 / 9431666265 | [10 empty] | 1 |  |  | Phase -1 | Purnea
47 | SSSM-17-2 | iwf.kZ;k¡ | जलालगढ़ | 2 | e0fo0 dBSyh | DILIP KUMAR, 9631032543 / 9431666265 | [10 empty] | 1 |  |  | Phase -1 | Purnea
48 | SSSM-17-3 | iwf.kZ;k¡ | जलालगढ़ | 3 | e0fo0 ,dEck | DILIP KUMAR, 9631032543 / 9431666265 | [10 empty] | 1 |  |  | Phase -1 | Purnea
49 | SSSM-18-1 | iwf.kZ;k¡ | कृत्यानन्द नगर | 1 | e0fo0 iz[kaM dkWyuh | MS ALAM CONSTR. WORKS & CO, 9199574775 9472103786 | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
50 | SSSM-18-2 | iwf.kZ;k¡ | कृत्यानन्द नगर | 2 | e0fo0 izlkniqj csynkjh | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [5 empty] | 1 | [7 empty] | Phase -1 | Purnea
51 | SSSM-18-3 | iwf.kZ;k¡ | कृत्यानन्द नगर | 3 | e0fo0 dk>k x.ks'kiqj | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
52 | SSSM-19-1 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 1 | e0fo0 fiijk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [10 empty] | 1 |  |  | Phase -1 | Purnea
53 | SSSM-19-2 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 2 | e0fo0 egjktiqj | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [11 empty] | 1 | Completed | Phase -1 | Purnea
54 | SSSM-20-1 | iwf.kZ;k¡ | श्रीनगर | 1 | e0fo0 txSyh | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [10 empty] | 1 |  |  | Phase -1 | Purnea
55 | SSSM-20-2 | iwf.kZ;k¡ | श्रीनगर | 2 | e0fo0 xaxk Hkou [kks[kk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [10 empty] | 1 |  |  | Phase -1 | Purnea
56 | SSSM-25-1 | vjfj;k | नरपतगंज | 1 | ,e0,l0 xks[kykiqj ch0,e0,l0 | Kailash Prasad Yadav Constructions Pvt Ltd. , 9431424763 | [10 empty] | 1 |  |  | Phase -1 | Purnea
57 | SSSM-25-2 | vjfj;k | नरपतगंज | 2 | ,e0,l0 csyk fjQwth | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [11 empty] | 1 | Completed | Phase -1 | Purnea
58 | SSSM-25-3 | vjfj;k | नरपतगंज | 3 | ,e0,l0 pUnk | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [10 empty] | 1 |  |  | Phase -1 | Purnea
59 | SSSM-26(A) | vjfj;k | रानीगंज | 1 | ,e0,l0 gjhnk,iqj | Krishna Ranjan Kumar, Araria | [11 empty] | 1 | Completed | Phase -1 | Purnea
60 | SSSM-26(B) | vjfj;k | रानीगंज | 1 | ,e0,l0 ukjk;.kiqj | MD ARFIN, 9006212706 | [10 empty] | 1 |  |  | Phase -1 | Purnea
61 | SSSM-26(C) | vjfj;k | रानीगंज | 1 | ;w0,e0,l0 nqekfj;k ckyd | MD ARFIN, 9006212706 | [10 empty] | 1 |  |  | Phase -1 | Purnea
62 | SSSM-27(A) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 vekSuk | KRISHNA RANJAN KUMAR,9939662452 | [11 empty] | 1 | Completed | Phase -1 | Purnea
63 | SSSM-27(B) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 iq.kZnkgk | CHANDAN ABHISHEK,9431284224 | [11 empty] | 1 | Completed | Phase -1 | Purnea
64 | SSSM-28(A) | vjfj;k | सिक्टी | 1 | ,e0,l0 xksjkxPN | Praveen, Araria | [11 empty] | 1 | Completed | Phase -1 | Purnea
65 | SSSM-28(B) | vjfj;k | सिक्टी | 1 | ;w0,e0,l0 fnefg;k | Md. Iftakhar Alam | [10 empty] | 1 |  |  | Phase -1 | Purnea
66 | SSSM-29 | vjfj;k | सिक्टी | 1 | ,e0,l0 ispkSyh | KUNAL KUSH | [7 empty] | 1 | [5 empty] | Phase -1 | Purnea
67 | SSSM-21(A) | if'pe pEikj.k | सिरिसिया | 1 | e0fo0 fljfl;k | KISHOR KUMAR,8298437834 | [10 empty] | 1 |  |  | Phase -1 | Tirhut West
68 | SSSM-21(B) | if'pe pEikj.k | बेहरा | 1 | e0fo0 >qedk mnwZ | MS SARASWATI COMPANY,9431491241 | [11 empty] | 1 |  | Phase -1 | Tirhut West
69 | SSSM-21(C) | if'pe pEikj.k | सूर्यपुर | 1 | mŒ ekŒ foŒ] Hkokuhiqj mnZw | MS SARASWATI COMPANY,9431491241 | [9 empty] | 1 |  |  |  | Phase -1 | Tirhut West
70 | SSSM-22(A) | if'pe pEikj.k | तेलपुर | 1 | m0e0fo0 rsyiqj ckyd | M/S BHATRDWAJ CONSTRUCTION |  |  | 1 | [9 empty] | Land not available | Phase -1 | Tirhut West
71 | SSSM-22(B) | if'pe pEikj.k | देउरवा | 1 | e0fo0 nsmjok | Ashukla | [10 empty] | 1 |  |  | Phase -1 | Tirhut West
72 | SSSM-22(C) | if'pe pEikj.k | धोबनी धर्मपुर | 1 | m0e0fo0 eqlgjh | SANJAY KUMAR MISHRA, 9546215798 | [10 empty] | 1 |  |  | Phase -1 | Tirhut West
73 | SSSM-22(D) | if'pe pEikj.k | मठिया | 1 | e0fo0 efB;k | AWADHESH SHUKLA, 9431203836 | [11 empty] | 1 | Completed | Phase -1 | Tirhut West
74 | SSSM-23(A) | if'pe pEikj.k | रखही | 1 | m0e0fo0 pEikj.k | SHAKAL DEO MISHRA,9006385958 | [11 empty] | 1 | Completed | Phase -1 | Tirhut West
75 | SSSM-23(B) | if'pe pEikj.k | शेरहवा | 1 | e0fo0 fllok cgqvjok | RAJ KISHORE AKELA,9430642227 | [11 empty] | 1 | Completed | Phase -1 | Tirhut West
76 | SSSM-23(C) | if'pe pEikj.k | पुरैनिया हरसरी | 1 | m0e0fo0 dksbZjxkok | SANJAY KUMAR MISHRA, 9546215798 |  |  | 1 | [9 empty] | Land not available | Phase -1 | Tirhut West
77 | SSSM-24(A) | if'pe pEikj.k | चैहटी | 1 | e0fo0 lkSdV | GYASUL AZAM, 9199932786 | [10 empty] | 1 |  | 50'X80' | Phase -1 | Tirhut West
78 | SSSM-24(B) | if'pe pEikj.k | मधुरि | 1 | m0e0fo0 idqgok iwohZ | GYASUL AZAM, 9199932786 | [10 empty] | 1 |  |  | Phase -1 | Tirhut West
79 | SSSM-30-1 | njHkaxk | दरभंगा सदर | 1 | e0fo0 Bdqjfu;k¡ | RAJENDRA PRASAD, 8797539347 | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
80 | SSSM-30-2 | njHkaxk | दरभंगा सदर | 2 | e0fo0 da'kh | RAJENDRA PRASAD, 8797539347 | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
81 | SSSM-31-1 | njHkaxk | मनीगाछी | 1 | e0fo0 pdfpUrkef.kiqj | S K CONSTRUCTION AND COMPANY,9471006199 | [10 empty] | 1 |  |  | Phase -1 | Darbhanga
82 | SSSM-32-1 | njHkaxk | अलीनगर | 1 | mnwZ e0fo0 vyhuxj | AJAY KUMAR PATHAK,9431034060 | [10 empty] | 1 |  |  | Phase -1 | Darbhanga
83 | SSSM-33-1 | njHkaxk | जाले | 1 | e0fo0 tgkxhj Vksy | SANJAY KUMAR, 8521954601 | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
84 | SSSM-33-2 | njHkaxk | जाले | 2 | e0fo0 vfg;kjh xksV | SANJAY KUMAR, 8521954601 | [7 empty] | 1 | [5 empty] | Phase -1 | Darbhanga
85 | SSSM-34(A) | njHkaxk | सिंहवाड़ा | 1 | e0fo0 jktks | BHUSAN KUMAR,9631681894 | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
86 | SSSM-34(B) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 cgqvkjk | SachinKhandelwal | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
87 | SSSM-34(C) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 xkSjhukFk czgeiqj | SachinKhandelwal | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
88 | SSSM-35(A) | njHkaxk | केवटी | 1 | e0fo0 cjgh | OM SHREE CONSTRUCTION, 9934426934 |  |  |  |  | 1 | [7 empty] | Land Dispute | Phase -1 | Darbhanga
89 | SSSM-35(B) | njHkaxk | केवटी | 1 | m0e0fo0 ykyxat | Rajesh Kumar, 9334374660 | [11 empty] | 1 | Completed | Phase -1 | Darbhanga
90 | SSSM-36-1 | njHkaxk | किरतपुर | 1 | e0fo0 fdjriqj | OM SHREE CONSTR. BEGUSARAI | [6 empty] | 1 | [6 empty] | Phase -1 | Darbhanga
91 | SSSM-37-1 | njHkaxk | गौराबौराम | 1 | e0fo0 ckSjke | OM SHREE CONSTR. BEGUSARAI | [7 empty] | 1 | [5 empty] | Phase -1 | Darbhanga
Total No. of SSSM (Phase-1) |  |  |  | 91 |  |  | 0 | 0 | 8 | 1 | 2 | 1 | 2 | 8 | 0 | 2 | 29 | 38

## Phase-2
BSEIDC Ltd. , Patna
Physical status of SSSM (Phase-2)
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Physical Status | [9 empty] | Remarks | Session | Division
[9 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[13 empty] | LL | RL | LL | RL
1 | SSSM-47(A) | fd'kuxat | cgknqjxat | 1 | e0 fo0 HkheVksyk | KAUSHAL KUMAR | [9 empty] | 1 |  |  |  | Phase-2 | Purnea
2 | SSSM-47(B) | fd'kuxat | cgknqjxat | 2 | mŒ eŒ foŒ eaMyVksyk Mksgj | MD ANZAR ALAM | [9 empty] | 1 |  |  |  | Phase-2 | Purnea
3 | SSSM-48-1 | fd'kuxat | fd'kuxat | 1 | e0 fo0 ikuhlky | Cancel | [11 empty] | 1 | Double Scheme. Match school name to group no. SSS-95 on COMPLETED | Phase-2 | Purnea
4 | SSSM-49(A) | fd'kuxat | dkspk/kkeu | 1 | m0 e0 fo0 dUgS;kckM+h | MANOJ KUMAR | [10 empty] | 1 |  |  | Phase-2 | Purnea
5 | SSSM-49(B) | fd'kuxat | dkspk/kkeu | 2 | m0 e0 fo0 eksgjk | BHOLINATH RAY |  |  |  |  | 1 | [8 empty] | Phase-2 | Purnea
6 | SSSM-49 ( C) | fd'kuxat | dkspk/kkeu | 3 | m0 e0 fo0 gfjHkk"kk | MD. ZULQUER NAIN | [10 empty] | 1 |  |  | Phase-2 | Purnea
7 | SSSM-50 (A) | fd'kuxat | iksfB;k | 1 | m0 e0 fo0 tkyw pkSd | No Bidder | [5 empty] | 1 | [6 empty] | Double Scheme. Match school name to group no. SSS-96 on Plinth Level | Phase-2 | Purnea
8 | SSSM-50 (B) | fd'kuxat | iksfB;k | 2 | m0 e0 fo0 lksukiwj | WALKS N WALKS | [9 empty] | 1 |  |  |  | Phase-2 | Purnea
9 | SSSM-50 ( C) | fd'kuxat | iksfB;k | 3 | m0 e0 fo0 HksykxkNh chjiqj | VATS INFRATECH PVT. LTD. | [7 empty] | 1 |  |  |  |  | Double Scheme. Match school name to group no. SSS-96 on GROUND FLOOR ROOF LEVEL | Phase-2 | Purnea
10 | SSSM-51 | fd'kuxat | VsjkxkPN | 1 | m0 e0 fo0 vkfnoklh Vksyk Hkksjgk | Pawan Kumar Agarwal | [7 empty] | 1 | [5 empty] | Phase-2 | Purnea
11 | SSSM-52 (A) | fd'kuxat | Bkdqjxat | 1 | m0 e0 fo0 ikapxkNh | Santosh agrawal | [7 empty] | 1 |  |  |  |  | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR LINTER LEVEL | Phase-2 | Purnea
12 | SSSM-52 (B) | fd'kuxat | Bkdqjxat | 2 | m0 e0 fo0 yks/kk | Santosh agrawal | [6 empty] | 1 | [5 empty] | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR LINTER LEVEL | Phase-2 | Purnea
13 | SSSM-52 ( C) | fd'kuxat | Bkdqjxat | 3 | e0 fo0 csgqyMkaxh | Santosh agrawal | [7 empty] | 1 |  |  |  |  | Double Scheme. Match school name to group no. SSS-92 on GROUND FLOOR ROOF LEVEL | Phase-2 | Purnea
14 | SSSM-38 | lhrke<+h | cktiÍh | 1 | ,e0 ,l0 fcyfg;k | Shree shiva Construction dist- muzaffarpur | [10 empty] | 1 |  | External Plaster , Grill Fitting Done Internal Plaster FF Running | Phase-2 | Tirhut East
15 | SSSM-41 | lqikSy | clariqj | 1 | e/; fo¦ky; ujirV~Vh | Madan kumar singh |  |  | 1 | [9 empty] | Not Started | Phase-2 | Koshi
16 | SSSM-42 (A) | xksikyxat | Fkkos | 1 | ,e0 ,l0 lsejk | PAWAN CONSTRUCTION | [10 empty] | 1 |  |  | Phase-2 | Saran
17 | SSSM-42 (B) | xksikyxat | Fkkos | 1 | ;w0 ,e0 ,l0 ukjk;.kiqj | GIRIDHAR GOPAL CONS. |  |  | 1 | [9 empty] | Land not available | Phase-2 | Saran
18 | SSSM-43 (A) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 lariqj | kumar manash construction |  |  | 1 | [9 empty] | Land not available | Phase-2 | Saran
19 | SSSM-43 (B) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 'ks[kijlk | Savitri Technocrates pvt. Ltd | [11 empty] | 1 | Completed | Phase-2 | Saran
20 | SSSM-43 (C ) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 dksygqvk | Savitri Technocrates pvt. Ltd | [11 empty] | 1 | Completed | Phase-2 | Saran
21 | SSSM-44 (A) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 gjiqj | sai Highway & builders pvt.ltd | [8 empty] | 1 |  |  |  |  | Phase-2 | Saran
22 | SSSM-44 (B) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 ewjkedlwniqj | Cancel | [11 empty] | 1 | Double Scheme. Match school name to group no. SSS-352 on COMPLETED | Phase-2 | Saran
23 | SSSM-45 (A) | ckadk | /kqjS;k | 1 | m0 e0 fo0 pyuk | Marcominfra Pvt. Ltd., 9934361315 |  |  | 1 | [10 empty] | Phase-2 | Bhagalpur
24 | SSSM-45 (B) | ckadk | /kqjS;k | 2 | m0 e0 fo0 rkfgjiqjk dU;k | Chitragupta construction | [7 empty] | 1 | [5 empty] | Phase-2 | Bhagalpur
25 | SSSM-45 (C ) | ckadk | /kqjS;k | 3 | m0 e0 fo0 vfgjks | Chitragupta construction | [10 empty] | 1 |  | G+2, DELAY DUE TO CHANGE IN DRAWING. Second Floor R.L | Phase-2 | Bhagalpur
26 | SSSM-46-1 | Hkkxyiqj | lugkSyk | 1 | e0 fo0 rsyokM+k | Baba Hans Construction | [11 empty] | 1 | Completed | Phase-2 | Bhagalpur
27 | SSSM-39 (A) | e/kqcuh | jfgdk | 1 | ,e0 ,l0 elufx;k | RAMDINESH SINGH |  |  | 1 | [9 empty] | No Location found | Phase-2 | Darbhanga
28 | SSSM-39 (B) | e/kqcuh | jfgdk | 2 | ,e0 ,l0 eyufx;k | RAMDINESH SINGH | [11 empty] | 1 | Completed | Phase-2 | Darbhanga
29 | SSSM-39 (C ) | e/kqcuh | jfgdk | 3 | ;w0,e0,l0 ckNVksy jkeiqj | RAMDINESH SINGH | [11 empty] | 1 | Completed | Phase-2 | Darbhanga
30 | SSSM-40-1 | e/kqcuh | dyqvkgh | 1 | ,e0 ,l0 eyey | RAMDINESH SINGH | [10 empty] | 1 |  |  | Phase-2 | Darbhanga
Total No. of SSSM (Phase-2) | [8 empty] | 5 | 0 | 1 | 1 | 1 | 5 | 1 | 3 | 6 | 7

## Phase-3,4,5
BSEIDC, PATNA
Progress report for the construction of SSSM (Phase-3,4 & 5)
Sl.No. | Gr. No | Division | EC | Name of District | Name of Block | Panchayat | S.N. | Name of School | Name of AgencyDate of Tender | A/A (Rs. In Lakh) | T/S(Rs. In Lakh) | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Tender Comitt. | Exec. Comm. | L.O.A | Contract Price (Rs. In Lakh) | Performance Security (Rs. In Lakh) | Date of Verification for Earnest Money issu to | Verification for Earnest Money Recived Date | Date of Submission (P.S) | verification for P.S. issued to Bank/P.O | verification received date | Aggrement No & date | Time of Completion | Retender |  | Retender | Tender Process | Physical Status | [9 empty] | Agreement Amount (in Lakhs) | Fin. Exp. (in lakh) | Financial Achievement (%) | Remarks | Session
[28 empty] | Technical Bid Opening | Fin. Bid opening |  |  | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[36 empty] | LL | RL | LL | RL
1 | SSSM-270 | Purnea | 96 | Katihar | dks<+k |  |  | eŒ foŒ ijekuUniqj | MOTILAL AGARWAL |  |  | 128.975 | [5 empty] | 9354/3.10.16 | [7 empty] | 216 SBD OF 2016-17 (16.02.17) | [13 empty] | 1 |  | 116.0775 |  |  |  | 3
2 | SSSM-271 | Purnea | 96 | Katihar | dks<+k |  |  | mRØŒ eŒ foŒ ckSjk | OASIS CREATIVE CONS. |  |  | 128.975 | [5 empty] | 9353/3.10.16 | [7 empty] | 175 SBD OF 2016-17 (24.01.17) | [9 empty] | 1 | [5 empty] | 116.0775 |  |  |  | 3
3 | SSSM-272 | Purnea | 96 | Katihar | dknok |  |  | mRØŒ eŒ foŒ lkxjFk | MOTILAL AGARWAL |  |  | 131.678 | [5 empty] | 9355/3.10.16 | [7 empty] | 217 SBD OF 2016-17 (16.02.17) | [12 empty] | 1 |  |  | 118.5102 |  |  |  | 3
4 | SSSM-273 | Purnea | 96 | Katihar | cyjkeiqj |  |  | mRØŒ eŒ foŒ lnh;u vkneiqj | [21 empty] | 1 | [14 empty] | TO BE RETENDER | 3
5 | SSSM-274 | Purnea | 96 | Katihar | ckjlksbZ |  |  | eŒ foŒ NksxM+k | EXCELLENT CONSTRUCTION |  |  | 135.279 | [5 empty] | 9356/3.10.16 | [7 empty] | 51 SBD of 2017-18 (27/05/2017) | [5 empty] | 1 | [9 empty] | 121.7511 |  |  |  | 3
6 | SSSM-275 | Purnea | 96 | Katihar | ckjlksbZ |  |  | eŒ foŒ ekykikM+k | RANA BRIJESH PRASAD |  |  | 133.966 | [5 empty] | 9357/3.10.16 | [18 empty] | 1 | [8 empty] | 3
7 | SSSM-276 | Purnea | 96 | Katihar | ckjlksbZ |  |  | eŒ foŒ d.kZiqj | RANA BRIJESH PRASAD |  |  | 133.791 | [5 empty] | 9395/3.10.16 | [14 empty] | 1 | [12 empty] | 3
8 | SSSM-277 | Purnea | 96 | Katihar | ckjlksbZ |  |  | mŒ eŒ foŒ gkV cyjkeiqj | UMAKANT SINGH |  |  | 133.791 | [5 empty] | 9396/3.10.16 | [15 empty] | 1 | [11 empty] | 3
9 | SSSM-278 | Purnea | 96 | Katihar | vkteuxj |  |  | eŒ foŒ ckywxat | [21 empty] | 1 | [14 empty] | MATCH WITH SSSM-4C | 3
10 | SSSM-279 | Purnea | 96 | Katihar | vkteuxj |  |  | eŒ foŒ eqdqfj;k | [23 empty] | 1 | [12 empty] | MATCH WITH USSS-140A | 3
11 | SSSM-280 | Purnea | 96 | Katihar | vkteuxj |  |  | eŒ foŒ ltuk | [23 empty] | 1 | [12 empty] | LAND NOT LOCATED | 3
12 | SSSM-281 | Purnea | 96 | Katihar | cjkjh |  |  | eŒ foŒ cfd;k | UMESH KR SINGH |  |  | 128.975 | [5 empty] | 9529/5.10.16 | [15 empty] | 1 | [11 empty] | 3
13 | SSSM-282 | Purnea | 96 | Katihar | cjkjh |  |  | mPp fo¦ky; ej[kkgk] ckyw?kkV] nqxkZiqj | UMAKANT SINGH |  |  | 128.975 | [5 empty] | 9530/5.10.16 | [13 empty] | 1 | [13 empty] | 3
14 | SSSM-288 | Darbhanga | 96 | Darbhanga |  |  |  | Shafi Muslim High School, Benta, District -Darbhanga | M/S MAHMMAD KAISER(L) |  |  | 130.66 | [5 empty] | 10744/08.11.16 | [13 empty] | 1 | [13 empty] | 3
15 | SSSM-289 | Darbhanga | 96 | Darbhanga |  |  |  | M.K.P. Vidyapati High School, Laheriasarai, District -Darbhanga | BHOLA SINGH(L) | [20 empty] | 1 | [14 empty] | TO BE RETENDER | 3
16 | SSSM-290 | Darbhanga | 96 | Darbhanga |  |  |  | Vasudev Mishra High School, Simri, District - Darbhanga | DAYARAM SINGH(L_) |  |  | 130.66 | [5 empty] | 10747/08.11.16 | [7 empty] | 108 SBD OF 16-17(06.12.16) | [13 empty] | 1 |  | 117.594 | 24.66 | 20.9705 |  | 3
17 | SSSM-291 | Darbhanga | 96 | Darbhanga |  |  |  | (+2) M.A.R.M. High School , Lalbagh ,District –Darbhanga | GIRDHARI LAL PODDAR(L) |  |  | 130.66 | [5 empty] | 10748/08.11.16 | [16 empty] | 1 | [10 empty] | 3
18 | SSSM-292 | Darbhanga | 96 | Darbhanga |  |  |  | Ramanand Mishra Balika (+2) School, Laheriasarai District -Darbhanga | ANOJ INTERPRISES(L) | [8 empty] | 3538/13.04.17 | [13 empty] | 1 | [13 empty] | 3 | 2 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 590.0103 | 24.66 | 20.9705
19 | SSSM-283 | Tirhut West | 97 | Vaishali |  |  |  | High school, Sherpur Jalal,Block Chakra kalan, district Vaisali. | ROHIT RAJ CONS.(L) |  |  | 129.166 | [5 empty] | 10746/08.11.16 | [7 empty] | 197 SBD OF 2016-17 (7.02.17) | [8 empty] | 1 | [6 empty] | 116.2494 | 20.35 | 17.5055 |  | 4
20 | SSSM-284 | Tirhut West | 97 | Vaishali |  |  |  | High school,Taal, Sehan, Block Chakra kalan, district Vaisali. | KUMARI SINDHU(L) |  |  | 129.166 | [5 empty] | 10745/08.11.16 | [7 empty] | 219 SBD OF 2016-17 (17.02.17) | [13 empty] | 1 |  | 116.2494 | 17.83 | 15.3377 |  | 4
21 | SSSM-285 | Saran | 97 | Gopalganj |  |  |  | High school Indrawan Bairan, Block Thawe district Gopalganj. | RAM PUKAR PRASAD(P) |  |  | 129.4444 | [5 empty] | 10449/29.10.16 | [7 empty] | 151 SBD OF 2016-17 (13.01.17) | [10 empty] | 1 |  |  |  |  | 116.4996 |  |  |  | 4
22 | SSSM-286 | Saran | 97 | Gopalganj |  |  |  | High school Devapur Purdil, block manjha,Distt.-Gopalganj | ANOJ INTERPRISES(L) |  |  | 130.236 | [5 empty] | 3035/13.4.17 | [13 empty] | 1 | [13 empty] | 4
23 | SSSM-287 | Saran | 97 | Gopalganj |  |  |  | High school Pakri Srikant, block Uchka Gaon, district Gopalganj. | MS ANOJ ENTERPRISES(p) |  |  | 130.628 | [5 empty] | 3036/13.04.17 | [13 empty] | 1 | [13 empty] | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 348.9984 | 38.18 | 32.8432 | 0 | 20
24 | SSSM-312 | Bhagalpur | 107 | Bhagalpur |  | Sanhaula |  | High School at Telaunadha | High School at Telaunadha | Sai Highway And Builders pvt ltd | [30 empty] | 1 | 1 | 104.035 | 99.9001 | Double Scheme. Match school name to group no. SSS-238 on COMPLETED | 5
25 | SSSM-307 | Darbhanga | 107 | Madhubani |  |  |  | High School at Malangiya | DELTA ENTERPRISES 9990845601 |  |  |  | 133.643 |  |  |  |  | 948/7.2.17 | [22 empty] | 1 |  |  |  | Double Scheme. Match school name to group no. SSSM-on COMPLETED | 5
26 | SSSM-308 | Darbhanga | 107 | Madhubani | Rahika |  |  | High School at Laxmipur | SANJEEV SHARMA 9470034042 |  |  |  | 133.735 |  |  |  |  | 951/7.02.17 | [13 empty] | 1 | [13 empty] | 5
27 | SSSM-309 | Darbhanga | 107 | Madhubani |  |  |  | High School at Rampur | [32 empty] | 1 |  |  |  |  | 5
28 | SSSM-310 | Darbhanga | 107 | Madhubani |  |  |  | High School at Malmal Dakshin | [31 empty] | 1 | [5 empty] | 5
29 | SSSM-311 | Darbhanga | 107 | Madhubani | Madhubani (Town) |  |  | High School at Madhopur | ARVIND THAKUR 9939753735 |  |  |  | 133.733 |  |  |  |  | 953/7.02.17 | [13 empty] | 1 | [13 empty] | 5
30 | SSSM-293 | Tirhut West | 107 | East Champaran | Ramgarhwa |  |  | High School Building at Murla | Virendra Kumar Chaudhari, East Champaran Bihar- | [31 empty] | 1 | 109.8985 | 73.63 | 67 | Double Scheme. Match school name to group no. SSS-5 on COMPLETED | 5
31 | SSSM-294 | Tirhut West | 107 | East Champaran | Dhaka |  |  | Upgraded High School Building at Bardhharwa Fateh Mohammad | [23 empty] | 1 | [13 empty] | 5
32 | SSSM-295 | Tirhut West | 107 | East Champaran |  |  |  | Upgraded High School Building at Phulwaria | BHAWANI BUILDCON AND PROJECT PVT LTD | [27 empty] | 1 |  |  |  |  | 238.7319 | 28.04 | 11.75 |  | 5
33 | SSSM-296 | Tirhut West | 107 | East Champaran |  |  |  | High School Building at Kundwa Chainpur | RANJAN GAYATRI CONSTRUCTION PRIVATE LIMITED 9473000873 |  |  | 132.73 | [5 empty] | 256/7.02.17 | [7 empty] | 12 SBD of 2017-18 (19.04.17) | [8 empty] | 1 | [6 empty] | 119.4588 |  |  |  | 5
34 | SSSM-297 | Tirhut West | 107 | East Champaran |  |  |  | Upgraded High School Building at Musoradha | MS S K ENTERPRISES 9431636923 |  |  | 132.732 | [5 empty] | 955/7.2.17 | [15 empty] | 1 | [11 empty] | 5
35 | SSSM-298 | Tirhut West | 107 | East Champaran |  |  |  | Upgraded High School at saphi | VIJAY KUMAR SINGH 9973980351 |  |  | 132.732 | [5 empty] | 949/7.2.17 | [7 empty] | 60 SBD of 17-18 (23.005.17) | [9 empty] | 1 | [5 empty] | 119.4588 |  |  |  | 5
36 | SSSM-299 | Tirhut West | 107 | East Champaran |  |  |  | Upgraded High School at Chandanwada (Urdu) | RANJAN GAYATRI CONSTRUCTION PRIVATE LIMITED 9473000873 |  |  | 132.732 | [5 empty] | 957/7.2.17 | [7 empty] | 13 SBD of 2017-18 (19.04.17) | [7 empty] | 1 | [7 empty] | 119.4588 |  |  |  | 5
37 | SSSM-300 | Tirhut West | 107 | East Champaran | Banjaria |  |  | Upgraded High School Building at Ajgarwa | DESHBANDHU KUMAR SINGH,7739855654 | [31 empty] | 1 | 112.435 | 60.19 | 53.53 | Double Scheme. Match school name to group no. USSS-176 on COMPLETED | 5
38 | SSSM-301 | Tirhut West | 107 | East Champaran | Narkatiya/Chodadano |  |  | High School Building at Pakariya(Urdu) | ROHAN CONSTRUCTION PRIVATE LIMITED 9661590724 |  |  | 132.786 | [5 empty] | 954/7.02.17 | [16 empty] | 1 | [10 empty] | 5
39 | SSSM-302 | Tirhut West | 107 | East Champaran | Aadapur |  |  | High School at Nakardeye | HARIOM CONSTRUCTION 7739513614, 8434352330 |  |  | 133.982 | [5 empty] | 852/7.02.17 | [13 empty] | 1 | [13 empty] | 5
40 | SSSM-303 | Tirhut West | 107 | East Champaran |  |  |  | High School at Dhabiya Dakshin | VIJAY KUMAR SINGH 9973980351 |  |  | 133.982 | [5 empty] | 950/7.02.17 | [7 empty] | 61 SBD of 17-18 (23.005.17) | [9 empty] | 1 | [5 empty] | 120.5838 |  |  |  | 5
41 | SSSM-304 | Tirhut West | 107 | East Champaran |  |  |  | High School at Laxmipur | Vijay Kumar Singh Persouni East Champaran-9471296790 | [31 empty] | 1 |  | 148.8 |  | Double Scheme. Match school name to group no. SSS-14 on COMPLETED | 5
42 | SSSM-305 | Tirhut West | 107 | East Champaran |  |  |  | High School at Bhawanipur Bazar | [31 empty] | 1 |  |  |  |  | Double Scheme. Match school name to group no. SSS-15 on Finishing Stage | 5
43 | SSSM-306 | Tirhut West | 107 | East Champaran | Aadapur |  |  | High Schhol at Boldarwa | HARIOM CONSTRUCTION 7739513614, 8434352330 |  |  | 133.982 | [5 empty] | 958/07.02.17 | [13 empty] | 1 | [13 empty] | 5 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 6 | 941.0256 | 414.695 | 232.1801 | 0
Total No. of SSSM (Phase-3,4 & 5) | [7 empty] | 43 | [21 empty] | 3 | 0 | 13 | 1 | 4 | 4 | 3 | 3 | 0 | 1 | 5 | 6
Note on AR45: admin: Total Const. Exps. Of SSS 92 charged to SSSM 52 A

## Not Started (hidden)
BSEIDC Ltd. , Patna
Pending Status of SSSM (Phase-1) reason of Not Started
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Not Started | [9 empty] | Remarks | Session | Division
1 | SSSM-1-3 | Katihar | अमदाबाद | 3 | e0fo0 ikjfn;kjk | Umakant Singh, 9431096239 |  |  | 1 | [9 empty] | LAND MADE AVAILABLE ON THE BANK OF GANGA RIVER. (DANGER OF EROSION) | Phase -1 | Purnea
2 | SSSM-3(A) | Katihar | बारसोई | 1 | e0fo0 XokyVksyh | RANA BIRESH PRATAP SINGH, 9430683578 |  |  | 1 | [9 empty] | 7 FEET DEEP WATER LOGGED LAND MADE AVAILABLE. | Phase -1 | Purnea
3 | SSSM-3(C) | Katihar | बारसोई | 1 | m0e0fo0 Qqgkxk¡o | R. P. Agarwal , Katihar |  |  | 1 | [9 empty] | Land not available 14 feet wide 80 feet length land available but it is being used as passage/play ground) letter has been sent to DEO for Land. | Phase -1 | Purnea
4 | SSSM-4(A) | Katihar | बलरामपुर | 1 | e0fo0 efydiqj | MUKESH KUMAR, 9431658565 |  |  | 1 | [9 empty] | Land enchroched, letter has been issued to DEO to solve the problem. | Phase -1 | Purnea
5 | SSSM-10-2 | Katihar | बरारी | 2 | e0fo0 Hk.Mkjry | BIRENDRA KUMAR SINGH, 9473440405 |  |  | 1 | [9 empty] | Land not registered in the name of school. | Phase -1 | Purnea
6 | SSSM-14(B) | Purnea | कसबा | 1 | e0fo0 yN.kiqj | M/S Excellent Construction |  |  | 1 | [9 empty] | Donners objection, Letter issued to DPO | Phase -1 | Purnea
7 | SSSM-22(A) | West Champaran | तेलपुर | 1 | m0e0fo0 rsyiqj ckyd | M/S BHATRDWAJ CONSTRUCTION |  |  | 1 | [9 empty] | Land not available | Phase -1 | Tirhut West
8 | SSSM-23(C) | West Champaran | पुरैनिया हरसरी | 1 | m0e0fo0 dksbZjxkok | SANJAY KUMAR MISHRA, 9546215798 |  |  | 1 | [9 empty] | Land not available | Phase -1 | Tirhut West
Pending list of total No. of SSSM (Phase-1) | [6 empty] | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending Status of SSSM (Phase-2) (EC - 86) reason of Not Started
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Not Started | [9 empty] | Remarks | Session | Division
1 | SSSM-45 (A) | Banka | /kqjS;k | 1 | m0 e0 fo0 pyuk | Marcominfra Pvt. Ltd., 9934361315 |  |  | 1 | [10 empty] | Phase-2 | Koshi
2 | SSSM-42 (B) | Gopalganj | Fkkos | 1 | ;w0 ,e0 ,l0 ukjk;.kiqj | GIRIDHAR GOPAL CONS. |  |  | 1 | [9 empty] | Land not available | Phase-2 | Saran
3 | SSSM-43 (A) | Gopalganj | eka>k | 1 | ;w0 ,e0 ,l0 lariqj | kumar manash construction |  |  | 1 | [9 empty] | Land not available | Phase-2 | Saran
4 | SSSM-39 (A) | Madhubani | jfgdk | 1 | ,e0 ,l0 elufx;k | RAMDINESH SINGH |  |  | 1 | [9 empty] | No Location found | Phase-2 | Bhagalpur
5 | SSSM-41 | Supual | clariqj | 1 | e/; fo¦ky; ujirV~Vh | Madan kumar singh |  |  | 1 | [9 empty] | Not Started | Phase-2 | Darbhanga
Pending list of SSSM (Phase-2) | [6 empty] | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Progress report for the construction of SSSM (Phase-3,4 & 5) EC-96, 97 & 107
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Retender | Tender Process | Not Started | [9 empty] | Remarks | Session | Division
1 | SSSM-288 | Darbhanga |  | 1 | Shafi Muslim High School, Benta, District -Darbhanga |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
2 | SSSM-292 | Darbhanga |  | 1 | Ramanand Mishra Balika (+2) School, Laheriasarai District -Darbhanga |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
3 | SSSM-294 | East Champaran | Dhaka | 1 | Upgraded High School Building at Bardhharwa Fateh Mohammad |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
4 | SSSM-302 | East Champaran | Aadapur | 1 | High School at Nakardeye |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
5 | SSSM-306 | East Champaran | Aadapur | 1 | High Schhol at Boldarwa |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
6 | SSSM-286 | Gopalganj |  | 1 | High school Devapur Purdil, block manjha,Distt.-Gopalganj |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
7 | SSSM-287 | Gopalganj |  | 1 | High school Pakri Srikant, block Uchka Gaon, district Gopalganj. |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
8 | SSSM-274 | Katihar | ckjlksbZ | 1 | eŒ foŒ NksxM+k |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
9 | SSSM-279 | Katihar | vkteuxj | 1 | eŒ foŒ eqdqfj;k |  |  |  | 1 | [9 empty] | MATCH WITH USSS-140A | Phase-3,4,5
10 | SSSM-280 | Katihar | vkteuxj | 1 | eŒ foŒ ltuk |  |  |  | 1 | [9 empty] | LAND NOT LOCATED | Phase-3,4,5
11 | SSSM-282 | Katihar | cjkjh | 1 | mPp fo¦ky; ej[kkgk] ckyw?kkV] nqxkZiqj |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
12 | SSSM-308 | Madhubani | Rahika | 1 | High School at Laxmipur |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
13 | SSSM-311 | Madhubani | Madhubani (Town) | 1 | High School at Madhopur |  |  |  | 1 | [9 empty] | Not Started | Phase-3,4,5
Pending list of Total No. Of SSM (Phase-3,4,5) | [6 empty] | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0