## USSS (2011-12)
BSEIDC Ltd., Patna
Physical Status of USSS (2011-12)
S.N. | Group No. | Division | Name of District | Name of Block | S.N. | Name of School | Name of Agency | Retrender | Tender Process | Physical Status | [9 empty] | Remarks | Session
[10 empty] | Not Start | Layout | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[14 empty] | LL | RL | LL | RL
1 | USSS-26-1 | Patna East | ukyUnk |  | 1 | Middle School, Basuan | Tender Process | 1 | [11 empty] | Retender | 2011-12
2 | USSS-26-2 | Patna East | ukyUnk |  | 2 | Middle School, Malikpur | Tender Process | 1 | [11 empty] | Retender | 2011-12
3 | USSS-26-3 | Patna East | ukyUnk |  | 3 | Middle School, Mohaddinpur | Tender Process | 1 | [11 empty] | Retender | 2011-12
4 | USSS-26-4 | Patna East | ukyUnk |  | 4 | Middle School, Jagdishpur Tayari | Tender Process | 1 | [11 empty] | Retender | 2011-12
5 | USSS-26-5 | Patna East | ukyUnk |  | 5 | Middle School, Puraini | Tender Process | 1 | [11 empty] | Retender | 2011-12
6 | USSS-26-6 | Patna East | ukyUnk |  | 6 | Middle School, Lodipur | Tender Process | 1 | [11 empty] | Retender | 2011-12
7 | USSS-27-1 | Patna East | iVuk |  | 1 | Middle School, Diwra | Tender Process | 1 | [11 empty] | Retender | 2011-12
8 | USSS-27-2 | Patna East | iVuk |  | 2 | Middle School, Samstichak | Tender Process | 1 | [11 empty] | Retender | 2011-12
9 | USSS-27-3 | Patna East | iVuk |  | 3 | Middle School, Pirbarhouna | Tender Process | 1 | [11 empty] | Retender | 2011-12
10 | USSS-27-4 | Patna East | iVuk |  | 4 | Middle School, Gangachak | Tender Process | 1 | [11 empty] | Retender | 2011-12
11 | USSS-28-1 | Patna East | iVuk |  | 1 | Middle School, Karai | Shilendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
12 | USSS-29-1 | Patna East | Hkkstiqj | Barhara | 1 | Govt. Middle School, Kudariya Parshurampur | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-14 | 2011-12
13 | USSS-29-2 | Patna East | Hkkstiqj | Barhara | 2 | Upgraded Middle School, Paiga | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-15 | 2011-12
14 | USSS-29-3 | Patna East | Hkkstiqj | Ara | 3 | Upgraded Middle School, Barouli | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-16 | 2011-12
15 | USSS-29-4 | Patna East | Hkkstiqj | Ara | 4 | Middle School, Barka Dumra | Narendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
16 | USSS-29-5 | Patna East | Hkkstiqj | Garahni | 5 | Upgraded Middle School, Dadiyabag | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-18 | 2011-12
17 | USSS-29-6 | Patna East | Hkkstiqj | Koielwar | 6 | Upgraded Middle School, Bhoparpur | Tender Process | 1 | [11 empty] | Not Start. 46/2013-19 | 2011-12
18 | USSS-30-1 | Patna East | Hkkstiqj | Tarari | 1 | Middle School, Sara | Narendra kumar |  |  | 1 | [9 empty] | Not Start. 46/2013-20 | 2011-12
19 | USSS-30-2 | Patna East | Hkkstiqj | Tarari | 2 | Middle School, Bhakura | Narendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
20 | USSS-30-3 | Patna East | Hkkstiqj | Pero | 3 | Middle School, Dhanpura | Narendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
21 | USSS-30-4 | Patna East | Hkkstiqj | Sahar | 4 | Middle School, Perhap | Narendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
22 | USSS-30-5 | Patna East | Hkkstiqj | Sahar | 5 | Middle School, Nonuar | Narendra kumar |  |  | 1 | [9 empty] | Not Start | 2011-12
23 | USSS-30-6 | Patna East | Hkkstiqj | Sahar | 6 | Middle School, Purhara | Tender Process | 1 | [11 empty] | Retender | 2011-12
24 | USSS-31-1 | Patna West | बक्‍सर | ब्रहम्‍पुर | 1 | Middle School, Bhadwar | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
25 | USSS-31-2 | Patna West | बक्‍सर | ब्रहम्‍पुर | 2 | Girl Middle School, Akrasi | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
26 | USSS-32-1 | Patna West | भभुआ कैमूर | चैनपुर | 1 | Middle School, Dhardihan | KRISHNA | [7 empty] | 1 | [5 empty] | 2011-12
27 | USSS-32-2 | Patna West | भभुआ कैमूर | चॉंद | 2 | Upgraded Middle School, Chouri | KRISHNA |  |  | 1 | [9 empty] | Encrochment | 2011-12
28 | USSS-32-3 | Patna West | भभुआ कैमूर | भगवानपुर | 3 | Middle School, Dadar | KRISHNA | [10 empty] | 1 |  | Sill level of FF | 2011-12
29 | USSS-32-4 | Patna West | भभुआ कैमूर | रामपुर | 4 | Middle School, Lohandi | KRISHNA | [7 empty] | 1 | [5 empty] | 2011-12
30 | USSS-32-5 | Patna West | भभुआ कैमूर | मोहनियॉं | 5 | Middle School, Badhani | KRISHNA | [7 empty] | 1 | [5 empty] | 2011-12
31 | USSS-33-1 | Patna West | रोहतास | दावत | 1 | Middle School, Parmdiha | Tender Process |  | 1 | [10 empty] | Tender Process | 2011-12
32 | USSS-33-2 | Patna West | रोहतास | नोखा | 2 | Middle School, Hathini | Tender Process |  | 1 | [10 empty] | Tender Process | 2011-12
33 | USSS-33-3 | Patna West | रोहतास | काराकाट | 3 | Middle School, Itdhiyan | Tender Process |  | 1 | [10 empty] | Tender Process | 2011-12
34 | USSS-34-1 | Patna West | रोहतास | अकोढ़ीगोला | 1 | Middle School, Gobardhanpur | SHALINI SINGH | [7 empty] | 1 | [5 empty] | 2011-12
35 | USSS-34-2 | Patna West | रोहतास | डिहरी | 2 | Middle School, Tandwa | SHALINI SINGH | [10 empty] | 1 |  |  | 2011-12
36 | USSS-34-3 | Patna West | रोहतास | काराकाट | 3 | Middle School, Danwar | SHALINI SINGH | [10 empty] | 1 |  |  | 2011-12
37 | USSS-35-1 | Patna West | रोहतास | करहगर | 1 | Upgraded Middle School, Rehari | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
38 | USSS-35-2 | Patna West | रोहतास | रोहतास | 2 | Middle School, Majhiyawan | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
39 | USSS-35-3 | Patna West | रोहतास |  | 3 | Middle School, Ghordihi | ADMINISTRATIVE APPROVAL NOT ALLOTED | 1 | [11 empty] | Tender Process | 2011-12
40 | USSS-36-1 | Magadh | tgkukckn |  | 1 | Middle School, Ahiyasa | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
41 | USSS-36-2 | Magadh | tgkukckn |  | 2 | Middle School,Sewnon | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
42 | USSS-36-3 | Magadh | tgkukckn |  | 3 | Middle School, Dewra | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
43 | USSS-37-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Kusumbasdiha | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
44 | USSS-37-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Pandu | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
45 | USSS-38-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Gamharia | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
46 | USSS-38-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School,Sondiha | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
47 | USSS-38-3 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Raslpur | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
48 | USSS-39-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Chourahi | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
49 | USSS-39-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Sonbarsa | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
50 | USSS-39-3 | Magadh | vkSjaaxkckn |  | 3 | Middle School, Dandwan | MS MATESHWARI CONSTRUCTION, 7766886737 |  |  | 1 | [9 empty] | Not Start | 2011-12
51 | USSS-40-1 | Magadh | vkSjaaxkckn |  | 1 | Middle School, Meh | MANOJ SINGH, 9939822131, 7033944511 |  |  | 1 | [9 empty] | Not Start | 2011-12
52 | USSS-40-2 | Magadh | vkSjaaxkckn |  | 2 | Middle School, Tamoli | MANOJ SINGH, 9939822131, 7033944511 |  |  | 1 | [9 empty] | Not Start | 2011-12
53 | USSS-41-1 | Magadh | x;k |  | 1 | Middle School, Shyamnagar Nima | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
54 | USSS-41-2 | Magadh | x;k |  | 2 | Middle School, Khajuria | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
55 | USSS-41-3 | Magadh | x;k |  | 3 | Middle School, Parsawan Khurd | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
56 | USSS-41-4 | Magadh | x;k |  | 4 | Middle School, Belauti | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
57 | USSS-41-5 | Magadh | x;k |  | 5 | Middle School,Bindhua | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
58 | USSS-42-1 | Magadh | x;k |  | 1 | Middle School, Sondiha | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
59 | USSS-42-2 | Magadh | x;k |  | 2 | Middle School, Angara | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
60 | USSS-42-3 | Magadh | x;k |  | 3 | Middle School, Punakalan | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
61 | USSS-42-4 | Magadh | x;k |  | 4 | Middle School, Noni | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
62 | USSS-43-1 | Magadh | x;k |  | 1 | Upgraded Middle School, Pater | Mithlesh Kumar Singh, 9931471924 | [8 empty] | 1 |  |  |  |  | 2011-12
63 | USSS-43-2 | Magadh | x;k |  | 2 | Middle School, Bitho | Mithlesh Kumar Singh, 9931471924 |  |  | 1 | [9 empty] | Local Dispute | 2011-12
64 | USSS-44-1 | Magadh | uoknk |  | 1 | Middle School, Bardhauna | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
65 | USSS-44-2 | Magadh | uoknk |  | 2 | Upgraded Middle School, Puraini | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
66 | USSS-44-3 | Magadh | uoknk |  | 3 | Middle School, Kalound | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
67 | USSS-44-4 | Magadh | uoknk |  | 4 | Middle School, Paingari | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
68 | USSS-44-5 | Magadh | uoknk |  | 5 | Upgraded Middle School, Bhatta | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
69 | USSS-17-1 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kishanpur | Retender | 1 | [11 empty] | Retender | 2011-12
70 | USSS-17-2 | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Tarchha | Retender | 1 | [11 empty] | Retender | 2011-12
71 | USSS-18-1 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Ghanshyamchak | Retender | 1 | [11 empty] | No Bidder | 2011-12
72 | USSS-19-1 | Bhagalpur | Hkkxyiqj |  | 1 | Middle School Kalgiganj | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
73 | USSS-19-2 | Bhagalpur | Hkkxyiqj |  | 2 | Middle School Dayalpur | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
74 | USSS-19-3 | Bhagalpur | Hkkxyiqj |  | 3 | Middle School Siya | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
75 | USSS-19-4 | Bhagalpur | Hkkxyiqj |  | 4 | Middle School Kishunichak | MS Rungta Enterprises, 9431265821 | [11 empty] | 1 |  | 2011-12
76 | USSS-20-1 | Bhagalpur | ckadk |  | 1 | Middle School kairi | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
77 | USSS-20-2 | Bhagalpur | ckadk |  | 2 | Middle School Bank | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
78 | USSS-20-3 | Bhagalpur | ckadk |  | 3 | Middle School Pathdda | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
79 | USSS-21-1 | Munger | ewaxsj |  | 1 | Middle School Harinmar Bishunpur | Tender Process | 1 | [11 empty] | Retender | 2011-12
80 | USSS-21-2 | Munger | ewaxsj |  | 2 | Middle School Manik Mandal Tola | Tender Process | 1 | [11 empty] | Retender | 2011-12
81 | USSS-21-3 | Munger | ewaxsj |  | 3 | Middle School Kalyanpur | Tender Process | 1 | [11 empty] | Retender | 2011-12
82 | USSS-21-4 | Munger | ewaxsj |  | 4 | Middle School Teghara | Tender Process | 1 | [11 empty] | Retender | 2011-12
83 | USSS-21-5 | Munger | ewaxsj |  | 5 | Middle School Dhudhaladih | Tender Process | 1 | [11 empty] | Retender | 2011-12
84 | USSS-22-1 | Munger | ewaxsj |  | 1 | Middle School Ramcharit Maidan | Tender Process | 1 | [11 empty] | Retender | 2011-12
85 | USSS-22-2 | Munger | ewaxsj |  | 2 | Middle School Madhura | Tender Process | 1 | [11 empty] | Retender | 2011-12
86 | USSS-22-3 | Munger | ewaxsj |  | 3 | Middle School, Dhobai | Tender Process | 1 | [11 empty] | Retender | 2011-12
87 | USSS-22-4 | Munger | ewaxsj |  | 4 | Middle School Nabgoi | Tender Process | 1 | [11 empty] | Retender | 2011-12
88 | USSS-23-1 | Munger | y[khljk; |  | 1 | Middle School, Bahachha | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
89 | USSS-23-2 | Munger | y[khljk; |  | 2 | Middle School Tarhari | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
90 | USSS-23-3 | Munger | y[khljk; |  | 3 | Middle School Nongarh | SUGEET KUMAR,9504681342 | [10 empty] | 1 |  |  | 2011-12
91 | USSS-23-4 | Munger | y[khljk; |  | 4 | Upgraded Middle School Surari | SUGEET KUMAR,9504681342 | [6 empty] | 1 | [6 empty] | 2011-12
92 | USSS-24-1 | Munger | y[khljk; |  | 1 | Upgraded Middle School Bihraura | Tender Process | 1 | [11 empty] | Retender | 2011-12
93 | USSS-24-2 | Munger | y[khljk; |  | 2 | Middle School Pokhrama | Tender Process | 1 | [11 empty] | Retender | 2011-12
94 | USSS-24-3 | Munger | y[khljk; |  | 3 | Upgraded Middle School Dhoni Kundi | Tender Process | 1 | [11 empty] | Retender | 2011-12
95 | USSS-25-1 | Munger | 'ks[kiqjk |  | 1 | Middle School, Akrama | Epitome Construction Pvt Ltd,8935825344 | [8 empty] | 1 |  |  |  |  | 2011-12
96 | USSS-25-2 | Munger | 'ks[kiqjk |  | 2 | Upgraded Middle School, Diha | Epitome Construction Pvt Ltd,8935825344 | [7 empty] | 1 | [5 empty] | 2011-12
97 | USSS-25-3 | Munger | 'ks[kiqjk |  | 3 | Middle School, Kutout | Epitome Construction Pvt Ltd,8935825344 | [10 empty] | 1 |  |  | 2011-12
98 | USSS-45-1 | Munger | tewbZ |  | 1 | Upgraded Middle School, Harla | Tender Process | 1 | [11 empty] | Retender | 2011-12
99 | USSS-45-2 | Munger | tewbZ |  | 2 | Middle School, Kairakado | Tender Process | 1 | [11 empty] | Retender | 2011-12
100 | USSS-45-3 | Munger | tewbZ |  | 3 | Middle School, Shobhakhan | Tender Process | 1 | [11 empty] | Retender | 2011-12
101 | USSS-45-4 | Munger | tewbZ |  | 4 | Middle School, Abgila Chourasa | Tender Process | 1 | [11 empty] | Retender | 2011-12
102 | USSS-47-1 | Munger | Munger | Birpur | 1 | Middle School Parra | Tender Process | 1 | [11 empty] | Retender | 2011-12
103 | USSS-47-2 | Munger | Munger | Bakhari | 2 | Middle School Lauchhe | Tender Process | 1 | [11 empty] | Retender | 2011-12
104 | USSS-47-3 | Munger | Munger | Birpur | 3 | Middle School Kharmauli | Tender Process | 1 | [11 empty] | Retender | 2011-12
105 | USSS-47-4 | Munger | Munger | Sahebpur Kamal | 4 | Middle School Hira Tol | Tender Process | 1 | [11 empty] | Retender | 2011-12
106 | USSS-47-5 | Munger | Munger | Mansurchak | 5 | Middle School Makdhampur | Tender Process | 1 | [11 empty] | Retender | 2011-12
107 | USSS-48-1 | Munger | Munger | Begusarai | 1 | Middle School Akaha | Tender Process | 1 | [11 empty] | Retender | 2011-12
108 | USSS-48-2 | Munger | Munger | Begusarai | 2 | Middle School Bhitsari | Tender Process | 1 | [11 empty] | Retender | 2011-12
109 | USSS-10-1 | Kosi | lgjlk |  | 1 | Middle School Dhamsaina | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
110 | USSS-6-1 | Purnea | vjfj;k |  | 1 | Middle School Mangalwar Chariya | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
111 | USSS-6-2 | Purnea | vjfj;k |  | 2 | Middle School Maldwar East | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
112 | USSS-7-1 | Purnea | fd'kuxat |  | 1 | Middle School Daula | BIRENDRA KUMAR SINGH,9473440405 |  |  | 1 | [9 empty] | Not Start | 2011-12
113 | USSS-8-1 | Purnea | iwf.kZ;k¡ |  | 1 | Middle School Rupauli | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
114 | USSS-8-2 | Purnea | iwf.kZ;k¡ |  | 2 | Middle School Rampur Tilak East | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
115 | USSS-8-3 | Purnea | iwf.kZ;k¡ |  | 3 | Middle School ,Mahendra Nagar Diyara | Tender Process | 1 | [11 empty] | No Bidder | 2011-12
116 | USSS-9-1 | Purnea | dfVgkj |  | 1 | Middle School Belwa | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2011-12
117 | USSS-9-2 | Purnea | dfVgkj |  | 2 | Middle School Kharsauta | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2011-12
118 | USSS-9-3 | Purnea | dfVgkj |  | 3 | Middle School Kalyan Gaon | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2011-12
119 | USSS-9-4 | Purnea | dfVgkj |  | 4 | Middle School Rampur | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [5 empty] | 2011-12
120 | USSS-4-1 | Tirhut East | lhrke<+h |  | 1 | Middle School Sutihara | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
121 | USSS-4-2 | Tirhut East | lhrke<+h |  | 2 | Middle School Bhantawari | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
122 | USSS-4-3 | Tirhut East | lhrke<+h |  | 3 | Middle School Rajwara | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
123 | USSS-12-1 | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bariyarpur | S R CONSTRUCTIONS PVT LTD, 7739441850 | [7 empty] | 1 |  |  |  |  | Roof casting done | 2011-12
124 | USSS-12-2 | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Dhabauli | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | insufficient land 40'x65' | 2011-12
125 | USSS-12-3 | Tirhut East | eqt¶Qjiqj |  | 3 | Middle School Lakhanpur | S R CONSTRUCTIONS PVT LTD, 7739441850 |  |  | 1 | [9 empty] | insufficient land 40'x80' | 2011-12
126 | USSS-13-1 | Tirhut East | eqt¶Qjiqj |  | 1 | Middle School Bhatauna | Tender Process | 1 | [11 empty] | Retender | 2011-12
127 | USSS-13-2 | Tirhut East | eqt¶Qjiqj |  | 2 | Middle School Sirkohiya | Tender Process | 1 | [11 empty] | Retender | 2011-12
128 | USSS-15-1 | Tirhut East | oS'kkyh |  | 1 | Upgraded Middle School Panapur Silaut | Tender Process | 1 | [11 empty] | Retender | 2011-12
129 | USSS-15-2 | Tirhut East | oS'kkyh |  | 2 | Upgraded Middle School Totha | Tender Process | 1 | [11 empty] | Retender | 2011-12
130 | USSS-15-3 | Tirhut East | oS'kkyh |  | 3 | Middle School Shital Bhakurhar | Tender Process | 1 | [11 empty] | Retender | 2011-12
131 | USSS-1-1 | Tirhut West | if'pe pEikj.k |  | 1 | Govt. Middle School Kumhiya | Tender Process | 1 | [11 empty] | Retender | 2011-12
132 | USSS-1-2 | Tirhut West | if'pe pEikj.k |  | 2 | Middle School Panchgawa | Tender Process | 1 | [11 empty] | Retender | 2011-12
133 | USSS-1-3 | Tirhut West | if'pe pEikj.k |  | 3 | Middle School Donwar | Tender Process | 1 | [11 empty] | Retender | 2011-12
134 | USSS-1-4 | Tirhut West | if'pe pEikj.k |  | 4 | Ugraded middle school malahi tola | Tender Process | 1 | [11 empty] | Retender | 2011-12
135 | USSS-2-1 | Tirhut West | iwohZ pEikj.k |  | 1 | Middle School Mali | ASIANA CONSTRACT PVT LTD, 9431088485 |  |  | 1 | [9 empty] | Not Start | 2011-12
136 | USSS-2-2 | Tirhut West | iwohZ pEikj.k |  | 2 | Middle School Chand parsa | ASIANA CONSTRACT PVT LTD, 9431088485 | [10 empty] | 1 |  |  | 2011-12
137 | USSS-2-3 | Tirhut West | iwohZ pEikj.k |  | 3 | Middle School Sitalpur | ASIANA CONSTRACT PVT LTD, 9431088485 | [9 empty] | 1 |  |  |  | 2011-12
138 | USSS-3-1 | Tirhut West | f'kogj |  | 1 | Middle School Dhankaul | Tender Process | 1 | [11 empty] | Retender | 2011-12
139 | USSS-3-2 | Tirhut West | f'kogj |  | 2 | Middle School Narayanpur | Tender Process | 1 | [11 empty] | Retender | 2011-12
140 | USSS-3-3 | Tirhut West | f'kogj |  | 3 | Middle School Khairadarp | Tender Process | 1 | [11 empty] | Retender | 2011-12
141 | USSS-5-1 | Darbhanga | e/kqcuh |  | 1 | Govt. Middle School Rudrapur | Kamlesh Kumar 934808205 | [11 empty] | 1 | inugurated | 2011-12
142 | USSS-5-2 | Darbhanga | e/kqcuh |  | 2 | Govt. Middle School Bhatra Ghat | Kamlesh Kumar 934808205 | [10 empty] | 1 |  |  | 2011-12
143 | USSS-11-1 | Darbhanga | njHkaxk |  | 1 | Upgraded Middle School Raj kharwar | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
144 | USSS-11-2 | Darbhanga | njHkaxk |  | 2 | Upgraded Middle School Tilkeshwar Sthan | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
145 | USSS-11-3 | Darbhanga | njHkaxk |  | 3 | Upgraded Middle School Raipur | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
146 | USSS-16-1 | Darbhanga | leLrhiqj |  | 1 | Middle School Isar Tola | Tender Process | 1 | [11 empty] | Tender Process | 2011-12
147 | USSS-14-1 | Saran | lhoku |  | 1 | Middle School Sahadulpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [5 empty] | 1 | [7 empty] | 2011-12
148 | USSS-14-2 | Saran | lhoku |  | 2 | Middle School Gamiyar | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land not available | 2011-12
149 | USSS-14-3 | Saran | lhoku |  | 3 | Middle School Daraunda | SHIV SHANKAR SINGH CONTRACT PVT LTD | [11 empty] | 1 |  | 2011-12
150 | USSS-14-4 | Saran | lhoku |  | 4 | Middle School, Baluya | SHIV SHANKAR SINGH CONTRACT PVT LTD | [7 empty] | 1 | [5 empty] | 2011-12
151 | USSS-14-5 | Saran | lhoku |  | 5 | Middle School Barka Manjha | SHIV SHANKAR SINGH CONTRACT PVT LTD | [8 empty] | 1 |  |  |  |  | 2011-12
152 | USSS-46-1 | Saran | lhoku |  | 1 | Middle School Sikatiya | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  |  | 1 | [9 empty] | 2011-12
153 | USSS-46-2 | Saran | lhoku |  | 2 | Middle School Kilpur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [6 empty] | 1 | [6 empty] | 2011-12
154 | USSS-46-3 | Saran | lhoku |  | 3 | Middle School Pratapur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [9 empty] | 1 |  |  |  | 2011-12
155 | USSS-46-4 | Saran | lhoku |  | 4 | Middle School Shivpur Sakra | SHIV SHANKAR SINGH CONTRACT PVT LTD |  |  | 1 | [9 empty] | Land Problem | 2011-12
156 | USSS-46-5 | Saran | lhoku |  | 5 | Middle School Balaipur | SHIV SHANKAR SINGH CONTRACT PVT LTD | [8 empty] | 1 |  |  |  |  | 2011-12
Total No. of USSS (2011-12) |  |  |  |  | 156 |  |  | 90 | 3 | 27 | 1 | 0 | 1 | 2 | 11 | 4 | 2 | 9 | 6
Note on H114: Cancel