## Sheet1
BSEIDC Ltd., Patna
Physical Status for Construction of Shiksha Bhawan
S.No. | Group No. | NAME OF DISTRICT | NAME OF SCHOOL | NAME OF AGENCY | Estimated Amount | L.O.A | Date of Aggrement | Retender | Tender Process | Not Start | Layout | Foundation | PL | Ground floor |  | 1st floor |  | 2nd Floor |  | Finishing | Complete | Agreement Amount (in Lakh) | Fin. Exp. (in lac) | Remarks | Division
[14 empty] | LL | RL | LL | RL | LL | RL
1 | SB-1 | Darbhanga | Shiksha Bhawan Darbhanga | Malti Singh | 212.2208 | ISSUED & 19/09/2012 | 82SBD of 2012-13&08/01/2013 | [13 empty] | 1 | 209.759 | 171.14 |  | Darbhanga
2 | SB-2 | Gaya | Shiksha Bhawan Gaya | Kaushlendra Kumar | 214 | 5933/01-11-14 | 767SBD of 2014-15 & 18/03/2015 | [13 empty] | 1 | 209.5319 | 35.65 |  | Magadh
3 | SB-3 | Vaishali | Shiksha Bhawan Vaishali | Ashutosh Kumar (7782969945) | 228 | 6983/8-12-14 |  |  |  | 1 | [13 empty] | Land not available | Tirhut East
4 | SB-4 | Saharsa | Shiksha Bhawan Saharsa | Ashok Kumar | 241 | 6982/8-12-14 | 108SBD of 2015-16 & 10/06/2015 | [12 empty] | 1 |  | 236.3615 | 105.36 |  | Koshi
5 | SB-5 | Kaimur | Shiksha Bhawan Kaimur | Navnirman Cons. | 225 | 41 Dated/3-1-15 | 144SBD of 2015-16 & 29/06/2015 | [8 empty] | 1 | [5 empty] | 201.6758 | 25.03 |  | Patna West
6 | SB-6 | Patna | Shiksha Bhawan Patna | Sanjay Construction | 228.53 | [14 empty] | 1 |  |  |  |  | Patna East
7 | SB-7 | Jehanabad | Shiksha Bhawan Jehanabad | M/S Kaushlendra Kumar | 221.12 | ISSUED | 578SBD of 2014-15 & 01/01/2015 | [12 empty] | 1 |  | 202.2699 |  |  | Magadh
8 | SB-8 | Samastipur | Shiksha Bhawan Samastipur | Shudha kant Enterprises | 234.78 | [14 empty] | 1 |  |  |  |  | Darbhanga
9 | SB-9 | Bhagalpur | Shiksha Bhawan Bhagalpur | Dharmendra Kumar | 228.86 |  |  |  |  | 1 | [13 empty] | Land Dispute | Bhagalpur
Total Number of Shiksha Bhawan |  |  | 9 |  |  |  |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 2 | 1059.5981 | 337.18