## List of SSSM
BSEIDC Ltd. , Patna
Physical status of SSSM
S.N. | Group No. | Name of District | Name of the Block | S.N. | Name of School | Name of Agency | Estimated Amount (in Lac) | Time of Completion | Retender | Tender Process | Physical Status | [9 empty] | Fin. Exp. (in lac) | Remarks | Session | Division
[11 empty] | Not Start | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[15 empty] | LL | RL | LL | RL
1 | SSSM-1-1 | dfVgkj | अमदाबाद | 1 | m0e0fo0 pkek | Umakant Singh,9431096239 | 342.51 | 15 ekg | [11 empty] | 1 | 91.56 | Inaugurated 2016 | Phase -1 | Purnea
2 | SSSM-1-2 | dfVgkj | अमदाबाद | 2 | e0fo0 turkxksikyiqj | Umakant Singh,9431096239 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
3 | SSSM-1-3 | dfVgkj | अमदाबाद | 3 | e0fo0 ikjfn;kjk | Umakant Singh,9431096239 |  |  |  |  | 1 | [10 empty] | LAND MADE AVAILABLE ON THE BANK OF GANGA RIVER. (DANGER OF EROSION) | Phase -1 | Purnea
4 | SSSM-2-1 | dfVgkj | आजमनगर | 1 | e0fo0 fldfV;k | BIRENDRA KUMAR SINGH, 9473440405 | 343.75 | 15 ekg | [9 empty] | 1 |  |  | 33.03 |  | Phase -1 | Purnea
5 | SSSM-2-2 | dfVgkj | आजमनगर | 2 | m0e0fo0 csyjkgh | BIRENDRA KUMAR SINGH, 9473440405 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
6 | SSSM-2-3 | dfVgkj | आजमनगर | 3 | m0e0fo0 rs?kM+k | BIRENDRA KUMAR SINGH, 9473440405 | [6 empty] | 1 | [9 empty] | Phase -1 | Purnea
7 | SSSM-3(A) | dfVgkj | बारसोई | 1 | e0fo0 XokyVksyh | RANA BIRESH PRATAP SINGH, 9430683578 | 115.71 | 15 ekg |  |  | 1 | [10 empty] | 7 FEET DEEP WATER LOGGED LAND MADE AVAILABLE. | Phase -1 | Purnea
8 | SSSM-3(B) | dfVgkj | बारसोई | 1 | e0fo0 [k#vk tehjk | RANA BIRESH PRATAP SINGH,9430683578 | 115.71 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
9 | SSSM-3(C) | dfVgkj | बारसोई | 1 | m0e0fo0 Qqgkxk¡o | R. P. Agarwal , Katihar | 115.71 | 15 ekg |  |  | 1 | [10 empty] | land not available( 14feet wide 80 feet length land available but it is being used as passage/play ground) letter has been sent to DEO for Land. | Phase -1 | Purnea
10 | SSSM-4(A) | dfVgkj | बलरामपुर | 1 | e0fo0 efydiqj | MUKESH KUMAR, 9431658565 | 115.34 | 15 ekg |  |  | 1 | [10 empty] | land enchroched, letter has been issued to DEO to solve the problem. | Phase -1 | Purnea
11 | SSSM-4(B) | dfVgkj | बलरामपुर | 1 | e0fo0 Qrsgiqj | Excelent Construction | 115.34 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
12 | SSSM-4(C) | dfVgkj | बलरामपुर | 1 | m0e0fo0 ckywxat fgUnh | R. P. Agarwal , Katihar | 115.34 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
13 | SSSM-5-1 | dfVgkj | फलका | 1 | e0fo0 eks0 uxj jkt/kkuh | BIRENDRA KUMAR SINGH, 9473440405 | 223.83 | 15 ekg |  |  | 1 | [10 empty] | Double scheme | Phase -1 | Purnea
14 | SSSM-5-2 | dfVgkj | फलका | 2 | e0fo0 Hkjfl;k | BIRENDRA KUMAR SINGH, 9473440405 | [7 empty] | 1 | [8 empty] | Phase -1 | Purnea
15 | SSSM-6-1 | dfVgkj | कोढ़ा | 1 | vH;kl e0fo0 eqlkiqj | BIRENDRA KUMAR SINGH, 9473440405 | 332.13 | 15 ekg | [7 empty] | 1 |  |  |  |  | 21.88 | GF roof casted, FF brickwork in progress | Phase -1 | Purnea
16 | SSSM-6-2 | dfVgkj | कोढ़ा | 2 | e0fo0 [ksfj;k | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | double scheme | Phase -1 | Purnea
17 | SSSM-6-3 | dfVgkj | कोढ़ा | 3 | e0fo0 fn?kM+h | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | double scheme | Phase -1 | Purnea
18 | SSSM-7-1 | dfVgkj | प्राणपुर | 1 | m0e0fo0 jkepUnziqj | PANKAJ KUMAR SINGH,9431229327 | 335.36 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
19 | SSSM-7-2 | dfVgkj | प्राणपुर | 2 | e0fo0 egknsoiqj | PANKAJ KUMAR SINGH,9431229327 | [13 empty] | 1 | 74.22 | Inaugurated 2016 | Phase -1 | Purnea
20 | SSSM-7-3 | dfVgkj | प्राणपुर | 3 | e0fo0 cq) uxj | PANKAJ KUMAR SINGH,9431229327 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
21 | SSSM-8-1 | dfVgkj | कटिहार | 1 | m0e0fo0 efu;k | PANKAJ KUMAR SINGH,9431229327 | 221.65 | 15 ekg | [9 empty] | 1 |  |  | 16.99 |  | Phase -1 | Purnea
22 | SSSM-8-2 | dfVgkj | कटिहार | 2 | e0fo0 cBSyh | PANKAJ KUMAR SINGH,9431229327 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
23 | SSSM-9-1 | dfVgkj | मनसाही | 1 | jk0e0fo0 eajxh | BIRENDRA KUMAR SINGH, 9473440405 | 222.46 | 15 ekg | [10 empty] | 1 |  | 21.69 |  | Phase -1 | Purnea
24 | SSSM-9-2 | dfVgkj | मनसाही | 2 | vk0e0fo0 jkuhirjk fla/k;k | BIRENDRA KUMAR SINGH, 9473440405 | [9 empty] | 1 | [6 empty] | Phase -1 | Purnea
25 | SSSM-10-1 | dfVgkj | बरारी | 1 | m0e0fo0 fxnjekjh | BIRENDRA KUMAR SINGH, 9473440405 | 222.01 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Purnea
26 | SSSM-10-2 | dfVgkj | बरारी | 2 | e0fo0 Hk.Mkjry | BIRENDRA KUMAR SINGH, 9473440405 |  |  |  |  | 1 | [10 empty] | Land not registered in the name of school. | Phase -1 | Purnea
27 | SSSM-11(A) | dfVgkj | मनिहारी | 1 | e0fo0 lqjkikjVky | MS EXCELLENT CONSTRUCTION, 9472021967 | 112.5 | 15 ekg | [9 empty] | 1 |  |  |  |  | Phase -1 | Purnea
28 | SSSM-11(B) | dfVgkj | मनिहारी | 1 | e0fo0 dkWVkdks'k | MS EXCELLENT CONSTRUCTION, 9472021967 | 112.5 | 15 ekg |  |  | 1 | [10 empty] | double scheme | Phase -1 | Purnea
29 | SSSM-12(A) | dfVgkj | कदवा | 1 | m0e0fo0 dpkSM+k iwoZ | R. P. Agarwal , Katihar | 112.57 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
30 | SSSM-12(B) | dfVgkj | कदवा | 1 | m0e0fo0 cSnk | MS EXCELLENT CONSTRUCTION,9472021967 | 112.57 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
31 | SSSM-13(A) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 y[kukjs | M/S Excellent Construction | 114 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
32 | SSSM-13(B) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 csydk | MD ARFIN,9006212706 | 114 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
33 | SSSM-13(C) | iwf.kZ;k¡ | अमौर | 1 | e0fo0 ckywVksyk] bLykeiqj | Gajmatia, Khushkibagh | 114 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Purnea
34 | SSSM-14(A) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 etxkek | SANJEEV RANJAN SINHA, 9472063463 | 111.74 | 15 ekg | [6 empty] | 1 | [7 empty] | Phase -1 | Purnea
35 | SSSM-14(B) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 yN.kiqj | M/S Excellent Construction | 111.74 | 15 ekg |  |  | 1 | [10 empty] | Donners objection, Letter issued to DPO | Phase -1 | Purnea
36 | SSSM-14(C) | iwf.kZ;k¡ | कसबा | 1 | e0fo0 eksguh | M/S Excellent Construction | 111.74 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
37 | SSSM-15(A) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 lkukiqj | Ashish Anand, Purnea | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
38 | SSSM-15(B) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 gjsjkeiqj | SAMRAT BUILDTECH (INDIA) PRIVATE LIMITED, 9973239801 | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
39 | SSSM-15(C) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 pjS;k | Bambam Kumar Singh | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
40 | SSSM-15(D) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 'kh'kckM+h | Gajmathia | 112.99 | 15 ekg |  |  | 1 | [10 empty] | Permission is not granted by shiksha samiti to demolish the old eXisting structure. In order to start the work | Phase -1 | Purnea
41 | SSSM-15(E) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 p¡nokj | HARIMOHAN BISHWAS,9955713757 | 112.99 | 15 ekg |  |  |  | 1 | [10 empty] | Phase -1 | Purnea
42 | SSSM-15(F) | iwf.kZ;k¡ | बैसी | 1 | e0fo0 uUnfu;k | Binod Yadav | 112.99 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
43 | SSSM-16(A) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 Mx#vk | HARIMOHAN BISHWAS,9955713757 | 112.25 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
44 | SSSM-16(B) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 pkSiM+k cyqvk | M/S Excellent Construction | 112.25 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
45 | SSSM-16(C) | iwf.kZ;k¡ | डगरुआ | 1 | e0fo0 fl;kj[ke | M/S Rana Pratap Singh, Purnea | 112.25 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
46 | SSSM-17-1 | iwf.kZ;k¡ | जलालगढ़ | 1 | e0fo0 efr;kjiqj | DILIP KUMAR, 9631032543 / 9431666265 | 338.09 | 15 ekg | [10 empty] | 1 |  | 58.5 |  | Phase -1 | Purnea
47 | SSSM-17-2 | iwf.kZ;k¡ | जलालगढ़ | 2 | e0fo0 dBSyh | DILIP KUMAR, 9631032543 / 9431666265 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
48 | SSSM-17-3 | iwf.kZ;k¡ | जलालगढ़ | 3 | e0fo0 ,dEck | DILIP KUMAR, 9631032543 / 9431666265 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
49 | SSSM-18-1 | iwf.kZ;k¡ | कृत्यानन्द नगर | 1 | e0fo0 iz[kaM dkWyuh | MS ALAM CONSTR. WORKS & CO, 9199574775 9472103786 | 333.26 | 15 ekg | [7 empty] | 1 |  |  |  |  | 21.07 |  | Phase -1 | Purnea
50 | SSSM-18-2 | iwf.kZ;k¡ | कृत्यानन्द नगर | 2 | e0fo0 izlkniqj csynkjh | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [6 empty] | 1 | [9 empty] | Phase -1 | Purnea
51 | SSSM-18-3 | iwf.kZ;k¡ | कृत्यानन्द नगर | 3 | e0fo0 dk>k x.ks'kiqj | MS ALAM CONSTRUCTION WORKS AND COMPANY, 9199574775 , 9472103786 | [9 empty] | 1 | [6 empty] | Phase -1 | Purnea
52 | SSSM-19-1 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 1 | e0fo0 fiijk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | 222.8 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
53 | SSSM-19-2 | iwf.kZ;k¡ | पूर्णियाँ इस्ट | 2 | e0fo0 egjktiqj | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [13 empty] | 1 |  |  | Phase -1 | Purnea
54 | SSSM-20-1 | iwf.kZ;k¡ | श्रीनगर | 1 | e0fo0 txSyh | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | 224.28 | 15 ekg |  |  |  |  | 1 | [9 empty] | Phase -1 | Purnea
55 | SSSM-20-2 | iwf.kZ;k¡ | श्रीनगर | 2 | e0fo0 xaxk Hkou [kks[kk | MS SHINING MADHUSUDHAN CONSTRUCTION, 9431884876 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
56 | SSSM-25-1 | vjfj;k | नरपतगंज | 1 | ,e0,l0 xks[kykiqj ch0,e0,l0 | Kailash Prasad Yadav Constructions Pvt Ltd. , 9431424763 | 353.03 | 15 ekg | [10 empty] | 1 |  | 23.84 |  | Phase -1 | Purnea
57 | SSSM-25-2 | vjfj;k | नरपतगंज | 2 | ,e0,l0 csyk fjQwth | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [13 empty] | 1 |  |  | Phase -1 | Purnea
58 | SSSM-25-3 | vjfj;k | नरपतगंज | 3 | ,e0,l0 pUnk | Kailash Prasad Yadav Constructions Pvt Ltd. ,9431424763 | [12 empty] | 1 |  |  |  | Phase -1 | Purnea
59 | SSSM-26(A) | vjfj;k | रानीगंज | 1 | ,e0,l0 gjhnk,iqj | Krishna Ranjan Kumar, Araria | 114.05 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
60 | SSSM-26(B) | vjfj;k | रानीगंज | 1 | ,e0,l0 ukjk;.kiqj | MD ARFIN, 9006212706 | 114.05 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
61 | SSSM-26(C) | vjfj;k | रानीगंज | 1 | ;w0,e0,l0 nqekfj;k ckyd | MD ARFIN, 9006212706 | 114.05 | 15 ekg | [9 empty] | 1 |  |  |  |  | Phase -1 | Purnea
62 | SSSM-27(A) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 vekSuk | KRISHNA RANJAN KUMAR,9939662452 | 116.06 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Purnea
63 | SSSM-27(B) | vjfj;k | फारबिसगंज | 1 | ,e0,l0 iq.kZnkgk | CHANDAN ABHISHEK,9431284224 | 116.06 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
64 | SSSM-28(A) | vjfj;k | सिक्टी | 1 | ,e0,l0 xksjkxPN | Praveen, Araria | 118.43 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Purnea
65 | SSSM-28(B) | vjfj;k | सिक्टी | 1 | ;w0,e0,l0 fnefg;k | Md. Iftakhar Alam | 118.43 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Purnea
66 | SSSM-29 | vjfj;k | सिक्टी | 1 | ,e0,l0 ispkSyh | Tender Process | 114.93 | 15 ekg |  | 1 | [11 empty] | Tender Process (NIT - 21 , 2015-16). Financial not open yet | Phase -1 | Purnea
67 | SSSM-21(A) | if'pe pEikj.k | सिरिसिया | 1 | e0fo0 fljfl;k | KISHOR KUMAR,8298437834 | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
68 | SSSM-21(B) | if'pe pEikj.k | बेहरा | 1 | e0fo0 >qedk mnwZ | MS SARASWATI COMPANY,9431491241 | 115.98 | 15 ekg | [11 empty] | 1 |  |  | Phase -1 | Tirhut West
69 | SSSM-21(C) | if'pe pEikj.k | सूर्यपुर | 1 | mŒ ekŒ foŒ] Hkokuhiqj mnZw | MS SARASWATI COMPANY,9431491241 | 115.98 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Tirhut West
70 | SSSM-22(A) | if'pe pEikj.k | तेलपुर | 1 | m0e0fo0 rsyiqj ckyd | M/S BHATRDWAJ CONSTRUCTION | 115.98 | 15 ekg |  |  | 1 | [10 empty] | Land not available | Phase -1 | Tirhut West
71 | SSSM-22(B) | if'pe pEikj.k | देउरवा | 1 | e0fo0 nsmjok | Ashukla | 115.98 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
72 | SSSM-22(C) | if'pe pEikj.k | धोबनी धर्मपुर | 1 | m0e0fo0 eqlgjh | SANJAY KUMAR MISHRA, 9546215798 | 115.98 | 15 ekg | [9 empty] | 1 |  |  |  |  | Phase -1 | Tirhut West
73 | SSSM-22(D) | if'pe pEikj.k | मठिया | 1 | e0fo0 efB;k | AWADHESH SHUKLA, 9431203836 | 115.98 | 15 ekg | [11 empty] | 1 | 14.28 |  | Phase -1 | Tirhut West
74 | SSSM-23(A) | if'pe pEikj.k | रखही | 1 | m0e0fo0 pEikj.k | SHAKAL DEO MISHRA,9006385958 | 115.55 | 15 ekg | [10 empty] | 1 |  |  |  | Phase -1 | Tirhut West
75 | SSSM-23(B) | if'pe pEikj.k | शेरहवा | 1 | e0fo0 fllok cgqvjok | RAJ KISHORE AKELA,9430642227 | 115.55 | 15 ekg | [11 empty] | 1 | 8.33 |  | Phase -1 | Tirhut West
76 | SSSM-23(C) | if'pe pEikj.k | पुरैनिया हरसरी | 1 | m0e0fo0 dksbZjxkok | SANJAY KUMAR MISHRA, 9546215798 | 115.55 | 15 ekg |  |  | 1 | [10 empty] | Land not available | Phase -1 | Tirhut West
77 | SSSM-24(A) | if'pe pEikj.k | चैहटी | 1 | e0fo0 lkSdV | GYASUL AZAM, 9199932786 | 116.39 | 15 ekg | [10 empty] | 1 |  |  | 50'X80' | Phase -1 | Tirhut West
78 | SSSM-24(B) | if'pe pEikj.k | मधुरि | 1 | m0e0fo0 idqgok iwohZ | GYASUL AZAM, 9199932786 | 116.39 | 15 ekg | [7 empty] | 1 | [6 empty] | Phase -1 | Tirhut West
79 | SSSM-30-1 | njHkaxk | दरभंगा सदर | 1 | e0fo0 Bdqjfu;k¡ | RAJENDRA PRASAD, 8797539347 | 225.8 | 15 ekg | [11 empty] | 1 | 59.48 | Inaugurated 2016 | Phase -1 | Darbhanga
80 | SSSM-30-2 | njHkaxk | दरभंगा सदर | 2 | e0fo0 da'kh | RAJENDRA PRASAD, 8797539347 | [13 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
81 | SSSM-31-1 | njHkaxk | मनीगाछी | 1 | e0fo0 pdfpUrkef.kiqj | S K CONSTRUCTION AND COMPANY,9471006199 | 114.2 | 15 ekg | [9 empty] | 1 |  |  |  |  | Phase -1 | Darbhanga
82 | SSSM-32-1 | njHkaxk | अलीनगर | 1 | mnwZ e0fo0 vyhuxj | AJAY KUMAR PATHAK,9431034060 | 114.27 | 15 ekg | [10 empty] | 1 |  | 21.61 |  | Phase -1 | Darbhanga
83 | SSSM-33-1 | njHkaxk | जाले | 1 | e0fo0 tgkxhj Vksy | SANJAY KUMAR, 8521954601 | 229.19 | 15 ekg | [11 empty] | 1 | 36.79 | Inaugurated 2016 | Phase -1 | Darbhanga
84 | SSSM-33-2 | njHkaxk | जाले | 2 | e0fo0 vfg;kjh xksV | SANJAY KUMAR, 8521954601 | [7 empty] | 1 | [8 empty] | Phase -1 | Darbhanga
85 | SSSM-34(A) | njHkaxk | सिंहवाड़ा | 1 | e0fo0 jktks | BHUSAN KUMAR,9631681894 | 113.32 | 15 ekg | [11 empty] | 1 | 20.33 | Inaugurated 2016 | Phase -1 | Darbhanga
86 | SSSM-34(B) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 cgqvkjk | SachinKhandelwal | 113.32 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
87 | SSSM-34(C) | njHkaxk | सिंहवाड़ा | 1 | m0e0fo0 xkSjhukFk czgeiqj | SachinKhandelwal | 113.32 | 15 ekg | [11 empty] | 1 |  | Inaugurated 2016 | Phase -1 | Darbhanga
88 | SSSM-35(A) | njHkaxk | केवटी | 1 | e0fo0 cjgh | OM SHREE CONSTRUCTION, 9934426934 | 112.93 | 15 ekg |  |  |  |  | 1 | [8 empty] | Land Dispute | Phase -1 | Darbhanga
89 | SSSM-35(B) | njHkaxk | केवटी | 1 | m0e0fo0 ykyxat | Rajesh Kumar, 9334374660 | 112.93 | 15 ekg | [10 empty] | 1 |  | 34.09 | Inaugurated 2016 | Phase -1 | Darbhanga
90 | SSSM-36-1 | njHkaxk | किरतपुर | 1 | e0fo0 fdjriqj | OM SHREE CONSTR. BEGUSARAI | 113.75 | 15 ekg |  |  | 1 | [10 empty] | Not Start. | Phase -1 | Darbhanga
91 | SSSM-37-1 | njHkaxk | गौराबौराम | 1 | e0fo0 ckSjke | OM SHREE CONSTR. BEGUSARAI | 114.25 | 15 ekg | [5 empty] | 1 | [8 empty] | Phase -1 | Darbhanga
92 | SSSM-47(A) | fd'kuxat | cgknqjxat | 1 | e0 fo0 HkheVksyk | KAUSHAL KUMAR | [6 empty] | 1 | [9 empty] | Phase-2 | Purnea
93 | SSSM-47(B) | fd'kuxat | cgknqjxat | 2 | mŒ eŒ foŒ eaMyVksyk Mksgj | MD ANZAR ALAM | [6 empty] | 1 | [9 empty] | Phase-2 | Purnea
94 | SSSM-48-1 | fd'kuxat | fd'kuxat | 1 | e0 fo0 ikuhlky | Cancel |  |  |  |  | 1 | [10 empty] | Cancel. Double Scheme | Phase-2 | Purnea
95 | SSSM-49(A) | fd'kuxat | dkspk/kkeu | 1 | m0 e0 fo0 dUgS;kckM+h | MANOJ KUMAR | [11 empty] | 1 |  |  |  |  | Phase-2 | Purnea
96 | SSSM-49(B) | fd'kuxat | dkspk/kkeu | 2 | m0 e0 fo0 eksgjk | BHOLINATH RAY | [6 empty] | 1 | [9 empty] | Phase-2 | Purnea
97 | SSSM-49 ( C) | fd'kuxat | dkspk/kkeu | 3 | m0 e0 fo0 gfjHkk"kk | MD. ZULQUER NAIN | [11 empty] | 1 |  |  |  |  | Phase-2 | Purnea
98 | SSSM-50 (A) | fd'kuxat | iksfB;k | 1 | m0 e0 fo0 tkyw pkSd | No Bidder |  |  |  |  | 1 | [10 empty] | Double Scheme. match to SSS-96-1 | Phase-2 | Purnea
99 | SSSM-50 (B) | fd'kuxat | iksfB;k | 2 | m0 e0 fo0 lksukiwj | WALKS N WALKS | [9 empty] | 1 | [6 empty] | Phase-2 | Purnea
100 | SSSM-50 ( C) | fd'kuxat | iksfB;k | 3 | m0 e0 fo0 HksykxkNh chjiqj | VATS INFRATECH PVT. LTD. |  |  |  |  | 1 | [10 empty] | Not Start. Double Scheme | Phase-2 | Purnea
101 | SSSM-51 | fd'kuxat | VsjkxkPN | 1 | m0 e0 fo0 vkfnoklh Vksyk Hkksjgk | Pawan Kumar Agarwal |  |  |  |  | 1 | [10 empty] | LOA Issue | Phase-2 | Purnea
102 | SSSM-52 (A) | fd'kuxat | Bkdqjxat | 1 | m0 e0 fo0 ikapxkNh | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Not Start. Double Scheme | Phase-2 | Purnea
103 | SSSM-52 (B) | fd'kuxat | Bkdqjxat | 2 | m0 e0 fo0 yks/kk | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Not Start. Double Scheme | Phase-2 | Purnea
104 | SSSM-52 ( C) | fd'kuxat | Bkdqjxat | 3 | e0 fo0 csgqyMkaxh | Santosh agrawal |  |  |  |  | 1 | [10 empty] | Not Start. Double Scheme | Phase-2 | Purnea
105 | SSSM-38 | lhrke<+h | cktiÍh | 1 | ,e0 ,l0 fcyfg;k | Shree shiva Construction dist- muzaffarpur | [11 empty] | 1 |  |  |  |  | Phase-2 | Tirhut East
106 | SSSM-41 | lqikSy | clariqj | 1 | e/; fo¦ky; ujirV~Vh | Madan kumar singh |  |  |  |  | 1 | [10 empty] | Not Start | Phase-2 | Koshi
107 | SSSM-42 (A) | xksikyxat | Fkkos | 1 | ,e0 ,l0 lsejk | PAWAN CONSTRUCTION | [9 empty] | 1 | [6 empty] | Phase-2 | Saran
108 | SSSM-42 (B) | xksikyxat | Fkkos | 1 | ;w0 ,e0 ,l0 ukjk;.kiqj | GIRIDHAR GOPAL CONS. |  |  |  |  | 1 | [10 empty] | Not Start. No Self Land of School. | Phase-2 | Saran
109 | SSSM-43 (A) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 lariqj | kumar manash construction |  |  |  |  | 1 | [10 empty] | Not Start. No Self Land of School. | Phase-2 | Saran
110 | SSSM-43 (B) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 'ks[kijlk | Savitri Technocrates pvt. Ltd | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Saran
111 | SSSM-43 (C ) | xksikyxat | eka>k | 1 | ;w0 ,e0 ,l0 dksygqvk | Savitri Technocrates pvt. Ltd | [13 empty] | 1 |  |  | Phase-2 | Saran
112 | SSSM-44 (A) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 gjiqj | sai Highway & builders pvt.ltd | [8 empty] | 1 | [7 empty] | Phase-2 | Saran
113 | SSSM-44 (B) | xksikyxat | mpdk xkao | 1 | ;w0 ,e0 ,l0 ewjkedlwniqj | Cancel |  |  |  |  | 1 | [10 empty] | Cancel Double Scheme | Phase-2 | Saran
114 | SSSM-45 (A) | ckadk | /kqjS;k | 1 | m0 e0 fo0 pyuk | Marcominfra Pvt. Ltd., 9934361315 |  |  |  |  | 1 | [10 empty] | LOA Issue | Phase-2 | Bhagalpur
115 | SSSM-45 (B) | ckadk | /kqjS;k | 2 | m0 e0 fo0 rkfgjiqjk dU;k | Chitragupta construction | [7 empty] | 1 | [8 empty] | Phase-2 | Bhagalpur
116 | SSSM-45 (C ) | ckadk | /kqjS;k | 3 | m0 e0 fo0 vfgjks | Chitragupta construction | [8 empty] | 1 | [7 empty] | Phase-2 | Bhagalpur
117 | SSSM-46-1 | Hkkxyiqj | lugkSyk | 1 | e0 fo0 rsyokM+k | Baba Hans Construction | [12 empty] | 1 |  |  |  | Phase-2 | Bhagalpur
118 | SSSM-39 (A) | e/kqcuh | jfgdk | 1 | ,e0 ,l0 elufx;k | RAMDINESH SINGH |  |  |  |  | 1 | [10 empty] | No Location found | Phase-2 | Darbhanga
119 | SSSM-39 (B) | e/kqcuh | jfgdk | 2 | ,e0 ,l0 eyufx;k | RAMDINESH SINGH | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Darbhanga
120 | SSSM-39 (C ) | e/kqcuh | jfgdk | 3 | ;w0,e0,l0 ckNVksy jkeiqj | RAMDINESH SINGH | [13 empty] | 1 |  | Inaugurated 2016 | Phase-2 | Darbhanga
121 | SSSM-40-1 | e/kqcuh | dyqvkgh | 1 | ,e0 ,l0 eyey | RAMDINESH SINGH | [12 empty] | 1 |  |  |  | Phase-2 | Darbhanga
Total No. of Schools (SSSM) |  |  |  | 121 |  |  |  |  | 0 | 1 | 27 | 1 | 7 | 4 | 3 | 11 | 0 | 9 | 28 | 30 | 557.69