## List of MS
BSEIDC, Patna
Status of Model School
Sl. NO. | Group no | Name of Division | Session | District | Block | SN | Name Of School |  | Physical Status
[8 empty] | Agreement Value | Not Start | LAY OUT | FOUND ATION | PL | Ground Floor |  | First Floor |  | Second Floor |  | FINI SHING | COMP LETE | Remarks
[13 empty] | LL | RL | LL. | RL. | LL. | RL.
1 | MS-1 | Koshi | 2009-10 | सहरसा | सोनबरसा | 1 | High School Sonbarsha | 273.3667 | [10 empty] | 1 |  | 1. Plaster and Kota work in Progress
2 | MS-1 | Koshi | 2009-10 | सहरसा | सोनबरसा | 2 | Govt. Basic School Surath | 273.3667 | [10 empty] | 1 |  | Work Stop. 2. Rest balance work - Painting external & Internal, Plumbing & Sanitary, Electrical wiring, Water Proofing, Windows Glass & Doors, Boring and Tiles
3 | MS-1 | Koshi | 2009-10 | सहरसा | Attar Kataiya | 3 | High School Menha | 273.3667 | [11 empty] | 1 | Inaugurated
4 | MS-2 | Koshi | 2009-10 | मधेपुरा | कुमारखंड | 1 | High School Kumarkhand | 272.65 | [9 empty] | 1 |  |  | 1. Structure Complete 2. Rest Balance - All Finishing Works .
5 | MS-2 | Koshi | 2009-10 | मधेपुरा | मधेपुरा | 2 | Shiv Nandan Pd.+2 School | 272.65 | [11 empty] | 1 | Inaugurated 16.07.2016
6 | MS-2 | Koshi | 2009-10 | मधेपुरा | आलमनगर | 3 | A.K.M. H/S Shah Alam Nagar | 272.65 | [11 empty] | 1 | Inaugurated 16.07.2016
7 | MS-3 | Koshi | 2009-10 | सुपौल | त्रिवेणीगंज | 1 | M/S.Daparkha | 283 | [11 empty] | 1 | Inaugurated
8 | MS-3 | Koshi | 2009-10 | सुपौल | बसंतपुर | 2 | H/S.Hirdya Nagar | 283 | [11 empty] | 1 | Inaugurated 16.07.2016
9 | MS-163 | Koshi | 2010-11 | सुपौल | किशनपुर | 1 | H/S, Kishanpur | 280.5 | [11 empty] | 1 | Inaugurated 16.07.2016
10 | MS-163 | Koshi | 2010-11 | सुपौल | सुपौल | 2 | H/S, Sukhpur | 280.5 | [11 empty] | 1 | Inaugurated
11 | MS-163 | Koshi | 2010-11 | सुपौल | पिपरा | 3 | Govt. Basic School, Basaha | 280.5 | [11 empty] | 1 | Inaugurated 16.07.2016
12 | MS-164 | Koshi | 2010-11 | सुपौल | राघोपुर | 1 | L.S. H/S, Simrahi Bazar, Raghopur | 285.7033 | [9 empty] | 1 |  |  | BrickWork IN PROGRESS
13 | MS-164 | Koshi | 2010-11 | सुपौल | प्रतापगंज | 2 | Public H/S, Pratapganj | 285.7033 | [11 empty] | 1 | Inaugurated 16.07.2016
14 | MS-164 | Koshi | 2010-11 | सुपौल | छातापुर | 3 | S.S. H/S, Sukhpur. Surpatganj | 285.7033 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-51) | bindup
15 | MS-165 | Koshi | 2010-11 | सुपौल | सरायगढ़ भपटियाही | 1 | B.G H/S, Bhaptiyahi | 262.13 | [11 empty] | 1 | Inaugurated 16.07.2016
16 | MS-29 | Tirhut East | 2009-10 | मुजफ्फरपुर | Kurhni | 1 | HS Chhajan Mohini | 263.9833 | [11 empty] | 1 | Inaugurated
17 | MS-29 | Tirhut East | 2009-10 | मुजफ्फरपुर | सकरा | 2 | Govt. Basic School, Rapeura | 263.9833 | [11 empty] | 1 | Inaugurated
18 | MS-29 | Tirhut East | 2009-10 | मुजफ्फरपुर | मुशहरी | 3 | H/S.Meghmath | 263.9833 | [11 empty] | 1 | Inaugurated
19 | MS-30 | Tirhut East | 2009-10 | वैशाली | जन्दाहा | 1 | R.B.S.Loma | 256.3404 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-52) | bindup
20 | MS-30 | Tirhut East | 2009-10 | वैशाली | पातेपुर | 2 | Govt. Basic School Bardiha | 256.3404 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-53) | bindup
21 | MS-30 | Tirhut East | 2009-10 | वैशाली | हाजीपुर | 3 | Govt. Basic School Jagdishpur | 256.3404 | [9 empty] | 1
22 | MS-30 | Tirhut East | 2009-10 | वैशाली | महुआ | 4 | M.S Singhara | 256.3404 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (SL.No.-1) | bindup
23 | MS-31 | Tirhut West | 2009-10 | पूर्वी चंपारण | कल्यानपुर | 1 | Govt. Basic School Madhopur Govind | 271.715 | [11 empty] | 1 | Inaugurated
24 | MS-31 | Tirhut West | 2009-10 | पूर्वी चंपारण | चकिया | 2 | B.A.A.P. H/S. Barachakia | 271.715 | [11 empty] | 1 | Inaugurated
25 | MS-32 | Tirhut West | 2009-10 | पश्चिम चम्पारण | बगहा-1 | 1 | Govt. Basic School Patilar | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
26 | MS-32 | Tirhut West | 2009-10 | पश्चिम चम्पारण | नरकटियागंज | 2 | H/S. Mathura Gokhula | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
27 | MS-32 | Tirhut West | 2009-10 | पश्चिम चम्पारण | मझौलिया | 3 | Govt. Basic School Mahna Mirjapur | 252.1833 | [11 empty] | 1 | Inaugurated 16.07.2016
28 | MS-33 | Tirhut East | 2009-10 | सीतामढी | रून्‍नीसैदपुर | 1 | H./S.Morsand | 261.77 | [11 empty] | 1 | Inaugurated
29 | MS-33 | Tirhut East | 2009-10 | सीतामढी | सोनबरसा | 2 | H/S. Sonbarsha | 261.77 | [11 empty] | 1 | Inaugurated
30 | MS-34 | Tirhut West | 2009-10 | शिवहर | तरियानी | 1 | H.S.Taiyari | 267.8533 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
31 | MS-34 | Tirhut West | 2009-10 | शिवहर | शिवहर | 2 | Govt. Basic School Bishahi | 267.8533 | [10 empty] | 1 |  | Painting done, Inside Finishing going on
32 | MS-34 | Tirhut West | 2009-10 | शिवहर | पुरनहिया | 3 | H/S. Sonoul Sultan | 267.8533 | [10 empty] | 1 |  | Painting done, Inside Finishing going on
33 | MS-109 | Tirhut East | 2010-11 | वैशाली | राघोपुर | 1 | T.R.S.S. H/S Jurawanpur | 266.15 | [11 empty] | 1
34 | MS-109 | Tirhut East | 2010-11 | वैशाली | महनार | 2 | Govt. Basic School, Karnauti | 266.15 | [11 empty] | 1 | Inaugurated
35 | MS-109 | Tirhut East | 2010-11 | वैशाली | बिदुपुर | 3 | Govt. Basic School, Chechar | 266.15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
36 | MS-110 | Tirhut East | 2010-11 | वैशाली | वैशाली | 1 | H.S H/S, Chintamanipur | 263.2033 | [11 empty] | 1 | Inaugurated
37 | MS-110 | Tirhut East | 2010-11 | वैशाली | पतेर्ही बेलसर | 2 | Govt. Basic School, Surhattha | 263.2033 | [11 empty] | 1 | Inaugurated
38 | MS-110 | Tirhut East | 2010-11 | वैशाली | लालगंज | 3 | Govt. Basic School, Michagadh | 263.2033 | [11 empty] | 1 | Inaugurated
39 | MS-111 | Tirhut East | 2010-11 | वैशाली | भगवानपुर | 1 | Govt. Basic School, Warispur | 264.4433 | [11 empty] | 1 | Inaugurated
40 | MS-111 | Tirhut East | 2010-11 | वैशाली | गोरौल | 2 | Govt. Basic School, Kanhauli | 264.4433 | [11 empty] | 1 | Inaugurated
41 | MS-111 | Tirhut East | 2010-11 | वैशाली | चेहरा कलां | 3 | B.N. H/S, Sehan | 264.4433 | [11 empty] | 1 | Inaugurated
42 | MS-112 | Tirhut East | 2010-11 | वैशाली | राजा पाकर | 1 | Govt. Basic School, Narayanpur | 269.39 | [11 empty] | 1 | Inaugurated
43 | MS-112 | Tirhut East | 2010-11 | वैशाली | देसरी | 2 | S.G.B.B.A.S. H/S, Bhatauliya | 269.39 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | L P Mandir on land Old Building to be Dismantle
44 | MS-112 | Tirhut East | 2010-11 | वैशाली | सहदे बुज़ुर्ग | 3 | Gandhi H/S, Sahadai Buzurg | 269.39 | [11 empty] | 1 | Inaugurated
45 | MS-120 | Tirhut East | 2010-11 | सीतामढी | रीगा | 1 | T.R.N.H.S, Sahbajpur Kharsan | 280.0925 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-2) | bindup
46 | MS-120 | Tirhut East | 2010-11 | सीतामढी | परसौनी | 2 | Govt. Basic School, Raghopur Bhakhari | 280.0925 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-3) | bindup
47 | MS-120 | Tirhut East | 2010-11 | सीतामढी | बेलसंड | 3 | Govt. Basic School, Machi Bhandari | 280.0925 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
48 | MS-121 | Tirhut East | 2010-11 | सीतामढी | नानपुर | 1 | Govt. Basic School, Janipur | 278.6509 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-4) | bindup
49 | MS-121 | Tirhut East | 2010-11 | सीतामढी | चोरौत | 2 | S.L.N.S H/S, Chorout | 278.6509 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-54) | bindup
50 | MS-121 | Tirhut East | 2010-11 | सीतामढी | सुरसंड | 3 | Saryu H/S, Sursand | 278.6509 | 1 | [11 empty] | Not Started
51 | MS-122 | Tirhut East | 2010-11 | सीतामढी | बाजपट्टी | 1 | S.R.P.N. H/S, Bajpatti | 283.4938 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-5) | bindup
52 | MS-122 | Tirhut East | 2010-11 | सीतामढी | मेजरगंज | 2 | J.B. H/S, Majorganj | 283.4938 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-55) | bindup
53 | MS-122 | Tirhut East | 2010-11 | सीतामढी | परिहार | 3 | S.G. H/S, Parihar | 283.4938 | 1 | [11 empty] | Local dispute
54 | MS-123 | Tirhut West | 2010-11 | पूर्वी चंपारण | पिपराकोठी | 1 | Govt. Basic School, Piprakothi | 261.765 | [11 empty] | 1 | Inaugurated
55 | MS-123 | Tirhut West | 2010-11 | पूर्वी चंपारण | कोटवा | 2 | H/S, Machh-agargawa | 261.765 | [11 empty] | 1 | Inaugurated
56 | MS-124 | Tirhut West | 2010-11 | पूर्वी चंपारण | मेहसी | 1 | High School, Mehsi | 268.515 | [11 empty] | 1 | Inaugurated 16.07.2016
57 | MS-124 | Tirhut West | 2010-11 | पूर्वी चंपारण | केशरिया | 2 | High School, Kesariya | 268.515 | [11 empty] | 1 | Inaugurated 16.07.2016
58 | MS-125 | Tirhut West | 2010-11 | पूर्वी चंपारण | तुरकौलिया | 1 | S.R.R. H/S, Turkaulia | 262.6233 | [10 empty] | 1
59 | MS-125 | Tirhut West | 2010-11 | पूर्वी चंपारण | सुगौली | 2 | Nand High School, Sugauli | 262.6233 | [11 empty] | 1 | Inaugurated 16.07.2016
60 | MS-125 | Tirhut West | 2010-11 | पूर्वी चंपारण | बंजरिया | 3 | H/S, Mokhlishpur | 262.6233 | [10 empty] | 1
61 | MS-126 | Tirhut West | 2010-11 | पूर्वी चंपारण | रक्सौल | 1 | H/S, Purandara Bhelahi | 279.2697 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-56) | bindup
62 | MS-126 | Tirhut West | 2010-11 | पूर्वी चंपारण | रामगढवा | 2 | Govt. Basic School, Siswaniya | 279.2697 | [10 empty] | 1
63 | MS-126 | Tirhut West | 2010-11 | पूर्वी चंपारण | छौङादानो | 3 | H/S, Chhoradano | 279.2697 | [11 empty] | 1 | Inaugurated 16.07.2016
64 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | आदापुर | 1 | Govt. Basic School, Bhawanati | 288.5047 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-6) | bindup
65 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | घोङासहन | 2 | Govt. Basic School, Bhelwa Circle | 288.5047 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-7) | bindup
66 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | ढाका | 3 | H/S, Dhaka | 288.5047 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-8) | bindup
67 | MS-128 | Tirhut West | 2010-11 | पूर्वी चंपारण | फेनहारा | 1 | H/S, Phenhara | 271.5133 | [10 empty] | 1
68 | MS-128 | Tirhut West | 2010-11 | पूर्वी चंपारण | चिरैया | 2 | M.S. H/S, Chiraiya | 271.5133 | [10 empty] | 1
69 | MS-128 | Tirhut West | 2010-11 | पूर्वी चंपारण | पताहि | 3 | H/S, Patahi | 271.5133 | [10 empty] | 1
70 | MS-129 | Tirhut West | 2010-11 | पूर्वी चंपारण | मधुबन | 1 | H/S, Madhuban | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
71 | MS-129 | Tirhut West | 2010-11 | पूर्वी चंपारण | तेतरिया | 2 | H/S, Tetaria | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
72 | MS-129 | Tirhut West | 2010-11 | पूर्वी चंपारण | पकङीदयाल | 3 | H/S, Barkawan | 277.03 | [11 empty] | 1 | Inaugurated 16.07.2016
73 | MS-130 | Tirhut West | 2010-11 | पूर्वी चंपारण | अरेराज | 1 | H/S, Areraj | 265.3 | [11 empty] | 1 | Inaugurated
74 | MS-130 | Tirhut West | 2010-11 | पूर्वी चंपारण | संग्रामपुर | 2 | H/S, Sangrampur | 265.3 | [11 empty] | 1 | Inaugurated
75 | MS-131 | Tirhut West | 2010-11 | पूर्वी चंपारण | हरसिद्धि | 1 | Govt. Basic School, Kritpur Mathiya | 270.425 | [11 empty] | 1 | Inaugurated 16.07.2016
76 | MS-131 | Tirhut West | 2010-11 | पूर्वी चंपारण | पहाङपुर | 2 | Govt. Basic School, Baluahar Siddhi | 270.425 | [11 empty] | 1
77 | MS-185 | Tirhut West | 2010-11 | पश्चिम चम्पारण | बैरिया | 1 | H/S, Bathna |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
78 | MS-185 | Tirhut West | 2010-11 | पश्चिम चम्पारण | ठकराहा | 2 | G.M. H/S, Thakaraha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
79 | MS-185 | Tirhut West | 2010-11 | पश्चिम चम्पारण | भितहां | 3 | H/S. Ajaynagar Rerha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
80 | MS-186 | Tirhut West | 2010-11 | पश्चिम चम्पारण | नौतन | 1 | Janta H/S, Telua |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
81 | MS-186 | Tirhut West | 2010-11 | पश्चिम चम्पारण | बेतिया | 2 | B.H.S.S, Bettiah |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
82 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | योगापट्टी | 1 | Govt. Basic School, Balua | 69.8047 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-57) | bindup
83 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | चनपटिया | 2 | Govt. Basic School, Chaubetola | 69.8047 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-58) | bindup
84 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | सिकटा | 3 | Janta H/S, Sikta | 69.8047 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-59) | bindup
85 | MS-188 | Tirhut West | 2010-11 | पश्चिम चम्पारण | रामनगर | 1 | H/S, Harinagar | 274.295 | [11 empty] | 1 | Inaugurated 16.07.2016
86 | MS-188 | Tirhut West | 2010-11 | पश्चिम चम्पारण | लौरिया | 2 | A.H. H/S, Bagahi | 274.295 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
87 | MS-189 | Tirhut West | 2010-11 | पश्चिम चम्पारण | पिपरासी | 1 | Govt. Basic School, Manjhariya | 290.425 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-9) | bindup
88 | MS-189 | Tirhut West | 2010-11 | पश्चिम चम्पारण | मधुबनी | 2 | M/S, Tamkuhwa | 290.425 | [10 empty] | 1 |  | plaster done, rest work in progress
89 | MS-190 | Tirhut West | 2010-11 | पश्चिम चम्पारण | गौनाहा | 1 | Govt. Basic School, Bhithakha |  | 1 | [11 empty] | Bind up List - 81 (S.No.-10) | bindup
90 | MS-190 | Tirhut West | 2010-11 | पश्चिम चम्पारण | मैनाटांड | 2 | R.S. H/S, Rampurwa |  | 1 | [11 empty] | Bind up List - 81 (S.No.-11) | bindup
91 | MS-9 | Darbhanga | 2009-10 | दरभंगा | बहादुरपुर | 1 | Govt. Basic School Ughara | 272.1833 | [11 empty] | 1 | Inaugurated
92 | MS-9 | Darbhanga | 2009-10 | दरभंगा | बहेरी | 2 | Govt. Basic School Machchhi | 272.1833 | [11 empty] | 1 | Inaugurated
93 | MS-9 | Darbhanga | 2009-10 | दरभंगा | दरभंगा | 3 | H/S,Atihar | 272.1833 | [11 empty] | 1 | Inaugurated
94 | MS-10 | Darbhanga | 2009-10 | मधुबनी | बेनीपट्टी | 1 | Govt. Basic School Shahpur | 269.825 | [11 empty] | 1 | Inaugurated
95 | MS-10 | Darbhanga | 2009-10 | मधुबनी | अंधराठाढ़ी | 2 | H/S.Andhra Thari | 269.825 | [11 empty] | 1 | Inaugurated
96 | MS-11 | Darbhanga | 2009-10 | समस्तीपुर | कलयानपुर | 1 | Govt. Basic School,Janardanpur | 263.31 | [11 empty] | 1 | Inaugurated
97 | MS-11 | Darbhanga | 2009-10 | समस्तीपुर | समस्तीपुर | 2 | Govt. Basic School,Chatauna | 263.31 | [11 empty] | 1 | Inaugurated
98 | MS-113 | Darbhanga | 2010-11 | मधुबनी | बासोपट्टी | 1 | Govt. Basic School, Sukhasi | 285.2691 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-12) | bindup
99 | MS-113 | Darbhanga | 2010-11 | मधुबनी | बिस्फी | 2 | Govt. Basic School, Simari | 285.2691 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-13) | bindup
100 | MS-114 | Darbhanga | 2010-11 | मधुबनी | हरलाखी | 1 | Govt. Basic School, Hisar | 285.1985 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-14) | bindup
101 | MS-114 | Darbhanga | 2010-11 | मधुबनी | मधवापुर | 2 | Govt. Basic School, Rema | 285.1985 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-15) | bindup
102 | MS-115 | Darbhanga | 2010-11 | मधुबनी | झंझारपुर | 1 | Kejriwal H/S, Jhanjharpur | 278.0067 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
103 | MS-115 | Darbhanga | 2010-11 | मधुबनी | लखनौर | 2 | High School, Lakhnaur | 278.0067 | [11 empty] | 1 | Inaugurated
104 | MS-115 | Darbhanga | 2010-11 | मधुबनी | मधेपुर | 3 | High School, Madhepur | 278.0067 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Dispute
105 | MS-116 | Darbhanga | 2010-11 | मधुबनी | बाबूबरही | 1 | J.N. H/S, Babubarhi | 279.2203 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-60) | bindup
106 | MS-116 | Darbhanga | 2010-11 | मधुबनी | पंडौल | 2 | Govt. Basic School, Maukarampur | 279.2203 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-61) | bindup
107 | MS-116 | Darbhanga | 2010-11 | मधुबनी | राजनगर | 3 | Govt. Basic School, Nakati | 279.2203 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-62) | bindup
108 | MS-117 | Darbhanga | 2010-11 | मधुबनी | घोघरडीहा | 1 | High School, Devadh | 289.52 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-15). Inaugurated 16.07.2016. | bindup
109 | MS-117 | Darbhanga | 2010-11 | मधुबनी | लौकही | 2 | High School, Laukhi | 289.52 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-63). Inaugurated 16.07.2016. | bindup
110 | MS-117 | Darbhanga | 2010-11 | मधुबनी | फुलपरास | 3 | High School, Phulparas | 289.52 | [10 empty] | 1 |  | Inaugurated 16.07.2016
111 | MS-118 | Darbhanga | 2010-11 | मधुबनी | जयनगर | 1 | High School, Jainagar | 285.0467 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-17) | bindup
112 | MS-118 | Darbhanga | 2010-11 | मधुबनी | कलुआही | 2 | High School, Narar | 285.0467 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-64) | bindup
113 | MS-118 | Darbhanga | 2010-11 | मधुबनी | खजौली | 3 | High School, Khajauli | 285.0467 | [11 empty] | 1
114 | MS-119 | Darbhanga | 2010-11 | मधुबनी | खुटौना | 1 | High School, Khutauna | 310.2473 | [11 empty] | 1 | Inaugurated 16.07.2016
115 | MS-119 | Darbhanga | 2010-11 | मधुबनी | लदनिया | 2 | High School, Matha Ladania | 310.2473 | [11 empty] | 1 | Inaugurated 16.07.2016
116 | MS-196 | Darbhanga | 2010-11 | समस्तीपुर | उजियारपुर | 1 | Govt. Basic School, Kariyara | 264.5567 | [11 empty] | 1 | Inaugurated
117 | MS-196 | Darbhanga | 2010-11 | समस्तीपुर | मोरवा | 2 | Govt. Basic School, Mariya | 264.5567 | [11 empty] | 1 | Inaugurated
118 | MS-196 | Darbhanga | 2010-11 | समस्तीपुर | रोसरा | 3 | Govt. Basic School, Dharmpur | 264.5567 | [11 empty] | 1 | Inaugurated
119 | MS-197 | Darbhanga | 2010-11 | समस्तीपुर | दलसिंघसराय | 1 | Govt. Basic School, Salkhani | 263.865 | [11 empty] | 1 | Inaugurated
120 | MS-197 | Darbhanga | 2010-11 | समस्तीपुर | बिभुतिपुर | 2 | L.L. H/S, Sirsi | 263.865 | [11 empty] | 1 | Inaugurated
121 | MS-198 | Darbhanga | 2010-11 | दरभंगा | बेनीपुर | 1 | Jayanand H/S. Bahera | 257.498 | [11 empty] | 1 | Inaugurated 16.07.2016
122 | MS-198 | Darbhanga | 2010-11 | दरभंगा | किरतपुर | 2 | H/S, Rasiyari | 257.498 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available (required land 293'x250' avlaible land25'x15')
123 | MS-199 | Darbhanga | 2010-11 | दरभंगा | घनश्यामपुर | 1 | Janta H/S, Shivnagar Gah | 276.465 | [11 empty] | 1 | Inaugurated
124 | MS-199 | Darbhanga | 2010-11 | दरभंगा | गौरबौरम | 2 | H/S, Azi | 276.465 | [11 empty] | 1 | Inaugurated 16.07.2016
125 | MS-200 | Darbhanga | 2010-11 | दरभंगा | केवटी | 1 | R.J. H/S, Keoti Baubari | 272.08 | [11 empty] | 1 | Bind up List - 81 (S.No.-18) Inaugurated 16.07.2016. | bindup
126 | MS-200 | Darbhanga | 2010-11 | दरभंगा | जाले | 2 | Govt. Basic School, Daughara | 272.08 | [11 empty] | 1 | Inaugurated
127 | MS-201 | Darbhanga | 2010-11 | दरभंगा | तारडीह | 1 | Govt. Basic School, Narayanpur | 272.815 | [11 empty] | 1 | Inaugurated 16.07.2016
128 | MS-201 | Darbhanga | 2010-11 | दरभंगा | मनीगाछी | 2 | High School, Nehra | 272.815 | [11 empty] | 1 | Inaugurated 16.07.2016
129 | MS-202 | Darbhanga | 2010-11 | दरभंगा | हायाघाट | 1 | Govt. Basic School, Sree rampur | 277.42 | [11 empty] | 1 | Inaugurated 16.07.2016
130 | MS-202 | Darbhanga | 2010-11 | दरभंगा | सिंघवारा | 2 | Govt. Basic School, Haripur Ladaur | 277.42 | [11 empty] | 1 | Inaugurated
131 | MS-202 | Darbhanga | 2010-11 | दरभंगा | हनुमाननगर | 3 | Govt. Basic School, Goraipatti | 277.42 | [11 empty] | 1 | Inaugurated
132 | MS-203 | Darbhanga | 2010-11 | दरभंगा | कुशेश्वर स्थान पूर्वी | 1 | S.K. H/S, Kusheshwar Asthan |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
133 | MS-203 | Darbhanga | 2010-11 | दरभंगा | कुशेश्वर स्थान | 2 | G.P. H/S, Bhahar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
134 | MS-203 | Darbhanga | 2010-11 | दरभंगा | बिरौल | 3 | Onkar H/S, Supaul Bazar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
135 | MS-12 | Patna East | 2009-10 | पटना | मसौढी | 1 | H/S.Masaurhi |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
136 | MS-12 | Patna East | 2009-10 | पटना | पुनपुन | 2 | H/S.Punpun |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
137 | MS-12 | Patna East | 2009-10 | पटना | पालीगंज | 3 | H/S Chandhosh |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started
138 | MS-13 | Patna East | 2009-10 | नालंदा | अस्था'वा | 1 | Govt. Basic School, Balwapur | 248.12 | [11 empty] | 1 | Inaugurated 16.07.2016
139 | MS-13 | Patna East | 2009-10 | नालंदा | रहुई | 2 | H/S.Mauriyachak Supasan | 248.12 | [11 empty] | 1
140 | MS-13 | Patna East | 2009-10 | नालंदा | हिलसा | 3 | H/S.Hilsa | 248.12 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-19) | bindup
141 | MS-14 | Patna East | 2009-10 | भोजपुर | पिरो | 1 | Govt. Basic School, Rajaiya | 249.9385 |  |  | 1 | 0 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-20) | bindup
142 | MS-14 | Patna East | 2009-10 | भोजपुर | तरारी | 2 | H/S.Barkagaon | 249.9385 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-21) | bindup
143 | MS-15 | Patna West | 2009-10 | रोहतास | सासाराम | 1 | H/S.Takia | 254.655 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | local dispute
144 | MS-15 | Patna West | 2009-10 | रोहतास | करहगर | 2 | Govt. Basic School, Sawan Bahar | 254.655 | [11 empty] | 1 | Inaugurated
145 | MS-16 | Patna West | 2009-10 | बक्‍सर | राजपुर | 1 | H/S.Rajpur | 279.43 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-22) | bindup
146 | MS-16 | Patna West | 2009-10 | बक्‍सर | इटाढी | 2 | Govt. Basic School, Unwas | 279.43 | [10 empty] | 1
147 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | मोहनियॉं | 1 | Govt. Basic School, Mohaniya | 266.0866 | [8 empty] | 1 |  |  |  | Bind up List - 81 (S.No.-23) | bindup
148 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | भभुआ | 2 | H/S.Akhlashpur | 266.0866 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-24) | bindup
149 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | दुर्गावती | 3 | H/S.Kampura | 266.0866 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-25) | bindup
150 | MS-101 | Patna East | 2010-11 | पटना | मनेर | 1 | M.Y. H/S, Gorakhatola | 270.8633 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not Available Site changed proposal goes to BMSP
151 | MS-101 | Patna East | 2010-11 | पटना | बिहटा | 2 | R.T.P. H/S, Bihta (Anandpur) | 270.8633 | [10 empty] | 1
152 | MS-101 | Patna East | 2010-11 | पटना | बिक्रम | 3 | D.D.S. H/S, Morlawa | 270.8633 | [11 empty] | 1 | Inaugurated
153 | MS-102 | Patna East | 2010-11 | पटना | दानापुर | 1 | R.G.S.S. School, khagaul | 272.9533 | [10 empty] | 1
154 | MS-102 | Patna East | 2010-11 | पटना | दुलिहन बाजार | 2 | Basidhar H/S, Bharatpur | 272.9533 | [11 empty] | 1 | Inaugurated
155 | MS-102 | Patna East | 2010-11 | पटना | नौबतपुर | 3 | Govt. H/S, Amarpur (Chiraura) | 272.9533 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-26) | bindup
156 | MS-103 | Patna East | 2010-11 | पटना | धनरूआ | 1 | H/S, Biroiyara | 266.355 | [10 empty] | 1
157 | MS-103 | Patna East | 2010-11 | पटना | खुसरुपुर | 2 | Mahadeo H/S, Khusrupur | 266.355 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-65) | bindup
158 | MS-104 | Patna East | 2010-11 | पटना | दनियावां | 1 | Rajkiyakrit H/S, Daniyawa | 265.115 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land not available
159 | MS-104 | Patna East | 2010-11 | पटना | फतुहॉ | 2 | A.N.S, H/S, Usfa | 265.115 | [10 empty] | 1
160 | MS-105 | Patna East | 2010-11 | पटना | बेल्‍छी | 1 | Govt. H/S, Saksohars | 267.5533 | [11 empty] | 1 | Inaugurated
161 | MS-105 | Patna East | 2010-11 | पटना | मोकामा | 2 | R.A. H/S, Mokama | 267.5533 | [11 empty] | 1 | Inaugurated
162 | MS-105 | Patna East | 2010-11 | पटना | पण्‍डारक | 3 | P.B.M. H/S, Pandark | 267.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
163 | MS-106 | Patna East | 2010-11 | पटना | घोसवरी | 1 | Govt. H/S, Kurmichak | 268.99 | [10 empty] | 1
164 | MS-106 | Patna East | 2010-11 | पटना | बख्तियारपुर | 2 | Govt. H/S, Sawani | 268.99 | [11 empty] | 1 | Inaugurated
165 | MS-106 | Patna East | 2010-11 | पटना | बाढ | 3 | Govt. H/S, Badhna | 268.99 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-27) | bindup
166 | MS-107 | Patna West | 2010-11 | बक्‍सर | बक्‍सर | 1 | Govt. Basic School, Karhansi | 260.5633 | [11 empty] | 1 | Inaugurated 16.07.2016
167 | MS-107 | Patna West | 2010-11 | बक्‍सर | चौसा | 2 | Govt. Basic School, Saraiya | 260.5633 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | School not locate
168 | MS-107 | Patna West | 2010-11 | बक्‍सर | डुमरॉंव | 3 | (+2) Raj H/S, Dumraon | 260.5633 | [11 empty] | 1 | Inaugurated 16.07.2016
169 | MS-108 | Patna West | 2010-11 | बक्‍सर | ब्रहम्‍पुर | 1 | (+2) B.N. H/S, Brahampur | 264.1167 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-28) | bindup
170 | MS-108 | Patna West | 2010-11 | बक्‍सर | सिमरी | 2 | (+2) H/S, Simri | 264.1167 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-29) | bindup
171 | MS-108 | Patna West | 2010-11 | बक्‍सर | केसठ | 3 | (+2) H/S, Kesath | 264.1167 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-30) | bindup
172 | MS-135 | Patna East | 2010-11 | भोजपुर | बरहारा | 1 | Govt. Basic School, Barhara | 261.4577 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not start
173 | MS-135 | Patna East | 2010-11 | भोजपुर | बिहिया | 2 | (+2) H/S, Bihia | 261.4577 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-31) | bindup
174 | MS-136 | Patna East | 2010-11 | भोजपुर | कोइलवर | 1 | M.B. H/S, Kulhariya | 260.46 | [10 empty] | 1
175 | MS-136 | Patna East | 2010-11 | भोजपुर | उदवंतनगर | 2 | H/S, Udwant Nagar | 260.46 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land dispute
176 | MS-136 | Patna East | 2010-11 | भोजपुर | चरपोखरी | 3 | Macha H/S, Barami | 260.46 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-32) | bindup
177 | MS-137 | Patna East | 2010-11 | भोजपुर | साहार | 1 | H/S, Sahar, Bhojpur | 254.915 | [11 empty] | 1 | Inaugurated
178 | MS-137 | Patna East | 2010-11 | भोजपुर | सन्देश | 2 | H/S, Sandesh | 254.915 | [11 empty] | 1 | Inaugurated
179 | MS-138 | Patna East | 2010-11 | भोजपुर | गरहनि | 1 | R.D. H/S, Garhani | 261.065 | [11 empty] | 1 | Inaugurated
180 | MS-138 | Patna East | 2010-11 | भोजपुर | अगिआव | 2 | Govt. Basic School, Agiaon | 261.065 | [11 empty] | 1 | Inaugurated 16.07.2016
181 | MS-139 | Patna East | 2010-11 | नालंदा | सिलाव | 1 | Gandhi h.s.Silaw |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
182 | MS-139 | Patna East | 2010-11 | नालंदा | राजगीर | 2 | R.D.H.S. Rajgir |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
183 | MS-140 | Patna East | 2010-11 | नालंदा | कतरीसराय | 1 | H.S. Badi | 251.6 | [11 empty] | 1 | Inaugurated
184 | MS-140 | Patna East | 2010-11 | नालंदा | गिरियक | 2 | H/S, Giriak Adampur | 251.6 | [11 empty] | 1 | Inaugurated
185 | MS-141 | Patna East | 2010-11 | नालंदा | नगरनौसा | 1 | H.S. Nagarnousa | 257.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Problem
186 | MS-141 | Patna East | 2010-11 | नालंदा | चण्डी | 2 | Govt. Basic School, Kaurnawa | 257.13 | [11 empty] | 1 | Inaugurated
187 | MS-142 | Patna East | 2010-11 | नालंदा | थरथरी | 1 | H/S, Bhathar | 248.765 | [11 empty] | 1 | handover
188 | MS-142 | Patna East | 2010-11 | नालंदा | नुरसराय | 2 | H/S, Noorsarai | 248.765 | [11 empty] | 1 | handover
189 | MS-143 | Patna East | 2010-11 | नालंदा | ईस्लामपुर | 1 | Govt. Basic School, Sanda | 249.4 | [11 empty] | 1 | Inaugurated
190 | MS-143 | Patna East | 2010-11 | नालंदा | बिन्द | 2 | H/S, Eksara | 249.4 | [11 empty] | 1 | Inaugurated
191 | MS-143 | Patna East | 2010-11 | नालंदा | ए'कगरसराय | 3 | S.S. Academy, Ekangarsarai | 249.4 | [11 empty] | 1 | Inaugurated
192 | MS-144 | Patna East | 2010-11 | नालंदा | हरनौत | 1 | Govt. Basic School, Gokulpur Math | 257.7167 | [11 empty] | 1 | Inaugurated 16.07.2016
193 | MS-144 | Patna East | 2010-11 | नालंदा | सरमेरा | 2 | H/S, Sarmera | 257.7167 | [11 empty] | 1 | Inaugurated
194 | MS-144 | Patna East | 2010-11 | नालंदा | बिन्द | 3 | H/S, Bind | 257.7167 | [11 empty] | 1 | Inaugurated
195 | MS-145 | Patna West | 2010-11 | रोहतास | अकोढ़ीगोला | 1 | H.S. Prem Nagar, Akodhigola | 254.4719 | [11 empty] | 1 | Inaugurated
196 | MS-145 | Patna West | 2010-11 | रोहतास | डिहरी | 2 | H.S. Dihri-on-sone, Dehri | 254.4719 | [11 empty] | 1 | Inaugurated
197 | MS-146 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 1 | Govt. Basic School, Kabhai | 269.2706 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-33) | bindup
198 | MS-146 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 2 | R.R. H.S. Suryappura | 269.2706 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-66) | bindup
199 | MS-146 | Patna West | 2010-11 | रोहतास | दावत | 3 | R.P.S. H.S.Kabai, Dawath | 269.2706 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-67) | bindup
200 | MS-147 | Patna West | 2010-11 | रोहतास | कोचस | 1 | H.S. Kochas | 269.1185 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-68) | bindup
201 | MS-147 | Patna West | 2010-11 | रोहतास | दिनारा | 2 | M.H.S. Basdihan, Dinara | 269.1185 | [10 empty] | 1
202 | MS-148 | Patna West | 2010-11 | रोहतास | नोखा | 1 | H.S. Garh Nokha, Nokha | 277.4303 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-69) Inaugurated 16.07.2016 | bindup
203 | MS-148 | Patna West | 2010-11 | रोहतास | काराकाट | 2 | S.S.D.H.S. Amauna, Karakat | 277.4303 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-34) Inaugurated 16.07.2016. | bindup
204 | MS-148 | Patna West | 2010-11 | रोहतास | नासरीगंज | 3 | Basant H.S. Itimiha Karma | 277.4303 | [10 empty] | 1 |  | Inaugurated 16.07.2016
205 | MS-149 | Patna West | 2010-11 | रोहतास | चेनारी | 1 | R.D.G.H.S. Chenari | 261.7963 | [11 empty] | 1 | Inaugurated 16.07.2016
206 | MS-149 | Patna West | 2010-11 | रोहतास | शिवसागर | 2 | S.D.H.S. Sheo Sagar | 261.7963 | [11 empty] | 1 | Inaugurated 16.07.2016
207 | MS-150 | Patna West | 2010-11 | रोहतास | नौहट्टा | 1 | H.S.Boulian | 266.18 | [11 empty] | 1 | Inaugurated
208 | MS-151 | Patna West | 2010-11 | रोहतास | तिलौथु | 1 | H.S.Tilauthu | 251.97 | [11 empty] | 1 | Inaugurated
209 | MS-35 | Purnea | 2009-10 | पूर्णिया | धमदाहा | 1 | Govt. Basic School Purandaha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
210 | MS-35 | Purnea | 2009-10 | पूर्णिया | बरहरा कोठी | 2 | Govt. Basic School Diwrawanar |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
211 | MS-35 | Purnea | 2009-10 | पूर्णिया | बनमनखी | 3 | Govt. Basic School Dheema |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
212 | MS-36 | Purnea | 2009-10 | अररिया | रानीगंज | 1 | H./S.Raniganj | 265.13 | [11 empty] | 1 | Inaugurated 16.07.2016
213 | MS-36 | Purnea | 2009-10 | अररिया | फारबिसगंज | 2 | Govt. Basic School Haripur | 265.13 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-70) | bindup
214 | MS-36 | Purnea | 2009-10 | अररिया | भरगामा | 3 | H/S.Bhargama | 265.13 | [11 empty] | 1 | Inaugurated 16.07.2016
215 | MS-37 | Purnea | 2009-10 | कटिहार | कोढा | 1 | Govt. Basic School, Gorawari | 261.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land litigation
216 | MS-37 | Purnea | 2009-10 | कटिहार | कटिहार | 2 | P.T.T.C Musapur | 261.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land litigation
217 | MS-37 | Purnea | 2009-10 | कटिहार | मनिहारी | 3 | H/S.Nawabganj | 261.1 | [11 empty] | 1 | Inaugurated
218 | MS-38 | Purnea | 2009-10 | किशनगंज | दिघलबैंक | 1 | H/S. Tulsiya | 268.65 | [11 empty] | 1 | Inaugurated
219 | MS-38 | Purnea | 2009-10 | किशनगंज | ठाकुरगंज | 2 | H/S. Thakurganj | 268.65 | [11 empty] | 1 | Inaugurated
220 | MS-166 | Purnea | 2010-11 | पूर्णिया | पूर्णिया पूर्व | 1 | Govt. Basic School, Chadirjiganj | 279.8518 | [11 empty] | 1 | Bind up List - 81 (S.No.-71) | bindup
221 | MS-166 | Purnea | 2010-11 | पूर्णिया | कृत्यानन्द नगर | 2 | Govt. Basic School, Kalyanpur | 279.8518 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-72) | bindup
222 | MS-166 | Purnea | 2010-11 | पूर्णिया | कसबा | 3 | Govt. Basic School, Sabdalpur | 279.8518 | [11 empty] | 1 | Bind up List - 81 (S.No.-73) | bindup
223 | MS-167 | Purnea | 2010-11 | पूर्णिया | जलालगढ | 1 | N.D. Rungta H/S, Jalalgarh | 265.5533 | [11 empty] | 1 | Inaugurated
224 | MS-167 | Purnea | 2010-11 | पूर्णिया | श्रीनगर | 2 | Govt. Basic School, Srinagar | 265.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
225 | MS-167 | Purnea | 2010-11 | पूर्णिया | डगरुआ | 3 | H/S, Soura | 265.5533 | [11 empty] | 1 | Inaugurated 16.07.2016
226 | MS-168 | Purnea | 2010-11 | पूर्णिया | बायसी | 1 | H/S, Baisi | 277.9267 | [11 empty] | 1 | Inaugurated 16.07.2016
227 | MS-168 | Purnea | 2010-11 | पूर्णिया | वैसा | 2 | T.N.H/S, Piyaji | 277.9267 | [11 empty] | 1 | Inaugurated
228 | MS-169 | Purnea | 2010-11 | पूर्णिया | भवानीपुर | 1 | Govt. Basic School, Barhari | 287.8399 | [11 empty] | 1 | Inaugurated 16.07.2016
229 | MS-169 | Purnea | 2010-11 | पूर्णिया | रूपौली | 2 | Govt. Basic School, Sapaha | 287.8399 | [11 empty] | 1 | Inaugurated 16.07.2016
230 | MS-170 | Purnea | 2010-11 | कटिहार | समेली | 1 | D.G. H/S, Krishna Ngr | 266.0706 | [11 empty] | 1 | Inaugurated 16.07.2016
231 | MS-170 | Purnea | 2010-11 | कटिहार | आजमनगर | 2 | R.K. H/S, Azam Ngr | 266.0706 | 1 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | LAND PROBLEM
232 | MS-171 | Purnea | 2010-11 | कटिहार | फलका | 1 | Govt. Basic School, Mangha | 261.711 | [8 empty] | 1 |  |  |  | Bind up List - 81 (S.No.-74) | bindup
233 | MS-171 | Purnea | 2010-11 | कटिहार | कुर्सेला | 2 | A.P. H/S Ayodhyaganj | 261.711 | [11 empty] | 1 | Inaugurated 16.07.2016
234 | MS-172 | Purnea | 2010-11 | कटिहार | डंडखोरा | 1 | SadaNand H/S, Dumaria |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | Retender
235 | MS-7 | Bhagalpur | 2009-10 | भागलपुर | सन्‍हौला | 1 | Govt. Basic School Bhuriya | 251.0533 | [11 empty] | 1 | Inaugurated
236 | MS-7 | Bhagalpur | 2009-10 | भागलपुर | कहलगांव | 2 | Govt. Basic School Shobhnathpur | 251.0533 | [11 empty] | 1 | Inaugurated
237 | MS-7 | Bhagalpur | 2009-10 | भागलपुर | पिरपैती | 3 | Govt. Basic School Panchrukhi | 251.0533 | [11 empty] | 1 | Inaugurated
238 | MS-8 | Bhagalpur | 2009-10 | बांका | कटोरिया | 1 | Govt. Basic School Karjhausa | 245.86 | [11 empty] | 1 | Inaugurated
239 | MS-8 | Bhagalpur | 2009-10 | बांका | बौंसी | 2 | H/S.Maniyarpur | 245.86 | [11 empty] | 1 | Inaugurated
240 | MS-133 | Bhagalpur | 2010-11 | बांका | रजौन | 1 | Govt. Basic School, Chilkawar | 268.9202 | [11 empty] | 1 | Inaugurated 16.07.2016
241 | MS-133 | Bhagalpur | 2010-11 | बांका | धोरैया | 2 | Tribhuwan Academy | 268.9202 | [11 empty] | 1 | Inaugurated 16.07.2016
242 | MS-204 | Bhagalpur | 2010-11 | भागलपुर | सबौर | 1 | H/S, Parsadih Simri | 255.71 | [11 empty] | 1 | Inaugurated 16.07.2016
243 | MS-204 | Bhagalpur | 2010-11 | भागलपुर | जगदीशपुर | 2 | Loknath H/S, Jagdishpur | 255.71 |  |  |  | . | [6 empty] | 1 |  | Bind up List - 81 (S.No.-75) | bindup
244 | MS-204 | Bhagalpur | 2010-11 | भागलपुर | नाथनगर | 3 | H/S, Shapur | 255.71 | [10 empty] | 1
245 | MS-205 | Bhagalpur | 2010-11 | भागलपुर | गोराडीह | 1 | H/S, Jamin Murhan Hat | 267.6047 | [11 empty] | 1 | handover
246 | MS-205 | Bhagalpur | 2010-11 | भागलपुर | शाहकुण्‍ड | 2 | Govt. Basic School, Hajipur | 267.6047 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-35) | bindup
247 | MS-205 | Bhagalpur | 2010-11 | भागलपुर | सुलतानगंज | 3 | H/S, Karharia | 267.6047 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-76) | bindup
248 | MS-206 | Bhagalpur | 2010-11 | भागलपुर | बिहपुर | 1 | M.S. H/S, Bihpur | 257.335 | [11 empty] | 1 | Inaugurated
249 | MS-206 | Bhagalpur | 2010-11 | भागलपुर | खारीक | 2 | Govt. Basic School, Telghi | 257.335 | [11 empty] | 1 | Inaugurated
250 | MS-207 | Bhagalpur | 2010-11 | भागलपुर | नवगछिया | 1 | H/S, Sahu Parbatta | 263.845 | [11 empty] | 1 | Inaugurated 16.07.2016
251 | MS-207 | Bhagalpur | 2010-11 | भागलपुर | गोपालपुर | 2 | Govt. Basic School, Tintanga | 263.845 | [11 empty] | 1 | Inaugurated 16.07.2016
252 | MS-24 | Magadh | 2009-10 | गया | फतेहपुर | 1 | H/S.Fatehpur | 261.2343 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-77) | bindup
253 | MS-24 | Magadh | 2009-10 | गया | वजीरगन्ज | 2 | H/S.Wazirgznj | 261.2343 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-36) | bindup
254 | MS-24 | Magadh | 2009-10 | गया | शेरघाटी | 3 | P.T.T.C. Sherghati | 261.2343 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Site to be changed.
255 | MS-25 | Magadh | 2009-10 | औरंगाबाद | मदनपुर | 1 | H/S.Beri | 260.8732 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-37) | bindup
256 | MS-25 | Magadh | 2009-10 | औरंगाबाद | नबीनगर | 2 | H/S.Nabinagar | 260.8732 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Not Started,
257 | MS-25 | Magadh | 2009-10 | औरंगाबाद | कुटुम्बा | 3 | Govt. Basic School, Rampur Parsa | 260.8732 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-38) | bindup
258 | MS-26 | Magadh | 2009-10 | जहानाबाद | मखदुमपुर | 1 | Govt. Basic School, Meera Bigha | 245.2 | [10 empty] | 1 |  | plaseter going on
259 | MS-26 | Magadh | 2009-10 | जहानाबाद | हुलासगंज | 2 | Govt. Basic School, Dogra | 245.2 | [10 empty] | 1 |  | plaster done, rest work in progress
260 | MS-27 | Magadh | 2009-10 | अरवल | करपी | 1 | Govt. Basic School, Pariyahi Bazar | 252.3738 | [10 empty] | 1 |  | Plaster going on
261 | MS-27 | Magadh | 2009-10 | अरवल | कलेर | 2 | H/S.Kaler | 252.3738 | [10 empty] | 1 |  | ,
262 | MS-28 | Magadh | 2009-10 | नवादा | सिरदला | 1 | H/S.Sirdala | 245.2067 | [10 empty] | 1 |  | Plaster going on
263 | MS-28 | Magadh | 2009-10 | नवादा | रजौली | 2 | H/S.Chiraita | 245.2067 | [10 empty] | 1 |  | Plaster going on
264 | MS-28 | Magadh | 2009-10 | नवादा | हिसुआ | 3 | Govt.Basic School Wagodar | 245.2067 | [10 empty] | 1 |  | Plaster going on
265 | MS-152 | Magadh | 2010-11 | अरवल | कुर्था | 1 | H/S, Kurtha |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
266 | MS-152 | Magadh | 2010-11 | अरवल | सोनभद्र बंशी सुर्यापूर | 2 | H/S, Khatangi |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
267 | MS-153 | Magadh | 2010-11 | गया | मानपुर | 1 | H.S.Rasalpur | 245.9767 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-39) | bindup
268 | MS-153 | Magadh | 2010-11 | गया | बोधगया | 2 | H.S. Bodhgaya | 245.9767 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-78) | bindup
269 | MS-153 | Magadh | 2010-11 | गया | बेलागन्ज | 3 | A.H.S. Belaganj | 245.9767 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-40) | bindup
270 | MS-154 | Magadh | 2010-11 | गया | टिकारी | 1 | Govt. Basic School, Bhawanpur | 259.0612 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-41) | bindup
271 | MS-154 | Magadh | 2010-11 | गया | कोन्च | 2 | G.H.S. Konch | 259.0612 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-42) | bindup
272 | MS-154 | Magadh | 2010-11 | गया | परैया | 3 | A.H.S. Paraiya | 259.0612 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-43) | bindup
273 | MS-155 | Magadh | 2010-11 | गया | टनकुप्पा | 1 | Govt. Basic School, Makhdumpur |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | Retender
274 | MS-155 | Magadh | 2010-11 | गया | गुरारु | 2 | B.S.H.S. Esmailpur |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Retender
275 | MS-156 | Magadh | 2010-11 | गया | डॊभी | 1 | Govt. Basic School, Bajaura | 263.173 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-44) | bindup
276 | MS-156 | Magadh | 2010-11 | गया | मोहनपुर | 2 | H.S.Mohanpur | 263.173 | [5 empty] | 1 | 0 | [5 empty] | Bind up List - 81 (S.No.-45) | bindup
277 | MS-156 | Magadh | 2010-11 | गया | बाराचट्टी | 3 | Govt. Basic School, Pataluka | 263.173 | 1 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | Not Started,
278 | MS-157 | Magadh | 2010-11 | गया | ईमामगन्ज | 1 | Govt. Basic School, Wara |  | 1 | 0 | 0 |  |  |  |  | 0
279 | MS-157 | Magadh | 2010-11 | गया | डुमरीया | 2 | J.H.S. Dumariya |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | MS-158 | Magadh | 2010-11 | गया | आमस | 1 | H.S. Amas | 262.4687 | [6 empty] | 1 | [5 empty] | Bind up List - 81 (S.No.-46) | bindup
281 | MS-158 | Magadh | 2010-11 | गया | गुरुआ | 2 | H.S. Bharsanthu (Bharaundha) | 262.4687 |  |  |  | 1 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-47) | bindup
282 | MS-158 | Magadh | 2010-11 | गया | मोहडा | 3 | Govt. Basic School, Jatian | 262.4687 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
283 | MS-159 | Magadh | 2010-11 | गया | अतरी | 1 | H.S.Tetua | 246.16 | [10 empty] | 1
284 | MS-159 | Magadh | 2010-11 | गया | बथानी | 2 | Govt. Basic School, Rahui | 246.16 | [10 empty] | 1 |  | plaster, flooring going on
285 | MS-159 | Magadh | 2010-11 | गया | खिजरसराय | 3 | H.S. Khijarsarai | 246.16 | [10 empty] | 1
286 | MS-160 | Magadh | 2010-11 | गया | Chandouti | 1 | H.S. Chandaouti | 245.61 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-79) | bindup
287 | MS-161 | Magadh | 2010-11 | जहानाबाद | घोसी | 1 | H.S. Ghoshi | 249.55 | [10 empty] | 1 |  | plaster done, rest work in progress
288 | MS-161 | Magadh | 2010-11 | जहानाबाद | जहानाबाद | 2 | H.S.Pandooe | 249.55 | [10 empty] | 1 |  | plaster done, rest work in progress
289 | MS-162 | Magadh | 2010-11 | जहानाबाद | मोदनगंज | 1 | H.S. Okari, Modanganj | 249.55 | [11 empty] | 1 | Inaugurated
290 | MS-162 | Magadh | 2010-11 | जहानाबाद | रातनीफरीदपुर | 2 | H.S. Sarta | 249.55 | [11 empty] | 1 | Inaugurated
291 | MS-177 | Magadh | 2010-11 | नवादा | कौवाकोल | 1 | Govt. Basic School, Baraun Bajitpur | 245.0467 | [10 empty] | 1
292 | MS-177 | Magadh | 2010-11 | नवादा | रोह | 2 | Inter School, Roh | 245.0467 | [10 empty] | 1 |  | plaster, flooring going on
293 | MS-177 | Magadh | 2010-11 | नवादा | नारदीगंज | 3 | Govt. Basic School, Nadariganj | 245.0467 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land not available
294 | MS-178 | Magadh | 2010-11 | नवादा | वारिसलिगंज | 1 | Govt. Basic School, Dariyapur | 247.0759 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | land not available
295 | MS-178 | Magadh | 2010-11 | नवादा | काशीचक | 2 | Inter School, Chandinawa | 247.0759 | [11 empty] | 1
296 | MS-179 | Magadh | 2010-11 | नवादा | गोविन्‍दपुर | 1 | Inter School, Govindpur | 250.4326 | [11 empty] | 1
297 | MS-179 | Magadh | 2010-11 | नवादा | पकरीबरावॉं | 2 | Inter School, Pakribarawan | 250.4326 | [11 empty] | 1
298 | MS-180 | Magadh | 2010-11 | नवादा | नरहट | 1 | Inter School, Narhat | 262.1334 | [11 empty] | 1 | Inaugurated 16.07.2016
299 | MS-180 | Magadh | 2010-11 | नवादा | अकबरपुर | 2 | Govt. Basic School, Gopalpur | 262.1334 | [11 empty] | 1 | Inaugurated 16.07.2016
300 | MS-181 | Magadh | 2010-11 | नवादा | मेसकौर | 1 | Inter School, Meskaur | 237.81 |  |  | 1 | 0 | 0 | 0 | 0 | [5 empty] | Bind up List - 81 (S.No.-48) | bindup
301 | MS-182 | Magadh | 2010-11 | औरंगाबाद | औरंगाबाद | 1 | Govt. M/S, Babhandi | 257.395 | [11 empty] | 1 | Inaugurated 16.07.2016
302 | MS-182 | Magadh | 2010-11 | औरंगाबाद | बारुन | 2 | R.D.B. H/S, Sunderganj | 257.395 | [11 empty] | 1 | Inaugurated 16.07.2016
303 | MS-183 | Magadh | 2010-11 | औरंगाबाद | देव | 1 | Govt. Basic School, Vishnupur | 257.4903 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-49) | bindup
304 | MS-183 | Magadh | 2010-11 | औरंगाबाद | रफीगंज | 2 | R.B.R. H/S, Rafiganj | 257.4903 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not Started,
305 | MS-184 | Magadh | 2010-11 | औरंगाबाद | हसपुरा | 1 | Govt. Basic School, Dindir | 254.09 | [10 empty] | 1
306 | MS-18 | Munger | 2009-10 | मुंगेर | धरहरा | 1 | Govt. Basic School, Ghatwari | 257.0628 | [10 empty] | 1
307 | MS-18 | Munger | 2009-10 | मुंगेर | हवेली खड़गपुर | 2 | Govt. Basic School, Khand Bihari | 257.0628 | [10 empty] | 1
308 | MS-19 | Munger | 2009-10 | जमुई | चकाई | 1 | H/S.Chakai | 241.98 | [10 empty] | 1
309 | MS-19 | Munger | 2009-10 | जमुई | खैरा | 2 | Govt. Basic School, Dawilgadh | 241.98 | [10 empty] | 1
310 | MS-19 | Munger | 2009-10 | जमुई | सोनो | 3 | M/S Batiya | 241.98 | [10 empty] | 1
311 | MS-20 | Munger | 2009-10 | लखीसराय | सुर्यगढ़ा | 1 | Govt. Basic School, Kiranpur | 253.495 | [11 empty] | 1
312 | MS-20 | Munger | 2009-10 | लखीसराय | हलसी | 2 | H/S. Halsi | 253.495 | [11 empty] | 1
313 | MS-21 | Munger | 2009-10 | शेखपुरा | बरबीघा | 1 | Govt. Basic School Sarba | 240.39 | [11 empty] | 1 | Inaugurated 16.07.2016
314 | MS-21 | Munger | 2009-10 | शेखपुरा | शेखपुरा | 2 | M/S. Sheikhpura | 240.39 | [11 empty] | 1 | Inaugurated 16.07.2016
315 | MS-22 | Munger | 2009-10 | खगड़िया | खगड़िया | 1 | Govt. Basic School ,Durgapur | 270.23 | [11 empty] | 1 | Inaugurated 16.07.2016
316 | MS-22 | Munger | 2009-10 | खगड़िया | गोगरी | 2 | Govt. Basic School ,Basua | 270.23 | [11 empty] | 1 | Inaugurated 16.07.2016
317 | MS-23 | Munger | 2009-10 | बेगूसराय | बेगूसराय | 1 | Govt. Basic School , Ulao | 252.9667 | [11 empty] | 1 | Inaugurated
318 | MS-23 | Munger | 2009-10 | बेगूसराय | गढ़पुरा | 2 | H/S.Mortar | 252.9667 | [11 empty] | 1 | Inaugurated
319 | MS-23 | Munger | 2009-10 | बेगूसराय | नावकोठी | 3 | H/S Samsa | 252.9667 | [11 empty] | 1 | Inaugurated
320 | MS-132 | Munger | 2010-11 | शेखपुरा | चेवाड़ा | 1 | H/S, Chewara | 241.86 | [11 empty] | 1 | Inaugurated
321 | MS-134 | Munger | 2010-11 | बेगूसराय | बलिया | 1 | Govt. H/S, Sadanandpur | 264.955 | [10 empty] | 1
322 | MS-134 | Munger | 2010-11 | बेगूसराय | तेघड़ा | 2 | Govt. Basic School, Bajatpur | 264.955 | [10 empty] | 1
323 | MS-173 | Munger | 2010-11 | जमुई | जमुई | 1 | Janta H/S, Sataya | 233.6767 | [11 empty] | 1 | Inaugurated 16.07.2016
324 | MS-173 | Munger | 2010-11 | जमुई | सिकन्‍दरा | 2 | J.S.P.S. H/S. Lachhuar | 233.6767 | [11 empty] | 1 | Inaugurated
325 | MS-173 | Munger | 2010-11 | जमुई | इस्लामनगर अलीगंज | 3 | M.R.P. H/S, Tajpur | 233.6767 | [11 empty] | 1 | Inaugurated 16.07.2016
326 | MS-174 | Munger | 2010-11 | जमुई | बरहट | 1 | Govt. Basic School, Barhat | 238.24 | [11 empty] | 1 | Inaugurated 16.07.2016
327 | MS-174 | Munger | 2010-11 | जमुई | लक्ष्‍मीपुर | 2 | Govt. Basic School, Kajinhara | 238.24 | [11 empty] | 1 | Inaugurated 16.07.2016
328 | MS-175 | Munger | 2010-11 | जमुई | गिद्धौर | 1 | M.C.Vidya Mandir, Gidhour | 227.535 | [11 empty] | 1 | Inaugurated 16.07.2016
329 | MS-175 | Munger | 2010-11 | जमुई | झाझा | 2 | M.G.S. H/S, Jhajha | 227.535 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | No Land. Drop
330 | MS-176 | Munger | 2010-11 | खगड़िया | बेलदौर | 1 | Gandhi H/S, Beldaur | 270.2833 | [10 empty] | 1
331 | MS-176 | Munger | 2010-11 | खगड़िया | मानसी | 2 | Gandhi H/S, Mansi | 270.2833 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | No Land. Drop
332 | MS-176 | Munger | 2010-11 | खगड़िया | चौथम | 3 | Brahma H/S, Pipra | 270.2833 | [10 empty] | 1
333 | MS-208 | Munger | 2010-11 | लखीसराय | रामगढ़ चौक | 1 | Govt. Basic School, Nandnama | 257.8893 | [9 empty] | 1 |  |  | Bind up List - 81 (S.No.-80) | bindup
334 | MS-208 | Munger | 2010-11 | लखीसराय | चानन | 2 | R.S. +2 H.S., Mananpur | 257.8893 | [10 empty] | 1 |  | Bind up List - 81 (S.No.-81) | bindup
335 | MS-209 | Munger | 2010-11 | लखीसराय | पिपरिया | 1 | M.R.M.P. +2 H.S., Ramchandrapur | 260.2802 | [11 empty] | 1 | flooring, plaster going on
336 | MS-209 | Munger | 2010-11 | लखीसराय | बड़हिया | 2 | Govt. Basic School, Bispur | 260.2802 | [10 empty] | 1
337 | MS-4 | Saran | 2009-10 | सारण | मांझी | 1 | M/S. Tajpur | 259.8067 | [7 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-50) | bindup
338 | MS-4 | Saran | 2009-10 | सारण | गरखा | 2 | H/S. Rampur Birbhan | 259.8067 | [11 empty] | 1 | Inaugurated
339 | MS-4 | Saran | 2009-10 | सारण | दरियापुर | 3 | Govt. Basic School Bhagwanpur | 259.8067 | [11 empty] | 1 | Inaugurated
340 | MS-5 | Saran | 2009-10 | सिवान | पचरुखी | 1 | H/S.Pachrukhi | 264.9533 | [11 empty] | 1 | Inaugurated
341 | MS-5 | Saran | 2009-10 | सिवान | आन्दर | 2 | Govt. Basic School Jayjor | 264.9533 | [11 empty] | 1 | Inaugurated
342 | MS-5 | Saran | 2009-10 | सिवान | रघुनाथपुर | 3 | Govt. Basic School Sarhara | 264.9533 | [11 empty] | 1 | Inaugurated
343 | MS-6 | Saran | 2009-10 | गोपालगंज | उचकागांव | 1 | H/S.Rahua Jamsar | 268.38 | [11 empty] | 1 | Inaugurated
344 | MS-6 | Saran | 2009-10 | गोपालगंज | बरौली | 2 | H/S.Sher | 268.38 | [11 empty] | 1 | Inaugurated
345 | MS-191 | Saran | 2010-11 | सारण | अमनौर | 1 | Govt. Basic School, Mandroli |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started
346 | MS-191 | Saran | 2010-11 | सारण | परसा | 2 | H/S, Parsa |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started
347 | MS-191 | Saran | 2010-11 | सारण | मढ़ौरा | 3 | Govt. Basic School, Agahara |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started
348 | MS-192 | Saran | 2010-11 | सारण | एकमा | 1 | Govt. Basic School, Rasulpur |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Not started
349 | MS-193 | Saran | 2010-11 | सिवान | हसनपुरा | 1 | C.B. H/S, Usari Dhanauti | 268.925 | [11 empty] | 1 | Inaugurated 16.07.2016
350 | MS-193 | Saran | 2010-11 | सिवान | दरौली | 2 | H/S, Don | 268.925 | [11 empty] | 1 | Inaugurated
351 | MS-194 | Saran | 2010-11 | सिवान | ज़िरादै | 1 | Mahendra H/S, Zeradei | 268.955 | [11 empty] | 1 | Inaugurated
352 | MS-194 | Saran | 2010-11 | सिवान | लकड़ी नबीगंज | 2 | Govt. Basic School, Jalalpur | 268.955 | [11 empty] | 1 | Inaugurated
353 | MS-195 | Saran | 2010-11 | सिवान | नौतन | 1 | H/S, Nawatan | 272.43 | [11 empty] | 1 | Inaugurated
[5 empty] | Total Schools | 353 |  | 85094.2994 | 57 | 0 | 2 | 1 | 0 | 17 | 1 | 27 | 2 | 7 | 69 | 169

## Sheet1 (hidden)
|  |  | Session | Bind up 81 |  | 216 |  |  | Not start
|  | MS |  | FF-RL (Total Schools) | FF-RL (Completed) | Finishing | Completed | Total
|  | Bindup completed | 09-10 | 16 | 7 | 24 | 45 | 76 | 12
|  | Bindup completed | 10-11 | 65 | 26 | 56 | 86 | 168 | 42
244
|  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | 2nd Floor |  | Finishing | Complete
[5 empty] | LL | RL | LL | RL | LL | RL |  |  | with bind up complete
| MS 9-10 | 0 | 1 | 1 | 0 | 4 | 0 | 7 | 2 | 2 | 24 | 45 | 69
31.3.2016 | MS 10-11 | 0 | 5 | 0 | 0 | 16 | 0 | 26 | 0 | 2 | 15 | 146
[13 empty] | Completed | 86
[13 empty] | Finishing | 75 | 30
[6 empty] | 09-10 | Completed | 45 |  |  |  | 10-11 | SS-RL | 2
[7 empty] | Finishing | 24 | 30 |  |  |  | SF-LL | 0
[7 empty] | SS-RL | 2 |  |  |  |  | (FF-RL) (Bindup) | 26 | as finishing stage
[7 empty] | SF-LL | 2 |  |  |  |  | Total | 189
| 2009-10 | 69 |  |  |  |  | Bindup (FF-RL) | 7 | as finishing stage |  |  |  | Not Start
| 2010-11 | 165 |  |  |  |  | Total | 80 |  |  |  |  | LAYOUT | 0
[13 empty] | Found | 5
[7 empty] | LAYOUT | 0 |  |  |  |  | Plinth | 0
[7 empty] | Found | 1 |  |  |  |  | GF-LL | 0
[7 empty] | Plinth | 1 |  |  |  |  | GF-RL | 16
[7 empty] | GF-LL | 0 |  |  |  |  | FF-LL | 0
[7 empty] | GF-RL | 4 |  |  |  |  | TOTAL | 21
[7 empty] | FF-LL | 0 | [5 empty] | 42
[7 empty] | TOTAL | 6 | [5 empty] | 210
[6 empty] | TS |  | 98 |  |  |  | TS | 8
[12 empty] | TOTAL Value of Schools | 255
[12 empty] | Retender | 247
[12 empty] | Total | 37 | 42
Contract A
[10 empty] | 34 |  | Not Start
[11 empty] | Process | 210
[11 empty] | NS | 37
[11 empty] | Retender | 8

## Bindup 81 (hidden)
Status of Model School Date:-29/02/2016
Sl. NO. | Group no | Name of Division | Session | District | Block | SN | Name Of School | [11 empty] | Remarks |  | Image
[8 empty] | LAY OUT | FOUND ATION | PL | Ground Floor |  | 1st Floor |  | 2nd Floor |  | FINI SHING | COMP LETE
[11 empty] | LL | RL | LL. | RL. | LL. | RL.
1 | MS-164 | Koshi | 2010-11 | सुपौल | छातापुर | 3 | S.S. H/S, Sukhpur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-51)
2 | MS-30 | Tirhut East | 2009-10 | वैशाली | जन्दाहा | 1 | R.B.S.Loma | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-52)
3 | MS-30 | Tirhut East | 2009-10 | वैशाली | पातेपुर | 2 | Govt. Basic School Bardiha | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (SL.No.-53)
4 | MS-30 | Tirhut East | 2009-10 | वैशाली | महुआ | 4 | M.S Singhara |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (SL.No.-1)
5 | MS-120 | Tirhut East | 2010-11 | सीतामढी | रीगा | 1 | T.R.N.H.S, Sahbajpur Kharsan |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-2)
46 | MS-120 | Tirhut East | 2010-11 | सीतामढी | परसौनी | 2 | Govt. Basic School, Raghopur Bhakhari |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-3)
48 | MS-121 | Tirhut East | 2010-11 | सीतामढी | नानपुर | 1 | Govt. Basic School, Janipur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-4)
49 | MS-121 | Tirhut East | 2010-11 | सीतामढी | चोरौत | 2 | S.L.N.S H/S, Chorout | [9 empty] | 1 |  | Bind up List - 81 (S.No.-54) | Finish | FF-RL
51 | MS-122 | Tirhut East | 2010-11 | सीतामढी | बाजपट्टी | 1 | S.R.P.N. H/S, Bajpatti |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-5)
52 | MS-122 | Tirhut East | 2010-11 | सीतामढी | मेजरगंज | 2 | J.B. H/S, Majorganj | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-55)
61 | MS-126 | Tirhut West | 2010-11 | पूर्वी चंपारण | रक्सौल | 1 | H/S, Purandara Bhelahi | [9 empty] | 1 |  | Bind up List - 81 (S.No.-56) | Finish | Roofing
64 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | आदापुर | 1 | Govt. Basic School, Bhawanati |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-6)
65 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | घोङासहन | 2 | Govt. Basic School, Bhelwa Circle | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-7)
66 | MS-127 | Tirhut West | 2010-11 | पूर्वी चंपारण | ढाका | 3 | H/S, Dhaka |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-8)
82 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | योगापट्टी | 1 | Govt. Basic School, Balua | [9 empty] | 1 |  | Bind up List - 81 (S.No.-57) | Finish | Plaster Internal
83 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | चनपटिया | 2 | Govt. Basic School, Chaubetola | [9 empty] | 1 |  | Bind up List - 81 (S.No.-58) | Finish | Painting
84 | MS-187 | Tirhut West | 2010-11 | पश्चिम चम्पारण | सिकटा | 3 | Janta H/S, Sikta | [9 empty] | 1 |  | Bind up List - 81 (S.No.-59) | Finish | Plaster
87 | MS-189 | Tirhut West | 2010-11 | पश्चिम चम्पारण | पिपरासी | 1 | Govt. Basic School, Manjhariya |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-9)
89 | MS-190 | Tirhut West | 2010-11 | पश्चिम चम्पारण | गौनाहा | 1 | Govt. Basic School, Bhithakha |  | 1 | [9 empty] | Bind up List - 81 (S.No.-10)
90 | MS-190 | Tirhut West | 2010-11 | पश्चिम चम्पारण | मैनाटांड | 2 | R.S. H/S, Rampurwa |  | 1 | [9 empty] | Bind up List - 81 (S.No.-11)
98 | MS-113 | Darbhanga | 2010-11 | मधुबनी | बासोपट्टी | 1 | Govt. Basic School, Sukhasi | [9 empty] | 1 |  | Bind up List - 81 (S.No.-12) | Finish | Plaster
99 | MS-113 | Darbhanga | 2010-11 | मधुबनी | बिस्फी | 2 | Govt. Basic School, Simari | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-13)
100 | MS-114 | Darbhanga | 2010-11 | मधुबनी | हरलाखी | 1 | Govt. Basic School, Hisar | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-14)
101 | MS-114 | Darbhanga | 2010-11 | मधुबनी | मधवापुर | 2 | Govt. Basic School, Rema | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-15)
105 | MS-116 | Darbhanga | 2010-11 | मधुबनी | बाबूबरही | 1 | J.N. H/S, Babubarhi | [7 empty] | X | X | 1 |  | Bind up List - 81 (S.No.-60) | Bindup | G+1
106 | MS-116 | Darbhanga | 2010-11 | मधुबनी | पंडौल | 2 | Govt. Basic School, Maukarampur | [7 empty] | X | X | 1 |  | Bind up List - 81 (S.No.-61) | Bindup | G+1
107 | MS-116 | Darbhanga | 2010-11 | मधुबनी | राजनगर | 3 | Govt. Basic School, Nakati | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-62)
108 | MS-117 | Darbhanga | 2010-11 | मधुबनी | घोघरडीहा | 1 | High School, Devadh | [9 empty] | 1 |  | Bind up List - 81 (S.No.-15) | Finish | Without Plaster
109 | MS-117 | Darbhanga | 2010-11 | मधुबनी | लौकही | 2 | High School, Laukhi | [9 empty] | 1 |  | Bind up List - 81 (S.No.-63) | Finish | Without Plaster
111 | MS-118 | Darbhanga | 2010-11 | मधुबनी | जयनगर | 1 | High School, Jainagar |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-17)
112 | MS-118 | Darbhanga | 2010-11 | मधुबनी | कलुआही | 2 | High School, Narar |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-64)
125 | MS-200 | Darbhanga | 2010-11 | दरभंगा | केवटी | 1 | R.J. H/S, Keoti Baubari | [9 empty] | 1 |  | Bind up List - 81 (S.No.-18) | Finish | Plaster is going on
140 | MS-13 | Patna East | 2009-10 | नालंदा | हिलसा | 3 | H/S.Hilsa |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-19)
141 | MS-14 | Patna East | 2009-10 | भोजपुर | पिरो | 1 | Govt. Basic School, Rajaiya |  | 1 | [9 empty] | Bind up List - 81 (S.No.-20)
142 | MS-14 | Patna East | 2009-10 | भोजपुर | तरारी | 2 | H/S.Barkagaon |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-21)
145 | MS-16 | Patna West | 2009-10 | बक्‍सर | राजपुर | 1 | H/S.Rajpur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-22)
147 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | मोहनियॉं | 1 | Govt. Basic School, Mohaniya | [7 empty] | 1 |  |  |  | Bind up List - 81 (S.No.-23) | SF-LL | G+2
148 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | भभुआ | 2 | H/S.Akhlashpur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-24)
149 | MS-17 | Patna West | 2009-10 | भभुआ कैमूर | दुर्गावती | 3 | H/S.Kampura | [7 empty] | 1 |  |  |  | Bind up List - 81 (S.No.-25) | SF-LL | G+2
155 | MS-102 | Patna East | 2010-11 | पटना | नौबतपुर | 3 | Govt. H/S, Amarpur (Chiraura) | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-26)
157 | MS-103 | Patna East | 2010-11 | पटना | खुसरुपुर | 2 | Mahadeo H/S, Khusrupur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-65)
165 | MS-106 | Patna East | 2010-11 | पटना | बाढ | 3 | Govt. H/S, Badhna |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-27)
169 | MS-108 | Patna West | 2010-11 | बक्‍सर | ब्रहम्‍पुर | 1 | (+2) B.N. H/S, Brahampur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-28)
170 | MS-108 | Patna West | 2010-11 | बक्‍सर | सिमरी | 2 | (+2) H/S, Simri |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-29)
171 | MS-108 | Patna West | 2010-11 | बक्‍सर | केसठ | 3 | (+2) H/S, Kesath |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-30)
173 | MS-135 | Patna East | 2010-11 | भोजपुर | बिहिया | 2 | (+2) H/S, Bihia | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-31)
176 | MS-136 | Patna East | 2010-11 | भोजपुर | चरपोखरी | 3 | Macha H/S, Barami | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-32)
197 | MS-146 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 1 | Govt. Basic School, Kabhai | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-33)
198 | MS-146 | Patna West | 2010-11 | रोहतास | बिक्रमगंज | 2 | R.R. H.S. Suryappura | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-66)
199 | MS-146 | Patna West | 2010-11 | रोहतास | दावत | 3 | R.P.S. H.S.Kabai, Dawath | [9 empty] | 1 |  | Bind up List - 81 (S.No.-67) | Finish | Without Plaster
200 | MS-147 | Patna West | 2010-11 | रोहतास | कोचस | 1 | H.S. Kochas | [9 empty] | 1 |  | Bind up List - 81 (S.No.-68) | Finish | Roofing
202 | MS-148 | Patna West | 2010-11 | रोहतास | नोखा | 1 | H.S. Garh Nokha, Nokha | [9 empty] | 1 |  | Bind up List - 81 (S.No.-69) | Finish | Without Plaster
203 | MS-148 | Patna West | 2010-11 | रोहतास | काराकाट | 2 | S.S.D.H.S. Amauna, Karakat | [9 empty] | 1 |  | Bind up List - 81 (S.No.-34) | Finish | Without Plaster
213 | MS-36 | Purnea | 2009-10 | अररिया | फारबिसगंज | 2 | Govt. Basic School Haripur | [9 empty] | 1 |  | Bind up List - 81 (S.No.-70) | Finish | Roofing
220 | MS-166 | Purnea | 2010-11 | पूर्णिया | पूर्णिया पूर्व | 1 | Govt. Basic School, Chadirjiganj | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-71)
221 | MS-166 | Purnea | 2010-11 | पूर्णिया | कृत्यानन्द नगर | 2 | Govt. Basic School, Kalyanpur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-72)
222 | MS-166 | Purnea | 2010-11 | पूर्णिया | कसबा | 3 | Govt. Basic School, Sabdalpur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-73)
232 | MS-171 | Purnea | 2010-11 | कटिहार | फलका | 1 | Govt. Basic School, Mangha | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-74)
243 | MS-204 | Bhagalpur | 2010-11 | भागलपुर | जगदीशपुर | 2 | Loknath H/S, Jagdishpur |  |  | . |  |  |  |  | X | X | 1 |  | Bind up List - 81 (S.No.-75) | Bindup | Painting done. G+1
246 | MS-205 | Bhagalpur | 2010-11 | भागलपुर | शाहकुण्‍ड | 2 | Govt. Basic School, Hajipur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-35)
247 | MS-205 | Bhagalpur | 2010-11 | भागलपुर | सुलतानगंज | 3 | H/S, Karharia | [7 empty] | X | X | 1 |  | Bind up List - 81 (S.No.-76) | Bindup | Plaster is going on. G+1
252 | MS-24 | Magadh | 2009-10 | गया | फतेहपुर | 1 | H/S.Fatehpur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-77)
253 | MS-24 | Magadh | 2009-10 | गया | वजीरगन्ज | 2 | H/S.Wazirgznj | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-36)
255 | MS-25 | Magadh | 2009-10 | औरंगाबाद | मदनपुर | 1 | H/S.Beri | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-37)
257 | MS-25 | Magadh | 2009-10 | औरंगाबाद | कुटुम्बा | 3 | Govt. Basic School, Rampur Parsa |  |  | 1 | [8 empty] | Bind up List - 81 (S.No.-38)
267 | MS-153 | Magadh | 2010-11 | गया | मानपुर | 1 | H.S.Rasalpur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-39)
268 | MS-153 | Magadh | 2010-11 | गया | बोधगया | 2 | H.S. Bodhgaya | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-78)
269 | MS-153 | Magadh | 2010-11 | गया | बेलागन्ज | 3 | A.H.S. Belaganj |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-40)
270 | MS-154 | Magadh | 2010-11 | गया | टिकारी | 1 | Govt. Basic School, Bhawanpur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-41)
271 | MS-154 | Magadh | 2010-11 | गया | कोन्च | 2 | G.H.S. Konch |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-42)
272 | MS-154 | Magadh | 2010-11 | गया | परैया | 3 | A.H.S. Paraiya |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-43)
275 | MS-156 | Magadh | 2010-11 | गया | डॊभी | 1 | Govt. Basic School, Bajaura |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-44)
276 | MS-156 | Magadh | 2010-11 | गया | मोहनपुर | 2 | H.S.Mohanpur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-45)
280 | MS-158 | Magadh | 2010-11 | गया | आमस | 1 | H.S. Amas |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-46)
281 | MS-158 | Magadh | 2010-11 | गया | गुरुआ | 2 | H.S. Bharsanthu (Bharaundha) |  | 1 | [9 empty] | Bind up List - 81 (S.No.-47)
286 | MS-160 | Magadh | 2010-11 | गया | Chandouti | 1 | H.S. Chandaouti | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-79)
300 | MS-181 | Magadh | 2010-11 | नवादा | मेसकौर | 1 | Inter School, Meskaur |  | 1 | [9 empty] | Bind up List - 81 (S.No.-48)
303 | MS-183 | Magadh | 2010-11 | औरंगाबाद | देव | 1 | Govt. Basic School, Vishnupur | [6 empty] | 1 |  |  |  |  | Bind up List - 81 (S.No.-49)
333 | MS-208 | Munger | 2010-11 | लखीसराय | रामगढ़ चौक | 1 | Govt. Basic School, Nandnama | [8 empty] | 1 |  |  | Bind up List - 81 (S.No.-80) | SF-RL | Plaster done
334 | MS-208 | Munger | 2010-11 | लखीसराय | चानन | 2 | R.S. +2 H.S., Mananpur | [7 empty] | X | X | 1 |  | Bind up List - 81 (S.No.-81) | Bindup | G+1
337 | MS-4 | Saran | 2009-10 | सारण | मांझी | 1 | M/S. Tajpur |  |  |  |  | 1 | [6 empty] | Bind up List - 81 (S.No.-50)
Total No. of Schools | [5 empty] | 81 |  | 0 | 5 | 1 | 0 | 25 | 0 | 28 | 2 | 1 | 19 | 0
[7 empty] | No. of Actual Bindup upto FF-RL | 5
[7 empty] | No. of as it same | 17