## Summary all acr (hidden)
BSEIDC, PATNA
Summary of all ACR | [22 empty] | Date:31.07.17
S.N. | EC Name | Name & Designation | Total Sanctioned |  |  | Contract Awarded (LOA Issued) |  | Agreement done |  | Physical Status | [7 empty] | Summary |  |  |  | Agreement Amount (in Lakh) | Fin. Exp. (in Lac) | Financial Achievent (%) | Remarks
|  |  | No. of Groups | No. of School | No. of Units | No. of Groups | No. of School | No. of Groups | No. of School | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete | In-Progress | not start | Inauguration
[13 empty] | LL | RL | LL | RL
1 | EC - 86 | 91 | 18 | 18 | 46 | 15 | 15 | 11 | 11 | 0 | 1 | 0 | 0 | 5 | 1 | 0 | 1 | 0 | 8 | 10 | 0 | 900.3537 | 175.17 | 19.4557
2 | EC - 97 | 30 | 0 | 20 | 134 | 10 | 10 | 4 | 4 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 6 | 14 | 0
3 | EC - 107 |  | 11 | 39 | 255 | 9 | 28 | 4 | 12 | 1 | 6 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 29 | 0
4 | EC - 110 |  |  |  | 171 | [13 empty] | 0 | 171 |  |  |  |  | DPR Under preparation
5 | EC - 116 |  |  |  | 480 | [13 empty] | 0 | 480 |  |  |  |  | DPR Under preparation
5 | EC - 129 |  |  |  | 955 | [13 empty] | 0 | 955 |  |  |  |  | DPR Under preparation
| Total ACR |  | 29 | 77 | 2041 | 34 | 53 | 19 | 27 | 1 | 7 | 2 | 4 | 7 | 2 | 0 | 1 | 0 | 24 | 1659 | 0 | 900.3537 | 175.17 | 19.4557

## ALL
BSEIDC Ltd., PATNA
Progress report for the construction of ACR
Sl.No. | Group wise Sl.No. | Gr. No | Division | Empower Committee No. | Name of District | Name of Block | Panchayat | S.N. | Name of School | Unit | [21 empty] | Retender | Tender Process | Not Start | Physical Report | [8 empty] | Agreement Amount (in Lakhs) | Fin. Exp. (in lakh) | Financial Achievement (%) | Remarks
[30 empty] | Technical Bid Opening | Fin. Bid opening |  |  |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[11 empty] | Name of AgencyDate of Tender | A/A (Rs. In Lakh) | T/S(Rs. In Lakh) | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Tender Comitt. | Exec. Comm. | L.O.A | Contract Price (Rs. In Lakh) | Performance Security (Rs. In Lakh) | Date of Verification for Earnest Money issu to | Verification for Earnest Money Recived Date | Date of Submission (P.S) | verification for P.S. issued to Bank/P.O | verification received date | Aggrement No & date | Time of Completion | Retender | [7 empty] | LL | RL | LL | RL
1 | 1 | ACR | Tirhut West | 86 | East Champaran | BANJARIYA |  |  | Sunderman High School | 4 | TUNTUN PANDEY |  |  | 21.9982 | [5 empty] | 6577/12.07.16 | [7 empty] | 236 F2 OF 2016-17 (02.03.17) | [10 empty] | 1 |  |  |  |  | 19.7984 |  |  | Flood Affected
2 | 2 | ACR | Tirhut East | 86 | Vaisali | Cherakala |  |  | Ababkarpur Madarsa | 4 | M/S OM SHREE INTERPRISES(4) |  |  | 21.3743 | [5 empty] | 6570/12.07.16 | [7 empty] | 231 F2 OF 2016-17 (27.02.17) | [10 empty] | 1 |  |  |  |  | 19.2369 |  |  | Flood Affected
3 | 3 | ACR | Tirhut East | 86 | Vaisali | Cherakala |  |  | Chehrakala Madarsa | 4 | MS. CHANDAN KUMAR 09934725409 '/ 8507324788 | [20 empty] | 1 | [14 empty] | Flood Affected
4 | 4 | ACR | Tirhut East | 86 | Sitamarhi | Bajpatti |  |  | Babulal Laxman Chaudhary School | 2 | MS. CHANDAN KUMAR 09934725409 '/ 8507324788 |  |  | 21.882 | [5 empty] | 13771/31.12. | [7 empty] | 20 F2 of 2017-18 (25.04.17) | [11 empty] | 1 |  |  |  | 21.882 |  |  | Flood Affected
5 | 5 | ACR | Tirhut East | 86 | Sitamarhi | Bajpatti |  |  | Project Girls High Schoool, Bahera, jahidpur | 2 | ANJU NANDAN 8873664419 |  |  | 21.8669 | [5 empty] | 13772/31.12.16 | [7 empty] | 34 F2 of 2017-18 (05.05.17) | [13 empty] | 1 |  | 19.6803 |  |  | Flood Affected
6 | 6 | ACR | Tirhut East | 86 | Sitamarhi | Bajpatti |  |  | Rajkiye middle School Bela Santi kutir | 2 | ANITA DEVI 9199700293 |  |  | 21.8596 | [5 empty] | 13780/31.12.16 | [14 empty] | 1 | [11 empty] | Flood Affected
7 | 7 | ACR | Saran | 86 | Gopalganj | Thawe |  |  | Ramchandrapur High School,Thawe | 6 | GANDHUCHHAPAR CONSTRUCTION PVT LTD |  |  | 41.3743 | [5 empty] | 6572/12.07.16 | [7 empty] | 110 F2 OF 2016-17 (13.12.16) | [11 empty] | 1 |  |  |  | 37.1751
8 | 8 | ACR | Patna East | 86 | Nalanda |  |  |  | Sahokhar High School | 24 | KRISHANDEO PRASAD |  |  | 302.4835 | [5 empty] | 6579/12.07.16 | [7 empty] | 176 SBD OF 2016-17 (24.01.17) | [12 empty] | 1 |  |  | 272.2351 | 85 |  | Flood Affected
9 | 9 | ACR | Patna East | 86 | Nalanda |  |  |  | Sarvodaya High School,Sohsarai | 1 | M/S DAYARAM SINGH |  |  | 229.4327 | [5 empty] | ISSUED | [7 empty] | 98SBD OF 2016-17 (24.11.16) | [5 empty] | 1 | [9 empty] | 206.4895 |  |  | Required old building demolision
10 | 10 | ACR | Patna East | 86 | Nalanda |  |  |  | Govt. Town High School At ManiramAkhara | 3 | SAI HIGHWAY & BUILDERS PVT LTD |  |  | 383.7986 | [5 empty] | 6571/12.07.16 | [7 empty] | 107 SBD OF 2016-17 (06.12.16) | [10 empty] | 1 |  |  |  |  | 345.4187 | 69.86 |  | 1st Floor B/W upto Sill Level
11 | 11 | ACR | Patna East | 86 | Nalanda |  |  |  | Rajkiyakrit Kanya High School Sohsarai | 1 | KRISHANDEO PRASAD |  |  | 127.2174 | [5 empty] | 6576/12.07.16 | [7 empty] | 28 SBD of 2017-18 (03.05.17 | [5 empty] | 1 | [9 empty] | 114.4957 |  |  | बालू के कारण कार्य बाद
12 | 12 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk dk’kheqy Åywe] csyf/k;k esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA ( (2) | 2 | ANITA DEVI 9199700293 | [8 empty] | I13770/31.12.16 | [13 empty] | 1 | [12 empty] | Agreement not done
13 | 13 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | Madarsa-Islahul Muslimeen ,Bhorakhap | 2 | MS. CHANDAN KUMAR 09934725409 '/ 8507324788 |  |  | 20.7618 | [5 empty] | 13781/31.12.16 | [7 empty] | 55 F2 of 2017-18 (22/05/2017) | [13 empty] | 1 |  | 18.6856
14 | 14 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk blykfe;k ;kdwc uxj] nsodqaMk esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA (2) | 2 | GAURI SHANKAR SINGH 9431460106 |  |  | 20.7618 | [5 empty] | 3034/13.04.17 | [13 empty] | 1 |  |  |  |  | s | [7 empty] | Land not available
15 | 15 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk tesmyk Åywe pdukFFkq esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA (2) | 2 | AMIT KUMAR 08050100000 |  |  | 20.7768 | [5 empty] | 13779/31.12.16 | [13 empty] | 1 | [12 empty] | Land Dispute
16 | 16 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | Madarsa-Islamia Anwarul Hoda ,Chhoti Naki | 2 | AMIT KUMAR 08050100000 |  |  | 20.7387 | [5 empty] | 13773/31.12.16 | [7 empty] | 1 F2 of 2017-18 (01.04.17) | [14 empty] | 1 | 18.6649
17 | 17 | ACR | Bhagalpur | 86 | Bhagalpur | txnh'kiqj |  |  | enjlk vuhlwy gqLuk esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
18 | 18 | ACR | Bhagalpur | 86 | Bhagalpur | txnh'kiqj |  |  | enjlk edlwnwy Åywe esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA (2) | 2 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
19 | 19 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | mPp fo¦ky; rktiqj | 6 | RAJESH .KUMAR 943024850000 |  |  | 442.2797 | [5 empty] | 13784/31..12.16 | [15 empty] | 1
20 | 20 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | çkFkfed fo¦ky; dlckVksyk | 6 | RAJESH .KUMAR 943024850000 |  |  | 449.2234 | [5 empty] | 13788/31.12.16 | [13 empty] | 1
21 | 21 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | mRØfer e/; fo¦ky; ljlkSuk | 3 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
22 | 22 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | mRØfer e/; fo¦ky; iwoÊ ckyd | 4 | JUGNOO KUMAR 8083370525 |  |  | 27.6225 | [5 empty] | 13789/31.12.16 | [7 empty] | 65 f2 of 2017-18 (24.05.17) | [10 empty] | 1 |  |  |  |  | 24.8602
23 | 23 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | çkFkfed fo¦ky; Hksjk[ksjk mnwZ rkrsjVksy | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
24 | 24 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | e/; fo¦ky; rktiqj | 4 | AMRENDRAKUMAR 9471454135 |  |  | 27.6225 | [5 empty] | 13787/31.12.16 | [13 empty] | 1
25 | 25 | ACR | Saran | 97 | Gopalganj | mpdkxk¡o |  |  | e/; fo¦ky; egsupk | 6 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
26 | 26 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | Z. A. Islamia College | 10 | shashi Kumar Singh 9546575203 |  |  | 63.2132 | [5 empty] | 962/7.02.17 | [7 empty] | 17 F2 of 2017-18 (25.04.17) | [11 empty] | 1 |  |  |  | 63.2132
27 | 27 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | ch- ,e- mPp fo¦ky; egknsok | 8 | UDAY ERECTORS PRIVATE LIMITED 9708798033 |  |  | 61.2422 | [5 empty] | 13786/31.12.16 | [7 empty] | 53 F2 of 2017-18 (17.05.17) | [5 empty] | 1
28 | 28 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | bLykfe;k mPp fo¦ky; lhoku | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
29 | 29 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | uxjikfydk e/; fo¦ky; | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
30 | 30 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | çkFkfed fo¦ky; “ks[k eksgYyk rsygÍk cktkj | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
31 | 31 | ACR | Saran | 97 | Siwan | gluiqjk |  |  | Public High School, Saholi | 15 | Sona Engicon Pvt Ltd 9431008581 |  |  | 95.9174 | [5 empty] | 13783/31.12.16 | [19 empty] | 1
32 | 32 | ACR | Saran | 97 | Siwan | gluiqjk |  |  | Gandhi Smarak High School, Laheji | 10 | shashi Kumar Singh 9546575203 |  |  | 63.2803 | [5 empty] | 961/7.02.17 | [7 empty] | 18 F2 of 2017-18 (25.04.17) | [9 empty] | 1 | [5 empty] | 63.2803
33 | 33 | ACR | Saran | 97 | Siwan | gluiqjk |  |  | Ckfydk mPp fo¦ky; gluiqjk(5) | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
34 | 34 | ACR | Saran | 97 | Siwan | cjgfj;k |  |  | G. M. High School, Barharia | 15 | BALINDRA CHAUDHARY9470843555 |  |  | 97.0008 | [5 empty] | 13798/31.12.16 | [17 empty] | 1
35 | 35 | ACR | Saran | 97 | Siwan | cjgfj;k |  |  | Dindayalpur High School | 10 | DEVENDRA KUMAR SINGH 8507572787 |  |  | 63.9637 | [5 empty] | 13785/31.12.16 | [19 empty] | 1
36 | 36 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; tekygÍk | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
37 | 37 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; xksikyiqj | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
38 | 38 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; rsrfj;k | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
39 | 39 | ACR-201 | Darbhanga | 107 | Madhubani | Madhubani (Town) |  |  | Suri High School at Madhubani.(6) | 6 | RAJA KUMAR 09334006548 '/ 09122485553 |  |  | 38.0871 | [5 empty] | 941/07.02.17 | 1 | [17 empty] | 1
40 | 40 | ACR-202 | Darbhanga | 107 | Madhubani | Bisfi |  |  | (i) High School at Parsauni (5) | 5 | MS TARA CONSTRUCTION 7070466123 |  | 466.1095 | [6 empty] | 940/07.02.17 | 1 | [12 empty] | 1
41 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (ii) High School at Nahas Khangraitha(5) | 5 | [10 empty] | 1 | [12 empty] | 1
42 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (iii) High School at Simiri (5) | 5 | [10 empty] | 1 | [12 empty] | 1
43 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (iv) Upgraded School at Noorchak (12) | 12 | [10 empty] | 1 | [12 empty] | 1
44 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (v) Middle School at AunsiBhabhangawa (18) | 18 | [10 empty] | 1 | [12 empty] | 1
45 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (vi) Upgraded School at Bhairwa(11) | 11 | [10 empty] | 1 | [12 empty] | 1
46 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (vii) Upgraded School at Shivaul (12) | 12 | [10 empty] | 1 | [12 empty] | 1
47 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (viii) Upgraded School at Bardha (7) | 7 | [10 empty] | 1 | [12 empty] | 1
48 | 41 | ACR-203 | Bhagalpur | 107 | Bhagalpur | Sanhaula |  |  | Bari Adarsh High School(8) | 8 | MILAN DRILLER & DEVELOPER PRIVATE LIMITED 9471452729 '/ 9973024980 |  |  | 49.0068 | [5 empty] | 959/07.02.17 | 1 | [12 empty] | 1
49 | 42 | ACR-204 | Koshi | 107 | Supual | Basantpur |  |  | (i) Upgraded middle school, Balbhadrapur(4) | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
50 |  |  | Koshi | 107 | Supual |  |  |  | (ii) Middle school at Narpatpatti(6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
51 |  |  | Koshi | 107 | Supual |  |  |  | (iii) Upgarded middle school at Deenbandhi(6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
52 |  |  | Koshi | 107 | Supual |  |  |  | (iv) Urdu middle school at Kamalpur (4) | 4 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
53 |  |  | Koshi | 107 | Supual |  |  |  | (v) Upgarded middle school at Parmanandpur (6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
54 |  |  | Koshi | 107 | Supual |  |  |  | (vi) Middle school at Parsa Urdu(6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
55 |  |  | Koshi | 107 | Supual |  |  |  | (vii) Middle school at Baria Kamal (2) | 2 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
56 |  |  | Koshi | 107 | Supual |  |  |  | (viii) Primary School at Kataiya(3) | 3 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
57 |  |  | Koshi | 107 | Supual |  |  |  | (ix)Upgarded middle school at Mohanpur (6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
58 |  |  | Koshi | 107 | Supual |  |  |  | (x) Upgraded middle school at Shankarpur(6) | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
59 | 43 | ACR-205 | Koshi | 107 | Supual | Supaul Town |  |  | (i) Upgraded middle school at Jhakrahi, New muslimTola(12) | 12 | AMOD KUMAR 9122088000 |  |  | 269.8077 | [5 empty] | 946/07.02.17 | 1 | [7 empty] | 255 SBD OF 2016-17 (30.03.17) | 1 |  |  |  | 1 | [11 empty] | 242.8269 | Land Available but NOC not given by School H.M.
60 |  |  | Koshi | 107 | Supual |  |  |  | (ii) Hazari Higher Secondary School at Supaul (12) | 12 | [10 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 | [11 empty] | Layout Done but work can not be started due to water logging after excavation
61 |  |  | Koshi | 107 | Supual |  |  |  | (iii) Babujan vishveshwar Balika High School at Supaul (6) | 6 | [10 empty] | 1 | [8 empty] | 1 |  |  |  | 1 | [12 empty] | Land Not Available
62 |  |  | Koshi | 107 | Supual |  |  |  | (iv) Higher Secondary School at Supaul (12) | 12 | [10 empty] | 1 | [8 empty] | 1 |  |  |  | 1 | [12 empty] | Land Not Available
63 | 44 | ACR-206 | Tirhut East | 107 | Sitamarhi | Parihar Block |  |  | Shri Gandhi High School (ACR with Stair room & Verandah) (1) | 1 | CHANDAN KUMAR Mob : 9471923405 |  |  | 21.5487 | [5 empty] | 944/07.02.17 | 1 | [7 empty] | 19 F2 of 2017-18 (25.04.17) | [13 empty] | 1 |  |  | 21.5487 | Pannel Work running
64 | 45 | ACR-207 | Tirhut West | 107 | East Champaran | Ramgarhwa |  |  | (i) Govt. High School at G.M. high school, Ramgarhwa (4) | 4 | VANSHAJ CONSTRUCTION 9631845631 |  |  | 153.9957 | [5 empty] | 947/07.02.17 | 1 | [7 empty] | 49 SBD OF 2017-18 (16.05.17) | 1 | [5 empty] | 1 | [9 empty] | 138.5961 | Flood Affected
65 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) High school at Adhkaparia (4) | 4 | [10 empty] | 1 | [8 empty] | 1 | [5 empty] | 1 | [10 empty] | Flood Affected
66 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iii) S.S. High School at Raghunathpur (4) | 4 | [10 empty] | 1 | [8 empty] | 1 | [5 empty] | 1 | [10 empty] | Flood Affected
67 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iv) High School at Sukhi Semra (6) | 6 | [10 empty] | 1 | [8 empty] | 1 | [6 empty] | 1 | [9 empty] | Flood Affected
68 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (v) R.D.P. girls high school at Ramgarhwa (6) | 6 | [10 empty] | 1 | [8 empty] | 1 | [5 empty] | 1 | [10 empty] | Flood Affected
69 | 46 | ACR-208 | Tirhut West | 107 | East Champaran | Dhaka |  |  | (i) Govt. High School at High School Dhaka (6) | 6 | SHAKAL DEO MISHRA 9006385958 |  |  | 151.5283 | [5 empty] | 943/07.02.17 | 1 | [13 empty] | 1 | [11 empty] | Flood Affected
70 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) Sarjeet high school at Bhandar (6) | 6 | [10 empty] | 1 | [13 empty] | 1 | [11 empty] | Flood Affected
71 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iii) Shri H.M. Balika High school at Kamarwa (6) | 6 | [10 empty] | 1 | [12 empty] | 1 | [12 empty] | Land Not Available
72 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iv)High School at Jataulia (6) | 6 | [10 empty] | 1 | [12 empty] | 1 | [12 empty] | Flood Affected
73 | 47 | ACR-209 | Tirhut West | 107 | East Champaran | Banjaria |  |  | (i) Govt. High School at High School Semra (8) | 8 | VIJAY KUMAR SINGH 9973980351 |  |  | 71.726 | [5 empty] | 960/07.02.17 | 1 | [7 empty] | 59 f2 of 2017-18 (23.05.17) | 1 | [5 empty] | 1 | [9 empty] | 64.5534 | Flood Affected
74 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) Dr. ZakirHussain high school at Mohmmadpur (4) | 4 | [10 empty] | 1 | [8 empty] | 1 | [7 empty] | 1 | [8 empty] | Flood Affected
75 | 48 | ACR-210 | Tirhut West | 107 | East Champaran | Narkatiaganj/ Chodadano |  |  | Govt. high school at JeetpurVishnupurwa (4) | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
76 | 49 | ACR-211 | Tirhut West | 107 | East Champaran | Adanpur |  |  | (i) Bansidhar high school (6) | 6 | RNS PROJECT 9470420900 |  |  | 64.4471 | [5 empty] | 942/07.02.17 | 1 | [12 empty] | 1
77 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) Project girls high school (4) | 4 | [10 empty] | 1 | [12 empty] | 1
Total No. of ACR Schools | [8 empty] | 77 | 456 | 0 | 0 | 466.1095 | 3487.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1 | 23 | 24 | 4 | 6 | 1 | 3 | 5 | 5 | 1 | 2 | 2 | 1245.1159 | 154.86 | 467.5251

## ALL (2) (hidden)
BSEIDC Ltd., PATNA
Pending list of ACR reason of Not Strated
Sl. No. | Group wise Sl. No. | Gr. No | Division | Empower Committee No. | Name of District | Name of Block | Panchayat | S.N. | Name of School | Unit | [21 empty] | Retender | Tender Process | Not Start | Physical Report | [8 empty] | Agreement Amount (in Lakhs) | Fin. Exp. (in lakh) | Financial Achievement (%) | Remarks
[30 empty] | Technical Bid Opening | Fin. Bid opening |  |  |  | Lay-out | Foundation | PL | Ground floor |  | 1st Floor |  | Finishing | Complete
[11 empty] | Name of AgencyDate of Tender | A/A (Rs. In Lakh) | T/S(Rs. In Lakh) | BOQ Amount ( in lac) | Date of Tender | Tech. Bid opening | Fin. Bid opening | Tender Comitt. | Exec. Comm. | L.O.A | Contract Price (Rs. In Lakh) | Performance Security (Rs. In Lakh) | Date of Verification for Earnest Money issu to | Verification for Earnest Money Recived Date | Date of Submission (P.S) | verification for P.S. issued to Bank/P.O | verification received date | Aggrement No & date | Time of Completion | Retender | [7 empty] | LL | RL | LL | RL
1 | 3 | ACR | Tirhut East | 86 | Vaisali | psgjkdykW |  |  | psgjkdykW enjlk esa pkj vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 4 | MS. CHANDAN KUMAR 09934725409 '/ 8507324788 | [22 empty] | 1
2 | 6 | ACR | Tirhut East | 86 | Sitamarhi | cktiÍh |  |  | jktdh; e/; fo¦ky;] csyk 'kkrhdqfVj esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | ANITA DEVI 9199700293 |  |  | 21.8596 | [5 empty] | 13780/31.12.16 | [13 empty] | 1
3 | 9 | ACR | Patna East | 86 | Nalanda |  |  |  | Sarvodaya High School,Sohsarai | 1 | M/S DAYARAM SINGH |  |  | 229.4327 | [5 empty] | ISSUED | [7 empty] | 98SBD OF 2016-17 (24.11.16) | [5 empty] | 1 | [9 empty] | 206.4895 |  |  | Not started
4 | 11 | ACR | Patna East | 86 | Nalanda |  |  |  | Rajkiyakrit Kanya High School Sohsarai | 1 | KRISHANDEO PRASAD |  |  | 127.2174 | [5 empty] | 6576/12.07.16 | [7 empty] | 28 SBD of 2017-18 (03.05.17 | [5 empty] | 1 | [9 empty] | 114.4957 |  |  | Not Started. Drawing to be Revised.
5 | 12 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk dk’kheqy Åywe] csyf/k;k esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | ANITA DEVI 9199700293 | [8 empty] | I13770/31.12.16 | [13 empty] | 1 | [12 empty] | Agreement not done
6 | 14 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk blykfe;k ;kdwc uxj] nsodqaMk esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA (2) | 2 | GAURI SHANKAR SINGH 9431460106 |  |  | 20.7618 | [5 empty] | 3034/13.04.17 | [13 empty] | 1 | [12 empty] | Land not available
7 | 15 | ACR | Bhagalpur | 86 | Bhagalpur | lUgkSy |  |  | enjlk tesmyk Åywe pdukFFkq esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | AMIT KUMAR 08050100000 |  |  | 20.7768 | [5 empty] | 13779/31.12.16 | [13 empty] | 1 | [12 empty] | Land Dispute
8 | 17 | ACR | Bhagalpur | 86 | Bhagalpur | txnh'kiqj |  |  | enjlk vuhlwy gqLuk esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
9 | 18 | ACR | Bhagalpur | 86 | Bhagalpur | txnh'kiqj |  |  | enjlk edlwnwy Åywe esa nks vfrfjDr oxZ d{k dk fuekZ.k dk;ZA | 2 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.9851 | 0
10 | 20 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | çkFkfed fo¦ky; dlckVksyk | 6 | RAJESH .KUMAR 943024850000 |  |  | 449.2234 | [5 empty] | 13788/31.12.16 | [13 empty] | 1
11 | 21 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | mRØfer e/; fo¦ky; ljlkSuk | 3 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
12 | 23 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | çkFkfed fo¦ky; Hksjk[ksjk mnwZ rkrsjVksy | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
13 | 24 | ACR | Darbhanga | 97 | Samastipur | rktiqj |  |  | e/; fo¦ky; rktiqj | 4 | AMRENDRAKUMAR 9471454135 |  |  | 27.6225 | [5 empty] | 13787/31.12.16 | [13 empty] | 1
14 | 25 | ACR | Saran | 97 | Gopalganj | mpdkxk¡o |  |  | e/; fo¦ky; egsupk | 6 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
15 | 27 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | ch- ,e- mPp fo¦ky; egknsok | 8 | UDAY ERECTORS PRIVATE LIMITED 9708798033 |  |  | 61.2422 | [5 empty] | 13786/31.12.16 | [7 empty] | 53 F2 of 2017-18 (17.05.17) | [5 empty] | 1
16 | 28 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | bLykfe;k mPp fo¦ky; lhoku | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
17 | 29 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | uxjikfydk e/; fo¦ky; | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
18 | 30 | ACR | Saran | 97 | Siwan | Lhoku lnj |  |  | çkFkfed fo¦ky; “ks[k eksgYyk rsygÍk cktkj | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
19 | 33 | ACR | Saran | 97 | Siwan | gluiqjk |  |  | Ckfydk mPp fo¦ky; gluiqjk | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
20 | 36 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; tekygÍk | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
21 | 37 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; xksikyiqj | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
22 | 38 | ACR | Saran | 97 | Siwan | gqlSuxat |  |  | mRØfer mnwZ e/; fo¦ky; rsrfj;k | 5 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 40 | ACR-202 | Darbhanga | 107 | Madhubani | Bisfi |  |  | (i) High School at Parsauni | 5 | MS TARA CONSTRUCTION 7070466123 |  | 466.1095 | [6 empty] | 940/07.02.17 | 1 | [12 empty] | 1
24 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (ii) High School at Nahas Khangraitha | 5 | [10 empty] | 1 | [12 empty] | 1
25 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (iii) High School at Simiri | 5 | [10 empty] | 1 | [12 empty] | 1
26 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (iv) Upgraded School at Noorchak | 12 | [10 empty] | 1 | [12 empty] | 1
27 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (v) Middle School at AunsiBhabhangawa | 18 | [10 empty] | 1 | [12 empty] | 1
28 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (vi) Upgraded School at Bhairwa | 11 | [10 empty] | 1 | [12 empty] | 1
29 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (vii) Upgraded School at Shivaul | 12 | [10 empty] | 1 | [12 empty] | 1
30 |  |  | Darbhanga | 107 | Madhubani |  |  |  | (viii) Upgraded School at Bardha | 7 | [10 empty] | 1 | [12 empty] | 1
31 | 41 | ACR-203 | Bhagalpur | 107 | Bhagalpur | Sanhaula |  |  | Bari Adarsh High School | 8 | MILAN DRILLER & DEVELOPER PRIVATE LIMITED 9471452729 '/ 9973024980 |  |  | 49.0068 | [5 empty] | 959/07.02.17 | 1 | [12 empty] | 1
32 | 42 | ACR-204 | Koshi | 107 | Supual | Basantpur |  |  | (i) Upgraded middle school, Balbhadrapur | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
33 |  |  | Koshi | 107 | Supual |  |  |  | (ii) Middle school at Narpatpatti | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
34 |  |  | Koshi | 107 | Supual |  |  |  | (iii) Upgarded middle school at Deenbandhi | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
35 |  |  | Koshi | 107 | Supual |  |  |  | (iv) Urdu middle school at Kamalpur | 4 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
36 |  |  | Koshi | 107 | Supual |  |  |  | (v) Upgarded middle school at Parmanandpur | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
37 |  |  | Koshi | 107 | Supual |  |  |  | (vi) Middle school at Parsa Urdu | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
38 |  |  | Koshi | 107 | Supual |  |  |  | (vii) Middle school at Baria Kamal | 2 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
39 |  |  | Koshi | 107 | Supual |  |  |  | (viii) Primary School at Kataiya | 3 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
40 |  |  | Koshi | 107 | Supual |  |  |  | (ix)Upgarded middle school at Mohanpur | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
41 |  |  | Koshi | 107 | Supual |  |  |  | (x) Upgraded middle school at Shankarpur | 6 | [22 empty] | 1 | [13 empty] | NIT-70 (2016-17)
42 | 43 | ACR-205 | Koshi | 107 | Supual | Supaul Town |  |  | (i) Upgraded middle school at Jhakrahi, New muslimTola(12) | 12 | AMOD KUMAR 9122088000 |  |  | 269.8077 | [5 empty] | 946/07.02.17 | 1 | [7 empty] | 255 SBD OF 2016-17 (30.03.17) | 1 |  |  |  | 1 | [11 empty] | 242.8269 | Land Available but NOC not given by School H.M.
43 |  |  | Koshi | 107 | Supual |  |  |  | (ii) Hazari Higher Secondary School at Supaul (12) | 12 | [10 empty] | 1 | [8 empty] | 1 |  |  |  | 1 | [12 empty] | Layout Done but work can not be started due to water logging after excavation
44 |  |  | Koshi | 107 | Supual |  |  |  | (iii) Babujan vishveshwar Balika High School at Supaul (6) | 6 | [10 empty] | 1 | [8 empty] | 1 |  |  |  | 1 | [12 empty] | Land Not Available
45 |  |  | Koshi | 107 | Supual |  |  |  | (iv) Higher Secondary School at Supaul (12) | 12 | [10 empty] | 1 | [8 empty] | 1 |  |  |  | 1 | [12 empty] | Land Not Available
46 | 46 | ACR-208 | Tirhut West | 107 | East Champaran | Dhaka |  |  | (i) Govt. High School at High School Dhaka (6) | 6 | SHAKAL DEO MISHRA 9006385958 |  |  | 151.5283 | [5 empty] | 943/07.02.17 | 1 | [12 empty] | 1
47 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) Sarjeet high school at Bhandar (6) | 6 | [10 empty] | 1 | [12 empty] | 1
48 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iii) Shri H.M. Balika High school at Kamarwa (6) | 6 | [10 empty] | 1 | [12 empty] | 1
49 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (iv)High School at Jataulia (6) | 6 | [10 empty] | 1 | [12 empty] | 1
50 | 48 | ACR-210 | Tirhut West | 107 | East Champaran | Narkatiaganj/ Chodadano |  |  | Govt. high school at JeetpurVishnupurwa (4) | 4 | Tender Process | [21 empty] | 1 | [13 empty] | NIT-70 (2016-17)
51 | 49 | ACR-211 | Tirhut West | 107 | East Champaran | Adanpur |  |  | (i) Bansidhar high school (6) | 6 | RNS PROJECT 9470420900 |  |  | 64.4471 | [5 empty] | 942/07.02.17 | 1 | [12 empty] | 1
52 |  |  | Tirhut West | 107 | East Champaran |  |  |  | (ii) Project girls high school (4) | 4 | [10 empty] | 1 | [12 empty] | 1 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.8269
Total No. of ACR Schools | [8 empty] | 52 | 294 | 0 | 0 | 466.1095 | 1492.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 23 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.9851 | 0 | 242.8269